## Start_Here
Project HEATWISE: risk what-if workbook
SPCE0019 Project Simulation · UCL Centre for Systems Engineering · companion to the dashboard at https://sbegucl.github.io/heatwise/
| Scenario | HEATWISE must retrofit 20 London public buildings (schools, care homes, libraries) with cool roofs, external shading and ventilation, and open them as community cooling centres. Works start on 5 April 2027 and are planned to take 22 weeks. The authorised budget is £9.8m, which includes a £1.2m management reserve, and the deadline is week 27 (11 October 2027). Your group is the project risk team. The register has already been identified and assessed.
| Your task | Run what-if scenarios to mitigate the High and Medium priority risks. For every response, assess the residual risk it leaves and the secondary risks it creates. Balance probability and financial impact against the budget and schedule, and argue for the approach that best meets the board's risk appetite. There is no single right answer: several quite different approaches perform similarly.
| Board risk appetite | At least 70% confidence of staying within the authorised budget, and at least 60% confidence of finishing by the deadline.
| Two tools, one model | The DASHBOARD (https://sbegucl.github.io/heatwise/) runs a Monte Carlo simulation (4,000 runs) and gives the CONFIDENCE levels: the chance of staying within budget and of finishing on time. This WORKBOOK gives the same model as transparent expected values (EMV), so you can trace every number. Expected values in both should agree closely. Confidence levels come only from the dashboard, because they depend on the full spread of outcomes, not just the averages.
| Real data | Risk R1 (hot days stopping roof work) is forecast from real daily maximum temperatures, 1979 to September 2026, at Heathrow, Wisley or Rothamsted. These are Met Office series published through ECA&D, refreshed weekly by an open-data pipeline (github.com/SBegUCL/heatwise/tree/main/data). Summer 2026 was the UK's warmest on record. See Heat_Forecast. All other costs, probabilities and options are illustrative teaching assumptions for you to challenge.
| Project KPIs | The dashboard reports schedule (SPI, schedule variance, milestones), cost (CPI, cost and budget variance), scope and quality (rework, first-time acceptance, defects), resource (crew utilisation), stakeholder satisfaction and value (ROI, benefits realisation). The KPIs sheet defines each one and works the week-10 earned-value calculation.
| Half-day plan | Round 1 (planning): prioritise, test responses, find secondary and residual risks, decide. Round 2 (week 10 update): a risk occurs, two risks close and the heat outlook worsens. Your Round 1 choices are locked, and you must recover. See Student_Tasks for timings.
| How to use | 1) Choose responses in the dashboard and press Save scenario for every what-if you test. 2) Press "Copy rows for the workbook" and paste into Scenario_Log (first empty row, column B). 3) Enter your chosen responses in Risk_Register column T (drop-down) to see the EMV view, then complete the contingency and comments columns. 4) Shortlist, weight, vote and decide in Decision. 5) In Round 2, record your recovery decisions on Round2_Update.
| Colour key | Blue bold text on yellow = input you may change. Black = formula. Green = value linked from another sheet. Red, amber and green fills show High, Medium and Low priority. Do not overwrite black cells.
| Honesty about the model | Risks are treated as independent, and every delay is assumed to sit on the critical path. Cost and delay of one event move together. Hot days are counted at an airport station, not on a city-centre roof. Each of these is a simplification for you to question in your recommendation.
Sheet map
| Project_Brief | Purpose, scope statement, SMART objectives and VUCA statement. Read first.
| Stakeholders_RACI | Stakeholder power/interest matrix (re-score it) and RACI matrix with checks.
| WBS_CBS | Work breakdown and cost breakdown structures; how your responses draw on the reserve.
| Success_Criteria | Output and outcome success criteria; record your forecasts.
| Baseline | Budget, schedule, overheads, heat policy and board targets: the project inputs.
| Risk_Register | The module risk register template, extended with your response, residual risk and secondary risk.
| Options | Catalogue of responses: cost, time, effect and the secondary risk each creates.
| Heat_Forecast | Hot-day counts, trend and 2027 forecast for the chosen London-area station; R1 EMV.
| KPIs | Definitions of the project KPIs, forecast KPIs from the EMV view, and the week-10 earned-value calculation.
| Scenario_Log | Paste target for scenarios saved on the dashboard.
| Decision | Weights, shortlist, scores, vote, decision and dissent log.
| Round2_Update | Week 10 update brief and your recovery decisions.
| Student_Tasks | Half-day timetable mapped to core-module frameworks and ILOs.
| Heat_Data | Source observations: daily maximum temperature, May–September 1979–2026, at Heathrow, Wisley and Rothamsted (do not edit).
| Sources | Data provenance and licence.

## Project_Brief
Project_Brief: purpose, scope, SMART objectives and VUCA
Read this before you start. The dashboard's Project brief tab shows the same content, linked to your live scenario.
| Purpose | London's summers are getting hotter. Summer 2026 was the UK's warmest on record, and Heathrow saw 31 days at or above 30°C against a 1991–2020 average of 5.5. Older schools, care homes and libraries overheat, and the people who use them, children, older and clinically vulnerable residents, are among those most at risk from heat. HEATWISE is a fictional, publicly funded project to retrofit 20 such buildings and open them as community cooling centres before summer 2028.
| Scope statement | The HEATWISE Delivery Project will design, procure, install, commission and hand over passive and low-energy cooling measures (cool roofs, external shading and ventilation upgrades) at 20 council-owned public buildings in eight London boroughs, and will set each building up to operate as a community cooling centre. Works run from 5 April 2027 for 22 weeks, with a deadline of week 27 (11 October 2027), within an authorised budget of £9.8m (base estimate £8.6m plus a £1.2m management reserve held by the sponsor).
| In scope | • Condition surveys, desk-based structural review and standard asbestos surveys at all 20 sites • Design of cool roofs, external shading and ventilation for each building • Planning and listed-building consents where required (3 heritage sites) • Procurement of contractors and materials • Installation: 20 cool roofs, external shading on south and west elevations, ventilation upgrades • Testing, commissioning and handover, including operation and maintenance training for building managers • Cooling-centre fit-out (signage, seating, drinking water) and a co-designed operating model • Indoor temperature sensors and a benefits monitoring plan
| Out of scope | • Air-conditioning or other active cooling (deliberately excluded: carbon and running cost) • Structural strengthening beyond what the roof works need • Running the cooling centres after handover (a business-as-usual cost for each borough) • Buildings outside the agreed list of 20 • Measuring benefits after summer 2028 (owned by the boroughs)
| Key deliverables | • 20 retrofitted buildings with completion certificates • Thermal performance test report for each building • Operation and maintenance manuals and trained building managers • A cooling-centre operating model agreed with each community • A benefits monitoring plan with indoor sensors live
| Constraints | • Budget: £9.8m authorised; any increase needs the sponsor's approval • Time: buildings must be open as cooling centres before summer 2028; the deadline is 11 October 2027 • Roof work stops at 30°C or above (HEATWISE site heat policy) • No active cooling; low-carbon measures only • CDM 2015 and building regulations apply
| Assumptions | • Sites are available for works from April 2027; school works avoid exam weeks • The 3 heritage sites need listed-building consent; the other 17 do not • Hot-day stoppages are allowed for up to 5 days (the 1991–2020 Heathrow average) • Prices are at Q1 2027 levels with a standard allowance for inflation
SMART objectives
| Objective | Specific | Measurable | Achievable | Relevant | Time-bound | Status (from KPIs / dashboard)
| O1 Deliver the scope | Retrofit and hand over all 20 named buildings (cool roof, shading, ventilation). | 20 of 20 completion certificates and handover packs signed; at least 60% confidence of meeting the deadline at approval (board risk appetite). | 22-week programme with 5 weeks of float; works proven elsewhere in London. | Delivers the cooling capacity the boroughs need before summer 2028. | By week 27, 11 October 2027. | Read "Chance of finishing by week 27" on the dashboard
| O2 Stay within budget | Complete the project within the authorised budget, including risk responses. | Final cost ≤ £9.8m; at least 70% confidence at approval (P70). | Base estimate £8.6m plus £1.2m management reserve. | Public funding is fixed; overspend displaces other services. | Final account agreed within 3 months of handover. | Expected within budget
| O3 Meet the quality standard | Each building meets its thermal performance specification at handover. | ≥ 90% of buildings accepted first time; ≤ 7.5 snags per building; cooling room ≤ 26°C when outside is 30°C. | Specification uses proven cool-roof and shading products. | A building that does not perform is not a cooling centre. | Tested at handover; confirmed in the first 30°C week of 2028. | Dashboard: first-time acceptance
| O4 Keep people safe | Deliver the works without serious harm to workers, building users or the public. | Zero RIDDOR-reportable incidents; heat-stress plan in place for every hot day. | CDM duties assigned; principal designer appointed. | Works take place at height, in heat and in occupied buildings. | Throughout the works. | Not modelled
| O5 Earn community support | Co-design each cooling centre's operating model with its users. | Stakeholder satisfaction ≥ 7.0 / 10 in the handover survey. | Engagement lead and budget in place from week 0. | Centres only help if people know about them and trust them. | Survey at handover, week 27. | Dashboard: stakeholder satisfaction
| O6 Realise the benefits | Operate all 20 buildings as cooling centres in summer 2028. | Open on 100% of UKHSA amber and red heat-health alert days; overheating hours in cooling rooms down ≥ 50% against 2026; benefits realisation ≥ 97% of the £13.5m plan. | Operating model and trained staff in place at handover. | This is why the project exists. | Measured 1 June – 30 September 2028. | Dashboard: benefits realisation
VUCA statement
| Dimension | What it means for HEATWISE | Register links | Leadership response (VUCA Prime)
| Volatility | Weather and prices change fast and by a lot. Hot days at Heathrow ranged from 5 in 2024 to 31 in 2026. Material prices swing with global markets. | R1, R7 | Vision: keep the outcome (centres open for summer 2028) fixed, and flex how and when work is done.
| Uncertainty | Key facts cannot be known in advance: whether asbestos is in each roof, whether consent will be granted, whether the membrane supplier will deliver, and how hot summer 2027 will be. | R2, R3, R4, R6 | Understanding: buy information early (surveys, pre-application meetings) and use forecasts as ranges, not single numbers.
| Complexity | 20 sites, 8 boroughs, 3 types of work, several contractors and many stakeholders, with dependencies (structure → plant; consent → design; materials → roofs). One response can create a new risk elsewhere. | Secondary risks S1a–S7b | Clarity: map dependencies (WBS, RACI) and check every response for secondary risks.
| Ambiguity | Key ideas have more than one meaning. How cool is 'cool enough'? Whose needs come first, schools' or care homes'? Which weather station represents London? Is success the buildings, or the lives protected? | R8, choice of station | Agility: agree definitions and success criteria early, test options cheaply and record why each choice was made.

## Stakeholders_RACI
Stakeholders_RACI: power/interest matrix and RACI
Power and interest are inputs (1–5): re-score them as a group and the quadrant updates. 4–5 counts as high. In the RACI, each task must have exactly one A.
| Stakeholder | Power | Interest | Quadrant | Engagement strategy | Risks they shape or carry
| Programme sponsor (London heat resilience fund) | 5 | 5 | Manage closely | Manage closely: monthly board, approves reserve and scope changes. | R7, X3, SX3
| Borough councils (building owners) | 4 | 5 | Manage closely | Manage closely: site access, consents, and they run the centres after handover. | R4, R6
| Roofing and building contractors | 4 | 4 | Manage closely | Manage closely: weekly progress, incentives, interfaces. | R5, S5a, S5b, S7a
| Local planning authority and conservation officers | 5 | 2 | Keep satisfied | Keep satisfied: early pre-application meetings, complete applications. | R4, S4a
| Health and Safety Executive | 5 | 1 | Keep satisfied | Keep satisfied: CDM compliance, asbestos and heat-stress controls. | R3, S3a
| Membrane and materials suppliers | 4 | 3 | Keep satisfied | Keep satisfied: firm delivery dates, early warning of shortages. | R2, S2a, S2b
| Head teachers and school governors | 3 | 5 | Keep informed | Keep informed and involve: work around term dates and exams. | R3, S3a
| Care home operators, residents and families | 2 | 5 | Keep informed | Keep informed and protect: vulnerable occupants; quiet working hours. | S1a, S6b
| Local residents near sites | 2 | 4 | Keep informed | Keep informed: notices, a named contact and co-design of opening hours. | R8, S1a, S4b
| UKHSA and public health teams | 2 | 4 | Keep informed | Keep informed: link the centres to heat-health alerts. | Outcome O6
| Insurers | 2 | 2 | Monitor | Monitor: policy terms and claims evidence. | R1c, S1c
| Local media | 3 | 1 | Monitor | Monitor: proactive news on progress; respond to complaints quickly. | Reputation
Quadrant counts
| Manage closely | 3
| Keep satisfied | 3
| Keep informed | 4
| Monitor | 2
RACI matrix
| Task (WBS) | SP | PM | CM | PD | SE | PL | PLN | CST | EL | CON | BM | A count | R count | Check
| 1.1 Project management and reporting | A | R | C |  |  |  |  | C | I |  | I | 1 | 1 | OK
| 1.2 Health and safety (CDM) and heat-stress plan | I | A | R | R | [5 empty] | C | I | 1 | 2 | OK
| 1.3 Stakeholder engagement and communications | I | A | C | [5 empty] | R |  | C | 1 | 1 | OK
| 2.1 Condition and structural surveys |  | A | I | C | R | [5 empty] | C | 1 | 1 | OK
| 2.2 Asbestos management surveys |  | I | I | A | [5 empty] | R | C | 1 | 1 | OK
| 2.3 Design: cool roofs, shading, ventilation |  | A | C | R | C |  |  | C |  |  | C | 1 | 1 | OK
| 2.4 Planning and listed-building consents | I | A |  | C |  |  | R |  | C |  |  | 1 | 1 | OK
| 3.1 Contractor procurement and contracts | C | A | C |  |  | R |  | C |  |  |  | 1 | 1 | OK
| 3.2 Materials procurement and logistics |  | A | C |  |  | R |  | C |  | I |  | 1 | 1 | OK
| 4.1 Site set-up and preliminaries |  | I | A | [6 empty] | R | C | 1 | 1 | OK
| 4.2–4.4 Install cool roofs, shading and ventilation |  | I | A | C | C |  |  |  |  | R | I | 1 | 1 | OK
| – Cost control, change and risk register | I | A | C |  |  | C |  | R |  |  |  | 1 | 1 | OK
| 5.1 Testing and commissioning |  | I | A | C | [5 empty] | R | I | 1 | 1 | OK
| 5.2 Handover and building-manager training | I | A | R | [6 empty] | R | C | 1 | 2 | OK
| 5.3 Cooling-centre fit-out and operating model | C | A | C | [5 empty] | R |  | R | 1 | 2 | OK
| 6.1 Benefits monitoring plan and sensors | A | R | [6 empty] | C |  | C | 1 | 1 | OK
Roles: SP = Sponsor · PM = Project manager · CM = Construction manager · PD = Principal designer · SE = Structural engineer · PL = Procurement lead · PLN = Planning lead · CST = Cost manager · EL = Engagement lead · CON = Contractors · BM = Building managers. R = Responsible, A = Accountable, C = Consulted, I = Informed.
Add a row for each secondary risk you accept, and name its Responsible and Accountable roles. Then copy the owner to Risk_Register.

## WBS_CBS
WBS_CBS: work breakdown and cost breakdown structures
Costs (£k) are inputs: the base estimate on Baseline should equal the CBS total (see the check). The bottom table shows how your chosen responses draw on the management reserve.
| WBS | Work package | Cost £k | Cost type | Share | Milestone | Register risks | Start week | End week | Planned value at status week £k | Earned value at status week £k
| 1 | Project management and assurance | 620 |  | 7.209% |  |  | 0 | 22 | 281.8182 | 259.2727
| 1.1 | Project management, reporting and assurance | 420 | Fees | 4.884% |  | R7 | 0 | 22 | 190.9091 | 175.6364
| 1.2 | Health and safety (CDM) and principal designer | 120 | Fees | 1.395% |  | R3 | 0 | 22 | 54.5455 | 50.1818
| 1.3 | Stakeholder engagement and communications | 80 | Fees | 0.9302% |  | R8 | 0 | 22 | 36.3636 | 33.4545
| 2 | Design and surveys | 630 |  | 7.326% |  |  | 0 | 4 | 630 | 630
| 2.1 | Condition surveys and desk-based structural review (20 sites) | 150 | Fees | 1.744% | M1 | R6 | 0 | 3 | 150 | 150
| 2.2 | Asbestos management surveys (standard) | 60 | Fees | 0.6977% | M1 | R3 | 0 | 3 | 60 | 60
| 2.3 | Design: cool roofs, shading and ventilation | 380 | Fees | 4.419% | M1 | R6 | 0 | 4 | 380 | 380
| 2.4 | Planning and listed-building consents | 40 | Fees | 0.4651% | M1 | R4 | 0 | 4 | 40 | 40
| 3 | Procurement | 2670 |  | 31.05% |  |  | 0 | 7 | 2670 | 2670
| 3.1 | Contractor procurement and contracts | 70 | Fees | 0.814% | M2 | R5, R7 | 0 | 2 | 70 | 70
| 3.2 | Materials: membrane, shading, ventilation units | 2600 | Materials | 30.23% | M2 | R2, R7 | 2 | 7 | 2600 | 2600
| 4 | Construction | 4240 |  | 49.3% |  |  | 0 | 22 | 1164.9351 | 973.8182
| 4.1 | Site set-up and preliminaries (22 weeks × £35k) | 770 | Preliminaries | 8.953% |  | All delays | 0 | 22 | 350 | 322
| 4.2 | Install cool roofs (20 roofs) | 1900 | Labour and plant | 22.09% | M3, M4 | R1, R3, R5 | 5 | 19 | 678.5714 | 570
| 4.3 | Install external shading | 750 | Labour and plant | 8.721% | M4 | R5 | 8 | 19 | 136.3636 | 81.8182
| 4.4 | Ventilation upgrades | 820 | Labour and plant | 9.535% | M4 | R6 | 10 | 20 | 0 | 0
| 5 | Commissioning, handover and cooling centres | 360 |  | 4.186% |  |  | 16 | 22 | 0 | 0
| 5.1 | Testing and commissioning (thermal performance) | 120 | Fees | 1.395% | M5 | S2c, S6b | 18 | 22 | 0 | 0
| 5.2 | Handover, O&M manuals and training | 60 | Fees | 0.6977% | M5 |  | 20 | 22 | 0 | 0
| 5.3 | Cooling-centre fit-out and operating model | 180 | Materials | 2.093% | M5 | R8 | 16 | 22 | 0 | 0
| 6 | Benefits monitoring | 80 |  | 0.9302% |  |  | 18 | 22 | 0 | 0
| 6.1 | Indoor sensors and benefits monitoring plan | 80 | Materials | 0.9302% | M5 |  | 18 | 22 | 0 | 0
|  | Base estimate (sum of work packages) | 8600 | [6 empty] | 4746.7532 | 4533.0909
|  | Check against Baseline base estimate | Matches
|  | Management reserve (sponsor) | 1200
|  | Authorised budget | 9800
Columns K–L time-phase the CBS: each package is spread evenly between its start and end weeks (stretched in proportion if responses add weeks). They feed the week-10 earned-value status on the KPIs sheet.
By cost type
|  | Cost type | Cost £k | Share
|  | Fees | 1500 | 17.44%
|  | Materials | 2860 | 33.26%
|  | Labour and plant | 3470 | 40.35%
|  | Preliminaries | 770 | 8.953%
Your scenario against the reserve (from Risk_Register)
|  | Risk responses bought (mitigation spend) | 0
|  | Expected cost of risks and delay | 1191.2448
|  | Expected call on the reserve | 1191.2448
|  | Reserve left (expected) | 8.7552
For the chance of the reserve lasting (P80), read the dashboard: expected values alone hide the spread.

## Success_Criteria
Success_Criteria: output (project) and outcome (benefit) success
Outputs: did we deliver what we said, on time, on budget and to quality? Outcomes: did it make the difference it was for? Record your forecast from the dashboard in the yellow column.
Output success criteria
| Criterion | Measure | Target | When measured | Workbook value | Your forecast (from dashboard)
| All 20 buildings retrofitted and handed over by the deadline | Completion certificates; handover by week 27 | 100% by 11 Oct 2027 | Handover | Dashboard only
| Delivered within the authorised budget | Final account against £9.8m | ≤ £9.8m (≥ 70% confidence at approval) | Final account | Dashboard only
| Buildings accepted first time | Share of buildings passing the thermal test without remedial work | ≥ 90% | Handover | Dashboard only
| Quality of finish | Snag items per building at handover | ≤ 7.5 | Handover | Dashboard only
| Delivered safely | RIDDOR-reportable incidents | 0 | Throughout | Not modelled
| Cost efficiency | CPI = BAC ÷ EAC | ≥ 0.95 | Monthly | 0.87834
Outcome success criteria
| Criterion | Measure | Target | When measured | Workbook value | Your forecast (from dashboard)
| Centres open when London needs them | Share of UKHSA amber and red heat-health alert days on which all 20 centres open | 100% in summer 2028 | Sept 2028 | Not modelled
| Buildings stay cooler | Hours above 26°C in cooling rooms, against the 2026 baseline | ≥ 50% fewer | Sept 2028 | Dashboard only
| Communities use and trust the centres | Visits per centre per heat-alert day; satisfaction survey | ≥ 40 visits; ≥ 7.0 / 10 | Handover and Sept 2028 | Dashboard only
| Value for public money | ROI on whole-life benefit (£13.5m planned) | ≥ 35% | Business case review | Dashboard only
| Benefits delivered as planned | Realised benefit ÷ planned benefit | ≥ 97% | Sept 2028 | Dashboard only
Discuss: which of your choices improve outputs at the expense of outcomes, or the other way round? Which would the sponsor, the boroughs and the care homes each prefer?

## Baseline
Baseline: project inputs
Blue on yellow = inputs. Money in £k unless stated. Changing an input here flows through every sheet (the dashboard uses the published defaults).
| Input | Value | Unit | Note
| Base estimate | 8600 | £k | Cost of the planned works before risk. Illustrative.
| Management reserve | 1200 | £k | Held by the sponsor for risk. Mitigation spend also comes out of the budget.
| Authorised budget | 9800 | £k | Base estimate + management reserve.
| Planned duration | 22 | weeks | From 5 April 2027.
| Deadline | 27 | week | Week 27 = 11 October 2027 (October half-term).
| Float | 5 | weeks | Deadline − planned duration.
| Site overheads (preliminaries) | 35 | £k/week | Every week beyond the plan costs this much. Used to cost delay in impact scores.
| Hot-day threshold | 30 | °C | HEATWISE site heat policy (illustrative): roof work stops when the maximum reaches this.
| Hot days allowed in programme | 5 | days | Weather allowance already in the 22-week plan: the 1991–2020 average at Heathrow (5.5 days), rounded down. Is a past average the right anchor?
| Standby cost per lost day | 40 | £k/day | Crews and plant standing across 20 sites. Illustrative.
| Time lost per hot day | 0.25 | weeks/day | A lost day plus re-mobilisation.
| Forecast year | 2027 | year | Year of the build.
| Heat forecast basis | trend | text | trend = linear trend 1979–2023 projected to the forecast year, plus historical variability; recent = last 10 summers; all = all 45 summers.
| Heat outlook multiplier | 1 | × | Round 1 = 1. Round 2 (hotter-than-normal seasonal outlook) = 1.35.
| Target confidence within budget | 70% | % | Board risk appetite.
| Target confidence on time | 60% | % | Board risk appetite.
| Weather station for the heat forecast | Heathrow | text | Heathrow (west London), Wisley (Surrey) or Rothamsted (Hertfordshire). Which best represents 20 sites across London?

## Options
Options: the response catalogue
Each response has a certain cost and may add time. It changes probability (P mult) or impact (impact/cost/delay mult), and may create a secondary risk. Inputs: edit with care, the dashboard uses the published values.
| Option ID | Risk | Strategy | Response | Cost £k | Weeks added | P mult | Impact mult | Cost mult | Delay mult | Heat exposure | Hot-day loss | Insured share | Secondary ID | Secondary risk | Sec. P | Sec. cost min £k | Sec. cost ML £k | Sec. cost max £k | Sec. delay min wk | Sec. delay ML wk | Sec. delay max wk | What it represents
| R1a | R1 | Reduce | Early and night shifts on hot days | 110 | 0 | 1 | 1 | 1 | 1 | 1 | 0.4 | 0 | S1a | Night-working noise complaints halt work at residential sites | 30% | 20 | 50 | 100 | 0 | 0.5 | 1.5 | Work 05:00–11:00 and after dark; each hot day loses 40% of a shift instead of a full shift.
| R1b | R1 | Avoid | Re-sequence: roofs in spring, interiors in July–August | 40 | 0.5 | 1 | 1 | 1 | 1 | 0.45 | 1 | 0 | S1b | Roof works squeezed into wetter spring weeks: rain delays | 35% | 40 | 80 | 160 | 0.5 | 1.5 | 3 | Only 45% of hot days now fall during roof works; re-sequencing adds half a week.
| R1c | R1 | Transfer | Parametric weather insurance | 90 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | S1c | Insurer disputes the claim (station reading vs site reading) | 20% | 20 | 40 | 80 | 0 | 0 | 0 | Pays 70% of heat-stoppage costs. Does not recover lost time.
| R2a | R2 | Avoid | Buy all membrane up front and store it | 120 | 0 | 0.2 | 1 | 1 | 1 | 1 | 1 | 0 | S2a | Stored membrane damaged or stolen at depot | 15% | 60 | 120 | 250 | 0.5 | 1 | 3 | Delivery risk mostly removed; storage and capital cost.
| R2b | R2 | Reduce | Qualify a second supplier | 80 | 0 | 0.55 | 0.6 | 1 | 1 | 1 | 1 | 0 | S2b | Two products on one roof: warranty and compatibility dispute | 20% | 40 | 90 | 200 | 0.5 | 1 | 2 | Fewer and shorter delays.
| R2c | R2 | Reduce | Specify cool-roof paint where roofs allow | 30 | 0 | 1 | 0.5 | 1 | 1 | 1 | 1 | 0 | S2c | Painted roofs fail the thermal performance test at handover | 30% | 60 | 140 | 300 | 0.5 | 1 | 2 | Halves dependence on membrane; paint is lower performing.
| R3a | R3 | Reduce | Intrusive asbestos surveys before start | 90 | 1 | 0.25 | 0.8 | 1 | 1 | 1 | 1 | 0 | S3a | Survey openings cause roof leaks in occupied buildings | 10% | 20 | 50 | 120 | 0 | 0.5 | 1 | Finds most asbestos in advance; surveys add a week.
| R3b | R3 | Reduce | Licensed removal contractor on standby | 60 | 0 | 1 | 1 | 0.75 | 0.4 | 1 | 1 | 0 |  | None identified | 0% | 0 | 0 | 0 | 0 | 0 | 0 | Same chance of finding asbestos; much faster response.
| R4a | R4 | Reduce | Pre-application meetings with conservation officers | 40 | 0.5 | 0.4 | 1 | 1 | 1 | 1 | 1 | 0 | S4a | Officers require design changes at heritage sites | 35% | 50 | 100 | 200 | 0.5 | 1 | 2 | Consent far more likely first time; engagement adds half a week.
| R4b | R4 | Avoid | Swap the 3 heritage sites for non-listed buildings | 60 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | S4b | Replacement sites draw objections and need fresh surveys | 35% | 30 | 60 | 150 | 0.5 | 1.5 | 3 | Removes the consent risk; replacement sites need new surveys and designs.
| R5a | R5 | Reduce | Appoint a second roofing contractor | 50 | 0 | 0.4 | 1 | 1 | 1 | 1 | 1 | 0 | S5a | Interface problems between two contractors | 25% | 30 | 60 | 130 | 0.5 | 1 | 2 | Spreads the work across two firms.
| R5b | R5 | Reduce | On-time completion bonus | 140 | 0 | 0.3 | 0.7 | 1 | 1 | 1 | 1 | 0 | S5b | Rushed work: defects and snagging at handover | 25% | 40 | 90 | 180 | 0 | 1 | 2 | Contractor prioritises HEATWISE crews.
| R6a | R6 | Reduce | Intrusive structural surveys and load tests of all roofs | 80 | 0.5 | 0.35 | 1 | 1 | 1 | 1 | 1 | 0 |  | None identified | 0% | 0 | 0 | 0 | 0 | 0 | 0 | Goes beyond the desk-based review in WBS 2.1, so strengthening is designed in where needed.
| R6b | R6 | Avoid | Lightweight design: no rooftop plant | 50 | 0 | 0.1 | 1 | 1 | 1 | 1 | 1 | 0 | S6b | Indoor units under-perform: cooling centres miss comfort target | 25% | 30 | 70 | 150 | 0 | 0.5 | 1 | Ventilation units go inside instead.
| R7a | R7 | Transfer | Fixed-price contract | 240 | 0 | 1 | 1 | 0.15 | 1 | 1 | 1 | 0 | S7a | Contractor becomes insolvent under the fixed price | 6% | 300 | 700 | 1400 | 4 | 8 | 14 | Contractor carries inflation risk for a premium.
| R7b | R7 | Reduce | Forward-buy steel and insulation | 50 | 0 | 1 | 1 | 0.6 | 1 | 1 | 1 | 0 | S7b | Forward-bought materials don't match final design | 15% | 20 | 50 | 120 | 0 | 0.5 | 1 | Locks in today's prices for the main materials.
| R8a | R8 | Reduce | Co-design opening hours with residents | 25 | 0 | 0.4 | 1 | 1 | 1 | 1 | 1 | 0 |  | None identified | 0% | 0 | 0 | 0 | 0 | 0 | 0 | Community workshops before opening.
Multipliers: 1 = no change, 0.5 = halves it, 0 = removes it. Heat options act on R1 only: exposure = share of hot days that fall during roof works; hot-day loss = share of a shift lost on a hot day; insured share = share of standby cost the insurer pays.

## Heat_Data
Heat_Data: daily maximum temperature, May–September 1979–2026, three London-area stations
Met Office National Climate Information Centre series via ECA&D blended data (valid observations only). Refreshed weekly at github.com/SBegUCL/heatwise/tree/main/data. Do not edit.
Date | Year | Month | Station | TX max °C
1979-05-01 | 1979 | 5 | Rothamsted | 7.4
1979-05-02 | 1979 | 5 | Rothamsted | 9.3
1979-05-03 | 1979 | 5 | Rothamsted | 7.7
1979-05-04 | 1979 | 5 | Rothamsted | 9.4
1979-05-05 | 1979 | 5 | Rothamsted | 10.7
1979-05-06 | 1979 | 5 | Rothamsted | 14.1
1979-05-07 | 1979 | 5 | Rothamsted | 15.1
1979-05-08 | 1979 | 5 | Rothamsted | 14.7
1979-05-09 | 1979 | 5 | Rothamsted | 13.3
1979-05-11 | 1979 | 5 | Rothamsted | 19.6
1979-05-12 | 1979 | 5 | Rothamsted | 23.2
1979-05-13 | 1979 | 5 | Rothamsted | 25.4
1979-05-14 | 1979 | 5 | Rothamsted | 25.6
1979-05-15 | 1979 | 5 | Rothamsted | 21.4
1979-05-17 | 1979 | 5 | Rothamsted | 14.9
1979-05-18 | 1979 | 5 | Rothamsted | 16.2
1979-05-19 | 1979 | 5 | Rothamsted | 13.5
1979-05-20 | 1979 | 5 | Rothamsted | 14.4
1979-05-21 | 1979 | 5 | Rothamsted | 14.5
1979-05-22 | 1979 | 5 | Rothamsted | 13.6
1979-05-23 | 1979 | 5 | Rothamsted | 13.1
1979-05-24 | 1979 | 5 | Rothamsted | 13.6
1979-05-25 | 1979 | 5 | Rothamsted | 14.8
1979-05-26 | 1979 | 5 | Rothamsted | 15.3
1979-05-27 | 1979 | 5 | Rothamsted | 14.3
1979-05-28 | 1979 | 5 | Rothamsted | 18
1979-05-29 | 1979 | 5 | Rothamsted | 17.4
1979-05-30 | 1979 | 5 | Rothamsted | 15.1
1979-05-31 | 1979 | 5 | Rothamsted | 17.1
1979-06-01 | 1979 | 6 | Rothamsted | 18.5
1979-06-02 | 1979 | 6 | Rothamsted | 16.6
1979-06-03 | 1979 | 6 | Rothamsted | 20.2
1979-06-04 | 1979 | 6 | Rothamsted | 19.2
1979-06-05 | 1979 | 6 | Rothamsted | 15.7
1979-06-06 | 1979 | 6 | Rothamsted | 14.3
1979-06-07 | 1979 | 6 | Rothamsted | 17.5
1979-06-08 | 1979 | 6 | Rothamsted | 19.2
1979-06-09 | 1979 | 6 | Rothamsted | 17.4
1979-06-10 | 1979 | 6 | Rothamsted | 16.7
1979-06-11 | 1979 | 6 | Rothamsted | 15.4
1979-06-12 | 1979 | 6 | Rothamsted | 17.3
1979-06-13 | 1979 | 6 | Rothamsted | 14.9
1979-06-14 | 1979 | 6 | Rothamsted | 14.1
1979-06-15 | 1979 | 6 | Rothamsted | 18.6
1979-06-16 | 1979 | 6 | Rothamsted | 19.9
1979-06-17 | 1979 | 6 | Rothamsted | 22.3
1979-06-18 | 1979 | 6 | Rothamsted | 24.5
1979-06-19 | 1979 | 6 | Rothamsted | 24.9
1979-06-20 | 1979 | 6 | Rothamsted | 20.9
1979-06-21 | 1979 | 6 | Rothamsted | 19.1
1979-06-22 | 1979 | 6 | Rothamsted | 18.3
1979-06-23 | 1979 | 6 | Rothamsted | 14.5
1979-06-24 | 1979 | 6 | Rothamsted | 16.7
1979-06-25 | 1979 | 6 | Rothamsted | 19.3
1979-06-26 | 1979 | 6 | Rothamsted | 18.9
1979-06-27 | 1979 | 6 | Rothamsted | 19.5
1979-06-28 | 1979 | 6 | Rothamsted | 15.3
1979-06-29 | 1979 | 6 | Rothamsted | 15.1
1979-06-30 | 1979 | 6 | Rothamsted | 17.2
1979-07-01 | 1979 | 7 | Rothamsted | 16.9
1979-07-02 | 1979 | 7 | Rothamsted | 19
1979-07-03 | 1979 | 7 | Rothamsted | 22.2
1979-07-04 | 1979 | 7 | Rothamsted | 23.7
1979-07-05 | 1979 | 7 | Rothamsted | 23.5
1979-07-06 | 1979 | 7 | Rothamsted | 20.1
1979-07-07 | 1979 | 7 | Rothamsted | 21.4
1979-07-08 | 1979 | 7 | Rothamsted | 19.3
1979-07-09 | 1979 | 7 | Rothamsted | 20.2
1979-07-10 | 1979 | 7 | Rothamsted | 19.1
1979-07-11 | 1979 | 7 | Rothamsted | 23.7
1979-07-12 | 1979 | 7 | Rothamsted | 24.8
1979-07-13 | 1979 | 7 | Rothamsted | 20.2
1979-07-14 | 1979 | 7 | Rothamsted | 19.7
1979-07-15 | 1979 | 7 | Rothamsted | 21.5
1979-07-16 | 1979 | 7 | Rothamsted | 25
1979-07-17 | 1979 | 7 | Rothamsted | 21
1979-07-19 | 1979 | 7 | Rothamsted | 19.9
1979-07-20 | 1979 | 7 | Rothamsted | 18.3
1979-07-21 | 1979 | 7 | Rothamsted | 15.5
1979-07-22 | 1979 | 7 | Rothamsted | 17.4
1979-07-23 | 1979 | 7 | Rothamsted | 22
1979-07-24 | 1979 | 7 | Rothamsted | 23.2
1979-07-25 | 1979 | 7 | Rothamsted | 24.8
1979-07-26 | 1979 | 7 | Rothamsted | 28
1979-07-27 | 1979 | 7 | Rothamsted | 25
1979-07-28 | 1979 | 7 | Rothamsted | 20.7
1979-07-29 | 1979 | 7 | Rothamsted | 21.9
1979-07-30 | 1979 | 7 | Rothamsted | 19.8
1979-07-31 | 1979 | 7 | Rothamsted | 21.9
1979-08-01 | 1979 | 8 | Rothamsted | 20.7
1979-08-02 | 1979 | 8 | Rothamsted | 19.9
1979-08-03 | 1979 | 8 | Rothamsted | 21.1
1979-08-04 | 1979 | 8 | Rothamsted | 22.3
1979-08-05 | 1979 | 8 | Rothamsted | 23.3
1979-08-06 | 1979 | 8 | Rothamsted | 21.6
1979-08-07 | 1979 | 8 | Rothamsted | 19.1
1979-08-08 | 1979 | 8 | Rothamsted | 17.1
1979-08-09 | 1979 | 8 | Rothamsted | 20
1979-08-10 | 1979 | 8 | Rothamsted | 23.4
1979-08-11 | 1979 | 8 | Rothamsted | 24.6
1979-08-13 | 1979 | 8 | Rothamsted | 19.7
1979-08-14 | 1979 | 8 | Rothamsted | 20.3
1979-08-15 | 1979 | 8 | Rothamsted | 19.2
1979-08-16 | 1979 | 8 | Rothamsted | 18.1
1979-08-17 | 1979 | 8 | Rothamsted | 18.3
1979-08-18 | 1979 | 8 | Rothamsted | 19
1979-08-19 | 1979 | 8 | Rothamsted | 21.2
1979-08-20 | 1979 | 8 | Rothamsted | 19.5
1979-08-21 | 1979 | 8 | Rothamsted | 18.5
1979-08-22 | 1979 | 8 | Rothamsted | 15
1979-08-23 | 1979 | 8 | Rothamsted | 16.5
1979-08-24 | 1979 | 8 | Rothamsted | 17
1979-08-25 | 1979 | 8 | Rothamsted | 17.1
1979-08-26 | 1979 | 8 | Rothamsted | 15.7
1979-08-27 | 1979 | 8 | Rothamsted | 20.9
1979-08-28 | 1979 | 8 | Rothamsted | 22.4
1979-08-29 | 1979 | 8 | Rothamsted | 24.6
1979-08-30 | 1979 | 8 | Rothamsted | 21.7
1979-08-31 | 1979 | 8 | Rothamsted | 21.2
1979-09-01 | 1979 | 9 | Rothamsted | 20.4
1979-09-02 | 1979 | 9 | Rothamsted | 17.8
1979-09-03 | 1979 | 9 | Rothamsted | 20.7
1979-09-04 | 1979 | 9 | Rothamsted | 22.4
1979-09-05 | 1979 | 9 | Rothamsted | 24.6
1979-09-06 | 1979 | 9 | Rothamsted | 21.1
1979-09-07 | 1979 | 9 | Rothamsted | 21.7
1979-09-08 | 1979 | 9 | Rothamsted | 21.9
1979-09-09 | 1979 | 9 | Rothamsted | 21.4
1979-09-10 | 1979 | 9 | Rothamsted | 21.6
1979-09-11 | 1979 | 9 | Rothamsted | 18
1979-09-12 | 1979 | 9 | Rothamsted | 16.8
1979-09-13 | 1979 | 9 | Rothamsted | 16.5
1979-09-14 | 1979 | 9 | Rothamsted | 15.6
1979-09-15 | 1979 | 9 | Rothamsted | 19.4
1979-09-16 | 1979 | 9 | Rothamsted | 20.2
1979-09-17 | 1979 | 9 | Rothamsted | 18
1979-09-18 | 1979 | 9 | Rothamsted | 17.8
1979-09-20 | 1979 | 9 | Rothamsted | 14.9
1979-09-21 | 1979 | 9 | Rothamsted | 12.6
1979-09-22 | 1979 | 9 | Rothamsted | 12.4
1979-09-23 | 1979 | 9 | Rothamsted | 15.2
1979-09-24 | 1979 | 9 | Rothamsted | 17.2
1979-09-25 | 1979 | 9 | Rothamsted | 19.7
1979-09-26 | 1979 | 9 | Rothamsted | 15.9
1979-09-27 | 1979 | 9 | Rothamsted | 15.9
1979-09-28 | 1979 | 9 | Rothamsted | 15.7
1979-09-29 | 1979 | 9 | Rothamsted | 17.1
1979-09-30 | 1979 | 9 | Rothamsted | 17.6
1980-05-01 | 1980 | 5 | Rothamsted | 13.2
1980-05-02 | 1980 | 5 | Rothamsted | 11.2
1980-05-03 | 1980 | 5 | Rothamsted | 14.7
1980-05-04 | 1980 | 5 | Rothamsted | 11.2
1980-05-05 | 1980 | 5 | Rothamsted | 11.8
1980-05-06 | 1980 | 5 | Rothamsted | 10.2
1980-05-07 | 1980 | 5 | Rothamsted | 8.5
1980-05-08 | 1980 | 5 | Rothamsted | 11.6
1980-05-09 | 1980 | 5 | Rothamsted | 17.5
1980-05-10 | 1980 | 5 | Rothamsted | 19.1
1980-05-11 | 1980 | 5 | Rothamsted | 22.5
1980-05-12 | 1980 | 5 | Rothamsted | 21.7
1980-05-13 | 1980 | 5 | Rothamsted | 18.9
1980-05-14 | 1980 | 5 | Rothamsted | 17.8
1980-05-15 | 1980 | 5 | Rothamsted | 18.7
1980-05-16 | 1980 | 5 | Rothamsted | 19.1
1980-05-17 | 1980 | 5 | Rothamsted | 21.5
1980-05-18 | 1980 | 5 | Rothamsted | 22.4
1980-05-20 | 1980 | 5 | Rothamsted | 19.4
1980-05-21 | 1980 | 5 | Rothamsted | 15.1
1980-05-23 | 1980 | 5 | Rothamsted | 12.8
1980-05-24 | 1980 | 5 | Rothamsted | 15.3
1980-05-25 | 1980 | 5 | Rothamsted | 17.6
1980-05-26 | 1980 | 5 | Rothamsted | 17.2
1980-05-27 | 1980 | 5 | Rothamsted | 17.8
1980-05-28 | 1980 | 5 | Rothamsted | 13.4
1980-05-29 | 1980 | 5 | Rothamsted | 15
1980-05-30 | 1980 | 5 | Rothamsted | 11
1980-05-31 | 1980 | 5 | Rothamsted | 17.1
1980-06-01 | 1980 | 6 | Rothamsted | 16.5
1980-06-02 | 1980 | 6 | Rothamsted | 24
1980-06-03 | 1980 | 6 | Rothamsted | 27.3
1980-06-04 | 1980 | 6 | Rothamsted | 26
1980-06-06 | 1980 | 6 | Rothamsted | 18.1
1980-06-07 | 1980 | 6 | Rothamsted | 18.1
1980-06-08 | 1980 | 6 | Rothamsted | 19.6
1980-06-09 | 1980 | 6 | Rothamsted | 19.2
1980-06-10 | 1980 | 6 | Rothamsted | 18.2
1980-06-11 | 1980 | 6 | Rothamsted | 21.9
1980-06-12 | 1980 | 6 | Rothamsted | 22.9
1980-06-13 | 1980 | 6 | Rothamsted | 17.7
1980-06-14 | 1980 | 6 | Rothamsted | 19.5
1980-06-15 | 1980 | 6 | Rothamsted | 17
1980-06-16 | 1980 | 6 | Rothamsted | 16.5
1980-06-17 | 1980 | 6 | Rothamsted | 18.6
1980-06-18 | 1980 | 6 | Rothamsted | 15.9
1980-06-19 | 1980 | 6 | Rothamsted | 15.5
1980-06-20 | 1980 | 6 | Rothamsted | 16.6
1980-06-21 | 1980 | 6 | Rothamsted | 14.9
1980-06-22 | 1980 | 6 | Rothamsted | 15.4
1980-06-23 | 1980 | 6 | Rothamsted | 14.1
1980-06-24 | 1980 | 6 | Rothamsted | 18.2
1980-06-25 | 1980 | 6 | Rothamsted | 17.6
1980-06-26 | 1980 | 6 | Rothamsted | 16.2
1980-06-27 | 1980 | 6 | Rothamsted | 16
1980-06-28 | 1980 | 6 | Rothamsted | 17.8
1980-06-29 | 1980 | 6 | Rothamsted | 17.4
1980-06-30 | 1980 | 6 | Rothamsted | 15
1980-07-01 | 1980 | 7 | Rothamsted | 19.2
1980-07-02 | 1980 | 7 | Rothamsted | 21
1980-07-03 | 1980 | 7 | Rothamsted | 17
1980-07-04 | 1980 | 7 | Rothamsted | 17.5
1980-07-05 | 1980 | 7 | Rothamsted | 18.5
1980-07-06 | 1980 | 7 | Rothamsted | 17.4
1980-07-07 | 1980 | 7 | Rothamsted | 14.1
1980-07-08 | 1980 | 7 | Rothamsted | 13
1980-07-09 | 1980 | 7 | Rothamsted | 14.9
1980-07-10 | 1980 | 7 | Rothamsted | 18.5
1980-07-11 | 1980 | 7 | Rothamsted | 16.5
1980-07-12 | 1980 | 7 | Rothamsted | 17.9
1980-07-13 | 1980 | 7 | Rothamsted | 14.1
1980-07-14 | 1980 | 7 | Rothamsted | 14.4
1980-07-15 | 1980 | 7 | Rothamsted | 17.4
1980-07-16 | 1980 | 7 | Rothamsted | 15.5
1980-07-17 | 1980 | 7 | Rothamsted | 16.7
1980-07-18 | 1980 | 7 | Rothamsted | 19.3
1980-07-19 | 1980 | 7 | Rothamsted | 16.2
1980-07-20 | 1980 | 7 | Rothamsted | 18
1980-07-21 | 1980 | 7 | Rothamsted | 21.2
1980-07-22 | 1980 | 7 | Rothamsted | 24
1980-07-23 | 1980 | 7 | Rothamsted | 23.2
1980-07-24 | 1980 | 7 | Rothamsted | 26
1980-07-25 | 1980 | 7 | Rothamsted | 22.4
1980-07-26 | 1980 | 7 | Rothamsted | 21.4
1980-07-27 | 1980 | 7 | Rothamsted | 24.3
1980-07-28 | 1980 | 7 | Rothamsted | 25.4
1980-07-29 | 1980 | 7 | Rothamsted | 20.6
1980-07-30 | 1980 | 7 | Rothamsted | 21.6
1980-07-31 | 1980 | 7 | Rothamsted | 22
1980-08-01 | 1980 | 8 | Rothamsted | 23.9
1980-08-02 | 1980 | 8 | Rothamsted | 22.9
1980-08-03 | 1980 | 8 | Rothamsted | 20.6
1980-08-04 | 1980 | 8 | Rothamsted | 18.8
1980-08-05 | 1980 | 8 | Rothamsted | 20.7
1980-08-06 | 1980 | 8 | Rothamsted | 23.6
1980-08-08 | 1980 | 8 | Rothamsted | 21
1980-08-09 | 1980 | 8 | Rothamsted | 23.4
1980-08-10 | 1980 | 8 | Rothamsted | 17.5
1980-08-11 | 1980 | 8 | Rothamsted | 19.5
1980-08-12 | 1980 | 8 | Rothamsted | 24.5
1980-08-13 | 1980 | 8 | Rothamsted | 23.5
1980-08-14 | 1980 | 8 | Rothamsted | 22.5
1980-08-15 | 1980 | 8 | Rothamsted | 22.9
1980-08-16 | 1980 | 8 | Rothamsted | 21.7
1980-08-17 | 1980 | 8 | Rothamsted | 21
1980-08-18 | 1980 | 8 | Rothamsted | 20.4
1980-08-19 | 1980 | 8 | Rothamsted | 24
1980-08-20 | 1980 | 8 | Rothamsted | 19.4
1980-08-21 | 1980 | 8 | Rothamsted | 17.2
1980-08-22 | 1980 | 8 | Rothamsted | 16.1
1980-08-23 | 1980 | 8 | Rothamsted | 18.9
1980-08-24 | 1980 | 8 | Rothamsted | 19.8
1980-08-25 | 1980 | 8 | Rothamsted | 21
1980-08-26 | 1980 | 8 | Rothamsted | 23.4
1980-08-27 | 1980 | 8 | Rothamsted | 22.1
1980-08-29 | 1980 | 8 | Rothamsted | 18.4
1980-08-30 | 1980 | 8 | Rothamsted | 18.6
1980-08-31 | 1980 | 8 | Rothamsted | 21.7
1980-09-01 | 1980 | 9 | Rothamsted | 21.9
1980-09-02 | 1980 | 9 | Rothamsted | 23.4
1980-09-03 | 1980 | 9 | Rothamsted | 19.4
1980-09-04 | 1980 | 9 | Rothamsted | 17.5
1980-09-05 | 1980 | 9 | Rothamsted | 20.7
1980-09-06 | 1980 | 9 | Rothamsted | 22.2
1980-09-07 | 1980 | 9 | Rothamsted | 20.5
1980-09-08 | 1980 | 9 | Rothamsted | 17
1980-09-09 | 1980 | 9 | Rothamsted | 18.1
1980-09-10 | 1980 | 9 | Rothamsted | 17.1
1980-09-11 | 1980 | 9 | Rothamsted | 18.7
1980-09-12 | 1980 | 9 | Rothamsted | 17
1980-09-13 | 1980 | 9 | Rothamsted | 19.5
1980-09-14 | 1980 | 9 | Rothamsted | 18.2
1980-09-15 | 1980 | 9 | Rothamsted | 19.2
1980-09-16 | 1980 | 9 | Rothamsted | 17
1980-09-17 | 1980 | 9 | Rothamsted | 17.4
1980-09-18 | 1980 | 9 | Rothamsted | 20.5
1980-09-19 | 1980 | 9 | Rothamsted | 18.9
1980-09-20 | 1980 | 9 | Rothamsted | 17.9
1980-09-21 | 1980 | 9 | Rothamsted | 19.1
1980-09-22 | 1980 | 9 | Rothamsted | 17.8
1980-09-23 | 1980 | 9 | Rothamsted | 17.9
1980-09-24 | 1980 | 9 | Rothamsted | 18.7
1980-09-25 | 1980 | 9 | Rothamsted | 19.2
1980-09-26 | 1980 | 9 | Rothamsted | 16.2
1980-09-27 | 1980 | 9 | Rothamsted | 14.6
1980-09-28 | 1980 | 9 | Rothamsted | 15.9
1980-09-29 | 1980 | 9 | Rothamsted | 17.4
1980-09-30 | 1980 | 9 | Rothamsted | 17.6
1981-05-01 | 1981 | 5 | Rothamsted | 8.8
1981-05-02 | 1981 | 5 | Rothamsted | 7.6
1981-05-03 | 1981 | 5 | Rothamsted | 11.2
1981-05-04 | 1981 | 5 | Rothamsted | 12.6
1981-05-05 | 1981 | 5 | Rothamsted | 16.5
1981-05-06 | 1981 | 5 | Rothamsted | 17.8
1981-05-07 | 1981 | 5 | Rothamsted | 16.8
1981-05-08 | 1981 | 5 | Rothamsted | 14.8
1981-05-09 | 1981 | 5 | Rothamsted | 14
1981-05-10 | 1981 | 5 | Rothamsted | 18.7
1981-05-11 | 1981 | 5 | Rothamsted | 17.2
1981-05-12 | 1981 | 5 | Rothamsted | 17
1981-05-13 | 1981 | 5 | Rothamsted | 15.9
1981-05-14 | 1981 | 5 | Rothamsted | 18.1
1981-05-15 | 1981 | 5 | Rothamsted | 13.8
1981-05-16 | 1981 | 5 | Rothamsted | 12.6
1981-05-17 | 1981 | 5 | Rothamsted | 14.1
1981-05-18 | 1981 | 5 | Rothamsted | 17
1981-05-19 | 1981 | 5 | Rothamsted | 21.6
1981-05-21 | 1981 | 5 | Rothamsted | 15.1
1981-05-22 | 1981 | 5 | Rothamsted | 14.2
1981-05-23 | 1981 | 5 | Rothamsted | 14.4
1981-05-24 | 1981 | 5 | Rothamsted | 12.1
1981-05-25 | 1981 | 5 | Rothamsted | 14.4
1981-05-26 | 1981 | 5 | Rothamsted | 16.7
1981-05-27 | 1981 | 5 | Rothamsted | 15.9
1981-05-28 | 1981 | 5 | Rothamsted | 16.6
1981-05-29 | 1981 | 5 | Rothamsted | 18.7
1981-05-30 | 1981 | 5 | Rothamsted | 20.7
1981-05-31 | 1981 | 5 | Rothamsted | 21
1981-06-01 | 1981 | 6 | Rothamsted | 18.4
1981-06-02 | 1981 | 6 | Rothamsted | 18.7
1981-06-03 | 1981 | 6 | Rothamsted | 16
1981-06-04 | 1981 | 6 | Rothamsted | 15.9
1981-06-05 | 1981 | 6 | Rothamsted | 17
1981-06-06 | 1981 | 6 | Rothamsted | 15.8
1981-06-07 | 1981 | 6 | Rothamsted | 18
1981-06-08 | 1981 | 6 | Rothamsted | 16.4
1981-06-09 | 1981 | 6 | Rothamsted | 16.1
1981-06-10 | 1981 | 6 | Rothamsted | 17.4
1981-06-11 | 1981 | 6 | Rothamsted | 15.1
1981-06-12 | 1981 | 6 | Rothamsted | 20.9
1981-06-13 | 1981 | 6 | Rothamsted | 24.5
1981-06-14 | 1981 | 6 | Rothamsted | 19
1981-06-16 | 1981 | 6 | Rothamsted | 13.1
1981-06-17 | 1981 | 6 | Rothamsted | 15.6
1981-06-18 | 1981 | 6 | Rothamsted | 13.5
1981-06-19 | 1981 | 6 | Rothamsted | 16.6
1981-06-20 | 1981 | 6 | Rothamsted | 15.7
1981-06-21 | 1981 | 6 | Rothamsted | 21.9
1981-06-22 | 1981 | 6 | Rothamsted | 19.3
1981-06-23 | 1981 | 6 | Rothamsted | 15.7
1981-06-24 | 1981 | 6 | Rothamsted | 13.8
1981-06-25 | 1981 | 6 | Rothamsted | 11.8
1981-06-26 | 1981 | 6 | Rothamsted | 13.9
1981-06-27 | 1981 | 6 | Rothamsted | 12.6
1981-06-28 | 1981 | 6 | Rothamsted | 17.6
1981-06-29 | 1981 | 6 | Rothamsted | 20
1981-06-30 | 1981 | 6 | Rothamsted | 18.3
1981-07-01 | 1981 | 7 | Rothamsted | 17.6
1981-07-02 | 1981 | 7 | Rothamsted | 18.1
1981-07-03 | 1981 | 7 | Rothamsted | 18.5
1981-07-04 | 1981 | 7 | Rothamsted | 19.5
1981-07-05 | 1981 | 7 | Rothamsted | 20.7
1981-07-06 | 1981 | 7 | Rothamsted | 23.4
1981-07-07 | 1981 | 7 | Rothamsted | 25.4
1981-07-08 | 1981 | 7 | Rothamsted | 25.2
1981-07-09 | 1981 | 7 | Rothamsted | 19.9
1981-07-10 | 1981 | 7 | Rothamsted | 20.3
1981-07-11 | 1981 | 7 | Rothamsted | 18.1
1981-07-12 | 1981 | 7 | Rothamsted | 20.9
1981-07-13 | 1981 | 7 | Rothamsted | 19.9
1981-07-14 | 1981 | 7 | Rothamsted | 20.9
1981-07-15 | 1981 | 7 | Rothamsted | 18.9
1981-07-16 | 1981 | 7 | Rothamsted | 17.1
1981-07-17 | 1981 | 7 | Rothamsted | 18.3
1981-07-18 | 1981 | 7 | Rothamsted | 21.3
1981-07-19 | 1981 | 7 | Rothamsted | 22.6
1981-07-20 | 1981 | 7 | Rothamsted | 23.2
1981-07-22 | 1981 | 7 | Rothamsted | 16.2
1981-07-23 | 1981 | 7 | Rothamsted | 13.3
1981-07-24 | 1981 | 7 | Rothamsted | 16.9
1981-07-25 | 1981 | 7 | Rothamsted | 22.3
1981-07-26 | 1981 | 7 | Rothamsted | 23.3
1981-07-27 | 1981 | 7 | Rothamsted | 25
1981-07-28 | 1981 | 7 | Rothamsted | 21.5
1981-07-29 | 1981 | 7 | Rothamsted | 22.5
1981-07-30 | 1981 | 7 | Rothamsted | 18.2
1981-07-31 | 1981 | 7 | Rothamsted | 17.2
1981-08-01 | 1981 | 8 | Rothamsted | 20.7
1981-08-02 | 1981 | 8 | Rothamsted | 24.8
1981-08-03 | 1981 | 8 | Rothamsted | 26.1
1981-08-04 | 1981 | 8 | Rothamsted | 27.4
1981-08-06 | 1981 | 8 | Rothamsted | 16.5
1981-08-07 | 1981 | 8 | Rothamsted | 16.8
1981-08-09 | 1981 | 8 | Rothamsted | 20.4
1981-08-10 | 1981 | 8 | Rothamsted | 23.5
1981-08-11 | 1981 | 8 | Rothamsted | 25.7
1981-08-12 | 1981 | 8 | Rothamsted | 24.4
1981-08-13 | 1981 | 8 | Rothamsted | 25
1981-08-14 | 1981 | 8 | Rothamsted | 24.5
1981-08-16 | 1981 | 8 | Rothamsted | 22.2
1981-08-17 | 1981 | 8 | Rothamsted | 22.5
1981-08-18 | 1981 | 8 | Rothamsted | 19.1
1981-08-19 | 1981 | 8 | Rothamsted | 18
1981-08-20 | 1981 | 8 | Rothamsted | 19.1
1981-08-21 | 1981 | 8 | Rothamsted | 20.1
1981-08-22 | 1981 | 8 | Rothamsted | 19.7
1981-08-23 | 1981 | 8 | Rothamsted | 22.8
1981-08-24 | 1981 | 8 | Rothamsted | 23.1
1981-08-25 | 1981 | 8 | Rothamsted | 25.2
1981-08-26 | 1981 | 8 | Rothamsted | 27.1
1981-08-27 | 1981 | 8 | Rothamsted | 22.6
1981-08-28 | 1981 | 8 | Rothamsted | 21.8
1981-08-29 | 1981 | 8 | Rothamsted | 21.6
1981-08-30 | 1981 | 8 | Rothamsted | 20.3
1981-08-31 | 1981 | 8 | Rothamsted | 18.1
1981-09-01 | 1981 | 9 | Rothamsted | 20.2
1981-09-02 | 1981 | 9 | Rothamsted | 20.4
1981-09-03 | 1981 | 9 | Rothamsted | 21.8
1981-09-04 | 1981 | 9 | Rothamsted | 23.2
1981-09-05 | 1981 | 9 | Rothamsted | 23.4
1981-09-06 | 1981 | 9 | Rothamsted | 20.8
1981-09-07 | 1981 | 9 | Rothamsted | 23.3
1981-09-08 | 1981 | 9 | Rothamsted | 22.6
1981-09-09 | 1981 | 9 | Rothamsted | 24.4
1981-09-10 | 1981 | 9 | Rothamsted | 20.9
1981-09-11 | 1981 | 9 | Rothamsted | 17.3
1981-09-12 | 1981 | 9 | Rothamsted | 17
1981-09-13 | 1981 | 9 | Rothamsted | 18.1
1981-09-14 | 1981 | 9 | Rothamsted | 21.1
1981-09-15 | 1981 | 9 | Rothamsted | 17.8
1981-09-16 | 1981 | 9 | Rothamsted | 19.6
1981-09-17 | 1981 | 9 | Rothamsted | 18.4
1981-09-18 | 1981 | 9 | Rothamsted | 17.4
1981-09-19 | 1981 | 9 | Rothamsted | 16.1
1981-09-20 | 1981 | 9 | Rothamsted | 18.4
1981-09-21 | 1981 | 9 | Rothamsted | 18.7
1981-09-22 | 1981 | 9 | Rothamsted | 17.3
1981-09-23 | 1981 | 9 | Rothamsted | 17.8
1981-09-24 | 1981 | 9 | Rothamsted | 16.7
1981-09-25 | 1981 | 9 | Rothamsted | 14.4
1981-09-26 | 1981 | 9 | Rothamsted | 16.5
1981-09-27 | 1981 | 9 | Rothamsted | 17
1981-09-28 | 1981 | 9 | Rothamsted | 16.7
1981-09-29 | 1981 | 9 | Rothamsted | 19.1
1981-09-30 | 1981 | 9 | Rothamsted | 18.9
1982-05-01 | 1982 | 5 | Rothamsted | 12.1
1982-05-02 | 1982 | 5 | Rothamsted | 12.4
1982-05-03 | 1982 | 5 | Rothamsted | 10.8
1982-05-04 | 1982 | 5 | Rothamsted | 10.6
1982-05-05 | 1982 | 5 | Rothamsted | 7.9
1982-05-06 | 1982 | 5 | Rothamsted | 10.3
1982-05-07 | 1982 | 5 | Rothamsted | 12.4
1982-05-08 | 1982 | 5 | Rothamsted | 14.7
1982-05-09 | 1982 | 5 | Rothamsted | 15.1
1982-05-10 | 1982 | 5 | Rothamsted | 16.5
1982-05-11 | 1982 | 5 | Rothamsted | 19.4
1982-05-12 | 1982 | 5 | Rothamsted | 20.9
1982-05-13 | 1982 | 5 | Rothamsted | 21.1
1982-05-14 | 1982 | 5 | Rothamsted | 23.6
1982-05-15 | 1982 | 5 | Rothamsted | 21.3
1982-05-16 | 1982 | 5 | Rothamsted | 17.6
1982-05-17 | 1982 | 5 | Rothamsted | 18.3
1982-05-18 | 1982 | 5 | Rothamsted | 16.7
1982-05-19 | 1982 | 5 | Rothamsted | 16.6
1982-05-20 | 1982 | 5 | Rothamsted | 17.9
1982-05-21 | 1982 | 5 | Rothamsted | 16.6
1982-05-22 | 1982 | 5 | Rothamsted | 14.4
1982-05-23 | 1982 | 5 | Rothamsted | 16.3
1982-05-24 | 1982 | 5 | Rothamsted | 18.3
1982-05-25 | 1982 | 5 | Rothamsted | 22
1982-05-26 | 1982 | 5 | Rothamsted | 15
1982-05-27 | 1982 | 5 | Rothamsted | 18.1
1982-05-28 | 1982 | 5 | Rothamsted | 22
1982-05-29 | 1982 | 5 | Rothamsted | 20.2
1982-05-30 | 1982 | 5 | Rothamsted | 24.2
1982-05-31 | 1982 | 5 | Rothamsted | 25.1
1982-06-01 | 1982 | 6 | Rothamsted | 24.8
1982-06-02 | 1982 | 6 | Rothamsted | 23.4
1982-06-03 | 1982 | 6 | Rothamsted | 26.3
1982-06-04 | 1982 | 6 | Rothamsted | 27
1982-06-05 | 1982 | 6 | Rothamsted | 24.7
1982-06-06 | 1982 | 6 | Rothamsted | 22.7
1982-06-07 | 1982 | 6 | Rothamsted | 23.8
1982-06-08 | 1982 | 6 | Rothamsted | 20.7
1982-06-09 | 1982 | 6 | Rothamsted | 17.6
1982-06-10 | 1982 | 6 | Rothamsted | 17.3
1982-06-11 | 1982 | 6 | Rothamsted | 16.7
1982-06-12 | 1982 | 6 | Rothamsted | 14.3
1982-06-13 | 1982 | 6 | Rothamsted | 15.8
1982-06-14 | 1982 | 6 | Rothamsted | 16.2
1982-06-15 | 1982 | 6 | Rothamsted | 19.8
1982-06-16 | 1982 | 6 | Rothamsted | 19.8
1982-06-17 | 1982 | 6 | Rothamsted | 17.6
1982-06-18 | 1982 | 6 | Rothamsted | 17.7
1982-06-19 | 1982 | 6 | Rothamsted | 21.1
1982-06-20 | 1982 | 6 | Rothamsted | 16.6
1982-06-21 | 1982 | 6 | Rothamsted | 18.6
1982-06-22 | 1982 | 6 | Rothamsted | 17.2
1982-06-23 | 1982 | 6 | Rothamsted | 20
1982-06-24 | 1982 | 6 | Rothamsted | 16.9
1982-06-25 | 1982 | 6 | Rothamsted | 16
1982-06-26 | 1982 | 6 | Rothamsted | 19.5
1982-06-27 | 1982 | 6 | Rothamsted | 18.5
1982-06-28 | 1982 | 6 | Rothamsted | 18.5
1982-06-29 | 1982 | 6 | Rothamsted | 20.1
1982-06-30 | 1982 | 6 | Rothamsted | 17.7
1982-07-01 | 1982 | 7 | Rothamsted | 19.9
1982-07-02 | 1982 | 7 | Rothamsted | 19.3
1982-07-03 | 1982 | 7 | Rothamsted | 17.1
1982-07-04 | 1982 | 7 | Rothamsted | 21
1982-07-05 | 1982 | 7 | Rothamsted | 21.7
1982-07-06 | 1982 | 7 | Rothamsted | 23.8
1982-07-07 | 1982 | 7 | Rothamsted | 26.9
1982-07-08 | 1982 | 7 | Rothamsted | 27.1
1982-07-09 | 1982 | 7 | Rothamsted | 22.7
1982-07-10 | 1982 | 7 | Rothamsted | 25.6
1982-07-12 | 1982 | 7 | Rothamsted | 25.2
1982-07-13 | 1982 | 7 | Rothamsted | 20.9
1982-07-14 | 1982 | 7 | Rothamsted | 21.2
1982-07-15 | 1982 | 7 | Rothamsted | 19
1982-07-16 | 1982 | 7 | Rothamsted | 22.5
1982-07-17 | 1982 | 7 | Rothamsted | 22.7
1982-07-18 | 1982 | 7 | Rothamsted | 22.6
1982-07-19 | 1982 | 7 | Rothamsted | 21
1982-07-20 | 1982 | 7 | Rothamsted | 18.5
1982-07-21 | 1982 | 7 | Rothamsted | 18.5
1982-07-22 | 1982 | 7 | Rothamsted | 16.5
1982-07-23 | 1982 | 7 | Rothamsted | 18.4
1982-07-24 | 1982 | 7 | Rothamsted | 23.4
1982-07-25 | 1982 | 7 | Rothamsted | 20.4
1982-07-26 | 1982 | 7 | Rothamsted | 16.8
1982-07-27 | 1982 | 7 | Rothamsted | 21.3
1982-07-28 | 1982 | 7 | Rothamsted | 23.4
1982-07-29 | 1982 | 7 | Rothamsted | 26.4
1982-07-30 | 1982 | 7 | Rothamsted | 25.1
1982-07-31 | 1982 | 7 | Rothamsted | 25.3
1982-08-01 | 1982 | 8 | Rothamsted | 25.2
1982-08-02 | 1982 | 8 | Rothamsted | 27.7
1982-08-03 | 1982 | 8 | Rothamsted | 25.1
1982-08-04 | 1982 | 8 | Rothamsted | 21.6
1982-08-05 | 1982 | 8 | Rothamsted | 24.2
1982-08-06 | 1982 | 8 | Rothamsted | 19
1982-08-07 | 1982 | 8 | Rothamsted | 24.6
1982-08-08 | 1982 | 8 | Rothamsted | 23.7
1982-08-09 | 1982 | 8 | Rothamsted | 23.6
1982-08-10 | 1982 | 8 | Rothamsted | 24
1982-08-11 | 1982 | 8 | Rothamsted | 22.4
1982-08-12 | 1982 | 8 | Rothamsted | 19.7
1982-08-13 | 1982 | 8 | Rothamsted | 19.5
1982-08-14 | 1982 | 8 | Rothamsted | 22.2
1982-08-15 | 1982 | 8 | Rothamsted | 19.7
1982-08-16 | 1982 | 8 | Rothamsted | 19
1982-08-17 | 1982 | 8 | Rothamsted | 18
1982-08-18 | 1982 | 8 | Rothamsted | 18.2
1982-08-19 | 1982 | 8 | Rothamsted | 17
1982-08-20 | 1982 | 8 | Rothamsted | 19.5
1982-08-21 | 1982 | 8 | Rothamsted | 19.6
1982-08-22 | 1982 | 8 | Rothamsted | 18.1
1982-08-23 | 1982 | 8 | Rothamsted | 15.8
1982-08-24 | 1982 | 8 | Rothamsted | 17.1
1982-08-25 | 1982 | 8 | Rothamsted | 18.5
1982-08-26 | 1982 | 8 | Rothamsted | 18.1
1982-08-27 | 1982 | 8 | Rothamsted | 19.7
1982-08-28 | 1982 | 8 | Rothamsted | 21.1
1982-08-29 | 1982 | 8 | Rothamsted | 19.4
1982-08-31 | 1982 | 8 | Rothamsted | 17.3
1982-09-01 | 1982 | 9 | Rothamsted | 19.6
1982-09-02 | 1982 | 9 | Rothamsted | 21.9
1982-09-03 | 1982 | 9 | Rothamsted | 22
1982-09-04 | 1982 | 9 | Rothamsted | 22.8
1982-09-06 | 1982 | 9 | Rothamsted | 21.1
1982-09-07 | 1982 | 9 | Rothamsted | 18.4
1982-09-08 | 1982 | 9 | Rothamsted | 21.5
1982-09-09 | 1982 | 9 | Rothamsted | 22.8
1982-09-10 | 1982 | 9 | Rothamsted | 19.4
1982-09-11 | 1982 | 9 | Rothamsted | 21.1
1982-09-12 | 1982 | 9 | Rothamsted | 20.7
1982-09-13 | 1982 | 9 | Rothamsted | 21
1982-09-14 | 1982 | 9 | Rothamsted | 24.6
1982-09-15 | 1982 | 9 | Rothamsted | 24.4
1982-09-16 | 1982 | 9 | Rothamsted | 23.7
1982-09-17 | 1982 | 9 | Rothamsted | 26.4
1982-09-19 | 1982 | 9 | Rothamsted | 19.4
1982-09-21 | 1982 | 9 | Rothamsted | 15
1982-09-22 | 1982 | 9 | Rothamsted | 17
1982-09-23 | 1982 | 9 | Rothamsted | 16.6
1982-09-24 | 1982 | 9 | Rothamsted | 19
1982-09-25 | 1982 | 9 | Rothamsted | 16.3
1982-09-26 | 1982 | 9 | Rothamsted | 14.7
1982-09-27 | 1982 | 9 | Rothamsted | 16.5
1982-09-29 | 1982 | 9 | Rothamsted | 17.1
1982-09-30 | 1982 | 9 | Rothamsted | 17.1
1983-05-02 | 1983 | 5 | Rothamsted | 11
1983-05-03 | 1983 | 5 | Rothamsted | 13.3
1983-05-04 | 1983 | 5 | Rothamsted | 16.7
1983-05-05 | 1983 | 5 | Rothamsted | 16.9
1983-05-06 | 1983 | 5 | Rothamsted | 15.4
1983-05-07 | 1983 | 5 | Rothamsted | 14.2
1983-05-08 | 1983 | 5 | Rothamsted | 13.2
1983-05-09 | 1983 | 5 | Rothamsted | 12.3
1983-05-10 | 1983 | 5 | Rothamsted | 12.5
1983-05-11 | 1983 | 5 | Rothamsted | 12.8
1983-05-12 | 1983 | 5 | Rothamsted | 14.4
1983-05-13 | 1983 | 5 | Rothamsted | 15.6
1983-05-14 | 1983 | 5 | Rothamsted | 14.4
1983-05-15 | 1983 | 5 | Rothamsted | 16.6
1983-05-16 | 1983 | 5 | Rothamsted | 13.4
1983-05-17 | 1983 | 5 | Rothamsted | 13.4
1983-05-18 | 1983 | 5 | Rothamsted | 13.5
1983-05-19 | 1983 | 5 | Rothamsted | 12.9
1983-05-20 | 1983 | 5 | Rothamsted | 13.7
1983-05-21 | 1983 | 5 | Rothamsted | 14.4
1983-05-22 | 1983 | 5 | Rothamsted | 14.5
1983-05-23 | 1983 | 5 | Rothamsted | 15.4
1983-05-24 | 1983 | 5 | Rothamsted | 17
1983-05-25 | 1983 | 5 | Rothamsted | 12.6
1983-05-26 | 1983 | 5 | Rothamsted | 13.1
1983-05-27 | 1983 | 5 | Rothamsted | 9.6
1983-05-28 | 1983 | 5 | Rothamsted | 13.5
1983-05-29 | 1983 | 5 | Rothamsted | 16.4
1983-05-30 | 1983 | 5 | Rothamsted | 20.4
1983-05-31 | 1983 | 5 | Rothamsted | 20.1
1983-06-01 | 1983 | 6 | Rothamsted | 16.7
1983-06-02 | 1983 | 6 | Rothamsted | 18
1983-06-03 | 1983 | 6 | Rothamsted | 20
1983-06-04 | 1983 | 6 | Rothamsted | 19.4
1983-06-05 | 1983 | 6 | Rothamsted | 19.1
1983-06-06 | 1983 | 6 | Rothamsted | 22.4
1983-06-07 | 1983 | 6 | Rothamsted | 23.3
1983-06-08 | 1983 | 6 | Rothamsted | 18.9
1983-06-09 | 1983 | 6 | Rothamsted | 18.9
1983-06-10 | 1983 | 6 | Rothamsted | 18.1
1983-06-11 | 1983 | 6 | Rothamsted | 18
1983-06-12 | 1983 | 6 | Rothamsted | 17.1
1983-06-13 | 1983 | 6 | Rothamsted | 16.6
1983-06-14 | 1983 | 6 | Rothamsted | 15.5
1983-06-15 | 1983 | 6 | Rothamsted | 16
1983-06-16 | 1983 | 6 | Rothamsted | 16.6
1983-06-17 | 1983 | 6 | Rothamsted | 19
1983-06-18 | 1983 | 6 | Rothamsted | 21.2
1983-06-19 | 1983 | 6 | Rothamsted | 23
1983-06-20 | 1983 | 6 | Rothamsted | 21.1
1983-06-21 | 1983 | 6 | Rothamsted | 20.2
1983-06-22 | 1983 | 6 | Rothamsted | 19.6
1983-06-24 | 1983 | 6 | Rothamsted | 20.6
1983-06-25 | 1983 | 6 | Rothamsted | 22.1
1983-06-27 | 1983 | 6 | Rothamsted | 18.8
1983-06-28 | 1983 | 6 | Rothamsted | 20.2
1983-06-29 | 1983 | 6 | Rothamsted | 16.6
1983-06-30 | 1983 | 6 | Rothamsted | 19.8
1983-07-01 | 1983 | 7 | Rothamsted | 22.5
1983-07-02 | 1983 | 7 | Rothamsted | 24.1
1983-07-03 | 1983 | 7 | Rothamsted | 25.7
1983-07-04 | 1983 | 7 | Rothamsted | 26.1
1983-07-05 | 1983 | 7 | Rothamsted | 24.9
1983-07-06 | 1983 | 7 | Rothamsted | 23.7
1983-07-07 | 1983 | 7 | Rothamsted | 25.5
1983-07-08 | 1983 | 7 | Rothamsted | 25.4
1983-07-09 | 1983 | 7 | Rothamsted | 24.2
1983-07-10 | 1983 | 7 | Rothamsted | 28.5
1983-07-11 | 1983 | 7 | Rothamsted | 27.2
1983-07-12 | 1983 | 7 | Rothamsted | 28.1
1983-07-13 | 1983 | 7 | Rothamsted | 29.5
1983-07-14 | 1983 | 7 | Rothamsted | 30.7
1983-07-15 | 1983 | 7 | Rothamsted | 30.8
1983-07-16 | 1983 | 7 | Rothamsted | 28.5
1983-07-17 | 1983 | 7 | Rothamsted | 25.7
1983-07-18 | 1983 | 7 | Rothamsted | 23.2
1983-07-20 | 1983 | 7 | Rothamsted | 22.6
1983-07-21 | 1983 | 7 | Rothamsted | 26.5
1983-07-22 | 1983 | 7 | Rothamsted | 22.5
1983-07-23 | 1983 | 7 | Rothamsted | 21.8
1983-07-24 | 1983 | 7 | Rothamsted | 24.2
1983-07-25 | 1983 | 7 | Rothamsted | 26.4
1983-07-26 | 1983 | 7 | Rothamsted | 24.4
1983-07-27 | 1983 | 7 | Rothamsted | 24.6
1983-07-28 | 1983 | 7 | Rothamsted | 29.5
1983-07-29 | 1983 | 7 | Rothamsted | 28.8
1983-07-30 | 1983 | 7 | Rothamsted | 28.7
1983-08-02 | 1983 | 8 | Rothamsted | 21.5
1983-08-03 | 1983 | 8 | Rothamsted | 22.8
1983-08-04 | 1983 | 8 | Rothamsted | 23.5
1983-08-05 | 1983 | 8 | Rothamsted | 19.7
1983-08-06 | 1983 | 8 | Rothamsted | 21
1983-08-07 | 1983 | 8 | Rothamsted | 24.6
1983-08-08 | 1983 | 8 | Rothamsted | 26
1983-08-09 | 1983 | 8 | Rothamsted | 22.6
1983-08-10 | 1983 | 8 | Rothamsted | 20.6
1983-08-11 | 1983 | 8 | Rothamsted | 23.7
1983-08-12 | 1983 | 8 | Rothamsted | 22.5
1983-08-13 | 1983 | 8 | Rothamsted | 28.5
1983-08-14 | 1983 | 8 | Rothamsted | 27
1983-08-15 | 1983 | 8 | Rothamsted | 24.2
1983-08-16 | 1983 | 8 | Rothamsted | 22.8
1983-08-17 | 1983 | 8 | Rothamsted | 25.5
1983-08-18 | 1983 | 8 | Rothamsted | 28.1
1983-08-19 | 1983 | 8 | Rothamsted | 23
1983-08-20 | 1983 | 8 | Rothamsted | 23.5
1983-08-21 | 1983 | 8 | Rothamsted | 24.2
1983-08-22 | 1983 | 8 | Rothamsted | 25
1983-08-23 | 1983 | 8 | Rothamsted | 20.1
1983-08-24 | 1983 | 8 | Rothamsted | 24
1983-08-25 | 1983 | 8 | Rothamsted | 25.2
1983-08-26 | 1983 | 8 | Rothamsted | 24.8
1983-08-27 | 1983 | 8 | Rothamsted | 19.1
1983-08-28 | 1983 | 8 | Rothamsted | 18.4
1983-08-29 | 1983 | 8 | Rothamsted | 20.8
1983-08-30 | 1983 | 8 | Rothamsted | 25.6
1983-08-31 | 1983 | 8 | Rothamsted | 19.9
1983-09-02 | 1983 | 9 | Rothamsted | 16.7
1983-09-03 | 1983 | 9 | Rothamsted | 21.2
1983-09-04 | 1983 | 9 | Rothamsted | 20.1
1983-09-05 | 1983 | 9 | Rothamsted | 18.4
1983-09-06 | 1983 | 9 | Rothamsted | 20.4
1983-09-07 | 1983 | 9 | Rothamsted | 17.8
1983-09-08 | 1983 | 9 | Rothamsted | 17.4
1983-09-09 | 1983 | 9 | Rothamsted | 15.9
1983-09-11 | 1983 | 9 | Rothamsted | 13.1
1983-09-12 | 1983 | 9 | Rothamsted | 14.4
1983-09-13 | 1983 | 9 | Rothamsted | 18.5
1983-09-14 | 1983 | 9 | Rothamsted | 17.2
1983-09-15 | 1983 | 9 | Rothamsted | 16
1983-09-16 | 1983 | 9 | Rothamsted | 16.6
1983-09-17 | 1983 | 9 | Rothamsted | 16.5
1983-09-18 | 1983 | 9 | Rothamsted | 16
1983-09-19 | 1983 | 9 | Rothamsted | 15.1
1983-09-20 | 1983 | 9 | Rothamsted | 12.1
1983-09-21 | 1983 | 9 | Rothamsted | 16.6
1983-09-22 | 1983 | 9 | Rothamsted | 20.8
1983-09-23 | 1983 | 9 | Rothamsted | 20.2
1983-09-24 | 1983 | 9 | Rothamsted | 19.1
1983-09-25 | 1983 | 9 | Rothamsted | 23.9
1983-09-26 | 1983 | 9 | Rothamsted | 18.4
1983-09-28 | 1983 | 9 | Rothamsted | 17.6
1983-09-29 | 1983 | 9 | Rothamsted | 15.5
1983-09-30 | 1983 | 9 | Rothamsted | 15.7
1984-05-01 | 1984 | 5 | Rothamsted | 15.5
1984-05-02 | 1984 | 5 | Rothamsted | 11.2
1984-05-03 | 1984 | 5 | Rothamsted | 15
1984-05-04 | 1984 | 5 | Rothamsted | 11.7
1984-05-05 | 1984 | 5 | Rothamsted | 11.7
1984-05-06 | 1984 | 5 | Rothamsted | 10.4
1984-05-07 | 1984 | 5 | Rothamsted | 10.1
1984-05-08 | 1984 | 5 | Rothamsted | 14.5
1984-05-09 | 1984 | 5 | Rothamsted | 12.7
1984-05-10 | 1984 | 5 | Rothamsted | 12.2
1984-05-11 | 1984 | 5 | Rothamsted | 12.9
1984-05-12 | 1984 | 5 | Rothamsted | 15
1984-05-13 | 1984 | 5 | Rothamsted | 15
1984-05-14 | 1984 | 5 | Rothamsted | 12.5
1984-05-15 | 1984 | 5 | Rothamsted | 15.9
1984-05-16 | 1984 | 5 | Rothamsted | 10.6
1984-05-18 | 1984 | 5 | Rothamsted | 15.6
1984-05-19 | 1984 | 5 | Rothamsted | 11
1984-05-20 | 1984 | 5 | Rothamsted | 12.4
1984-05-21 | 1984 | 5 | Rothamsted | 12.6
1984-05-22 | 1984 | 5 | Rothamsted | 16.4
1984-05-23 | 1984 | 5 | Rothamsted | 20.5
1984-05-27 | 1984 | 5 | Rothamsted | 9.4
1984-05-28 | 1984 | 5 | Rothamsted | 14.6
1984-05-29 | 1984 | 5 | Rothamsted | 18.7
1984-05-30 | 1984 | 5 | Rothamsted | 18
1984-05-31 | 1984 | 5 | Rothamsted | 12.8
1984-06-01 | 1984 | 6 | Rothamsted | 16.1
1984-06-02 | 1984 | 6 | Rothamsted | 15.5
1984-06-03 | 1984 | 6 | Rothamsted | 16
1984-06-04 | 1984 | 6 | Rothamsted | 14.3
1984-06-05 | 1984 | 6 | Rothamsted | 17.5
1984-06-06 | 1984 | 6 | Rothamsted | 19.8
1984-06-07 | 1984 | 6 | Rothamsted | 18.4
1984-06-08 | 1984 | 6 | Rothamsted | 20.8
1984-06-09 | 1984 | 6 | Rothamsted | 23.1
1984-06-10 | 1984 | 6 | Rothamsted | 15.1
1984-06-11 | 1984 | 6 | Rothamsted | 18.3
1984-06-12 | 1984 | 6 | Rothamsted | 19.1
1984-06-13 | 1984 | 6 | Rothamsted | 20.9
1984-06-14 | 1984 | 6 | Rothamsted | 22.4
1984-06-15 | 1984 | 6 | Rothamsted | 22.5
1984-06-16 | 1984 | 6 | Rothamsted | 23.6
1984-06-17 | 1984 | 6 | Rothamsted | 24.6
1984-06-18 | 1984 | 6 | Rothamsted | 25
1984-06-19 | 1984 | 6 | Rothamsted | 25.6
1984-06-21 | 1984 | 6 | Rothamsted | 19.8
1984-06-22 | 1984 | 6 | Rothamsted | 17.5
1984-06-23 | 1984 | 6 | Rothamsted | 19.3
1984-06-24 | 1984 | 6 | Rothamsted | 20.4
1984-06-25 | 1984 | 6 | Rothamsted | 23.4
1984-06-26 | 1984 | 6 | Rothamsted | 21.6
1984-06-28 | 1984 | 6 | Rothamsted | 16.4
1984-06-29 | 1984 | 6 | Rothamsted | 16.8
1984-06-30 | 1984 | 6 | Rothamsted | 21.6
1984-07-01 | 1984 | 7 | Rothamsted | 16.2
1984-07-02 | 1984 | 7 | Rothamsted | 19.5
1984-07-03 | 1984 | 7 | Rothamsted | 20.1
1984-07-04 | 1984 | 7 | Rothamsted | 24.5
1984-07-05 | 1984 | 7 | Rothamsted | 26.2
1984-07-06 | 1984 | 7 | Rothamsted | 26.6
1984-07-07 | 1984 | 7 | Rothamsted | 29.4
1984-07-08 | 1984 | 7 | Rothamsted | 21.8
1984-07-09 | 1984 | 7 | Rothamsted | 22.7
1984-07-10 | 1984 | 7 | Rothamsted | 22
1984-07-11 | 1984 | 7 | Rothamsted | 18.8
1984-07-12 | 1984 | 7 | Rothamsted | 20.3
1984-07-13 | 1984 | 7 | Rothamsted | 19.1
1984-07-14 | 1984 | 7 | Rothamsted | 17.8
1984-07-15 | 1984 | 7 | Rothamsted | 20
1984-07-16 | 1984 | 7 | Rothamsted | 21.7
1984-07-17 | 1984 | 7 | Rothamsted | 22.1
1984-07-18 | 1984 | 7 | Rothamsted | 19.9
1984-07-19 | 1984 | 7 | Rothamsted | 19.4
1984-07-20 | 1984 | 7 | Rothamsted | 25.5
1984-07-21 | 1984 | 7 | Rothamsted | 23.8
1984-07-22 | 1984 | 7 | Rothamsted | 23.7
1984-07-23 | 1984 | 7 | Rothamsted | 22.9
1984-07-24 | 1984 | 7 | Rothamsted | 19.6
1984-07-25 | 1984 | 7 | Rothamsted | 21.6
1984-07-26 | 1984 | 7 | Rothamsted | 28.2
1984-07-27 | 1984 | 7 | Rothamsted | 29.5
1984-07-28 | 1984 | 7 | Rothamsted | 26.7
1984-07-29 | 1984 | 7 | Rothamsted | 27.1
1984-07-30 | 1984 | 7 | Rothamsted | 23.4
1984-07-31 | 1984 | 7 | Rothamsted | 24
1984-08-01 | 1984 | 8 | Rothamsted | 21.3
1984-08-02 | 1984 | 8 | Rothamsted | 21.6
1984-08-03 | 1984 | 8 | Rothamsted | 18.7
1984-08-04 | 1984 | 8 | Rothamsted | 18.5
1984-08-05 | 1984 | 8 | Rothamsted | 22.4
1984-08-06 | 1984 | 8 | Rothamsted | 17.2
1984-08-07 | 1984 | 8 | Rothamsted | 19.5
1984-08-08 | 1984 | 8 | Rothamsted | 22.1
1984-08-09 | 1984 | 8 | Rothamsted | 18.6
1984-08-10 | 1984 | 8 | Rothamsted | 21.5
1984-08-11 | 1984 | 8 | Rothamsted | 22.3
1984-08-12 | 1984 | 8 | Rothamsted | 23.4
1984-08-13 | 1984 | 8 | Rothamsted | 24.7
1984-08-14 | 1984 | 8 | Rothamsted | 23.3
1984-08-15 | 1984 | 8 | Rothamsted | 21.9
1984-08-16 | 1984 | 8 | Rothamsted | 22.9
1984-08-17 | 1984 | 8 | Rothamsted | 25
1984-08-18 | 1984 | 8 | Rothamsted | 27.1
1984-08-19 | 1984 | 8 | Rothamsted | 27.9
1984-08-20 | 1984 | 8 | Rothamsted | 27.3
1984-08-21 | 1984 | 8 | Rothamsted | 25.7
1984-08-22 | 1984 | 8 | Rothamsted | 24.7
1984-08-23 | 1984 | 8 | Rothamsted | 23.6
1984-08-24 | 1984 | 8 | Rothamsted | 22.2
1984-08-25 | 1984 | 8 | Rothamsted | 24.3
1984-08-26 | 1984 | 8 | Rothamsted | 25
1984-08-27 | 1984 | 8 | Rothamsted | 25.2
1984-08-28 | 1984 | 8 | Rothamsted | 25.5
1984-08-29 | 1984 | 8 | Rothamsted | 24.9
1984-08-30 | 1984 | 8 | Rothamsted | 24.1
1984-08-31 | 1984 | 8 | Rothamsted | 23.9
1984-09-01 | 1984 | 9 | Rothamsted | 24.3
1984-09-02 | 1984 | 9 | Rothamsted | 23
1984-09-04 | 1984 | 9 | Rothamsted | 14.4
1984-09-05 | 1984 | 9 | Rothamsted | 16.2
1984-09-06 | 1984 | 9 | Rothamsted | 15.5
1984-09-07 | 1984 | 9 | Rothamsted | 18.5
1984-09-08 | 1984 | 9 | Rothamsted | 18.8
1984-09-10 | 1984 | 9 | Rothamsted | 20.4
1984-09-11 | 1984 | 9 | Rothamsted | 20.7
1984-09-12 | 1984 | 9 | Rothamsted | 19.3
1984-09-13 | 1984 | 9 | Rothamsted | 17.5
1984-09-15 | 1984 | 9 | Rothamsted | 16.9
1984-09-16 | 1984 | 9 | Rothamsted | 15.1
1984-09-17 | 1984 | 9 | Rothamsted | 15.5
1984-09-18 | 1984 | 9 | Rothamsted | 16
1984-09-19 | 1984 | 9 | Rothamsted | 14.9
1984-09-20 | 1984 | 9 | Rothamsted | 13.1
1984-09-21 | 1984 | 9 | Rothamsted | 15.2
1984-09-23 | 1984 | 9 | Rothamsted | 12.6
1984-09-24 | 1984 | 9 | Rothamsted | 14.1
1984-09-25 | 1984 | 9 | Rothamsted | 15.6
1984-09-26 | 1984 | 9 | Rothamsted | 16.5
1984-09-27 | 1984 | 9 | Rothamsted | 19.6
1984-09-28 | 1984 | 9 | Rothamsted | 17.5
1984-09-29 | 1984 | 9 | Rothamsted | 15.2
1984-09-30 | 1984 | 9 | Rothamsted | 15.6
1985-05-01 | 1985 | 5 | Rothamsted | 11.3
1985-05-02 | 1985 | 5 | Rothamsted | 8.1
1985-05-03 | 1985 | 5 | Rothamsted | 11.7
1985-05-04 | 1985 | 5 | Rothamsted | 11.1
1985-05-05 | 1985 | 5 | Rothamsted | 16
1985-05-06 | 1985 | 5 | Rothamsted | 15.8
1985-05-07 | 1985 | 5 | Rothamsted | 13.3
1985-05-08 | 1985 | 5 | Rothamsted | 13.8
1985-05-09 | 1985 | 5 | Rothamsted | 10.6
1985-05-10 | 1985 | 5 | Rothamsted | 7.6
1985-05-11 | 1985 | 5 | Rothamsted | 11.2
1985-05-12 | 1985 | 5 | Rothamsted | 11.7
1985-05-13 | 1985 | 5 | Rothamsted | 10.7
1985-05-14 | 1985 | 5 | Rothamsted | 15.2
1985-05-15 | 1985 | 5 | Rothamsted | 18.5
1985-05-16 | 1985 | 5 | Rothamsted | 19
1985-05-17 | 1985 | 5 | Rothamsted | 19.5
1985-05-19 | 1985 | 5 | Rothamsted | 17.2
1985-05-20 | 1985 | 5 | Rothamsted | 15.4
1985-05-21 | 1985 | 5 | Rothamsted | 12.5
1985-05-22 | 1985 | 5 | Rothamsted | 15.2
1985-05-23 | 1985 | 5 | Rothamsted | 16
1985-05-24 | 1985 | 5 | Rothamsted | 19
1985-05-25 | 1985 | 5 | Rothamsted | 19.8
1985-05-26 | 1985 | 5 | Rothamsted | 17
1985-05-27 | 1985 | 5 | Rothamsted | 17.2
1985-05-28 | 1985 | 5 | Rothamsted | 17
1985-05-29 | 1985 | 5 | Rothamsted | 17.4
1985-05-30 | 1985 | 5 | Rothamsted | 17.6
1985-05-31 | 1985 | 5 | Rothamsted | 20.4
1985-06-01 | 1985 | 6 | Rothamsted | 21.5
1985-06-02 | 1985 | 6 | Rothamsted | 23.1
1985-06-03 | 1985 | 6 | Rothamsted | 21.9
1985-06-04 | 1985 | 6 | Rothamsted | 19.7
1985-06-06 | 1985 | 6 | Rothamsted | 11.4
1985-06-07 | 1985 | 6 | Rothamsted | 14.1
1985-06-08 | 1985 | 6 | Rothamsted | 15.4
1985-06-09 | 1985 | 6 | Rothamsted | 15.7
1985-06-10 | 1985 | 6 | Rothamsted | 16
1985-06-11 | 1985 | 6 | Rothamsted | 14.6
1985-06-12 | 1985 | 6 | Rothamsted | 15
1985-06-13 | 1985 | 6 | Rothamsted | 15.5
1985-06-14 | 1985 | 6 | Rothamsted | 15.9
1985-06-15 | 1985 | 6 | Rothamsted | 15.9
1985-06-16 | 1985 | 6 | Rothamsted | 17.5
1985-06-17 | 1985 | 6 | Rothamsted | 16.2
1985-06-18 | 1985 | 6 | Rothamsted | 17.1
1985-06-19 | 1985 | 6 | Rothamsted | 18.8
1985-06-21 | 1985 | 6 | Rothamsted | 15.4
1985-06-22 | 1985 | 6 | Rothamsted | 17.7
1985-06-23 | 1985 | 6 | Rothamsted | 18.4
1985-06-24 | 1985 | 6 | Rothamsted | 16.4
1985-06-25 | 1985 | 6 | Rothamsted | 16.9
1985-06-26 | 1985 | 6 | Rothamsted | 17.6
1985-06-27 | 1985 | 6 | Rothamsted | 16.8
1985-06-28 | 1985 | 6 | Rothamsted | 19.9
1985-06-29 | 1985 | 6 | Rothamsted | 20.6
1985-06-30 | 1985 | 6 | Rothamsted | 21.1
1985-07-01 | 1985 | 7 | Rothamsted | 22.2
1985-07-02 | 1985 | 7 | Rothamsted | 22.1
1985-07-03 | 1985 | 7 | Rothamsted | 24.8
1985-07-04 | 1985 | 7 | Rothamsted | 24.7
1985-07-05 | 1985 | 7 | Rothamsted | 20
1985-07-06 | 1985 | 7 | Rothamsted | 20.5
1985-07-07 | 1985 | 7 | Rothamsted | 23.4
1985-07-08 | 1985 | 7 | Rothamsted | 19.1
1985-07-09 | 1985 | 7 | Rothamsted | 20.1
1985-07-10 | 1985 | 7 | Rothamsted | 19.1
1985-07-11 | 1985 | 7 | Rothamsted | 22
1985-07-12 | 1985 | 7 | Rothamsted | 26.5
1985-07-13 | 1985 | 7 | Rothamsted | 23.7
1985-07-15 | 1985 | 7 | Rothamsted | 19.6
1985-07-16 | 1985 | 7 | Rothamsted | 19.7
1985-07-17 | 1985 | 7 | Rothamsted | 17.9
1985-07-18 | 1985 | 7 | Rothamsted | 18.1
1985-07-19 | 1985 | 7 | Rothamsted | 18
1985-07-20 | 1985 | 7 | Rothamsted | 19.5
1985-07-21 | 1985 | 7 | Rothamsted | 19.3
1985-07-22 | 1985 | 7 | Rothamsted | 23
1985-07-23 | 1985 | 7 | Rothamsted | 24.8
1985-07-24 | 1985 | 7 | Rothamsted | 26
1985-07-25 | 1985 | 7 | Rothamsted | 19.5
1985-07-26 | 1985 | 7 | Rothamsted | 21.7
1985-07-27 | 1985 | 7 | Rothamsted | 18.1
1985-07-28 | 1985 | 7 | Rothamsted | 16.5
1985-07-29 | 1985 | 7 | Rothamsted | 18.6
1985-07-30 | 1985 | 7 | Rothamsted | 22
1985-07-31 | 1985 | 7 | Rothamsted | 18.7
1985-08-01 | 1985 | 8 | Rothamsted | 15.5
1985-08-02 | 1985 | 8 | Rothamsted | 18.3
1985-08-03 | 1985 | 8 | Rothamsted | 15.9
1985-08-04 | 1985 | 8 | Rothamsted | 18.1
1985-08-05 | 1985 | 8 | Rothamsted | 18.9
1985-08-06 | 1985 | 8 | Rothamsted | 15.5
1985-08-07 | 1985 | 8 | Rothamsted | 19.5
1985-08-08 | 1985 | 8 | Rothamsted | 17.2
1985-08-09 | 1985 | 8 | Rothamsted | 18.8
1985-08-10 | 1985 | 8 | Rothamsted | 18.4
1985-08-11 | 1985 | 8 | Rothamsted | 18.6
1985-08-12 | 1985 | 8 | Rothamsted | 19.6
1985-08-13 | 1985 | 8 | Rothamsted | 19.7
1985-08-14 | 1985 | 8 | Rothamsted | 18.2
1985-08-15 | 1985 | 8 | Rothamsted | 19.1
1985-08-16 | 1985 | 8 | Rothamsted | 20.6
1985-08-17 | 1985 | 8 | Rothamsted | 19.3
1985-08-18 | 1985 | 8 | Rothamsted | 20.2
1985-08-19 | 1985 | 8 | Rothamsted | 20
1985-08-20 | 1985 | 8 | Rothamsted | 21.6
1985-08-21 | 1985 | 8 | Rothamsted | 19.2
1985-08-22 | 1985 | 8 | Rothamsted | 17.6
1985-08-23 | 1985 | 8 | Rothamsted | 17.3
1985-08-24 | 1985 | 8 | Rothamsted | 18.2
1985-08-25 | 1985 | 8 | Rothamsted | 16.6
1985-08-26 | 1985 | 8 | Rothamsted | 19.1
1985-08-27 | 1985 | 8 | Rothamsted | 22
1985-08-28 | 1985 | 8 | Rothamsted | 24.6
1985-08-29 | 1985 | 8 | Rothamsted | 24.2
1985-08-30 | 1985 | 8 | Rothamsted | 19.6
1985-08-31 | 1985 | 8 | Rothamsted | 15.5
1985-09-01 | 1985 | 9 | Rothamsted | 14.8
1985-09-02 | 1985 | 9 | Rothamsted | 16.9
1985-09-03 | 1985 | 9 | Rothamsted | 15.2
1985-09-04 | 1985 | 9 | Rothamsted | 16.6
1985-09-05 | 1985 | 9 | Rothamsted | 15.8
1985-09-06 | 1985 | 9 | Rothamsted | 18.8
1985-09-07 | 1985 | 9 | Rothamsted | 18.9
1985-09-08 | 1985 | 9 | Rothamsted | 19.5
1985-09-09 | 1985 | 9 | Rothamsted | 21
1985-09-10 | 1985 | 9 | Rothamsted | 23.8
1985-09-11 | 1985 | 9 | Rothamsted | 24.7
1985-09-12 | 1985 | 9 | Rothamsted | 17.1
1985-09-13 | 1985 | 9 | Rothamsted | 14.9
1985-09-14 | 1985 | 9 | Rothamsted | 16.7
1985-09-15 | 1985 | 9 | Rothamsted | 17.9
1985-09-16 | 1985 | 9 | Rothamsted | 19.8
1985-09-17 | 1985 | 9 | Rothamsted | 21
1985-09-18 | 1985 | 9 | Rothamsted | 19.5
1985-09-19 | 1985 | 9 | Rothamsted | 16.9
1985-09-20 | 1985 | 9 | Rothamsted | 18.5
1985-09-21 | 1985 | 9 | Rothamsted | 20
1985-09-22 | 1985 | 9 | Rothamsted | 19.3
1985-09-23 | 1985 | 9 | Rothamsted | 17.2
1985-09-24 | 1985 | 9 | Rothamsted | 18.7
1985-09-25 | 1985 | 9 | Rothamsted | 22.4
1985-09-26 | 1985 | 9 | Rothamsted | 21.9
1985-09-27 | 1985 | 9 | Rothamsted | 20.3
1985-09-28 | 1985 | 9 | Rothamsted | 22.7
1985-09-29 | 1985 | 9 | Rothamsted | 23
1985-09-30 | 1985 | 9 | Rothamsted | 26.4
1986-05-01 | 1986 | 5 | Rothamsted | 21.1
1986-05-02 | 1986 | 5 | Rothamsted | 13.3
1986-05-03 | 1986 | 5 | Rothamsted | 13.8
1986-05-04 | 1986 | 5 | Rothamsted | 13.2
1986-05-05 | 1986 | 5 | Rothamsted | 15.6
1986-05-06 | 1986 | 5 | Rothamsted | 11.8
1986-05-07 | 1986 | 5 | Rothamsted | 14.8
1986-05-08 | 1986 | 5 | Rothamsted | 15.6
1986-05-09 | 1986 | 5 | Rothamsted | 17.2
1986-05-10 | 1986 | 5 | Rothamsted | 14.8
1986-05-11 | 1986 | 5 | Rothamsted | 14.2
1986-05-12 | 1986 | 5 | Rothamsted | 14.5
1986-05-13 | 1986 | 5 | Rothamsted | 14.7
1986-05-14 | 1986 | 5 | Rothamsted | 13.4
1986-05-15 | 1986 | 5 | Rothamsted | 15.4
1986-05-16 | 1986 | 5 | Rothamsted | 14.3
1986-05-17 | 1986 | 5 | Rothamsted | 15.5
1986-05-18 | 1986 | 5 | Rothamsted | 19.4
1986-05-19 | 1986 | 5 | Rothamsted | 17.7
1986-05-21 | 1986 | 5 | Rothamsted | 15.4
1986-05-22 | 1986 | 5 | Rothamsted | 15.1
1986-05-23 | 1986 | 5 | Rothamsted | 15.3
1986-05-24 | 1986 | 5 | Rothamsted | 17
1986-05-25 | 1986 | 5 | Rothamsted | 17.1
1986-05-26 | 1986 | 5 | Rothamsted | 14.9
1986-05-27 | 1986 | 5 | Rothamsted | 13.8
1986-05-28 | 1986 | 5 | Rothamsted | 13.9
1986-05-29 | 1986 | 5 | Rothamsted | 13.9
1986-05-30 | 1986 | 5 | Rothamsted | 12.1
1986-05-31 | 1986 | 5 | Rothamsted | 16.5
1986-06-01 | 1986 | 6 | Rothamsted | 18.1
1986-06-02 | 1986 | 6 | Rothamsted | 15.3
1986-06-03 | 1986 | 6 | Rothamsted | 12.9
1986-06-04 | 1986 | 6 | Rothamsted | 12.5
1986-06-05 | 1986 | 6 | Rothamsted | 13.4
1986-06-06 | 1986 | 6 | Rothamsted | 16.2
1986-06-07 | 1986 | 6 | Rothamsted | 16.4
1986-06-08 | 1986 | 6 | Rothamsted | 16.1
1986-06-09 | 1986 | 6 | Rothamsted | 16
1986-06-10 | 1986 | 6 | Rothamsted | 14.1
1986-06-11 | 1986 | 6 | Rothamsted | 18.7
1986-06-12 | 1986 | 6 | Rothamsted | 22.2
1986-06-13 | 1986 | 6 | Rothamsted | 22.9
1986-06-14 | 1986 | 6 | Rothamsted | 25
1986-06-15 | 1986 | 6 | Rothamsted | 27.1
1986-06-16 | 1986 | 6 | Rothamsted | 20.6
1986-06-17 | 1986 | 6 | Rothamsted | 18.9
1986-06-18 | 1986 | 6 | Rothamsted | 20.6
1986-06-19 | 1986 | 6 | Rothamsted | 17.9
1986-06-20 | 1986 | 6 | Rothamsted | 21
1986-06-21 | 1986 | 6 | Rothamsted | 18.9
1986-06-22 | 1986 | 6 | Rothamsted | 15.9
1986-06-23 | 1986 | 6 | Rothamsted | 19.2
1986-06-24 | 1986 | 6 | Rothamsted | 23.8
1986-06-25 | 1986 | 6 | Rothamsted | 24.9
1986-06-26 | 1986 | 6 | Rothamsted | 27.4
1986-06-27 | 1986 | 6 | Rothamsted | 27.8
1986-06-28 | 1986 | 6 | Rothamsted | 26.8
1986-06-29 | 1986 | 6 | Rothamsted | 26.8
1986-06-30 | 1986 | 6 | Rothamsted | 24.3
1986-07-01 | 1986 | 7 | Rothamsted | 26
1986-07-02 | 1986 | 7 | Rothamsted | 22.5
1986-07-03 | 1986 | 7 | Rothamsted | 22.1
1986-07-04 | 1986 | 7 | Rothamsted | 19.2
1986-07-05 | 1986 | 7 | Rothamsted | 19.6
1986-07-06 | 1986 | 7 | Rothamsted | 18.5
1986-07-07 | 1986 | 7 | Rothamsted | 19.8
1986-07-08 | 1986 | 7 | Rothamsted | 18.1
1986-07-09 | 1986 | 7 | Rothamsted | 20.6
1986-07-10 | 1986 | 7 | Rothamsted | 19
1986-07-11 | 1986 | 7 | Rothamsted | 17.2
1986-07-12 | 1986 | 7 | Rothamsted | 20.2
1986-07-13 | 1986 | 7 | Rothamsted | 24.7
1986-07-14 | 1986 | 7 | Rothamsted | 27.6
1986-07-15 | 1986 | 7 | Rothamsted | 26
1986-07-17 | 1986 | 7 | Rothamsted | 17.6
1986-07-18 | 1986 | 7 | Rothamsted | 18.6
1986-07-19 | 1986 | 7 | Rothamsted | 22
1986-07-20 | 1986 | 7 | Rothamsted | 20.1
1986-07-21 | 1986 | 7 | Rothamsted | 19.4
1986-07-22 | 1986 | 7 | Rothamsted | 16.5
1986-07-23 | 1986 | 7 | Rothamsted | 21.1
1986-07-24 | 1986 | 7 | Rothamsted | 21
1986-07-25 | 1986 | 7 | Rothamsted | 22.4
1986-07-26 | 1986 | 7 | Rothamsted | 21.1
1986-07-27 | 1986 | 7 | Rothamsted | 21
1986-07-28 | 1986 | 7 | Rothamsted | 20.5
1986-07-29 | 1986 | 7 | Rothamsted | 17.5
1986-07-30 | 1986 | 7 | Rothamsted | 20
1986-07-31 | 1986 | 7 | Rothamsted | 20
1986-08-01 | 1986 | 8 | Rothamsted | 21
1986-08-03 | 1986 | 8 | Rothamsted | 18.7
1986-08-04 | 1986 | 8 | Rothamsted | 19.9
1986-08-05 | 1986 | 8 | Rothamsted | 23.1
1986-08-06 | 1986 | 8 | Rothamsted | 20.5
1986-08-07 | 1986 | 8 | Rothamsted | 20.5
1986-08-08 | 1986 | 8 | Rothamsted | 21.2
1986-08-09 | 1986 | 8 | Rothamsted | 23
1986-08-11 | 1986 | 8 | Rothamsted | 18.1
1986-08-12 | 1986 | 8 | Rothamsted | 20.9
1986-08-13 | 1986 | 8 | Rothamsted | 21.7
1986-08-14 | 1986 | 8 | Rothamsted | 21
1986-08-15 | 1986 | 8 | Rothamsted | 20.2
1986-08-16 | 1986 | 8 | Rothamsted | 17.9
1986-08-17 | 1986 | 8 | Rothamsted | 17.6
1986-08-18 | 1986 | 8 | Rothamsted | 17.6
1986-08-19 | 1986 | 8 | Rothamsted | 19
1986-08-20 | 1986 | 8 | Rothamsted | 17.1
1986-08-21 | 1986 | 8 | Rothamsted | 19.1
1986-08-22 | 1986 | 8 | Rothamsted | 17.2
1986-08-23 | 1986 | 8 | Rothamsted | 17.9
1986-08-24 | 1986 | 8 | Rothamsted | 15.1
1986-08-25 | 1986 | 8 | Rothamsted | 16.1
1986-08-26 | 1986 | 8 | Rothamsted | 16.3
1986-08-27 | 1986 | 8 | Rothamsted | 16.7
1986-08-28 | 1986 | 8 | Rothamsted | 16
1986-08-29 | 1986 | 8 | Rothamsted | 14
1986-08-30 | 1986 | 8 | Rothamsted | 17.6
1986-08-31 | 1986 | 8 | Rothamsted | 15.4
1986-09-01 | 1986 | 9 | Rothamsted | 20.9
1986-09-03 | 1986 | 9 | Rothamsted | 18.2
1986-09-04 | 1986 | 9 | Rothamsted | 18.6
1986-09-05 | 1986 | 9 | Rothamsted | 15.5
1986-09-06 | 1986 | 9 | Rothamsted | 18.4
1986-09-07 | 1986 | 9 | Rothamsted | 15.1
1986-09-08 | 1986 | 9 | Rothamsted | 16.1
1986-09-09 | 1986 | 9 | Rothamsted | 14.7
1986-09-10 | 1986 | 9 | Rothamsted | 14.7
1986-09-11 | 1986 | 9 | Rothamsted | 15.1
1986-09-12 | 1986 | 9 | Rothamsted | 13.7
1986-09-13 | 1986 | 9 | Rothamsted | 14
1986-09-15 | 1986 | 9 | Rothamsted | 13.1
1986-09-16 | 1986 | 9 | Rothamsted | 13.1
1986-09-17 | 1986 | 9 | Rothamsted | 14.4
1986-09-18 | 1986 | 9 | Rothamsted | 15.9
1986-09-19 | 1986 | 9 | Rothamsted | 19.6
1986-09-20 | 1986 | 9 | Rothamsted | 19.1
1986-09-21 | 1986 | 9 | Rothamsted | 19.3
1986-09-22 | 1986 | 9 | Rothamsted | 20.1
1986-09-24 | 1986 | 9 | Rothamsted | 15
1986-09-25 | 1986 | 9 | Rothamsted | 16.8
1986-09-26 | 1986 | 9 | Rothamsted | 17.8
1986-09-27 | 1986 | 9 | Rothamsted | 20.1
1986-09-28 | 1986 | 9 | Rothamsted | 18.4
1986-09-29 | 1986 | 9 | Rothamsted | 16.7
1986-09-30 | 1986 | 9 | Rothamsted | 15.5
1987-05-02 | 1987 | 5 | Rothamsted | 8.6
1987-05-03 | 1987 | 5 | Rothamsted | 10.9
1987-05-04 | 1987 | 5 | Rothamsted | 12.6
1987-05-05 | 1987 | 5 | Rothamsted | 15.4
1987-05-06 | 1987 | 5 | Rothamsted | 15.2
1987-05-07 | 1987 | 5 | Rothamsted | 19.3
1987-05-08 | 1987 | 5 | Rothamsted | 21.3
1987-05-09 | 1987 | 5 | Rothamsted | 12.8
1987-05-10 | 1987 | 5 | Rothamsted | 13.3
1987-05-11 | 1987 | 5 | Rothamsted | 11.5
1987-05-12 | 1987 | 5 | Rothamsted | 12.1
1987-05-13 | 1987 | 5 | Rothamsted | 12.5
1987-05-14 | 1987 | 5 | Rothamsted | 9.9
1987-05-15 | 1987 | 5 | Rothamsted | 13.1
1987-05-16 | 1987 | 5 | Rothamsted | 11.7
1987-05-17 | 1987 | 5 | Rothamsted | 11
1987-05-18 | 1987 | 5 | Rothamsted | 14.7
1987-05-19 | 1987 | 5 | Rothamsted | 11.5
1987-05-20 | 1987 | 5 | Rothamsted | 11.9
1987-05-21 | 1987 | 5 | Rothamsted | 11.4
1987-05-22 | 1987 | 5 | Rothamsted | 10.7
1987-05-23 | 1987 | 5 | Rothamsted | 17.4
1987-05-24 | 1987 | 5 | Rothamsted | 16.2
1987-05-25 | 1987 | 5 | Rothamsted | 19.8
1987-05-26 | 1987 | 5 | Rothamsted | 16.7
1987-05-27 | 1987 | 5 | Rothamsted | 15.9
1987-05-28 | 1987 | 5 | Rothamsted | 17.3
1987-05-29 | 1987 | 5 | Rothamsted | 17.9
1987-05-30 | 1987 | 5 | Rothamsted | 19.1
1987-05-31 | 1987 | 5 | Rothamsted | 18.5
1987-06-01 | 1987 | 6 | Rothamsted | 14.5
1987-06-02 | 1987 | 6 | Rothamsted | 17.6
1987-06-03 | 1987 | 6 | Rothamsted | 18
1987-06-04 | 1987 | 6 | Rothamsted | 14.1
1987-06-05 | 1987 | 6 | Rothamsted | 15.8
1987-06-06 | 1987 | 6 | Rothamsted | 14.3
1987-06-07 | 1987 | 6 | Rothamsted | 12.7
1987-06-08 | 1987 | 6 | Rothamsted | 12.3
1987-06-09 | 1987 | 6 | Rothamsted | 15.6
1987-06-10 | 1987 | 6 | Rothamsted | 15
1987-06-11 | 1987 | 6 | Rothamsted | 16.7
1987-06-12 | 1987 | 6 | Rothamsted | 14.4
1987-06-13 | 1987 | 6 | Rothamsted | 14.4
1987-06-14 | 1987 | 6 | Rothamsted | 14.9
1987-06-15 | 1987 | 6 | Rothamsted | 15
1987-06-16 | 1987 | 6 | Rothamsted | 15.3
1987-06-17 | 1987 | 6 | Rothamsted | 16.3
1987-06-18 | 1987 | 6 | Rothamsted | 14.7
1987-06-19 | 1987 | 6 | Rothamsted | 18.2
1987-06-20 | 1987 | 6 | Rothamsted | 16.9
1987-06-21 | 1987 | 6 | Rothamsted | 16.5
1987-06-22 | 1987 | 6 | Rothamsted | 17.9
1987-06-23 | 1987 | 6 | Rothamsted | 17.6
1987-06-24 | 1987 | 6 | Rothamsted | 16
1987-06-25 | 1987 | 6 | Rothamsted | 19
1987-06-26 | 1987 | 6 | Rothamsted | 21.1
1987-06-27 | 1987 | 6 | Rothamsted | 23.6
1987-06-28 | 1987 | 6 | Rothamsted | 26.5
1987-06-29 | 1987 | 6 | Rothamsted | 21.8
1987-06-30 | 1987 | 6 | Rothamsted | 19.1
1987-07-01 | 1987 | 7 | Rothamsted | 20
1987-07-02 | 1987 | 7 | Rothamsted | 21.4
1987-07-03 | 1987 | 7 | Rothamsted | 23.7
1987-07-04 | 1987 | 7 | Rothamsted | 25.3
1987-07-05 | 1987 | 7 | Rothamsted | 26.4
1987-07-06 | 1987 | 7 | Rothamsted | 22.9
1987-07-07 | 1987 | 7 | Rothamsted | 20.7
1987-07-08 | 1987 | 7 | Rothamsted | 19.6
1987-07-09 | 1987 | 7 | Rothamsted | 24.3
1987-07-10 | 1987 | 7 | Rothamsted | 23.8
1987-07-11 | 1987 | 7 | Rothamsted | 21.4
1987-07-12 | 1987 | 7 | Rothamsted | 23.3
1987-07-13 | 1987 | 7 | Rothamsted | 22.9
1987-07-14 | 1987 | 7 | Rothamsted | 20.9
1987-07-15 | 1987 | 7 | Rothamsted | 18
1987-07-16 | 1987 | 7 | Rothamsted | 15.1
1987-07-17 | 1987 | 7 | Rothamsted | 16
1987-07-18 | 1987 | 7 | Rothamsted | 15.2
1987-07-19 | 1987 | 7 | Rothamsted | 17.6
1987-07-21 | 1987 | 7 | Rothamsted | 16
1987-07-22 | 1987 | 7 | Rothamsted | 15.1
1987-07-23 | 1987 | 7 | Rothamsted | 17.9
1987-07-24 | 1987 | 7 | Rothamsted | 15.7
1987-07-25 | 1987 | 7 | Rothamsted | 18.8
1987-07-26 | 1987 | 7 | Rothamsted | 18.9
1987-07-27 | 1987 | 7 | Rothamsted | 20.3
1987-07-28 | 1987 | 7 | Rothamsted | 21
1987-07-29 | 1987 | 7 | Rothamsted | 17.7
1987-07-30 | 1987 | 7 | Rothamsted | 23.3
1987-07-31 | 1987 | 7 | Rothamsted | 18.8
1987-08-01 | 1987 | 8 | Rothamsted | 19.9
1987-08-02 | 1987 | 8 | Rothamsted | 20
1987-08-03 | 1987 | 8 | Rothamsted | 16.9
1987-08-04 | 1987 | 8 | Rothamsted | 16.9
1987-08-05 | 1987 | 8 | Rothamsted | 18.6
1987-08-06 | 1987 | 8 | Rothamsted | 17.5
1987-08-07 | 1987 | 8 | Rothamsted | 16.5
1987-08-08 | 1987 | 8 | Rothamsted | 17.1
1987-08-09 | 1987 | 8 | Rothamsted | 18.5
1987-08-10 | 1987 | 8 | Rothamsted | 17.8
1987-08-11 | 1987 | 8 | Rothamsted | 20.1
1987-08-12 | 1987 | 8 | Rothamsted | 21.5
1987-08-13 | 1987 | 8 | Rothamsted | 22
1987-08-14 | 1987 | 8 | Rothamsted | 25
1987-08-15 | 1987 | 8 | Rothamsted | 26.7
1987-08-16 | 1987 | 8 | Rothamsted | 24.8
1987-08-17 | 1987 | 8 | Rothamsted | 23.8
1987-08-18 | 1987 | 8 | Rothamsted | 24.1
1987-08-19 | 1987 | 8 | Rothamsted | 26.9
1987-08-20 | 1987 | 8 | Rothamsted | 27.8
1987-08-21 | 1987 | 8 | Rothamsted | 22.4
1987-08-22 | 1987 | 8 | Rothamsted | 20.1
1987-08-23 | 1987 | 8 | Rothamsted | 15.5
1987-08-24 | 1987 | 8 | Rothamsted | 14
1987-08-25 | 1987 | 8 | Rothamsted | 16.3
1987-08-26 | 1987 | 8 | Rothamsted | 15.2
1987-08-27 | 1987 | 8 | Rothamsted | 23
1987-08-28 | 1987 | 8 | Rothamsted | 20.2
1987-08-29 | 1987 | 8 | Rothamsted | 21.9
1987-08-30 | 1987 | 8 | Rothamsted | 18.8
1987-08-31 | 1987 | 8 | Rothamsted | 24
1987-09-01 | 1987 | 9 | Rothamsted | 19
1987-09-02 | 1987 | 9 | Rothamsted | 20.9
1987-09-03 | 1987 | 9 | Rothamsted | 20.9
1987-09-04 | 1987 | 9 | Rothamsted | 20.6
1987-09-05 | 1987 | 9 | Rothamsted | 17
1987-09-06 | 1987 | 9 | Rothamsted | 18.8
1987-09-07 | 1987 | 9 | Rothamsted | 19.2
1987-09-08 | 1987 | 9 | Rothamsted | 19
1987-09-09 | 1987 | 9 | Rothamsted | 18.5
1987-09-10 | 1987 | 9 | Rothamsted | 19.6
1987-09-11 | 1987 | 9 | Rothamsted | 20.2
1987-09-13 | 1987 | 9 | Rothamsted | 19.1
1987-09-14 | 1987 | 9 | Rothamsted | 18.1
1987-09-15 | 1987 | 9 | Rothamsted | 17.5
1987-09-16 | 1987 | 9 | Rothamsted | 21.8
1987-09-17 | 1987 | 9 | Rothamsted | 18.3
1987-09-19 | 1987 | 9 | Rothamsted | 22.6
1987-09-20 | 1987 | 9 | Rothamsted | 21.3
1987-09-22 | 1987 | 9 | Rothamsted | 18.5
1987-09-23 | 1987 | 9 | Rothamsted | 14.8
1987-09-24 | 1987 | 9 | Rothamsted | 15.3
1987-09-25 | 1987 | 9 | Rothamsted | 13.6
1987-09-26 | 1987 | 9 | Rothamsted | 12.7
1987-09-27 | 1987 | 9 | Rothamsted | 12.1
1987-09-28 | 1987 | 9 | Rothamsted | 13.3
1987-09-29 | 1987 | 9 | Rothamsted | 14.6
1987-09-30 | 1987 | 9 | Rothamsted | 15.6
1988-05-01 | 1988 | 5 | Rothamsted | 15.1
1988-05-02 | 1988 | 5 | Rothamsted | 14.6
1988-05-03 | 1988 | 5 | Rothamsted | 15
1988-05-04 | 1988 | 5 | Rothamsted | 16.1
1988-05-05 | 1988 | 5 | Rothamsted | 18.7
1988-05-06 | 1988 | 5 | Rothamsted | 17.9
1988-05-07 | 1988 | 5 | Rothamsted | 19.7
1988-05-09 | 1988 | 5 | Rothamsted | 14
1988-05-10 | 1988 | 5 | Rothamsted | 12
1988-05-11 | 1988 | 5 | Rothamsted | 18.3
1988-05-12 | 1988 | 5 | Rothamsted | 19.5
1988-05-13 | 1988 | 5 | Rothamsted | 21.5
1988-05-14 | 1988 | 5 | Rothamsted | 21.3
1988-05-15 | 1988 | 5 | Rothamsted | 19.1
1988-05-16 | 1988 | 5 | Rothamsted | 16.5
1988-05-17 | 1988 | 5 | Rothamsted | 10.8
1988-05-18 | 1988 | 5 | Rothamsted | 11.6
1988-05-19 | 1988 | 5 | Rothamsted | 14.4
1988-05-20 | 1988 | 5 | Rothamsted | 16.6
1988-05-21 | 1988 | 5 | Rothamsted | 16
1988-05-22 | 1988 | 5 | Rothamsted | 15.5
1988-05-23 | 1988 | 5 | Rothamsted | 17.4
1988-05-24 | 1988 | 5 | Rothamsted | 17.1
1988-05-25 | 1988 | 5 | Rothamsted | 16.7
1988-05-26 | 1988 | 5 | Rothamsted | 17.4
1988-05-27 | 1988 | 5 | Rothamsted | 18
1988-05-28 | 1988 | 5 | Rothamsted | 14.7
1988-05-29 | 1988 | 5 | Rothamsted | 15
1988-05-30 | 1988 | 5 | Rothamsted | 16.4
1988-05-31 | 1988 | 5 | Rothamsted | 18
1988-06-01 | 1988 | 6 | Rothamsted | 15.8
1988-06-02 | 1988 | 6 | Rothamsted | 15.3
1988-06-03 | 1988 | 6 | Rothamsted | 14.1
1988-06-04 | 1988 | 6 | Rothamsted | 14.5
1988-06-05 | 1988 | 6 | Rothamsted | 15.8
1988-06-06 | 1988 | 6 | Rothamsted | 16.5
1988-06-07 | 1988 | 6 | Rothamsted | 15.4
1988-06-09 | 1988 | 6 | Rothamsted | 12.4
1988-06-10 | 1988 | 6 | Rothamsted | 15.5
1988-06-11 | 1988 | 6 | Rothamsted | 18.4
1988-06-12 | 1988 | 6 | Rothamsted | 21.4
1988-06-13 | 1988 | 6 | Rothamsted | 19.8
1988-06-14 | 1988 | 6 | Rothamsted | 17.8
1988-06-15 | 1988 | 6 | Rothamsted | 16.5
1988-06-16 | 1988 | 6 | Rothamsted | 15.2
1988-06-17 | 1988 | 6 | Rothamsted | 18.3
1988-06-18 | 1988 | 6 | Rothamsted | 22.1
1988-06-19 | 1988 | 6 | Rothamsted | 22.6
1988-06-20 | 1988 | 6 | Rothamsted | 21.1
1988-06-21 | 1988 | 6 | Rothamsted | 19.2
1988-06-22 | 1988 | 6 | Rothamsted | 21.5
1988-06-23 | 1988 | 6 | Rothamsted | 20.2
1988-06-24 | 1988 | 6 | Rothamsted | 21.6
1988-06-25 | 1988 | 6 | Rothamsted | 18
1988-06-27 | 1988 | 6 | Rothamsted | 15.2
1988-06-28 | 1988 | 6 | Rothamsted | 20.5
1988-06-29 | 1988 | 6 | Rothamsted | 22.4
1988-06-30 | 1988 | 6 | Rothamsted | 18.1
1988-07-01 | 1988 | 7 | Rothamsted | 16.5
1988-07-02 | 1988 | 7 | Rothamsted | 14.9
1988-07-03 | 1988 | 7 | Rothamsted | 15.7
1988-07-04 | 1988 | 7 | Rothamsted | 19.6
1988-07-05 | 1988 | 7 | Rothamsted | 17.6
1988-07-06 | 1988 | 7 | Rothamsted | 18.3
1988-07-07 | 1988 | 7 | Rothamsted | 18.2
1988-07-08 | 1988 | 7 | Rothamsted | 18.5
1988-07-09 | 1988 | 7 | Rothamsted | 17
1988-07-10 | 1988 | 7 | Rothamsted | 19.5
1988-07-11 | 1988 | 7 | Rothamsted | 19
1988-07-12 | 1988 | 7 | Rothamsted | 18
1988-07-13 | 1988 | 7 | Rothamsted | 15.4
1988-07-14 | 1988 | 7 | Rothamsted | 18.4
1988-07-15 | 1988 | 7 | Rothamsted | 17.4
1988-07-16 | 1988 | 7 | Rothamsted | 18.4
1988-07-17 | 1988 | 7 | Rothamsted | 20.3
1988-07-18 | 1988 | 7 | Rothamsted | 18.5
1988-07-19 | 1988 | 7 | Rothamsted | 21.5
1988-07-20 | 1988 | 7 | Rothamsted | 21
1988-07-21 | 1988 | 7 | Rothamsted | 20
1988-07-22 | 1988 | 7 | Rothamsted | 21.4
1988-07-23 | 1988 | 7 | Rothamsted | 19.2
1988-07-24 | 1988 | 7 | Rothamsted | 19.9
1988-07-25 | 1988 | 7 | Rothamsted | 19.8
1988-07-26 | 1988 | 7 | Rothamsted | 19.3
1988-07-27 | 1988 | 7 | Rothamsted | 15.9
1988-07-28 | 1988 | 7 | Rothamsted | 17.9
1988-07-29 | 1988 | 7 | Rothamsted | 18.8
1988-07-30 | 1988 | 7 | Rothamsted | 17.1
1988-07-31 | 1988 | 7 | Rothamsted | 17.8
1988-08-01 | 1988 | 8 | Rothamsted | 17.6
1988-08-02 | 1988 | 8 | Rothamsted | 19.2
1988-08-03 | 1988 | 8 | Rothamsted | 20.2
1988-08-04 | 1988 | 8 | Rothamsted | 22.3
1988-08-05 | 1988 | 8 | Rothamsted | 26.6
1988-08-06 | 1988 | 8 | Rothamsted | 27.4
1988-08-07 | 1988 | 8 | Rothamsted | 24.6
1988-08-08 | 1988 | 8 | Rothamsted | 22.5
1988-08-09 | 1988 | 8 | Rothamsted | 22.4
1988-08-10 | 1988 | 8 | Rothamsted | 18.5
1988-08-11 | 1988 | 8 | Rothamsted | 19.3
1988-08-12 | 1988 | 8 | Rothamsted | 18
1988-08-13 | 1988 | 8 | Rothamsted | 21.7
1988-08-14 | 1988 | 8 | Rothamsted | 21.1
1988-08-15 | 1988 | 8 | Rothamsted | 22.1
1988-08-16 | 1988 | 8 | Rothamsted | 24.7
1988-08-17 | 1988 | 8 | Rothamsted | 24.2
1988-08-18 | 1988 | 8 | Rothamsted | 20
1988-08-19 | 1988 | 8 | Rothamsted | 18.9
1988-08-20 | 1988 | 8 | Rothamsted | 16.5
1988-08-21 | 1988 | 8 | Rothamsted | 18.1
1988-08-22 | 1988 | 8 | Rothamsted | 20.5
1988-08-23 | 1988 | 8 | Rothamsted | 19.7
1988-08-25 | 1988 | 8 | Rothamsted | 20.5
1988-08-26 | 1988 | 8 | Rothamsted | 22.9
1988-08-28 | 1988 | 8 | Rothamsted | 18.8
1988-08-29 | 1988 | 8 | Rothamsted | 18.4
1988-08-30 | 1988 | 8 | Rothamsted | 18.4
1988-08-31 | 1988 | 8 | Rothamsted | 17.3
1988-09-01 | 1988 | 9 | Rothamsted | 16.8
1988-09-02 | 1988 | 9 | Rothamsted | 17.9
1988-09-03 | 1988 | 9 | Rothamsted | 18.7
1988-09-04 | 1988 | 9 | Rothamsted | 21.2
1988-09-05 | 1988 | 9 | Rothamsted | 22.7
1988-09-06 | 1988 | 9 | Rothamsted | 24.9
1988-09-07 | 1988 | 9 | Rothamsted | 24.6
1988-09-08 | 1988 | 9 | Rothamsted | 21
1988-09-09 | 1988 | 9 | Rothamsted | 22.4
1988-09-10 | 1988 | 9 | Rothamsted | 17.8
1988-09-11 | 1988 | 9 | Rothamsted | 16.2
1988-09-12 | 1988 | 9 | Rothamsted | 13.1
1988-09-13 | 1988 | 9 | Rothamsted | 13
1988-09-14 | 1988 | 9 | Rothamsted | 14
1988-09-15 | 1988 | 9 | Rothamsted | 17.7
1988-09-16 | 1988 | 9 | Rothamsted | 16.9
1988-09-17 | 1988 | 9 | Rothamsted | 17.2
1988-09-18 | 1988 | 9 | Rothamsted | 15.8
1988-09-19 | 1988 | 9 | Rothamsted | 14
1988-09-20 | 1988 | 9 | Rothamsted | 15.9
1988-09-21 | 1988 | 9 | Rothamsted | 18.4
1988-09-22 | 1988 | 9 | Rothamsted | 15.5
1988-09-23 | 1988 | 9 | Rothamsted | 14.1
1988-09-24 | 1988 | 9 | Rothamsted | 17.4
1988-09-25 | 1988 | 9 | Rothamsted | 19.6
1988-09-28 | 1988 | 9 | Rothamsted | 14.7
1988-09-29 | 1988 | 9 | Rothamsted | 13
1988-09-30 | 1988 | 9 | Rothamsted | 14.7
1989-05-01 | 1989 | 5 | Rothamsted | 17.5
1989-05-02 | 1989 | 5 | Rothamsted | 21.4
1989-05-03 | 1989 | 5 | Rothamsted | 21.8
1989-05-04 | 1989 | 5 | Rothamsted | 23
1989-05-06 | 1989 | 5 | Rothamsted | 17.6
1989-05-07 | 1989 | 5 | Rothamsted | 20.4
1989-05-08 | 1989 | 5 | Rothamsted | 15.6
1989-05-09 | 1989 | 5 | Rothamsted | 15.9
1989-05-10 | 1989 | 5 | Rothamsted | 15.3
1989-05-11 | 1989 | 5 | Rothamsted | 12.6
1989-05-12 | 1989 | 5 | Rothamsted | 13.9
1989-05-13 | 1989 | 5 | Rothamsted | 16.3
1989-05-14 | 1989 | 5 | Rothamsted | 19.4
1989-05-15 | 1989 | 5 | Rothamsted | 18.2
1989-05-16 | 1989 | 5 | Rothamsted | 20.1
1989-05-17 | 1989 | 5 | Rothamsted | 22.5
1989-05-18 | 1989 | 5 | Rothamsted | 22.5
1989-05-19 | 1989 | 5 | Rothamsted | 23
1989-05-20 | 1989 | 5 | Rothamsted | 24.5
1989-05-21 | 1989 | 5 | Rothamsted | 23.5
1989-05-22 | 1989 | 5 | Rothamsted | 27.7
1989-05-23 | 1989 | 5 | Rothamsted | 27
1989-05-25 | 1989 | 5 | Rothamsted | 16.7
1989-05-26 | 1989 | 5 | Rothamsted | 17.4
1989-05-27 | 1989 | 5 | Rothamsted | 19.5
1989-05-28 | 1989 | 5 | Rothamsted | 20.4
1989-05-30 | 1989 | 5 | Rothamsted | 14.6
1989-05-31 | 1989 | 5 | Rothamsted | 10.8
1989-06-01 | 1989 | 6 | Rothamsted | 15.4
1989-06-02 | 1989 | 6 | Rothamsted | 12.2
1989-06-03 | 1989 | 6 | Rothamsted | 14.2
1989-06-04 | 1989 | 6 | Rothamsted | 15.5
1989-06-05 | 1989 | 6 | Rothamsted | 11.6
1989-06-06 | 1989 | 6 | Rothamsted | 14
1989-06-07 | 1989 | 6 | Rothamsted | 14.7
1989-06-08 | 1989 | 6 | Rothamsted | 17.2
1989-06-09 | 1989 | 6 | Rothamsted | 20
1989-06-10 | 1989 | 6 | Rothamsted | 22
1989-06-11 | 1989 | 6 | Rothamsted | 26.6
1989-06-12 | 1989 | 6 | Rothamsted | 26.7
1989-06-13 | 1989 | 6 | Rothamsted | 25.1
1989-06-14 | 1989 | 6 | Rothamsted | 24.6
1989-06-15 | 1989 | 6 | Rothamsted | 25.2
1989-06-16 | 1989 | 6 | Rothamsted | 25.8
1989-06-17 | 1989 | 6 | Rothamsted | 24.5
1989-06-18 | 1989 | 6 | Rothamsted | 27.1
1989-06-19 | 1989 | 6 | Rothamsted | 27.6
1989-06-20 | 1989 | 6 | Rothamsted | 21.8
1989-06-21 | 1989 | 6 | Rothamsted | 17.9
1989-06-22 | 1989 | 6 | Rothamsted | 22.6
1989-06-23 | 1989 | 6 | Rothamsted | 23.6
1989-06-24 | 1989 | 6 | Rothamsted | 25.6
1989-06-25 | 1989 | 6 | Rothamsted | 21.6
1989-06-26 | 1989 | 6 | Rothamsted | 17.4
1989-06-27 | 1989 | 6 | Rothamsted | 17.4
1989-06-28 | 1989 | 6 | Rothamsted | 18
1989-06-29 | 1989 | 6 | Rothamsted | 19.6
1989-06-30 | 1989 | 6 | Rothamsted | 19.4
1989-07-01 | 1989 | 7 | Rothamsted | 18
1989-07-02 | 1989 | 7 | Rothamsted | 22.7
1989-07-03 | 1989 | 7 | Rothamsted | 23.7
1989-07-04 | 1989 | 7 | Rothamsted | 25.5
1989-07-05 | 1989 | 7 | Rothamsted | 28.7
1989-07-07 | 1989 | 7 | Rothamsted | 22.4
1989-07-09 | 1989 | 7 | Rothamsted | 23.5
1989-07-10 | 1989 | 7 | Rothamsted | 24.1
1989-07-11 | 1989 | 7 | Rothamsted | 20.2
1989-07-12 | 1989 | 7 | Rothamsted | 22.6
1989-07-13 | 1989 | 7 | Rothamsted | 20.6
1989-07-14 | 1989 | 7 | Rothamsted | 26.4
1989-07-15 | 1989 | 7 | Rothamsted | 23.3
1989-07-16 | 1989 | 7 | Rothamsted | 26.6
1989-07-17 | 1989 | 7 | Rothamsted | 22.1
1989-07-18 | 1989 | 7 | Rothamsted | 26.5
1989-07-19 | 1989 | 7 | Rothamsted | 27.2
1989-07-20 | 1989 | 7 | Rothamsted | 29.5
1989-07-21 | 1989 | 7 | Rothamsted | 31.7
1989-07-22 | 1989 | 7 | Rothamsted | 30.1
1989-07-23 | 1989 | 7 | Rothamsted | 28.2
1989-07-24 | 1989 | 7 | Rothamsted | 28.6
1989-07-25 | 1989 | 7 | Rothamsted | 24.1
1989-07-26 | 1989 | 7 | Rothamsted | 24.1
1989-07-27 | 1989 | 7 | Rothamsted | 24.8
1989-07-28 | 1989 | 7 | Rothamsted | 24.3
1989-07-29 | 1989 | 7 | Rothamsted | 18.5
1989-07-30 | 1989 | 7 | Rothamsted | 18
1989-07-31 | 1989 | 7 | Rothamsted | 20.1
1989-08-01 | 1989 | 8 | Rothamsted | 21.8
1989-08-02 | 1989 | 8 | Rothamsted | 24.7
1989-08-03 | 1989 | 8 | Rothamsted | 23.1
1989-08-04 | 1989 | 8 | Rothamsted | 25.5
1989-08-05 | 1989 | 8 | Rothamsted | 27.3
1989-08-06 | 1989 | 8 | Rothamsted | 25.5
1989-08-07 | 1989 | 8 | Rothamsted | 24.4
1989-08-08 | 1989 | 8 | Rothamsted | 25.3
1989-08-09 | 1989 | 8 | Rothamsted | 19
1989-08-10 | 1989 | 8 | Rothamsted | 23
1989-08-11 | 1989 | 8 | Rothamsted | 23
1989-08-12 | 1989 | 8 | Rothamsted | 21.1
1989-08-13 | 1989 | 8 | Rothamsted | 22.5
1989-08-14 | 1989 | 8 | Rothamsted | 22.2
1989-08-15 | 1989 | 8 | Rothamsted | 22.9
1989-08-16 | 1989 | 8 | Rothamsted | 20.5
1989-08-17 | 1989 | 8 | Rothamsted | 21.4
1989-08-18 | 1989 | 8 | Rothamsted | 25.7
1989-08-19 | 1989 | 8 | Rothamsted | 27.8
1989-08-20 | 1989 | 8 | Rothamsted | 24.4
1989-08-21 | 1989 | 8 | Rothamsted | 23.4
1989-08-22 | 1989 | 8 | Rothamsted | 24.2
1989-08-23 | 1989 | 8 | Rothamsted | 24.7
1989-08-24 | 1989 | 8 | Rothamsted | 19.8
1989-08-25 | 1989 | 8 | Rothamsted | 21.3
1989-08-26 | 1989 | 8 | Rothamsted | 17.4
1989-08-27 | 1989 | 8 | Rothamsted | 18.5
1989-08-28 | 1989 | 8 | Rothamsted | 17.6
1989-08-29 | 1989 | 8 | Rothamsted | 25
1989-08-31 | 1989 | 8 | Rothamsted | 19
1989-09-01 | 1989 | 9 | Rothamsted | 16.2
1989-09-02 | 1989 | 9 | Rothamsted | 18
1989-09-03 | 1989 | 9 | Rothamsted | 20.1
1989-09-04 | 1989 | 9 | Rothamsted | 21.5
1989-09-05 | 1989 | 9 | Rothamsted | 25
1989-09-06 | 1989 | 9 | Rothamsted | 26
1989-09-07 | 1989 | 9 | Rothamsted | 20.1
1989-09-09 | 1989 | 9 | Rothamsted | 19.4
1989-09-10 | 1989 | 9 | Rothamsted | 17.8
1989-09-11 | 1989 | 9 | Rothamsted | 20
1989-09-12 | 1989 | 9 | Rothamsted | 20
1989-09-14 | 1989 | 9 | Rothamsted | 19.6
1989-09-15 | 1989 | 9 | Rothamsted | 20.2
1989-09-16 | 1989 | 9 | Rothamsted | 18.6
1989-09-17 | 1989 | 9 | Rothamsted | 21.4
1989-09-18 | 1989 | 9 | Rothamsted | 19.4
1989-09-19 | 1989 | 9 | Rothamsted | 21.5
1989-09-20 | 1989 | 9 | Rothamsted | 25.5
1989-09-21 | 1989 | 9 | Rothamsted | 18.5
1989-09-22 | 1989 | 9 | Rothamsted | 18.1
1989-09-23 | 1989 | 9 | Rothamsted | 20.2
1989-09-24 | 1989 | 9 | Rothamsted | 21.5
1989-09-25 | 1989 | 9 | Rothamsted | 17.5
1989-09-26 | 1989 | 9 | Rothamsted | 16.4
1989-09-27 | 1989 | 9 | Rothamsted | 15.7
1989-09-28 | 1989 | 9 | Rothamsted | 16.2
1989-09-29 | 1989 | 9 | Rothamsted | 15.1
1989-09-30 | 1989 | 9 | Rothamsted | 12.9
1990-05-01 | 1990 | 5 | Rothamsted | 23.6
1990-05-02 | 1990 | 5 | Rothamsted | 25.4
1990-05-03 | 1990 | 5 | Rothamsted | 24.5
1990-05-04 | 1990 | 5 | Rothamsted | 24.9
1990-05-05 | 1990 | 5 | Rothamsted | 22.4
1990-05-06 | 1990 | 5 | Rothamsted | 15.2
1990-05-07 | 1990 | 5 | Rothamsted | 17.7
1990-05-08 | 1990 | 5 | Rothamsted | 13.2
1990-05-09 | 1990 | 5 | Rothamsted | 13.8
1990-05-10 | 1990 | 5 | Rothamsted | 11.7
1990-05-11 | 1990 | 5 | Rothamsted | 13.9
1990-05-12 | 1990 | 5 | Rothamsted | 14.5
1990-05-13 | 1990 | 5 | Rothamsted | 17.9
1990-05-14 | 1990 | 5 | Rothamsted | 20
1990-05-15 | 1990 | 5 | Rothamsted | 17.6
1990-05-16 | 1990 | 5 | Rothamsted | 19.1
1990-05-17 | 1990 | 5 | Rothamsted | 13.1
1990-05-18 | 1990 | 5 | Rothamsted | 13.3
1990-05-19 | 1990 | 5 | Rothamsted | 17.3
1990-05-20 | 1990 | 5 | Rothamsted | 18
1990-05-21 | 1990 | 5 | Rothamsted | 17
1990-05-22 | 1990 | 5 | Rothamsted | 21
1990-05-23 | 1990 | 5 | Rothamsted | 16.4
1990-05-24 | 1990 | 5 | Rothamsted | 15.4
1990-05-25 | 1990 | 5 | Rothamsted | 17
1990-05-26 | 1990 | 5 | Rothamsted | 19.6
1990-05-27 | 1990 | 5 | Rothamsted | 20.4
1990-05-28 | 1990 | 5 | Rothamsted | 19
1990-05-29 | 1990 | 5 | Rothamsted | 18.5
1990-05-30 | 1990 | 5 | Rothamsted | 22.5
1990-05-31 | 1990 | 5 | Rothamsted | 22.1
1990-06-01 | 1990 | 6 | Rothamsted | 17.4
1990-06-02 | 1990 | 6 | Rothamsted | 15.4
1990-06-03 | 1990 | 6 | Rothamsted | 17.3
1990-06-04 | 1990 | 6 | Rothamsted | 15.3
1990-06-05 | 1990 | 6 | Rothamsted | 15.5
1990-06-06 | 1990 | 6 | Rothamsted | 16
1990-06-07 | 1990 | 6 | Rothamsted | 13
1990-06-08 | 1990 | 6 | Rothamsted | 16.3
1990-06-09 | 1990 | 6 | Rothamsted | 16.4
1990-06-11 | 1990 | 6 | Rothamsted | 12.5
1990-06-12 | 1990 | 6 | Rothamsted | 12.7
1990-06-13 | 1990 | 6 | Rothamsted | 15.5
1990-06-14 | 1990 | 6 | Rothamsted | 17.2
1990-06-15 | 1990 | 6 | Rothamsted | 19.7
1990-06-16 | 1990 | 6 | Rothamsted | 21.5
1990-06-17 | 1990 | 6 | Rothamsted | 18.9
1990-06-18 | 1990 | 6 | Rothamsted | 21
1990-06-19 | 1990 | 6 | Rothamsted | 19
1990-06-20 | 1990 | 6 | Rothamsted | 15.1
1990-06-21 | 1990 | 6 | Rothamsted | 18.5
1990-06-22 | 1990 | 6 | Rothamsted | 17.9
1990-06-23 | 1990 | 6 | Rothamsted | 17
1990-06-24 | 1990 | 6 | Rothamsted | 21.7
1990-06-25 | 1990 | 6 | Rothamsted | 23.3
1990-06-26 | 1990 | 6 | Rothamsted | 23.1
1990-06-27 | 1990 | 6 | Rothamsted | 19.7
1990-06-28 | 1990 | 6 | Rothamsted | 21.8
1990-06-29 | 1990 | 6 | Rothamsted | 19.6
1990-06-30 | 1990 | 6 | Rothamsted | 18
1990-07-01 | 1990 | 7 | Rothamsted | 17.1
1990-07-02 | 1990 | 7 | Rothamsted | 19.1
1990-07-03 | 1990 | 7 | Rothamsted | 16.9
1990-07-04 | 1990 | 7 | Rothamsted | 17
1990-07-05 | 1990 | 7 | Rothamsted | 19
1990-07-06 | 1990 | 7 | Rothamsted | 21.4
1990-07-07 | 1990 | 7 | Rothamsted | 23.5
1990-07-09 | 1990 | 7 | Rothamsted | 19.4
1990-07-10 | 1990 | 7 | Rothamsted | 26.3
1990-07-11 | 1990 | 7 | Rothamsted | 26.2
1990-07-12 | 1990 | 7 | Rothamsted | 25.1
1990-07-13 | 1990 | 7 | Rothamsted | 22.2
1990-07-14 | 1990 | 7 | Rothamsted | 28.7
1990-07-15 | 1990 | 7 | Rothamsted | 22.9
1990-07-16 | 1990 | 7 | Rothamsted | 24.8
1990-07-17 | 1990 | 7 | Rothamsted | 26.4
1990-07-18 | 1990 | 7 | Rothamsted | 27.8
1990-07-19 | 1990 | 7 | Rothamsted | 29.6
1990-07-20 | 1990 | 7 | Rothamsted | 30
1990-07-21 | 1990 | 7 | Rothamsted | 22
1990-07-22 | 1990 | 7 | Rothamsted | 21.7
1990-07-23 | 1990 | 7 | Rothamsted | 23
1990-07-24 | 1990 | 7 | Rothamsted | 24.6
1990-07-25 | 1990 | 7 | Rothamsted | 22.7
1990-07-26 | 1990 | 7 | Rothamsted | 25.2
1990-07-27 | 1990 | 7 | Rothamsted | 25.4
1990-07-28 | 1990 | 7 | Rothamsted | 24.4
1990-07-29 | 1990 | 7 | Rothamsted | 22.5
1990-07-30 | 1990 | 7 | Rothamsted | 25.2
1990-07-31 | 1990 | 7 | Rothamsted | 30.3
1990-08-01 | 1990 | 8 | Rothamsted | 31.6
1990-08-02 | 1990 | 8 | Rothamsted | 33.8
1990-08-03 | 1990 | 8 | Rothamsted | 31.6
1990-08-05 | 1990 | 8 | Rothamsted | 18.9
1990-08-06 | 1990 | 8 | Rothamsted | 20.6
1990-08-07 | 1990 | 8 | Rothamsted | 24.3
1990-08-08 | 1990 | 8 | Rothamsted | 25.5
1990-08-09 | 1990 | 8 | Rothamsted | 25.3
1990-08-10 | 1990 | 8 | Rothamsted | 25.4
1990-08-11 | 1990 | 8 | Rothamsted | 28
1990-08-12 | 1990 | 8 | Rothamsted | 23.5
1990-08-13 | 1990 | 8 | Rothamsted | 20.6
1990-08-14 | 1990 | 8 | Rothamsted | 21.2
1990-08-15 | 1990 | 8 | Rothamsted | 19.9
1990-08-16 | 1990 | 8 | Rothamsted | 19.1
1990-08-17 | 1990 | 8 | Rothamsted | 17.9
1990-08-18 | 1990 | 8 | Rothamsted | 20.3
1990-08-19 | 1990 | 8 | Rothamsted | 19.4
1990-08-20 | 1990 | 8 | Rothamsted | 20.2
1990-08-21 | 1990 | 8 | Rothamsted | 24.9
1990-08-22 | 1990 | 8 | Rothamsted | 26.5
1990-08-23 | 1990 | 8 | Rothamsted | 27
1990-08-24 | 1990 | 8 | Rothamsted | 26.4
1990-08-25 | 1990 | 8 | Rothamsted | 23.9
1990-08-26 | 1990 | 8 | Rothamsted | 22.9
1990-08-27 | 1990 | 8 | Rothamsted | 25.6
1990-08-28 | 1990 | 8 | Rothamsted | 28
1990-08-30 | 1990 | 8 | Rothamsted | 19.4
1990-08-31 | 1990 | 8 | Rothamsted | 21
1990-09-01 | 1990 | 9 | Rothamsted | 23.6
1990-09-02 | 1990 | 9 | Rothamsted | 22.5
1990-09-03 | 1990 | 9 | Rothamsted | 18.1
1990-09-04 | 1990 | 9 | Rothamsted | 19.1
1990-09-05 | 1990 | 9 | Rothamsted | 16.9
1990-09-06 | 1990 | 9 | Rothamsted | 17.1
1990-09-07 | 1990 | 9 | Rothamsted | 17.7
1990-09-08 | 1990 | 9 | Rothamsted | 19.9
1990-09-09 | 1990 | 9 | Rothamsted | 18.5
1990-09-10 | 1990 | 9 | Rothamsted | 20
1990-09-11 | 1990 | 9 | Rothamsted | 20
1990-09-12 | 1990 | 9 | Rothamsted | 19.6
1990-09-13 | 1990 | 9 | Rothamsted | 19.7
1990-09-14 | 1990 | 9 | Rothamsted | 18
1990-09-15 | 1990 | 9 | Rothamsted | 16.3
1990-09-16 | 1990 | 9 | Rothamsted | 14.3
1990-09-17 | 1990 | 9 | Rothamsted | 19.8
1990-09-18 | 1990 | 9 | Rothamsted | 15.2
1990-09-19 | 1990 | 9 | Rothamsted | 14.2
1990-09-20 | 1990 | 9 | Rothamsted | 14.2
1990-09-21 | 1990 | 9 | Rothamsted | 13.5
1990-09-22 | 1990 | 9 | Rothamsted | 13.5
1990-09-23 | 1990 | 9 | Rothamsted | 14
1990-09-24 | 1990 | 9 | Rothamsted | 14.6
1990-09-25 | 1990 | 9 | Rothamsted | 14.6
1990-09-26 | 1990 | 9 | Rothamsted | 14.8
1990-09-27 | 1990 | 9 | Rothamsted | 19.7
1990-09-28 | 1990 | 9 | Rothamsted | 17
1990-09-29 | 1990 | 9 | Rothamsted | 18.9
1991-05-01 | 1991 | 5 | Rothamsted | 9.7
1991-05-02 | 1991 | 5 | Rothamsted | 9.9
1991-05-03 | 1991 | 5 | Rothamsted | 9.8
1991-05-04 | 1991 | 5 | Rothamsted | 8.6
1991-05-05 | 1991 | 5 | Rothamsted | 8.1
1991-05-06 | 1991 | 5 | Rothamsted | 8.9
1991-05-07 | 1991 | 5 | Rothamsted | 12.6
1991-05-08 | 1991 | 5 | Rothamsted | 13.1
1991-05-09 | 1991 | 5 | Rothamsted | 15.5
1991-05-10 | 1991 | 5 | Rothamsted | 13.5
1991-05-11 | 1991 | 5 | Rothamsted | 18
1991-05-12 | 1991 | 5 | Rothamsted | 18.6
1991-05-14 | 1991 | 5 | Rothamsted | 13.3
1991-05-15 | 1991 | 5 | Rothamsted | 10.4
1991-05-16 | 1991 | 5 | Rothamsted | 10.9
1991-05-17 | 1991 | 5 | Rothamsted | 13.4
1991-05-18 | 1991 | 5 | Rothamsted | 16.6
1991-05-19 | 1991 | 5 | Rothamsted | 19.7
1991-05-20 | 1991 | 5 | Rothamsted | 22.1
1991-05-21 | 1991 | 5 | Rothamsted | 19.3
1991-05-22 | 1991 | 5 | Rothamsted | 16.1
1991-05-23 | 1991 | 5 | Rothamsted | 17.7
1991-05-24 | 1991 | 5 | Rothamsted | 19.9
1991-05-25 | 1991 | 5 | Rothamsted | 15.2
1991-05-26 | 1991 | 5 | Rothamsted | 18.5
1991-05-28 | 1991 | 5 | Rothamsted | 11.5
1991-05-29 | 1991 | 5 | Rothamsted | 11.6
1991-05-30 | 1991 | 5 | Rothamsted | 11.8
1991-05-31 | 1991 | 5 | Rothamsted | 12
1991-06-01 | 1991 | 6 | Rothamsted | 13.6
1991-06-02 | 1991 | 6 | Rothamsted | 12.6
1991-06-03 | 1991 | 6 | Rothamsted | 12.9
1991-06-04 | 1991 | 6 | Rothamsted | 14.9
1991-06-05 | 1991 | 6 | Rothamsted | 15.6
1991-06-06 | 1991 | 6 | Rothamsted | 13.6
1991-06-07 | 1991 | 6 | Rothamsted | 15.6
1991-06-08 | 1991 | 6 | Rothamsted | 17.8
1991-06-09 | 1991 | 6 | Rothamsted | 17
1991-06-10 | 1991 | 6 | Rothamsted | 15.5
1991-06-11 | 1991 | 6 | Rothamsted | 18.2
1991-06-12 | 1991 | 6 | Rothamsted | 16.5
1991-06-13 | 1991 | 6 | Rothamsted | 17
1991-06-14 | 1991 | 6 | Rothamsted | 14.6
1991-06-15 | 1991 | 6 | Rothamsted | 15.4
1991-06-16 | 1991 | 6 | Rothamsted | 13.5
1991-06-17 | 1991 | 6 | Rothamsted | 13.3
1991-06-18 | 1991 | 6 | Rothamsted | 16
1991-06-19 | 1991 | 6 | Rothamsted | 17.5
1991-06-20 | 1991 | 6 | Rothamsted | 20.5
1991-06-21 | 1991 | 6 | Rothamsted | 17.3
1991-06-22 | 1991 | 6 | Rothamsted | 15.1
1991-06-23 | 1991 | 6 | Rothamsted | 15.6
1991-06-24 | 1991 | 6 | Rothamsted | 17.8
1991-06-25 | 1991 | 6 | Rothamsted | 18.2
1991-06-26 | 1991 | 6 | Rothamsted | 18.2
1991-06-27 | 1991 | 6 | Rothamsted | 18.1
1991-06-28 | 1991 | 6 | Rothamsted | 19
1991-06-29 | 1991 | 6 | Rothamsted | 20.9
1991-06-30 | 1991 | 6 | Rothamsted | 19.8
1991-07-01 | 1991 | 7 | Rothamsted | 19.4
1991-07-02 | 1991 | 7 | Rothamsted | 21.1
1991-07-03 | 1991 | 7 | Rothamsted | 24.8
1991-07-04 | 1991 | 7 | Rothamsted | 24.7
1991-07-05 | 1991 | 7 | Rothamsted | 23.3
1991-07-06 | 1991 | 7 | Rothamsted | 24.2
1991-07-07 | 1991 | 7 | Rothamsted | 18.8
1991-07-08 | 1991 | 7 | Rothamsted | 20.6
1991-07-09 | 1991 | 7 | Rothamsted | 24
1991-07-10 | 1991 | 7 | Rothamsted | 26.2
1991-07-12 | 1991 | 7 | Rothamsted | 17.9
1991-07-13 | 1991 | 7 | Rothamsted | 22.5
1991-07-14 | 1991 | 7 | Rothamsted | 19.2
1991-07-15 | 1991 | 7 | Rothamsted | 20
1991-07-16 | 1991 | 7 | Rothamsted | 19.5
1991-07-17 | 1991 | 7 | Rothamsted | 22
1991-07-18 | 1991 | 7 | Rothamsted | 19.5
1991-07-19 | 1991 | 7 | Rothamsted | 22.5
1991-07-20 | 1991 | 7 | Rothamsted | 20.2
1991-07-21 | 1991 | 7 | Rothamsted | 22.6
1991-07-22 | 1991 | 7 | Rothamsted | 25.6
1991-07-24 | 1991 | 7 | Rothamsted | 19.7
1991-07-25 | 1991 | 7 | Rothamsted | 22.5
1991-07-26 | 1991 | 7 | Rothamsted | 23.5
1991-07-27 | 1991 | 7 | Rothamsted | 23.8
1991-07-28 | 1991 | 7 | Rothamsted | 26.1
1991-07-29 | 1991 | 7 | Rothamsted | 20.1
1991-07-30 | 1991 | 7 | Rothamsted | 22.5
1991-07-31 | 1991 | 7 | Rothamsted | 23
1991-08-01 | 1991 | 8 | Rothamsted | 23.9
1991-08-02 | 1991 | 8 | Rothamsted | 23.9
1991-08-03 | 1991 | 8 | Rothamsted | 23.8
1991-08-04 | 1991 | 8 | Rothamsted | 23.7
1991-08-05 | 1991 | 8 | Rothamsted | 21.2
1991-08-07 | 1991 | 8 | Rothamsted | 22.4
1991-08-08 | 1991 | 8 | Rothamsted | 23.6
1991-08-09 | 1991 | 8 | Rothamsted | 25.5
1991-08-10 | 1991 | 8 | Rothamsted | 20.6
1991-08-11 | 1991 | 8 | Rothamsted | 21.9
1991-08-12 | 1991 | 8 | Rothamsted | 22.3
1991-08-13 | 1991 | 8 | Rothamsted | 24.6
1991-08-14 | 1991 | 8 | Rothamsted | 23.6
1991-08-15 | 1991 | 8 | Rothamsted | 22.4
1991-08-16 | 1991 | 8 | Rothamsted | 22.4
1991-08-17 | 1991 | 8 | Rothamsted | 20
1991-08-18 | 1991 | 8 | Rothamsted | 23.5
1991-08-19 | 1991 | 8 | Rothamsted | 23.9
1991-08-20 | 1991 | 8 | Rothamsted | 26
1991-08-21 | 1991 | 8 | Rothamsted | 23
1991-08-23 | 1991 | 8 | Rothamsted | 20.8
1991-08-24 | 1991 | 8 | Rothamsted | 22.6
1991-08-25 | 1991 | 8 | Rothamsted | 24.5
1991-08-26 | 1991 | 8 | Rothamsted | 24.4
1991-08-27 | 1991 | 8 | Rothamsted | 22
1991-08-28 | 1991 | 8 | Rothamsted | 22.3
1991-08-29 | 1991 | 8 | Rothamsted | 24.2
1991-08-30 | 1991 | 8 | Rothamsted | 25.1
1991-08-31 | 1991 | 8 | Rothamsted | 27.7
1991-09-01 | 1991 | 9 | Rothamsted | 25.6
1991-09-02 | 1991 | 9 | Rothamsted | 22.4
1991-09-03 | 1991 | 9 | Rothamsted | 25
1991-09-04 | 1991 | 9 | Rothamsted | 24.2
1991-09-06 | 1991 | 9 | Rothamsted | 19.6
1991-09-07 | 1991 | 9 | Rothamsted | 22.7
1991-09-08 | 1991 | 9 | Rothamsted | 22
1991-09-09 | 1991 | 9 | Rothamsted | 24.1
1991-09-10 | 1991 | 9 | Rothamsted | 16
1991-09-11 | 1991 | 9 | Rothamsted | 19.8
1991-09-12 | 1991 | 9 | Rothamsted | 22.1
1991-09-13 | 1991 | 9 | Rothamsted | 23.5
1991-09-14 | 1991 | 9 | Rothamsted | 19.8
1991-09-15 | 1991 | 9 | Rothamsted | 20
1991-09-16 | 1991 | 9 | Rothamsted | 20.2
1991-09-17 | 1991 | 9 | Rothamsted | 18
1991-09-18 | 1991 | 9 | Rothamsted | 17.9
1991-09-19 | 1991 | 9 | Rothamsted | 18.8
1991-09-20 | 1991 | 9 | Rothamsted | 23.1
1991-09-21 | 1991 | 9 | Rothamsted | 17.1
1991-09-22 | 1991 | 9 | Rothamsted | 18.6
1991-09-23 | 1991 | 9 | Rothamsted | 15
1991-09-24 | 1991 | 9 | Rothamsted | 17.7
1991-09-25 | 1991 | 9 | Rothamsted | 15.9
1991-09-27 | 1991 | 9 | Rothamsted | 12.7
1991-09-28 | 1991 | 9 | Rothamsted | 15.4
1991-09-29 | 1991 | 9 | Rothamsted | 13.4
1991-09-30 | 1991 | 9 | Rothamsted | 15.5
1992-05-01 | 1992 | 5 | Rothamsted | 11.5
1992-05-02 | 1992 | 5 | Rothamsted | 13.9
1992-05-03 | 1992 | 5 | Rothamsted | 16.1
1992-05-04 | 1992 | 5 | Rothamsted | 13.3
1992-05-05 | 1992 | 5 | Rothamsted | 19
1992-05-06 | 1992 | 5 | Rothamsted | 18.6
1992-05-08 | 1992 | 5 | Rothamsted | 13.7
1992-05-09 | 1992 | 5 | Rothamsted | 11.6
1992-05-10 | 1992 | 5 | Rothamsted | 13.5
1992-05-11 | 1992 | 5 | Rothamsted | 15.5
1992-05-12 | 1992 | 5 | Rothamsted | 21.1
1992-05-13 | 1992 | 5 | Rothamsted | 26
1992-05-14 | 1992 | 5 | Rothamsted | 18.8
1992-05-15 | 1992 | 5 | Rothamsted | 18
1992-05-16 | 1992 | 5 | Rothamsted | 15.9
1992-05-17 | 1992 | 5 | Rothamsted | 19.4
1992-05-18 | 1992 | 5 | Rothamsted | 24
1992-05-19 | 1992 | 5 | Rothamsted | 24
1992-05-20 | 1992 | 5 | Rothamsted | 25
1992-05-21 | 1992 | 5 | Rothamsted | 24.1
1992-05-22 | 1992 | 5 | Rothamsted | 23.5
1992-05-23 | 1992 | 5 | Rothamsted | 25.3
1992-05-24 | 1992 | 5 | Rothamsted | 24.4
1992-05-25 | 1992 | 5 | Rothamsted | 23.4
1992-05-26 | 1992 | 5 | Rothamsted | 21
1992-05-27 | 1992 | 5 | Rothamsted | 23.3
1992-05-29 | 1992 | 5 | Rothamsted | 19
1992-05-30 | 1992 | 5 | Rothamsted | 21
1992-05-31 | 1992 | 5 | Rothamsted | 19
1992-06-01 | 1992 | 6 | Rothamsted | 18.9
1992-06-02 | 1992 | 6 | Rothamsted | 19.5
1992-06-04 | 1992 | 6 | Rothamsted | 14
1992-06-05 | 1992 | 6 | Rothamsted | 21.3
1992-06-06 | 1992 | 6 | Rothamsted | 17
1992-06-07 | 1992 | 6 | Rothamsted | 20.6
1992-06-08 | 1992 | 6 | Rothamsted | 21.5
1992-06-09 | 1992 | 6 | Rothamsted | 22.2
1992-06-10 | 1992 | 6 | Rothamsted | 20.9
1992-06-11 | 1992 | 6 | Rothamsted | 21.6
1992-06-12 | 1992 | 6 | Rothamsted | 23.2
1992-06-13 | 1992 | 6 | Rothamsted | 24.2
1992-06-14 | 1992 | 6 | Rothamsted | 24.5
1992-06-15 | 1992 | 6 | Rothamsted | 19
1992-06-16 | 1992 | 6 | Rothamsted | 17.9
1992-06-17 | 1992 | 6 | Rothamsted | 16.2
1992-06-18 | 1992 | 6 | Rothamsted | 14.4
1992-06-19 | 1992 | 6 | Rothamsted | 17.9
1992-06-20 | 1992 | 6 | Rothamsted | 21.1
1992-06-21 | 1992 | 6 | Rothamsted | 19.4
1992-06-22 | 1992 | 6 | Rothamsted | 19.8
1992-06-23 | 1992 | 6 | Rothamsted | 19.3
1992-06-24 | 1992 | 6 | Rothamsted | 22.5
1992-06-25 | 1992 | 6 | Rothamsted | 23.5
1992-06-26 | 1992 | 6 | Rothamsted | 24.6
1992-06-27 | 1992 | 6 | Rothamsted | 25
1992-06-28 | 1992 | 6 | Rothamsted | 27.2
1992-06-29 | 1992 | 6 | Rothamsted | 22.8
1992-06-30 | 1992 | 6 | Rothamsted | 20.5
1992-07-01 | 1992 | 7 | Rothamsted | 18.1
1992-07-02 | 1992 | 7 | Rothamsted | 16.5
1992-07-03 | 1992 | 7 | Rothamsted | 18.6
1992-07-04 | 1992 | 7 | Rothamsted | 18
1992-07-05 | 1992 | 7 | Rothamsted | 20
1992-07-06 | 1992 | 7 | Rothamsted | 17.3
1992-07-07 | 1992 | 7 | Rothamsted | 18.1
1992-07-08 | 1992 | 7 | Rothamsted | 19.6
1992-07-09 | 1992 | 7 | Rothamsted | 17.3
1992-07-10 | 1992 | 7 | Rothamsted | 17.4
1992-07-11 | 1992 | 7 | Rothamsted | 19.7
1992-07-12 | 1992 | 7 | Rothamsted | 18.1
1992-07-13 | 1992 | 7 | Rothamsted | 20
1992-07-14 | 1992 | 7 | Rothamsted | 21.2
1992-07-15 | 1992 | 7 | Rothamsted | 23.2
1992-07-16 | 1992 | 7 | Rothamsted | 22.9
1992-07-17 | 1992 | 7 | Rothamsted | 22.6
1992-07-18 | 1992 | 7 | Rothamsted | 21.8
1992-07-19 | 1992 | 7 | Rothamsted | 20.2
1992-07-20 | 1992 | 7 | Rothamsted | 22
1992-07-21 | 1992 | 7 | Rothamsted | 22
1992-07-22 | 1992 | 7 | Rothamsted | 21.5
1992-07-23 | 1992 | 7 | Rothamsted | 22.9
1992-07-24 | 1992 | 7 | Rothamsted | 21.4
1992-07-25 | 1992 | 7 | Rothamsted | 19.4
1992-07-26 | 1992 | 7 | Rothamsted | 19.6
1992-07-27 | 1992 | 7 | Rothamsted | 21.1
1992-07-28 | 1992 | 7 | Rothamsted | 24.1
1992-07-29 | 1992 | 7 | Rothamsted | 25
1992-07-30 | 1992 | 7 | Rothamsted | 26.2
1992-07-31 | 1992 | 7 | Rothamsted | 26
1992-08-01 | 1992 | 8 | Rothamsted | 20.7
1992-08-02 | 1992 | 8 | Rothamsted | 21.3
1992-08-03 | 1992 | 8 | Rothamsted | 20.9
1992-08-04 | 1992 | 8 | Rothamsted | 21.6
1992-08-05 | 1992 | 8 | Rothamsted | 22.5
1992-08-06 | 1992 | 8 | Rothamsted | 24.4
1992-08-07 | 1992 | 8 | Rothamsted | 22.9
1992-08-08 | 1992 | 8 | Rothamsted | 23.4
1992-08-09 | 1992 | 8 | Rothamsted | 21.8
1992-08-10 | 1992 | 8 | Rothamsted | 18.6
1992-08-11 | 1992 | 8 | Rothamsted | 18.5
1992-08-12 | 1992 | 8 | Rothamsted | 16
1992-08-13 | 1992 | 8 | Rothamsted | 17.2
1992-08-14 | 1992 | 8 | Rothamsted | 21
1992-08-15 | 1992 | 8 | Rothamsted | 19.2
1992-08-16 | 1992 | 8 | Rothamsted | 20.4
1992-08-17 | 1992 | 8 | Rothamsted | 19
1992-08-18 | 1992 | 8 | Rothamsted | 21.6
1992-08-19 | 1992 | 8 | Rothamsted | 18.4
1992-08-20 | 1992 | 8 | Rothamsted | 21.4
1992-08-21 | 1992 | 8 | Rothamsted | 19.3
1992-08-22 | 1992 | 8 | Rothamsted | 18.5
1992-08-23 | 1992 | 8 | Rothamsted | 18.2
1992-08-24 | 1992 | 8 | Rothamsted | 21.5
1992-08-25 | 1992 | 8 | Rothamsted | 17.6
1992-08-26 | 1992 | 8 | Rothamsted | 19.5
1992-08-27 | 1992 | 8 | Rothamsted | 19
1992-08-28 | 1992 | 8 | Rothamsted | 18
1992-08-29 | 1992 | 8 | Rothamsted | 16.6
1992-08-30 | 1992 | 8 | Rothamsted | 16.9
1992-08-31 | 1992 | 8 | Rothamsted | 15.8
1992-09-01 | 1992 | 9 | Rothamsted | 20.1
1992-09-02 | 1992 | 9 | Rothamsted | 16.1
1992-09-03 | 1992 | 9 | Rothamsted | 15.1
1992-09-04 | 1992 | 9 | Rothamsted | 16
1992-09-05 | 1992 | 9 | Rothamsted | 15.8
1992-09-06 | 1992 | 9 | Rothamsted | 16.4
1992-09-07 | 1992 | 9 | Rothamsted | 15.6
1992-09-08 | 1992 | 9 | Rothamsted | 16.6
1992-09-09 | 1992 | 9 | Rothamsted | 19.7
1992-09-10 | 1992 | 9 | Rothamsted | 16.9
1992-09-11 | 1992 | 9 | Rothamsted | 16.5
1992-09-12 | 1992 | 9 | Rothamsted | 14.6
1992-09-13 | 1992 | 9 | Rothamsted | 17
1992-09-14 | 1992 | 9 | Rothamsted | 17.7
1992-09-15 | 1992 | 9 | Rothamsted | 18.4
1992-09-16 | 1992 | 9 | Rothamsted | 20.1
1992-09-17 | 1992 | 9 | Rothamsted | 19.2
1992-09-19 | 1992 | 9 | Rothamsted | 18.9
1992-09-20 | 1992 | 9 | Rothamsted | 16
1992-09-21 | 1992 | 9 | Rothamsted | 16.1
1992-09-23 | 1992 | 9 | Rothamsted | 17.1
1992-09-24 | 1992 | 9 | Rothamsted | 13.8
1992-09-25 | 1992 | 9 | Rothamsted | 21.9
1992-09-26 | 1992 | 9 | Rothamsted | 21.8
1992-09-27 | 1992 | 9 | Rothamsted | 22.4
1992-09-28 | 1992 | 9 | Rothamsted | 19
1992-09-29 | 1992 | 9 | Rothamsted | 15.6
1992-09-30 | 1992 | 9 | Rothamsted | 15.5
1993-05-02 | 1993 | 5 | Rothamsted | 11.9
1993-05-03 | 1993 | 5 | Rothamsted | 13.5
1993-05-04 | 1993 | 5 | Rothamsted | 13.1
1993-05-05 | 1993 | 5 | Rothamsted | 12.9
1993-05-06 | 1993 | 5 | Rothamsted | 14.1
1993-05-07 | 1993 | 5 | Rothamsted | 14.1
1993-05-08 | 1993 | 5 | Rothamsted | 13.9
1993-05-09 | 1993 | 5 | Rothamsted | 18.9
1993-05-10 | 1993 | 5 | Rothamsted | 22
1993-05-11 | 1993 | 5 | Rothamsted | 16.5
1993-05-12 | 1993 | 5 | Rothamsted | 14.1
1993-05-13 | 1993 | 5 | Rothamsted | 14.9
1993-05-14 | 1993 | 5 | Rothamsted | 14.1
1993-05-15 | 1993 | 5 | Rothamsted | 17.8
1993-05-16 | 1993 | 5 | Rothamsted | 21.6
1993-05-17 | 1993 | 5 | Rothamsted | 18
1993-05-18 | 1993 | 5 | Rothamsted | 17.1
1993-05-20 | 1993 | 5 | Rothamsted | 15.7
1993-05-21 | 1993 | 5 | Rothamsted | 17.2
1993-05-22 | 1993 | 5 | Rothamsted | 20.9
1993-05-23 | 1993 | 5 | Rothamsted | 22.5
1993-05-24 | 1993 | 5 | Rothamsted | 17.5
1993-05-25 | 1993 | 5 | Rothamsted | 17
1993-05-27 | 1993 | 5 | Rothamsted | 15.9
1993-05-28 | 1993 | 5 | Rothamsted | 19.1
1993-05-29 | 1993 | 5 | Rothamsted | 14.9
1993-05-30 | 1993 | 5 | Rothamsted | 16
1993-05-31 | 1993 | 5 | Rothamsted | 19.2
1993-06-01 | 1993 | 6 | Rothamsted | 18.8
1993-06-02 | 1993 | 6 | Rothamsted | 16.4
1993-06-03 | 1993 | 6 | Rothamsted | 20.9
1993-06-04 | 1993 | 6 | Rothamsted | 21.8
1993-06-05 | 1993 | 6 | Rothamsted | 23.9
1993-06-06 | 1993 | 6 | Rothamsted | 24.6
1993-06-07 | 1993 | 6 | Rothamsted | 26.7
1993-06-08 | 1993 | 6 | Rothamsted | 24.9
1993-06-09 | 1993 | 6 | Rothamsted | 22.5
1993-06-10 | 1993 | 6 | Rothamsted | 18.5
1993-06-12 | 1993 | 6 | Rothamsted | 15.3
1993-06-13 | 1993 | 6 | Rothamsted | 16.5
1993-06-14 | 1993 | 6 | Rothamsted | 19
1993-06-15 | 1993 | 6 | Rothamsted | 16
1993-06-16 | 1993 | 6 | Rothamsted | 19.5
1993-06-17 | 1993 | 6 | Rothamsted | 18.3
1993-06-18 | 1993 | 6 | Rothamsted | 18.3
1993-06-19 | 1993 | 6 | Rothamsted | 18.2
1993-06-20 | 1993 | 6 | Rothamsted | 16.5
1993-06-21 | 1993 | 6 | Rothamsted | 17.7
1993-06-22 | 1993 | 6 | Rothamsted | 17.4
1993-06-23 | 1993 | 6 | Rothamsted | 19.3
1993-06-24 | 1993 | 6 | Rothamsted | 19.3
1993-06-25 | 1993 | 6 | Rothamsted | 21.4
1993-06-26 | 1993 | 6 | Rothamsted | 22.1
1993-06-27 | 1993 | 6 | Rothamsted | 21
1993-06-28 | 1993 | 6 | Rothamsted | 22.3
1993-06-29 | 1993 | 6 | Rothamsted | 24.9
1993-06-30 | 1993 | 6 | Rothamsted | 20
1993-07-01 | 1993 | 7 | Rothamsted | 23.1
1993-07-02 | 1993 | 7 | Rothamsted | 25
1993-07-03 | 1993 | 7 | Rothamsted | 25.5
1993-07-05 | 1993 | 7 | Rothamsted | 21.4
1993-07-06 | 1993 | 7 | Rothamsted | 21
1993-07-07 | 1993 | 7 | Rothamsted | 21
1993-07-09 | 1993 | 7 | Rothamsted | 16.5
1993-07-10 | 1993 | 7 | Rothamsted | 16.8
1993-07-11 | 1993 | 7 | Rothamsted | 16.1
1993-07-12 | 1993 | 7 | Rothamsted | 16.7
1993-07-13 | 1993 | 7 | Rothamsted | 22
1993-07-14 | 1993 | 7 | Rothamsted | 21.2
1993-07-15 | 1993 | 7 | Rothamsted | 21
1993-07-16 | 1993 | 7 | Rothamsted | 19.6
1993-07-17 | 1993 | 7 | Rothamsted | 20
1993-07-18 | 1993 | 7 | Rothamsted | 19
1993-07-19 | 1993 | 7 | Rothamsted | 17.1
1993-07-20 | 1993 | 7 | Rothamsted | 16.9
1993-07-21 | 1993 | 7 | Rothamsted | 21
1993-07-22 | 1993 | 7 | Rothamsted | 23.4
1993-07-24 | 1993 | 7 | Rothamsted | 18.5
1993-07-25 | 1993 | 7 | Rothamsted | 18
1993-07-26 | 1993 | 7 | Rothamsted | 20
1993-07-27 | 1993 | 7 | Rothamsted | 21.5
1993-07-28 | 1993 | 7 | Rothamsted | 18.8
1993-07-29 | 1993 | 7 | Rothamsted | 20
1993-07-30 | 1993 | 7 | Rothamsted | 18.2
1993-07-31 | 1993 | 7 | Rothamsted | 20.6
1993-08-01 | 1993 | 8 | Rothamsted | 20.4
1993-08-02 | 1993 | 8 | Rothamsted | 20.4
1993-08-03 | 1993 | 8 | Rothamsted | 19.5
1993-08-04 | 1993 | 8 | Rothamsted | 18.2
1993-08-05 | 1993 | 8 | Rothamsted | 19.6
1993-08-06 | 1993 | 8 | Rothamsted | 21.9
1993-08-07 | 1993 | 8 | Rothamsted | 19.6
1993-08-08 | 1993 | 8 | Rothamsted | 22
1993-08-10 | 1993 | 8 | Rothamsted | 19.9
1993-08-11 | 1993 | 8 | Rothamsted | 19
1993-08-12 | 1993 | 8 | Rothamsted | 19.6
1993-08-13 | 1993 | 8 | Rothamsted | 24
1993-08-14 | 1993 | 8 | Rothamsted | 20.5
1993-08-15 | 1993 | 8 | Rothamsted | 20
1993-08-16 | 1993 | 8 | Rothamsted | 21.1
1993-08-17 | 1993 | 8 | Rothamsted | 21.9
1993-08-18 | 1993 | 8 | Rothamsted | 24.1
1993-08-19 | 1993 | 8 | Rothamsted | 23.6
1993-08-20 | 1993 | 8 | Rothamsted | 22.1
1993-08-22 | 1993 | 8 | Rothamsted | 15.7
1993-08-23 | 1993 | 8 | Rothamsted | 16
1993-08-24 | 1993 | 8 | Rothamsted | 16.7
1993-08-25 | 1993 | 8 | Rothamsted | 15.8
1993-08-26 | 1993 | 8 | Rothamsted | 16.2
1993-08-27 | 1993 | 8 | Rothamsted | 19
1993-08-28 | 1993 | 8 | Rothamsted | 21.5
1993-08-29 | 1993 | 8 | Rothamsted | 22.3
1993-08-30 | 1993 | 8 | Rothamsted | 18.3
1993-08-31 | 1993 | 8 | Rothamsted | 22.7
1993-09-01 | 1993 | 9 | Rothamsted | 18.4
1993-09-02 | 1993 | 9 | Rothamsted | 15.6
1993-09-03 | 1993 | 9 | Rothamsted | 14.5
1993-09-04 | 1993 | 9 | Rothamsted | 16.5
1993-09-05 | 1993 | 9 | Rothamsted | 17.5
1993-09-06 | 1993 | 9 | Rothamsted | 21.3
1993-09-07 | 1993 | 9 | Rothamsted | 19.2
1993-09-08 | 1993 | 9 | Rothamsted | 18.5
1993-09-09 | 1993 | 9 | Rothamsted | 16.5
1993-09-10 | 1993 | 9 | Rothamsted | 17.5
1993-09-11 | 1993 | 9 | Rothamsted | 15
1993-09-12 | 1993 | 9 | Rothamsted | 16.5
1993-09-14 | 1993 | 9 | Rothamsted | 15.4
1993-09-15 | 1993 | 9 | Rothamsted | 12.9
1993-09-16 | 1993 | 9 | Rothamsted | 15.1
1993-09-17 | 1993 | 9 | Rothamsted | 16
1993-09-18 | 1993 | 9 | Rothamsted | 19.1
1993-09-19 | 1993 | 9 | Rothamsted | 15.7
1993-09-20 | 1993 | 9 | Rothamsted | 18.7
1993-09-21 | 1993 | 9 | Rothamsted | 18.7
1993-09-22 | 1993 | 9 | Rothamsted | 15.8
1993-09-23 | 1993 | 9 | Rothamsted | 15.3
1993-09-24 | 1993 | 9 | Rothamsted | 11.8
1993-09-25 | 1993 | 9 | Rothamsted | 12.7
1993-09-27 | 1993 | 9 | Rothamsted | 11.5
1993-09-28 | 1993 | 9 | Rothamsted | 13.1
1993-09-29 | 1993 | 9 | Rothamsted | 14.1
1993-09-30 | 1993 | 9 | Rothamsted | 12.4
1994-05-01 | 1994 | 5 | Rothamsted | 15.5
1994-05-02 | 1994 | 5 | Rothamsted | 19.3
1994-05-03 | 1994 | 5 | Rothamsted | 14.1
1994-05-04 | 1994 | 5 | Rothamsted | 11.8
1994-05-05 | 1994 | 5 | Rothamsted | 15.3
1994-05-06 | 1994 | 5 | Rothamsted | 13
1994-05-07 | 1994 | 5 | Rothamsted | 15.2
1994-05-08 | 1994 | 5 | Rothamsted | 15.1
1994-05-09 | 1994 | 5 | Rothamsted | 16.2
1994-05-10 | 1994 | 5 | Rothamsted | 16.5
1994-05-11 | 1994 | 5 | Rothamsted | 15.1
1994-05-12 | 1994 | 5 | Rothamsted | 18.5
1994-05-13 | 1994 | 5 | Rothamsted | 19.5
1994-05-14 | 1994 | 5 | Rothamsted | 18.6
1994-05-17 | 1994 | 5 | Rothamsted | 11.6
1994-05-18 | 1994 | 5 | Rothamsted | 11.5
1994-05-19 | 1994 | 5 | Rothamsted | 15
1994-05-20 | 1994 | 5 | Rothamsted | 12.4
1994-05-21 | 1994 | 5 | Rothamsted | 14.5
1994-05-22 | 1994 | 5 | Rothamsted | 14.6
1994-05-23 | 1994 | 5 | Rothamsted | 13
1994-05-24 | 1994 | 5 | Rothamsted | 11.6
1994-05-25 | 1994 | 5 | Rothamsted | 10.8
1994-05-26 | 1994 | 5 | Rothamsted | 10.3
1994-05-27 | 1994 | 5 | Rothamsted | 12.5
1994-05-28 | 1994 | 5 | Rothamsted | 14
1994-05-29 | 1994 | 5 | Rothamsted | 16
1994-05-30 | 1994 | 5 | Rothamsted | 19.7
1994-05-31 | 1994 | 5 | Rothamsted | 24.2
1994-06-01 | 1994 | 6 | Rothamsted | 17.7
1994-06-02 | 1994 | 6 | Rothamsted | 15.7
1994-06-04 | 1994 | 6 | Rothamsted | 15.5
1994-06-05 | 1994 | 6 | Rothamsted | 20.2
1994-06-06 | 1994 | 6 | Rothamsted | 19.4
1994-06-08 | 1994 | 6 | Rothamsted | 13.5
1994-06-09 | 1994 | 6 | Rothamsted | 14.4
1994-06-10 | 1994 | 6 | Rothamsted | 18
1994-06-11 | 1994 | 6 | Rothamsted | 19
1994-06-12 | 1994 | 6 | Rothamsted | 21.5
1994-06-13 | 1994 | 6 | Rothamsted | 21.7
1994-06-14 | 1994 | 6 | Rothamsted | 21.5
1994-06-15 | 1994 | 6 | Rothamsted | 21.1
1994-06-16 | 1994 | 6 | Rothamsted | 23
1994-06-17 | 1994 | 6 | Rothamsted | 19.7
1994-06-18 | 1994 | 6 | Rothamsted | 18.8
1994-06-19 | 1994 | 6 | Rothamsted | 17.3
1994-06-20 | 1994 | 6 | Rothamsted | 16.8
1994-06-21 | 1994 | 6 | Rothamsted | 19.6
1994-06-22 | 1994 | 6 | Rothamsted | 22.5
1994-06-23 | 1994 | 6 | Rothamsted | 25.3
1994-06-24 | 1994 | 6 | Rothamsted | 21.2
1994-06-25 | 1994 | 6 | Rothamsted | 19.7
1994-06-26 | 1994 | 6 | Rothamsted | 24.3
1994-06-27 | 1994 | 6 | Rothamsted | 26.1
1994-06-28 | 1994 | 6 | Rothamsted | 19.6
1994-06-29 | 1994 | 6 | Rothamsted | 22.4
1994-06-30 | 1994 | 6 | Rothamsted | 24
1994-07-01 | 1994 | 7 | Rothamsted | 26.5
1994-07-02 | 1994 | 7 | Rothamsted | 26.2
1994-07-03 | 1994 | 7 | Rothamsted | 23
1994-07-04 | 1994 | 7 | Rothamsted | 20.3
1994-07-05 | 1994 | 7 | Rothamsted | 19.2
1994-07-06 | 1994 | 7 | Rothamsted | 20.9
1994-07-07 | 1994 | 7 | Rothamsted | 20.8
1994-07-08 | 1994 | 7 | Rothamsted | 23.3
1994-07-09 | 1994 | 7 | Rothamsted | 25.2
1994-07-10 | 1994 | 7 | Rothamsted | 28.5
1994-07-11 | 1994 | 7 | Rothamsted | 30.6
1994-07-13 | 1994 | 7 | Rothamsted | 24.5
1994-07-14 | 1994 | 7 | Rothamsted | 21.1
1994-07-15 | 1994 | 7 | Rothamsted | 22.8
1994-07-16 | 1994 | 7 | Rothamsted | 23.3
1994-07-17 | 1994 | 7 | Rothamsted | 23.3
1994-07-18 | 1994 | 7 | Rothamsted | 24.2
1994-07-19 | 1994 | 7 | Rothamsted | 26.5
1994-07-20 | 1994 | 7 | Rothamsted | 27.8
1994-07-21 | 1994 | 7 | Rothamsted | 25.6
1994-07-22 | 1994 | 7 | Rothamsted | 26.4
1994-07-23 | 1994 | 7 | Rothamsted | 30.2
1994-07-24 | 1994 | 7 | Rothamsted | 28.5
1994-07-26 | 1994 | 7 | Rothamsted | 25.5
1994-07-28 | 1994 | 7 | Rothamsted | 24.5
1994-07-29 | 1994 | 7 | Rothamsted | 28.6
1994-07-30 | 1994 | 7 | Rothamsted | 24.8
1994-07-31 | 1994 | 7 | Rothamsted | 22.8
1994-08-01 | 1994 | 8 | Rothamsted | 22.8
1994-08-02 | 1994 | 8 | Rothamsted | 25.4
1994-08-03 | 1994 | 8 | Rothamsted | 24
1994-08-04 | 1994 | 8 | Rothamsted | 26
1994-08-05 | 1994 | 8 | Rothamsted | 23.5
1994-08-06 | 1994 | 8 | Rothamsted | 23.2
1994-08-07 | 1994 | 8 | Rothamsted | 21.9
1994-08-08 | 1994 | 8 | Rothamsted | 21.8
1994-08-09 | 1994 | 8 | Rothamsted | 17.3
1994-08-10 | 1994 | 8 | Rothamsted | 17.1
1994-08-11 | 1994 | 8 | Rothamsted | 18.3
1994-08-12 | 1994 | 8 | Rothamsted | 19.6
1994-08-13 | 1994 | 8 | Rothamsted | 19
1994-08-14 | 1994 | 8 | Rothamsted | 22
1994-08-15 | 1994 | 8 | Rothamsted | 23.6
1994-08-16 | 1994 | 8 | Rothamsted | 17.6
1994-08-17 | 1994 | 8 | Rothamsted | 20.6
1994-08-18 | 1994 | 8 | Rothamsted | 21.4
1994-08-19 | 1994 | 8 | Rothamsted | 19.6
1994-08-20 | 1994 | 8 | Rothamsted | 22
1994-08-21 | 1994 | 8 | Rothamsted | 24.2
1994-08-22 | 1994 | 8 | Rothamsted | 21.1
1994-08-23 | 1994 | 8 | Rothamsted | 21.2
1994-08-24 | 1994 | 8 | Rothamsted | 19.1
1994-08-25 | 1994 | 8 | Rothamsted | 22.5
1994-08-26 | 1994 | 8 | Rothamsted | 19.9
1994-08-27 | 1994 | 8 | Rothamsted | 18.6
1994-08-28 | 1994 | 8 | Rothamsted | 19.1
1994-08-29 | 1994 | 8 | Rothamsted | 19
1994-08-30 | 1994 | 8 | Rothamsted | 17
1994-08-31 | 1994 | 8 | Rothamsted | 15.7
1994-09-01 | 1994 | 9 | Rothamsted | 20
1994-09-02 | 1994 | 9 | Rothamsted | 17.9
1994-09-03 | 1994 | 9 | Rothamsted | 19
1994-09-04 | 1994 | 9 | Rothamsted | 17.9
1994-09-05 | 1994 | 9 | Rothamsted | 16.5
1994-09-06 | 1994 | 9 | Rothamsted | 19
1994-09-07 | 1994 | 9 | Rothamsted | 16.9
1994-09-08 | 1994 | 9 | Rothamsted | 17.8
1994-09-09 | 1994 | 9 | Rothamsted | 16.8
1994-09-10 | 1994 | 9 | Rothamsted | 17.2
1994-09-11 | 1994 | 9 | Rothamsted | 16.8
1994-09-12 | 1994 | 9 | Rothamsted | 18.5
1994-09-13 | 1994 | 9 | Rothamsted | 18.5
1994-09-15 | 1994 | 9 | Rothamsted | 12.4
1994-09-16 | 1994 | 9 | Rothamsted | 13.5
1994-09-17 | 1994 | 9 | Rothamsted | 13
1994-09-18 | 1994 | 9 | Rothamsted | 12.1
1994-09-19 | 1994 | 9 | Rothamsted | 13.3
1994-09-20 | 1994 | 9 | Rothamsted | 18.6
1994-09-21 | 1994 | 9 | Rothamsted | 18.1
1994-09-22 | 1994 | 9 | Rothamsted | 18.1
1994-09-23 | 1994 | 9 | Rothamsted | 17
1994-09-25 | 1994 | 9 | Rothamsted | 15.6
1994-09-26 | 1994 | 9 | Rothamsted | 17
1994-09-27 | 1994 | 9 | Rothamsted | 17.1
1994-09-28 | 1994 | 9 | Rothamsted | 15
1994-09-29 | 1994 | 9 | Rothamsted | 13.7
1994-09-30 | 1994 | 9 | Rothamsted | 15.1
1995-05-01 | 1995 | 5 | Rothamsted | 21.7
1995-05-02 | 1995 | 5 | Rothamsted | 23.1
1995-05-03 | 1995 | 5 | Rothamsted | 24.8
1995-05-04 | 1995 | 5 | Rothamsted | 25
1995-05-05 | 1995 | 5 | Rothamsted | 24.4
1995-05-06 | 1995 | 5 | Rothamsted | 23.9
1995-05-08 | 1995 | 5 | Rothamsted | 14.3
1995-05-09 | 1995 | 5 | Rothamsted | 13.3
1995-05-10 | 1995 | 5 | Rothamsted | 10
1995-05-11 | 1995 | 5 | Rothamsted | 8.8
1995-05-12 | 1995 | 5 | Rothamsted | 11
1995-05-13 | 1995 | 5 | Rothamsted | 12.6
1995-05-14 | 1995 | 5 | Rothamsted | 14.8
1995-05-15 | 1995 | 5 | Rothamsted | 12.7
1995-05-17 | 1995 | 5 | Rothamsted | 13
1995-05-18 | 1995 | 5 | Rothamsted | 14.5
1995-05-19 | 1995 | 5 | Rothamsted | 14
1995-05-20 | 1995 | 5 | Rothamsted | 14.6
1995-05-21 | 1995 | 5 | Rothamsted | 17.6
1995-05-22 | 1995 | 5 | Rothamsted | 20.1
1995-05-23 | 1995 | 5 | Rothamsted | 20.1
1995-05-24 | 1995 | 5 | Rothamsted | 17.9
1995-05-25 | 1995 | 5 | Rothamsted | 18.5
1995-05-26 | 1995 | 5 | Rothamsted | 19.1
1995-05-27 | 1995 | 5 | Rothamsted | 19.4
1995-05-28 | 1995 | 5 | Rothamsted | 16.9
1995-05-29 | 1995 | 5 | Rothamsted | 15.8
1995-05-30 | 1995 | 5 | Rothamsted | 17.4
1995-05-31 | 1995 | 5 | Rothamsted | 16.8
1995-06-01 | 1995 | 6 | Rothamsted | 16.6
1995-06-02 | 1995 | 6 | Rothamsted | 14.5
1995-06-03 | 1995 | 6 | Rothamsted | 15
1995-06-04 | 1995 | 6 | Rothamsted | 17
1995-06-05 | 1995 | 6 | Rothamsted | 17.7
1995-06-06 | 1995 | 6 | Rothamsted | 16.5
1995-06-08 | 1995 | 6 | Rothamsted | 15.5
1995-06-09 | 1995 | 6 | Rothamsted | 14.1
1995-06-10 | 1995 | 6 | Rothamsted | 13.2
1995-06-11 | 1995 | 6 | Rothamsted | 12.3
1995-06-12 | 1995 | 6 | Rothamsted | 11.5
1995-06-13 | 1995 | 6 | Rothamsted | 14.2
1995-06-14 | 1995 | 6 | Rothamsted | 15.5
1995-06-15 | 1995 | 6 | Rothamsted | 16
1995-06-16 | 1995 | 6 | Rothamsted | 16.1
1995-06-17 | 1995 | 6 | Rothamsted | 20.5
1995-06-18 | 1995 | 6 | Rothamsted | 23.4
1995-06-19 | 1995 | 6 | Rothamsted | 22.3
1995-06-20 | 1995 | 6 | Rothamsted | 19.9
1995-06-21 | 1995 | 6 | Rothamsted | 20.6
1995-06-22 | 1995 | 6 | Rothamsted | 18.4
1995-06-24 | 1995 | 6 | Rothamsted | 19.9
1995-06-25 | 1995 | 6 | Rothamsted | 22.2
1995-06-26 | 1995 | 6 | Rothamsted | 23
1995-06-27 | 1995 | 6 | Rothamsted | 27.8
1995-06-28 | 1995 | 6 | Rothamsted | 27.9
1995-06-29 | 1995 | 6 | Rothamsted | 30.4
1995-06-30 | 1995 | 6 | Rothamsted | 20.6
1995-07-01 | 1995 | 7 | Rothamsted | 20.4
1995-07-02 | 1995 | 7 | Rothamsted | 17.9
1995-07-03 | 1995 | 7 | Rothamsted | 20
1995-07-04 | 1995 | 7 | Rothamsted | 22.8
1995-07-05 | 1995 | 7 | Rothamsted | 23.6
1995-07-06 | 1995 | 7 | Rothamsted | 23.3
1995-07-07 | 1995 | 7 | Rothamsted | 26
1995-07-08 | 1995 | 7 | Rothamsted | 25.7
1995-07-09 | 1995 | 7 | Rothamsted | 30.4
1995-07-10 | 1995 | 7 | Rothamsted | 27.7
1995-07-11 | 1995 | 7 | Rothamsted | 25.4
1995-07-12 | 1995 | 7 | Rothamsted | 23.2
1995-07-13 | 1995 | 7 | Rothamsted | 23.1
1995-07-14 | 1995 | 7 | Rothamsted | 20
1995-07-15 | 1995 | 7 | Rothamsted | 21.9
1995-07-16 | 1995 | 7 | Rothamsted | 21.4
1995-07-17 | 1995 | 7 | Rothamsted | 23.9
1995-07-18 | 1995 | 7 | Rothamsted | 24.8
1995-07-19 | 1995 | 7 | Rothamsted | 30
1995-07-20 | 1995 | 7 | Rothamsted | 26.7
1995-07-21 | 1995 | 7 | Rothamsted | 21.5
1995-07-22 | 1995 | 7 | Rothamsted | 24.1
1995-07-23 | 1995 | 7 | Rothamsted | 26.4
1995-07-24 | 1995 | 7 | Rothamsted | 26.2
1995-07-25 | 1995 | 7 | Rothamsted | 24.6
1995-07-26 | 1995 | 7 | Rothamsted | 23
1995-07-27 | 1995 | 7 | Rothamsted | 26.5
1995-07-28 | 1995 | 7 | Rothamsted | 29.8
1995-07-29 | 1995 | 7 | Rothamsted | 30.1
1995-07-30 | 1995 | 7 | Rothamsted | 30.4
1995-07-31 | 1995 | 7 | Rothamsted | 31.7
1995-08-01 | 1995 | 8 | Rothamsted | 30.6
1995-08-02 | 1995 | 8 | Rothamsted | 29.4
1995-08-03 | 1995 | 8 | Rothamsted | 29.3
1995-08-04 | 1995 | 8 | Rothamsted | 25.6
1995-08-05 | 1995 | 8 | Rothamsted | 23.9
1995-08-06 | 1995 | 8 | Rothamsted | 20
1995-08-07 | 1995 | 8 | Rothamsted | 19.5
1995-08-08 | 1995 | 8 | Rothamsted | 24.1
1995-08-09 | 1995 | 8 | Rothamsted | 27.1
1995-08-10 | 1995 | 8 | Rothamsted | 29.4
1995-08-11 | 1995 | 8 | Rothamsted | 29.5
1995-08-12 | 1995 | 8 | Rothamsted | 23.3
1995-08-13 | 1995 | 8 | Rothamsted | 23.5
1995-08-14 | 1995 | 8 | Rothamsted | 28.1
1995-08-15 | 1995 | 8 | Rothamsted | 28.2
1995-08-16 | 1995 | 8 | Rothamsted | 26.5
1995-08-17 | 1995 | 8 | Rothamsted | 28
1995-08-18 | 1995 | 8 | Rothamsted | 29
1995-08-19 | 1995 | 8 | Rothamsted | 27.5
1995-08-20 | 1995 | 8 | Rothamsted | 28.2
1995-08-21 | 1995 | 8 | Rothamsted | 28.4
1995-08-22 | 1995 | 8 | Rothamsted | 22.2
1995-08-23 | 1995 | 8 | Rothamsted | 22.8
1995-08-24 | 1995 | 8 | Rothamsted | 24.5
1995-08-25 | 1995 | 8 | Rothamsted | 22.9
1995-08-27 | 1995 | 8 | Rothamsted | 18.1
1995-08-28 | 1995 | 8 | Rothamsted | 15.9
1995-08-29 | 1995 | 8 | Rothamsted | 20.6
1995-08-30 | 1995 | 8 | Rothamsted | 19.1
1995-08-31 | 1995 | 8 | Rothamsted | 18
1995-09-01 | 1995 | 9 | Rothamsted | 17.2
1995-09-02 | 1995 | 9 | Rothamsted | 19.2
1995-09-03 | 1995 | 9 | Rothamsted | 19.2
1995-09-04 | 1995 | 9 | Rothamsted | 18.5
1995-09-05 | 1995 | 9 | Rothamsted | 19.5
1995-09-06 | 1995 | 9 | Rothamsted | 17.5
1995-09-07 | 1995 | 9 | Rothamsted | 17.4
1995-09-08 | 1995 | 9 | Rothamsted | 20.3
1995-09-09 | 1995 | 9 | Rothamsted | 17.2
1995-09-10 | 1995 | 9 | Rothamsted | 18.7
1995-09-11 | 1995 | 9 | Rothamsted | 18
1995-09-12 | 1995 | 9 | Rothamsted | 17.9
1995-09-13 | 1995 | 9 | Rothamsted | 18.8
1995-09-14 | 1995 | 9 | Rothamsted | 15.7
1995-09-15 | 1995 | 9 | Rothamsted | 17.3
1995-09-16 | 1995 | 9 | Rothamsted | 16.9
1995-09-17 | 1995 | 9 | Rothamsted | 19
1995-09-18 | 1995 | 9 | Rothamsted | 16.4
1995-09-20 | 1995 | 9 | Rothamsted | 17.5
1995-09-21 | 1995 | 9 | Rothamsted | 18.3
1995-09-22 | 1995 | 9 | Rothamsted | 17.3
1995-09-23 | 1995 | 9 | Rothamsted | 14.1
1995-09-24 | 1995 | 9 | Rothamsted | 15.6
1995-09-25 | 1995 | 9 | Rothamsted | 16
1995-09-26 | 1995 | 9 | Rothamsted | 14.2
1995-09-27 | 1995 | 9 | Rothamsted | 14
1995-09-28 | 1995 | 9 | Rothamsted | 14.5
1995-09-29 | 1995 | 9 | Rothamsted | 16.5
1995-09-30 | 1995 | 9 | Rothamsted | 18.1
1996-05-02 | 1996 | 5 | Rothamsted | 11.1
1996-05-03 | 1996 | 5 | Rothamsted | 10.9
1996-05-04 | 1996 | 5 | Rothamsted | 10.9
1996-05-05 | 1996 | 5 | Rothamsted | 13.6
1996-05-06 | 1996 | 5 | Rothamsted | 13.2
1996-05-07 | 1996 | 5 | Rothamsted | 11
1996-05-08 | 1996 | 5 | Rothamsted | 10.8
1996-05-09 | 1996 | 5 | Rothamsted | 10.3
1996-05-10 | 1996 | 5 | Rothamsted | 10
1996-05-11 | 1996 | 5 | Rothamsted | 13.2
1996-05-12 | 1996 | 5 | Rothamsted | 15
1996-05-13 | 1996 | 5 | Rothamsted | 14.7
1996-05-14 | 1996 | 5 | Rothamsted | 13.8
1996-05-15 | 1996 | 5 | Rothamsted | 8.6
1996-05-16 | 1996 | 5 | Rothamsted | 7.8
1996-05-17 | 1996 | 5 | Rothamsted | 8.2
1996-05-18 | 1996 | 5 | Rothamsted | 11.3
1996-05-19 | 1996 | 5 | Rothamsted | 14.7
1996-05-20 | 1996 | 5 | Rothamsted | 14.5
1996-05-21 | 1996 | 5 | Rothamsted | 13.9
1996-05-22 | 1996 | 5 | Rothamsted | 15.2
1996-05-23 | 1996 | 5 | Rothamsted | 13
1996-05-24 | 1996 | 5 | Rothamsted | 16.1
1996-05-25 | 1996 | 5 | Rothamsted | 14.1
1996-05-26 | 1996 | 5 | Rothamsted | 13.8
1996-05-27 | 1996 | 5 | Rothamsted | 15.6
1996-05-28 | 1996 | 5 | Rothamsted | 19
1996-05-29 | 1996 | 5 | Rothamsted | 23.6
1996-05-31 | 1996 | 5 | Rothamsted | 16.1
1996-06-01 | 1996 | 6 | Rothamsted | 17.6
1996-06-02 | 1996 | 6 | Rothamsted | 17.6
1996-06-03 | 1996 | 6 | Rothamsted | 21
1996-06-04 | 1996 | 6 | Rothamsted | 25.8
1996-06-05 | 1996 | 6 | Rothamsted | 28.4
1996-06-06 | 1996 | 6 | Rothamsted | 29.1
1996-06-08 | 1996 | 6 | Rothamsted | 20.5
1996-06-09 | 1996 | 6 | Rothamsted | 22
1996-06-10 | 1996 | 6 | Rothamsted | 20.6
1996-06-11 | 1996 | 6 | Rothamsted | 19
1996-06-12 | 1996 | 6 | Rothamsted | 19.5
1996-06-13 | 1996 | 6 | Rothamsted | 20.4
1996-06-14 | 1996 | 6 | Rothamsted | 22.5
1996-06-15 | 1996 | 6 | Rothamsted | 24.6
1996-06-16 | 1996 | 6 | Rothamsted | 25.6
1996-06-17 | 1996 | 6 | Rothamsted | 19.4
1996-06-18 | 1996 | 6 | Rothamsted | 21.5
1996-06-19 | 1996 | 6 | Rothamsted | 15.5
1996-06-20 | 1996 | 6 | Rothamsted | 14.5
1996-06-21 | 1996 | 6 | Rothamsted | 15.3
1996-06-22 | 1996 | 6 | Rothamsted | 19.8
1996-06-23 | 1996 | 6 | Rothamsted | 20.5
1996-06-24 | 1996 | 6 | Rothamsted | 24.4
1996-06-25 | 1996 | 6 | Rothamsted | 23.1
1996-06-26 | 1996 | 6 | Rothamsted | 22.1
1996-06-27 | 1996 | 6 | Rothamsted | 18.1
1996-06-28 | 1996 | 6 | Rothamsted | 16.5
1996-06-29 | 1996 | 6 | Rothamsted | 19.5
1996-06-30 | 1996 | 6 | Rothamsted | 17.2
1996-07-01 | 1996 | 7 | Rothamsted | 17.4
1996-07-02 | 1996 | 7 | Rothamsted | 17.5
1996-07-03 | 1996 | 7 | Rothamsted | 19.8
1996-07-04 | 1996 | 7 | Rothamsted | 18.5
1996-07-05 | 1996 | 7 | Rothamsted | 17
1996-07-06 | 1996 | 7 | Rothamsted | 19.4
1996-07-07 | 1996 | 7 | Rothamsted | 17.8
1996-07-08 | 1996 | 7 | Rothamsted | 19.5
1996-07-09 | 1996 | 7 | Rothamsted | 24.2
1996-07-10 | 1996 | 7 | Rothamsted | 24.1
1996-07-11 | 1996 | 7 | Rothamsted | 21.8
1996-07-12 | 1996 | 7 | Rothamsted | 24.4
1996-07-13 | 1996 | 7 | Rothamsted | 24.1
1996-07-14 | 1996 | 7 | Rothamsted | 22.2
1996-07-15 | 1996 | 7 | Rothamsted | 20.2
1996-07-16 | 1996 | 7 | Rothamsted | 23.7
1996-07-17 | 1996 | 7 | Rothamsted | 25.6
1996-07-18 | 1996 | 7 | Rothamsted | 24.5
1996-07-19 | 1996 | 7 | Rothamsted | 26.9
1996-07-20 | 1996 | 7 | Rothamsted | 28.6
1996-07-21 | 1996 | 7 | Rothamsted | 30.4
1996-07-22 | 1996 | 7 | Rothamsted | 25
1996-07-24 | 1996 | 7 | Rothamsted | 23.4
1996-07-25 | 1996 | 7 | Rothamsted | 26.9
1996-07-26 | 1996 | 7 | Rothamsted | 21.6
1996-07-27 | 1996 | 7 | Rothamsted | 21.2
1996-07-28 | 1996 | 7 | Rothamsted | 23
1996-07-29 | 1996 | 7 | Rothamsted | 21.7
1996-07-30 | 1996 | 7 | Rothamsted | 23.2
1996-07-31 | 1996 | 7 | Rothamsted | 22
1996-08-01 | 1996 | 8 | Rothamsted | 19.5
1996-08-02 | 1996 | 8 | Rothamsted | 21
1996-08-03 | 1996 | 8 | Rothamsted | 23.4
1996-08-04 | 1996 | 8 | Rothamsted | 24.5
1996-08-05 | 1996 | 8 | Rothamsted | 21
1996-08-06 | 1996 | 8 | Rothamsted | 21.3
1996-08-07 | 1996 | 8 | Rothamsted | 21.8
1996-08-08 | 1996 | 8 | Rothamsted | 20.8
1996-08-09 | 1996 | 8 | Rothamsted | 22
1996-08-10 | 1996 | 8 | Rothamsted | 22.1
1996-08-11 | 1996 | 8 | Rothamsted | 20.5
1996-08-12 | 1996 | 8 | Rothamsted | 21.5
1996-08-13 | 1996 | 8 | Rothamsted | 18
1996-08-14 | 1996 | 8 | Rothamsted | 22.1
1996-08-15 | 1996 | 8 | Rothamsted | 25.3
1996-08-16 | 1996 | 8 | Rothamsted | 26.3
1996-08-17 | 1996 | 8 | Rothamsted | 29
1996-08-18 | 1996 | 8 | Rothamsted | 29.4
1996-08-19 | 1996 | 8 | Rothamsted | 23.5
1996-08-20 | 1996 | 8 | Rothamsted | 23.7
1996-08-21 | 1996 | 8 | Rothamsted | 22
1996-08-22 | 1996 | 8 | Rothamsted | 20.1
1996-08-23 | 1996 | 8 | Rothamsted | 20.2
1996-08-24 | 1996 | 8 | Rothamsted | 20
1996-08-25 | 1996 | 8 | Rothamsted | 19.5
1996-08-26 | 1996 | 8 | Rothamsted | 18.9
1996-08-27 | 1996 | 8 | Rothamsted | 19.3
1996-08-28 | 1996 | 8 | Rothamsted | 16.2
1996-08-29 | 1996 | 8 | Rothamsted | 17.7
1996-08-30 | 1996 | 8 | Rothamsted | 17.3
1996-08-31 | 1996 | 8 | Rothamsted | 19.3
1996-09-01 | 1996 | 9 | Rothamsted | 19.6
1996-09-02 | 1996 | 9 | Rothamsted | 19.5
1996-09-03 | 1996 | 9 | Rothamsted | 17.5
1996-09-04 | 1996 | 9 | Rothamsted | 21.7
1996-09-05 | 1996 | 9 | Rothamsted | 19.5
1996-09-06 | 1996 | 9 | Rothamsted | 19
1996-09-07 | 1996 | 9 | Rothamsted | 18.6
1996-09-08 | 1996 | 9 | Rothamsted | 17.4
1996-09-09 | 1996 | 9 | Rothamsted | 15.1
1996-09-10 | 1996 | 9 | Rothamsted | 18.7
1996-09-11 | 1996 | 9 | Rothamsted | 15.8
1996-09-12 | 1996 | 9 | Rothamsted | 16.4
1996-09-13 | 1996 | 9 | Rothamsted | 18
1996-09-14 | 1996 | 9 | Rothamsted | 21.3
1996-09-15 | 1996 | 9 | Rothamsted | 20.5
1996-09-16 | 1996 | 9 | Rothamsted | 18
1996-09-17 | 1996 | 9 | Rothamsted | 13.8
1996-09-18 | 1996 | 9 | Rothamsted | 13.5
1996-09-19 | 1996 | 9 | Rothamsted | 13.8
1996-09-20 | 1996 | 9 | Rothamsted | 15.5
1996-09-21 | 1996 | 9 | Rothamsted | 14.5
1996-09-22 | 1996 | 9 | Rothamsted | 13.5
1996-09-23 | 1996 | 9 | Rothamsted | 17
1996-09-24 | 1996 | 9 | Rothamsted | 18.5
1996-09-25 | 1996 | 9 | Rothamsted | 16.5
1996-09-26 | 1996 | 9 | Rothamsted | 17.6
1996-09-27 | 1996 | 9 | Rothamsted | 18.2
1996-09-28 | 1996 | 9 | Rothamsted | 18.3
1996-09-30 | 1996 | 9 | Rothamsted | 15
1997-05-01 | 1997 | 5 | Rothamsted | 23.8
1997-05-02 | 1997 | 5 | Rothamsted | 23.1
1997-05-03 | 1997 | 5 | Rothamsted | 17.9
1997-05-04 | 1997 | 5 | Rothamsted | 16.8
1997-05-06 | 1997 | 5 | Rothamsted | 10.8
1997-05-07 | 1997 | 5 | Rothamsted | 11.4
1997-05-08 | 1997 | 5 | Rothamsted | 13.4
1997-05-09 | 1997 | 5 | Rothamsted | 13.4
1997-05-10 | 1997 | 5 | Rothamsted | 14.1
1997-05-11 | 1997 | 5 | Rothamsted | 13.9
1997-05-12 | 1997 | 5 | Rothamsted | 15.7
1997-05-13 | 1997 | 5 | Rothamsted | 17.5
1997-05-14 | 1997 | 5 | Rothamsted | 17.4
1997-05-15 | 1997 | 5 | Rothamsted | 20.9
1997-05-16 | 1997 | 5 | Rothamsted | 22.9
1997-05-17 | 1997 | 5 | Rothamsted | 19.5
1997-05-18 | 1997 | 5 | Rothamsted | 17.7
1997-05-19 | 1997 | 5 | Rothamsted | 16.7
1997-05-21 | 1997 | 5 | Rothamsted | 12.4
1997-05-22 | 1997 | 5 | Rothamsted | 13.4
1997-05-23 | 1997 | 5 | Rothamsted | 14.2
1997-05-24 | 1997 | 5 | Rothamsted | 16.7
1997-05-25 | 1997 | 5 | Rothamsted | 20.8
1997-05-26 | 1997 | 5 | Rothamsted | 16.2
1997-05-27 | 1997 | 5 | Rothamsted | 15.4
1997-05-28 | 1997 | 5 | Rothamsted | 21.4
1997-05-29 | 1997 | 5 | Rothamsted | 22.7
1997-05-30 | 1997 | 5 | Rothamsted | 21.2
1997-05-31 | 1997 | 5 | Rothamsted | 18
1997-06-01 | 1997 | 6 | Rothamsted | 20.5
1997-06-02 | 1997 | 6 | Rothamsted | 19.7
1997-06-03 | 1997 | 6 | Rothamsted | 21.2
1997-06-04 | 1997 | 6 | Rothamsted | 24.5
1997-06-05 | 1997 | 6 | Rothamsted | 24.4
1997-06-06 | 1997 | 6 | Rothamsted | 22.4
1997-06-07 | 1997 | 6 | Rothamsted | 19.5
1997-06-08 | 1997 | 6 | Rothamsted | 21.3
1997-06-09 | 1997 | 6 | Rothamsted | 23.1
1997-06-10 | 1997 | 6 | Rothamsted | 22.6
1997-06-11 | 1997 | 6 | Rothamsted | 19
1997-06-12 | 1997 | 6 | Rothamsted | 20.3
1997-06-13 | 1997 | 6 | Rothamsted | 17.4
1997-06-14 | 1997 | 6 | Rothamsted | 16.5
1997-06-15 | 1997 | 6 | Rothamsted | 17.1
1997-06-16 | 1997 | 6 | Rothamsted | 18.2
1997-06-17 | 1997 | 6 | Rothamsted | 19.1
1997-06-18 | 1997 | 6 | Rothamsted | 15.4
1997-06-19 | 1997 | 6 | Rothamsted | 15.4
1997-06-20 | 1997 | 6 | Rothamsted | 15.8
1997-06-21 | 1997 | 6 | Rothamsted | 16.4
1997-06-22 | 1997 | 6 | Rothamsted | 18.2
1997-06-23 | 1997 | 6 | Rothamsted | 17.3
1997-06-24 | 1997 | 6 | Rothamsted | 13.8
1997-06-25 | 1997 | 6 | Rothamsted | 14
1997-06-27 | 1997 | 6 | Rothamsted | 16.7
1997-06-28 | 1997 | 6 | Rothamsted | 16.5
1997-06-29 | 1997 | 6 | Rothamsted | 14.1
1997-06-30 | 1997 | 6 | Rothamsted | 17.5
1997-07-01 | 1997 | 7 | Rothamsted | 17.2
1997-07-02 | 1997 | 7 | Rothamsted | 15.1
1997-07-03 | 1997 | 7 | Rothamsted | 17.6
1997-07-04 | 1997 | 7 | Rothamsted | 19.9
1997-07-05 | 1997 | 7 | Rothamsted | 22.7
1997-07-06 | 1997 | 7 | Rothamsted | 24.5
1997-07-07 | 1997 | 7 | Rothamsted | 25.6
1997-07-08 | 1997 | 7 | Rothamsted | 24.4
1997-07-09 | 1997 | 7 | Rothamsted | 21
1997-07-10 | 1997 | 7 | Rothamsted | 21.8
1997-07-11 | 1997 | 7 | Rothamsted | 23.4
1997-07-12 | 1997 | 7 | Rothamsted | 23.4
1997-07-13 | 1997 | 7 | Rothamsted | 22.5
1997-07-14 | 1997 | 7 | Rothamsted | 24.7
1997-07-15 | 1997 | 7 | Rothamsted | 20.6
1997-07-17 | 1997 | 7 | Rothamsted | 19.2
1997-07-18 | 1997 | 7 | Rothamsted | 21.7
1997-07-19 | 1997 | 7 | Rothamsted | 22.5
1997-07-20 | 1997 | 7 | Rothamsted | 23.1
1997-07-21 | 1997 | 7 | Rothamsted | 24.2
1997-07-22 | 1997 | 7 | Rothamsted | 25.8
1997-07-23 | 1997 | 7 | Rothamsted | 23.5
1997-07-24 | 1997 | 7 | Rothamsted | 22.4
1997-07-25 | 1997 | 7 | Rothamsted | 19.3
1997-07-26 | 1997 | 7 | Rothamsted | 22.4
1997-07-27 | 1997 | 7 | Rothamsted | 23.1
1997-07-28 | 1997 | 7 | Rothamsted | 25.6
1997-07-29 | 1997 | 7 | Rothamsted | 22.5
1997-07-31 | 1997 | 7 | Rothamsted | 23.6
1997-08-01 | 1997 | 8 | Rothamsted | 20.3
1997-08-02 | 1997 | 8 | Rothamsted | 19.7
1997-08-03 | 1997 | 8 | Rothamsted | 20.5
1997-08-04 | 1997 | 8 | Rothamsted | 22.7
1997-08-05 | 1997 | 8 | Rothamsted | 26
1997-08-06 | 1997 | 8 | Rothamsted | 27.1
1997-08-07 | 1997 | 8 | Rothamsted | 29.6
1997-08-08 | 1997 | 8 | Rothamsted | 28.9
1997-08-09 | 1997 | 8 | Rothamsted | 30.3
1997-08-10 | 1997 | 8 | Rothamsted | 29
1997-08-11 | 1997 | 8 | Rothamsted | 29
1997-08-12 | 1997 | 8 | Rothamsted | 26.4
1997-08-13 | 1997 | 8 | Rothamsted | 25.5
1997-08-14 | 1997 | 8 | Rothamsted | 28
1997-08-15 | 1997 | 8 | Rothamsted | 28.2
1997-08-16 | 1997 | 8 | Rothamsted | 26.4
1997-08-17 | 1997 | 8 | Rothamsted | 28.6
1997-08-18 | 1997 | 8 | Rothamsted | 29.2
1997-08-19 | 1997 | 8 | Rothamsted | 26.6
1997-08-20 | 1997 | 8 | Rothamsted | 25
1997-08-21 | 1997 | 8 | Rothamsted | 25.3
1997-08-22 | 1997 | 8 | Rothamsted | 25.3
1997-08-23 | 1997 | 8 | Rothamsted | 23.5
1997-08-25 | 1997 | 8 | Rothamsted | 21
1997-08-26 | 1997 | 8 | Rothamsted | 17.7
1997-08-27 | 1997 | 8 | Rothamsted | 19.8
1997-08-28 | 1997 | 8 | Rothamsted | 19.6
1997-08-29 | 1997 | 8 | Rothamsted | 18.7
1997-08-30 | 1997 | 8 | Rothamsted | 22.5
1997-08-31 | 1997 | 8 | Rothamsted | 19.9
1997-09-01 | 1997 | 9 | Rothamsted | 20.5
1997-09-02 | 1997 | 9 | Rothamsted | 18
1997-09-03 | 1997 | 9 | Rothamsted | 20.2
1997-09-04 | 1997 | 9 | Rothamsted | 17.8
1997-09-05 | 1997 | 9 | Rothamsted | 19.3
1997-09-06 | 1997 | 9 | Rothamsted | 20.6
1997-09-07 | 1997 | 9 | Rothamsted | 21.2
1997-09-08 | 1997 | 9 | Rothamsted | 20.2
1997-09-09 | 1997 | 9 | Rothamsted | 19.9
1997-09-10 | 1997 | 9 | Rothamsted | 19.4
1997-09-11 | 1997 | 9 | Rothamsted | 17.8
1997-09-12 | 1997 | 9 | Rothamsted | 16.1
1997-09-13 | 1997 | 9 | Rothamsted | 17.7
1997-09-14 | 1997 | 9 | Rothamsted | 19.1
1997-09-15 | 1997 | 9 | Rothamsted | 20.9
1997-09-16 | 1997 | 9 | Rothamsted | 19.3
1997-09-17 | 1997 | 9 | Rothamsted | 23.1
1997-09-19 | 1997 | 9 | Rothamsted | 17.6
1997-09-20 | 1997 | 9 | Rothamsted | 17.4
1997-09-21 | 1997 | 9 | Rothamsted | 19.2
1997-09-22 | 1997 | 9 | Rothamsted | 19.1
1997-09-23 | 1997 | 9 | Rothamsted | 18
1997-09-24 | 1997 | 9 | Rothamsted | 18
1997-09-25 | 1997 | 9 | Rothamsted | 19.5
1997-09-26 | 1997 | 9 | Rothamsted | 17
1997-09-27 | 1997 | 9 | Rothamsted | 18.5
1997-09-28 | 1997 | 9 | Rothamsted | 22.5
1997-09-29 | 1997 | 9 | Rothamsted | 19.2
1997-09-30 | 1997 | 9 | Rothamsted | 23.6
1998-05-01 | 1998 | 5 | Rothamsted | 13.3
1998-05-02 | 1998 | 5 | Rothamsted | 10.6
1998-05-03 | 1998 | 5 | Rothamsted | 14.4
1998-05-04 | 1998 | 5 | Rothamsted | 12.8
1998-05-05 | 1998 | 5 | Rothamsted | 15.7
1998-05-06 | 1998 | 5 | Rothamsted | 14.3
1998-05-07 | 1998 | 5 | Rothamsted | 22.5
1998-05-08 | 1998 | 5 | Rothamsted | 21.2
1998-05-09 | 1998 | 5 | Rothamsted | 19
1998-05-10 | 1998 | 5 | Rothamsted | 18.7
1998-05-11 | 1998 | 5 | Rothamsted | 17.6
1998-05-12 | 1998 | 5 | Rothamsted | 21.9
1998-05-13 | 1998 | 5 | Rothamsted | 22.2
1998-05-14 | 1998 | 5 | Rothamsted | 23.1
1998-05-15 | 1998 | 5 | Rothamsted | 21.7
1998-05-16 | 1998 | 5 | Rothamsted | 19.5
1998-05-17 | 1998 | 5 | Rothamsted | 21.2
1998-05-18 | 1998 | 5 | Rothamsted | 21.8
1998-05-19 | 1998 | 5 | Rothamsted | 21.5
1998-05-20 | 1998 | 5 | Rothamsted | 15.5
1998-05-21 | 1998 | 5 | Rothamsted | 15.6
1998-05-22 | 1998 | 5 | Rothamsted | 15.5
1998-05-23 | 1998 | 5 | Rothamsted | 15.8
1998-05-24 | 1998 | 5 | Rothamsted | 18
1998-05-25 | 1998 | 5 | Rothamsted | 14.5
1998-05-27 | 1998 | 5 | Rothamsted | 15.6
1998-05-28 | 1998 | 5 | Rothamsted | 18
1998-05-29 | 1998 | 5 | Rothamsted | 20.9
1998-05-30 | 1998 | 5 | Rothamsted | 18.7
1998-05-31 | 1998 | 5 | Rothamsted | 19.3
1998-06-01 | 1998 | 6 | Rothamsted | 16.8
1998-06-02 | 1998 | 6 | Rothamsted | 16.5
1998-06-03 | 1998 | 6 | Rothamsted | 13.5
1998-06-04 | 1998 | 6 | Rothamsted | 16.8
1998-06-05 | 1998 | 6 | Rothamsted | 21.5
1998-06-06 | 1998 | 6 | Rothamsted | 18.7
1998-06-07 | 1998 | 6 | Rothamsted | 16.1
1998-06-08 | 1998 | 6 | Rothamsted | 19.1
1998-06-09 | 1998 | 6 | Rothamsted | 17.3
1998-06-11 | 1998 | 6 | Rothamsted | 15.5
1998-06-12 | 1998 | 6 | Rothamsted | 14.2
1998-06-13 | 1998 | 6 | Rothamsted | 17.1
1998-06-14 | 1998 | 6 | Rothamsted | 15.9
1998-06-15 | 1998 | 6 | Rothamsted | 16.3
1998-06-16 | 1998 | 6 | Rothamsted | 16.6
1998-06-17 | 1998 | 6 | Rothamsted | 18.6
1998-06-18 | 1998 | 6 | Rothamsted | 23.5
1998-06-19 | 1998 | 6 | Rothamsted | 26.5
1998-06-20 | 1998 | 6 | Rothamsted | 23.2
1998-06-22 | 1998 | 6 | Rothamsted | 19.5
1998-06-23 | 1998 | 6 | Rothamsted | 21.9
1998-06-24 | 1998 | 6 | Rothamsted | 18.3
1998-06-25 | 1998 | 6 | Rothamsted | 15.6
1998-06-26 | 1998 | 6 | Rothamsted | 18.8
1998-06-27 | 1998 | 6 | Rothamsted | 19.7
1998-06-28 | 1998 | 6 | Rothamsted | 17.7
1998-06-29 | 1998 | 6 | Rothamsted | 17.8
1998-06-30 | 1998 | 6 | Rothamsted | 18.2
1998-07-02 | 1998 | 7 | Rothamsted | 18.1
1998-07-03 | 1998 | 7 | Rothamsted | 18.9
1998-07-04 | 1998 | 7 | Rothamsted | 20.9
1998-07-05 | 1998 | 7 | Rothamsted | 17
1998-07-06 | 1998 | 7 | Rothamsted | 19
1998-07-07 | 1998 | 7 | Rothamsted | 21.1
1998-07-08 | 1998 | 7 | Rothamsted | 21.1
1998-07-09 | 1998 | 7 | Rothamsted | 20
1998-07-10 | 1998 | 7 | Rothamsted | 16.5
1998-07-11 | 1998 | 7 | Rothamsted | 16.9
1998-07-12 | 1998 | 7 | Rothamsted | 17.5
1998-07-13 | 1998 | 7 | Rothamsted | 18.1
1998-07-14 | 1998 | 7 | Rothamsted | 18.8
1998-07-15 | 1998 | 7 | Rothamsted | 20.1
1998-07-16 | 1998 | 7 | Rothamsted | 19.8
1998-07-17 | 1998 | 7 | Rothamsted | 19.8
1998-07-18 | 1998 | 7 | Rothamsted | 22
1998-07-19 | 1998 | 7 | Rothamsted | 25.1
1998-07-20 | 1998 | 7 | Rothamsted | 20.4
1998-07-21 | 1998 | 7 | Rothamsted | 21.2
1998-07-22 | 1998 | 7 | Rothamsted | 21.7
1998-07-23 | 1998 | 7 | Rothamsted | 20.8
1998-07-24 | 1998 | 7 | Rothamsted | 21.1
1998-07-25 | 1998 | 7 | Rothamsted | 20.1
1998-07-26 | 1998 | 7 | Rothamsted | 22
1998-07-27 | 1998 | 7 | Rothamsted | 21.4
1998-07-28 | 1998 | 7 | Rothamsted | 20.9
1998-07-29 | 1998 | 7 | Rothamsted | 21.3
1998-07-30 | 1998 | 7 | Rothamsted | 21.3
1998-07-31 | 1998 | 7 | Rothamsted | 20.1
1998-08-01 | 1998 | 8 | Rothamsted | 17.9
1998-08-02 | 1998 | 8 | Rothamsted | 17.2
1998-08-03 | 1998 | 8 | Rothamsted | 21.8
1998-08-04 | 1998 | 8 | Rothamsted | 25.1
1998-08-05 | 1998 | 8 | Rothamsted | 26.4
1998-08-06 | 1998 | 8 | Rothamsted | 26.7
1998-08-07 | 1998 | 8 | Rothamsted | 27.9
1998-08-08 | 1998 | 8 | Rothamsted | 24.7
1998-08-09 | 1998 | 8 | Rothamsted | 28.9
1998-08-10 | 1998 | 8 | Rothamsted | 28.1
1998-08-11 | 1998 | 8 | Rothamsted | 21.9
1998-08-12 | 1998 | 8 | Rothamsted | 20.5
1998-08-13 | 1998 | 8 | Rothamsted | 25.2
1998-08-14 | 1998 | 8 | Rothamsted | 21
1998-08-15 | 1998 | 8 | Rothamsted | 22.9
1998-08-16 | 1998 | 8 | Rothamsted | 22.5
1998-08-17 | 1998 | 8 | Rothamsted | 21
1998-08-18 | 1998 | 8 | Rothamsted | 23.4
1998-08-19 | 1998 | 8 | Rothamsted | 20
1998-08-20 | 1998 | 8 | Rothamsted | 21.4
1998-08-21 | 1998 | 8 | Rothamsted | 19.4
1998-08-22 | 1998 | 8 | Rothamsted | 18.2
1998-08-23 | 1998 | 8 | Rothamsted | 16.7
1998-08-24 | 1998 | 8 | Rothamsted | 19.9
1998-08-25 | 1998 | 8 | Rothamsted | 14.8
1998-08-26 | 1998 | 8 | Rothamsted | 18.6
1998-08-27 | 1998 | 8 | Rothamsted | 18.8
1998-08-28 | 1998 | 8 | Rothamsted | 20.5
1998-08-29 | 1998 | 8 | Rothamsted | 20
1998-08-30 | 1998 | 8 | Rothamsted | 20.8
1998-08-31 | 1998 | 8 | Rothamsted | 23.4
1998-09-01 | 1998 | 9 | Rothamsted | 22.6
1998-09-02 | 1998 | 9 | Rothamsted | 20.1
1998-09-03 | 1998 | 9 | Rothamsted | 18.6
1998-09-04 | 1998 | 9 | Rothamsted | 17.5
1998-09-05 | 1998 | 9 | Rothamsted | 19.3
1998-09-06 | 1998 | 9 | Rothamsted | 22
1998-09-07 | 1998 | 9 | Rothamsted | 21.1
1998-09-08 | 1998 | 9 | Rothamsted | 20.6
1998-09-09 | 1998 | 9 | Rothamsted | 18.5
1998-09-10 | 1998 | 9 | Rothamsted | 16.9
1998-09-12 | 1998 | 9 | Rothamsted | 14.2
1998-09-13 | 1998 | 9 | Rothamsted | 16.5
1998-09-14 | 1998 | 9 | Rothamsted | 17.3
1998-09-15 | 1998 | 9 | Rothamsted | 16.3
1998-09-16 | 1998 | 9 | Rothamsted | 16.4
1998-09-17 | 1998 | 9 | Rothamsted | 20
1998-09-18 | 1998 | 9 | Rothamsted | 21
1998-09-19 | 1998 | 9 | Rothamsted | 19.8
1998-09-20 | 1998 | 9 | Rothamsted | 19.7
1998-09-22 | 1998 | 9 | Rothamsted | 19.7
1998-09-23 | 1998 | 9 | Rothamsted | 20.3
1998-09-24 | 1998 | 9 | Rothamsted | 21.4
1998-09-25 | 1998 | 9 | Rothamsted | 21
1998-09-27 | 1998 | 9 | Rothamsted | 17.5
1998-09-29 | 1998 | 9 | Rothamsted | 17.2
1998-09-30 | 1998 | 9 | Rothamsted | 16.2
1999-05-01 | 1999 | 5 | Rothamsted | 18.4
1999-05-02 | 1999 | 5 | Rothamsted | 20.6
1999-05-03 | 1999 | 5 | Rothamsted | 16.1
1999-05-04 | 1999 | 5 | Rothamsted | 17.8
1999-05-05 | 1999 | 5 | Rothamsted | 16.5
1999-05-06 | 1999 | 5 | Rothamsted | 16.3
1999-05-07 | 1999 | 5 | Rothamsted | 15.4
1999-05-08 | 1999 | 5 | Rothamsted | 19.4
1999-05-09 | 1999 | 5 | Rothamsted | 16
1999-05-10 | 1999 | 5 | Rothamsted | 16.7
1999-05-11 | 1999 | 5 | Rothamsted | 15.6
1999-05-12 | 1999 | 5 | Rothamsted | 14.2
1999-05-13 | 1999 | 5 | Rothamsted | 17
1999-05-14 | 1999 | 5 | Rothamsted | 14
1999-05-15 | 1999 | 5 | Rothamsted | 15.4
1999-05-16 | 1999 | 5 | Rothamsted | 15.4
1999-05-17 | 1999 | 5 | Rothamsted | 16.5
1999-05-18 | 1999 | 5 | Rothamsted | 21.5
1999-05-19 | 1999 | 5 | Rothamsted | 20.7
1999-05-20 | 1999 | 5 | Rothamsted | 16.7
1999-05-21 | 1999 | 5 | Rothamsted | 15.6
1999-05-22 | 1999 | 5 | Rothamsted | 17.6
1999-05-23 | 1999 | 5 | Rothamsted | 17
1999-05-24 | 1999 | 5 | Rothamsted | 16.3
1999-05-25 | 1999 | 5 | Rothamsted | 20
1999-05-26 | 1999 | 5 | Rothamsted | 23.1
1999-05-27 | 1999 | 5 | Rothamsted | 20.1
1999-05-28 | 1999 | 5 | Rothamsted | 23
1999-05-30 | 1999 | 5 | Rothamsted | 15.9
1999-05-31 | 1999 | 5 | Rothamsted | 21
1999-06-01 | 1999 | 6 | Rothamsted | 19.5
1999-06-02 | 1999 | 6 | Rothamsted | 16.4
1999-06-03 | 1999 | 6 | Rothamsted | 16.1
1999-06-04 | 1999 | 6 | Rothamsted | 15.6
1999-06-05 | 1999 | 6 | Rothamsted | 17.8
1999-06-06 | 1999 | 6 | Rothamsted | 17
1999-06-07 | 1999 | 6 | Rothamsted | 16.1
1999-06-08 | 1999 | 6 | Rothamsted | 17.3
1999-06-09 | 1999 | 6 | Rothamsted | 15.6
1999-06-10 | 1999 | 6 | Rothamsted | 14.4
1999-06-11 | 1999 | 6 | Rothamsted | 15.5
1999-06-12 | 1999 | 6 | Rothamsted | 19.5
1999-06-13 | 1999 | 6 | Rothamsted | 21.5
1999-06-14 | 1999 | 6 | Rothamsted | 23.4
1999-06-15 | 1999 | 6 | Rothamsted | 24.2
1999-06-16 | 1999 | 6 | Rothamsted | 19.8
1999-06-17 | 1999 | 6 | Rothamsted | 21.8
1999-06-18 | 1999 | 6 | Rothamsted | 19.6
1999-06-19 | 1999 | 6 | Rothamsted | 17.4
1999-06-20 | 1999 | 6 | Rothamsted | 15.5
1999-06-21 | 1999 | 6 | Rothamsted | 17
1999-06-22 | 1999 | 6 | Rothamsted | 19.2
1999-06-23 | 1999 | 6 | Rothamsted | 20.1
1999-06-24 | 1999 | 6 | Rothamsted | 20.7
1999-06-25 | 1999 | 6 | Rothamsted | 24
1999-06-26 | 1999 | 6 | Rothamsted | 16.6
1999-06-27 | 1999 | 6 | Rothamsted | 17.1
1999-06-28 | 1999 | 6 | Rothamsted | 16.8
1999-06-29 | 1999 | 6 | Rothamsted | 18.7
1999-06-30 | 1999 | 6 | Rothamsted | 20.4
1999-07-01 | 1999 | 7 | Rothamsted | 25.1
1999-07-02 | 1999 | 7 | Rothamsted | 21.8
1999-07-03 | 1999 | 7 | Rothamsted | 20.2
1999-07-04 | 1999 | 7 | Rothamsted | 22.5
1999-07-05 | 1999 | 7 | Rothamsted | 25
1999-07-06 | 1999 | 7 | Rothamsted | 22.7
1999-07-07 | 1999 | 7 | Rothamsted | 24.6
1999-07-08 | 1999 | 7 | Rothamsted | 22.4
1999-07-09 | 1999 | 7 | Rothamsted | 24.4
1999-07-10 | 1999 | 7 | Rothamsted | 24.8
1999-07-11 | 1999 | 7 | Rothamsted | 21.2
1999-07-12 | 1999 | 7 | Rothamsted | 23.9
1999-07-13 | 1999 | 7 | Rothamsted | 18.2
1999-07-14 | 1999 | 7 | Rothamsted | 19.2
1999-07-15 | 1999 | 7 | Rothamsted | 20.8
1999-07-16 | 1999 | 7 | Rothamsted | 23.9
1999-07-17 | 1999 | 7 | Rothamsted | 26.2
1999-07-18 | 1999 | 7 | Rothamsted | 24.6
1999-07-19 | 1999 | 7 | Rothamsted | 23.4
1999-07-21 | 1999 | 7 | Rothamsted | 16.8
1999-07-22 | 1999 | 7 | Rothamsted | 24.1
1999-07-23 | 1999 | 7 | Rothamsted | 27.8
1999-07-24 | 1999 | 7 | Rothamsted | 25.2
1999-07-25 | 1999 | 7 | Rothamsted | 20.3
1999-07-26 | 1999 | 7 | Rothamsted | 20
1999-07-27 | 1999 | 7 | Rothamsted | 23
1999-07-28 | 1999 | 7 | Rothamsted | 26.8
1999-07-29 | 1999 | 7 | Rothamsted | 27.8
1999-07-30 | 1999 | 7 | Rothamsted | 29.2
1999-07-31 | 1999 | 7 | Rothamsted | 30
1999-08-01 | 1999 | 8 | Rothamsted | 29.2
1999-08-02 | 1999 | 8 | Rothamsted | 21.7
1999-08-03 | 1999 | 8 | Rothamsted | 26.5
1999-08-04 | 1999 | 8 | Rothamsted | 25
1999-08-05 | 1999 | 8 | Rothamsted | 24.7
1999-08-06 | 1999 | 8 | Rothamsted | 19.6
1999-08-07 | 1999 | 8 | Rothamsted | 21.6
1999-08-08 | 1999 | 8 | Rothamsted | 20
1999-08-10 | 1999 | 8 | Rothamsted | 18.4
1999-08-11 | 1999 | 8 | Rothamsted | 18.9
1999-08-12 | 1999 | 8 | Rothamsted | 19.9
1999-08-13 | 1999 | 8 | Rothamsted | 21.5
1999-08-14 | 1999 | 8 | Rothamsted | 19.7
1999-08-15 | 1999 | 8 | Rothamsted | 18.2
1999-08-16 | 1999 | 8 | Rothamsted | 15.4
1999-08-17 | 1999 | 8 | Rothamsted | 17.8
1999-08-18 | 1999 | 8 | Rothamsted | 15.4
1999-08-19 | 1999 | 8 | Rothamsted | 18.3
1999-08-20 | 1999 | 8 | Rothamsted | 17.5
1999-08-21 | 1999 | 8 | Rothamsted | 17.7
1999-08-22 | 1999 | 8 | Rothamsted | 19.6
1999-08-23 | 1999 | 8 | Rothamsted | 19.4
1999-08-24 | 1999 | 8 | Rothamsted | 23.8
1999-08-25 | 1999 | 8 | Rothamsted | 21.9
1999-08-26 | 1999 | 8 | Rothamsted | 20.9
1999-08-27 | 1999 | 8 | Rothamsted | 23.5
1999-08-28 | 1999 | 8 | Rothamsted | 22
1999-08-29 | 1999 | 8 | Rothamsted | 22
1999-08-30 | 1999 | 8 | Rothamsted | 20.5
1999-08-31 | 1999 | 8 | Rothamsted | 23.4
1999-09-01 | 1999 | 9 | Rothamsted | 25.3
1999-09-02 | 1999 | 9 | Rothamsted | 25.2
1999-09-03 | 1999 | 9 | Rothamsted | 26
1999-09-04 | 1999 | 9 | Rothamsted | 27
1999-09-05 | 1999 | 9 | Rothamsted | 26
1999-09-06 | 1999 | 9 | Rothamsted | 22.7
1999-09-07 | 1999 | 9 | Rothamsted | 21.9
1999-09-08 | 1999 | 9 | Rothamsted | 20.4
1999-09-09 | 1999 | 9 | Rothamsted | 23.8
1999-09-10 | 1999 | 9 | Rothamsted | 27.8
1999-09-12 | 1999 | 9 | Rothamsted | 18.9
1999-09-14 | 1999 | 9 | Rothamsted | 15.8
1999-09-15 | 1999 | 9 | Rothamsted | 17
1999-09-16 | 1999 | 9 | Rothamsted | 19
1999-09-17 | 1999 | 9 | Rothamsted | 18.1
1999-09-18 | 1999 | 9 | Rothamsted | 17.7
1999-09-19 | 1999 | 9 | Rothamsted | 16.4
1999-09-20 | 1999 | 9 | Rothamsted | 19.2
1999-09-21 | 1999 | 9 | Rothamsted | 20.1
1999-09-22 | 1999 | 9 | Rothamsted | 18.5
1999-09-23 | 1999 | 9 | Rothamsted | 17.5
1999-09-24 | 1999 | 9 | Rothamsted | 18.9
1999-09-26 | 1999 | 9 | Rothamsted | 17.5
1999-09-27 | 1999 | 9 | Rothamsted | 17.2
1999-09-28 | 1999 | 9 | Rothamsted | 17
1999-09-29 | 1999 | 9 | Rothamsted | 16.3
1999-09-30 | 1999 | 9 | Rothamsted | 15
2000-05-01 | 2000 | 5 | Rothamsted | 13
2000-05-03 | 2000 | 5 | Rothamsted | 10.9
2000-05-04 | 2000 | 5 | Rothamsted | 16.2
2000-05-05 | 2000 | 5 | Rothamsted | 23.3
2000-05-06 | 2000 | 5 | Rothamsted | 20.1
2000-05-07 | 2000 | 5 | Rothamsted | 15.9
2000-05-08 | 2000 | 5 | Rothamsted | 17.8
2000-05-09 | 2000 | 5 | Rothamsted | 15.4
2000-05-10 | 2000 | 5 | Rothamsted | 15.6
2000-05-11 | 2000 | 5 | Rothamsted | 16.5
2000-05-12 | 2000 | 5 | Rothamsted | 22.1
2000-05-13 | 2000 | 5 | Rothamsted | 23.6
2000-05-14 | 2000 | 5 | Rothamsted | 24.6
2000-05-15 | 2000 | 5 | Rothamsted | 21.1
2000-05-17 | 2000 | 5 | Rothamsted | 13.7
2000-05-18 | 2000 | 5 | Rothamsted | 12.7
2000-05-19 | 2000 | 5 | Rothamsted | 15.1
2000-05-20 | 2000 | 5 | Rothamsted | 14.4
2000-05-21 | 2000 | 5 | Rothamsted | 17.4
2000-05-22 | 2000 | 5 | Rothamsted | 13.1
2000-05-23 | 2000 | 5 | Rothamsted | 15.8
2000-05-24 | 2000 | 5 | Rothamsted | 15.1
2000-05-25 | 2000 | 5 | Rothamsted | 12.4
2000-05-26 | 2000 | 5 | Rothamsted | 13.6
2000-05-27 | 2000 | 5 | Rothamsted | 13.8
2000-05-28 | 2000 | 5 | Rothamsted | 15.6
2000-05-29 | 2000 | 5 | Rothamsted | 14.9
2000-05-30 | 2000 | 5 | Rothamsted | 17.7
2000-05-31 | 2000 | 5 | Rothamsted | 16.5
2000-06-01 | 2000 | 6 | Rothamsted | 17.6
2000-06-02 | 2000 | 6 | Rothamsted | 22.3
2000-06-03 | 2000 | 6 | Rothamsted | 17.8
2000-06-04 | 2000 | 6 | Rothamsted | 14.1
2000-06-05 | 2000 | 6 | Rothamsted | 17.3
2000-06-06 | 2000 | 6 | Rothamsted | 18.7
2000-06-07 | 2000 | 6 | Rothamsted | 21.8
2000-06-08 | 2000 | 6 | Rothamsted | 17.1
2000-06-09 | 2000 | 6 | Rothamsted | 18.1
2000-06-10 | 2000 | 6 | Rothamsted | 18.1
2000-06-11 | 2000 | 6 | Rothamsted | 23.8
2000-06-12 | 2000 | 6 | Rothamsted | 20.5
2000-06-13 | 2000 | 6 | Rothamsted | 20.3
2000-06-14 | 2000 | 6 | Rothamsted | 20.3
2000-06-15 | 2000 | 6 | Rothamsted | 20.9
2000-06-16 | 2000 | 6 | Rothamsted | 24.9
2000-06-17 | 2000 | 6 | Rothamsted | 28.7
2000-06-18 | 2000 | 6 | Rothamsted | 29.7
2000-06-20 | 2000 | 6 | Rothamsted | 18.3
2000-06-21 | 2000 | 6 | Rothamsted | 17.4
2000-06-22 | 2000 | 6 | Rothamsted | 18
2000-06-24 | 2000 | 6 | Rothamsted | 16.1
2000-06-25 | 2000 | 6 | Rothamsted | 18.5
2000-06-26 | 2000 | 6 | Rothamsted | 20.5
2000-06-27 | 2000 | 6 | Rothamsted | 19.1
2000-06-28 | 2000 | 6 | Rothamsted | 17.5
2000-06-29 | 2000 | 6 | Rothamsted | 18
2000-06-30 | 2000 | 6 | Rothamsted | 20
2000-07-01 | 2000 | 7 | Rothamsted | 20.6
2000-07-02 | 2000 | 7 | Rothamsted | 22.7
2000-07-04 | 2000 | 7 | Rothamsted | 16.3
2000-07-05 | 2000 | 7 | Rothamsted | 22.1
2000-07-07 | 2000 | 7 | Rothamsted | 16.7
2000-07-08 | 2000 | 7 | Rothamsted | 17.2
2000-07-10 | 2000 | 7 | Rothamsted | 15
2000-07-11 | 2000 | 7 | Rothamsted | 18.1
2000-07-12 | 2000 | 7 | Rothamsted | 19.7
2000-07-14 | 2000 | 7 | Rothamsted | 16.7
2000-07-15 | 2000 | 7 | Rothamsted | 16.4
2000-07-16 | 2000 | 7 | Rothamsted | 20.4
2000-07-17 | 2000 | 7 | Rothamsted | 22.8
2000-07-18 | 2000 | 7 | Rothamsted | 23.4
2000-07-19 | 2000 | 7 | Rothamsted | 23.6
2000-07-20 | 2000 | 7 | Rothamsted | 24.1
2000-07-21 | 2000 | 7 | Rothamsted | 18.4
2000-07-22 | 2000 | 7 | Rothamsted | 17.4
2000-07-23 | 2000 | 7 | Rothamsted | 15.6
2000-07-24 | 2000 | 7 | Rothamsted | 18.8
2000-07-25 | 2000 | 7 | Rothamsted | 22.7
2000-07-26 | 2000 | 7 | Rothamsted | 23.5
2000-07-27 | 2000 | 7 | Rothamsted | 21.8
2000-07-28 | 2000 | 7 | Rothamsted | 24.5
2000-07-29 | 2000 | 7 | Rothamsted | 24.8
2000-07-30 | 2000 | 7 | Rothamsted | 24.7
2000-07-31 | 2000 | 7 | Rothamsted | 23.9
2000-08-01 | 2000 | 8 | Rothamsted | 22.6
2000-08-02 | 2000 | 8 | Rothamsted | 18.6
2000-08-03 | 2000 | 8 | Rothamsted | 21.6
2000-08-04 | 2000 | 8 | Rothamsted | 23.2
2000-08-05 | 2000 | 8 | Rothamsted | 24.2
2000-08-06 | 2000 | 8 | Rothamsted | 23.1
2000-08-07 | 2000 | 8 | Rothamsted | 21.2
2000-08-08 | 2000 | 8 | Rothamsted | 22.3
2000-08-09 | 2000 | 8 | Rothamsted | 24
2000-08-10 | 2000 | 8 | Rothamsted | 24
2000-08-11 | 2000 | 8 | Rothamsted | 26.2
2000-08-12 | 2000 | 8 | Rothamsted | 23.1
2000-08-13 | 2000 | 8 | Rothamsted | 22.4
2000-08-14 | 2000 | 8 | Rothamsted | 23.3
2000-08-15 | 2000 | 8 | Rothamsted | 22.3
2000-08-16 | 2000 | 8 | Rothamsted | 22.2
2000-08-17 | 2000 | 8 | Rothamsted | 18.2
2000-08-18 | 2000 | 8 | Rothamsted | 21.9
2000-08-19 | 2000 | 8 | Rothamsted | 21.3
2000-08-20 | 2000 | 8 | Rothamsted | 20.5
2000-08-21 | 2000 | 8 | Rothamsted | 21.7
2000-08-22 | 2000 | 8 | Rothamsted | 22.5
2000-08-23 | 2000 | 8 | Rothamsted | 26.4
2000-08-24 | 2000 | 8 | Rothamsted | 24.6
2000-08-25 | 2000 | 8 | Rothamsted | 19.6
2000-08-26 | 2000 | 8 | Rothamsted | 21.9
2000-08-27 | 2000 | 8 | Rothamsted | 20
2000-08-28 | 2000 | 8 | Rothamsted | 20.7
2000-08-29 | 2000 | 8 | Rothamsted | 20.5
2000-08-30 | 2000 | 8 | Rothamsted | 20.6
2000-08-31 | 2000 | 8 | Rothamsted | 17.5
2000-09-01 | 2000 | 9 | Rothamsted | 18.9
2000-09-02 | 2000 | 9 | Rothamsted | 17.3
2000-09-03 | 2000 | 9 | Rothamsted | 19.3
2000-09-04 | 2000 | 9 | Rothamsted | 18.2
2000-09-05 | 2000 | 9 | Rothamsted | 20
2000-09-06 | 2000 | 9 | Rothamsted | 18.1
2000-09-07 | 2000 | 9 | Rothamsted | 18
2000-09-08 | 2000 | 9 | Rothamsted | 22.5
2000-09-09 | 2000 | 9 | Rothamsted | 24.8
2000-09-10 | 2000 | 9 | Rothamsted | 26.3
2000-09-11 | 2000 | 9 | Rothamsted | 22.1
2000-09-12 | 2000 | 9 | Rothamsted | 20.1
2000-09-13 | 2000 | 9 | Rothamsted | 19.3
2000-09-14 | 2000 | 9 | Rothamsted | 16.6
2000-09-15 | 2000 | 9 | Rothamsted | 17.4
2000-09-16 | 2000 | 9 | Rothamsted | 17.8
2000-09-17 | 2000 | 9 | Rothamsted | 14.9
2000-09-18 | 2000 | 9 | Rothamsted | 15
2000-09-19 | 2000 | 9 | Rothamsted | 15.9
2000-09-20 | 2000 | 9 | Rothamsted | 17.7
2000-09-21 | 2000 | 9 | Rothamsted | 20.2
2000-09-22 | 2000 | 9 | Rothamsted | 23.1
2000-09-24 | 2000 | 9 | Rothamsted | 17.4
2000-09-25 | 2000 | 9 | Rothamsted | 19.4
2000-09-26 | 2000 | 9 | Rothamsted | 16.6
2000-09-27 | 2000 | 9 | Rothamsted | 17.5
2000-09-28 | 2000 | 9 | Rothamsted | 18.5
2000-09-29 | 2000 | 9 | Rothamsted | 17
2000-09-30 | 2000 | 9 | Rothamsted | 17.3
2001-05-01 | 2001 | 5 | Rothamsted | 14.2
2001-05-02 | 2001 | 5 | Rothamsted | 15.1
2001-05-03 | 2001 | 5 | Rothamsted | 11.5
2001-05-04 | 2001 | 5 | Rothamsted | 12.5
2001-05-05 | 2001 | 5 | Rothamsted | 11.5
2001-05-06 | 2001 | 5 | Rothamsted | 14.2
2001-05-07 | 2001 | 5 | Rothamsted | 15.9
2001-05-08 | 2001 | 5 | Rothamsted | 16.9
2001-05-09 | 2001 | 5 | Rothamsted | 22.3
2001-05-10 | 2001 | 5 | Rothamsted | 24.8
2001-05-11 | 2001 | 5 | Rothamsted | 22.9
2001-05-12 | 2001 | 5 | Rothamsted | 23.8
2001-05-14 | 2001 | 5 | Rothamsted | 17.3
2001-05-15 | 2001 | 5 | Rothamsted | 17.1
2001-05-17 | 2001 | 5 | Rothamsted | 14.3
2001-05-18 | 2001 | 5 | Rothamsted | 15
2001-05-19 | 2001 | 5 | Rothamsted | 17.5
2001-05-20 | 2001 | 5 | Rothamsted | 17
2001-05-21 | 2001 | 5 | Rothamsted | 18.4
2001-05-22 | 2001 | 5 | Rothamsted | 21.4
2001-05-23 | 2001 | 5 | Rothamsted | 20.3
2001-05-24 | 2001 | 5 | Rothamsted | 19
2001-05-25 | 2001 | 5 | Rothamsted | 22.4
2001-05-26 | 2001 | 5 | Rothamsted | 19.5
2001-05-27 | 2001 | 5 | Rothamsted | 23.4
2001-05-28 | 2001 | 5 | Rothamsted | 23.4
2001-05-29 | 2001 | 5 | Rothamsted | 21.3
2001-05-30 | 2001 | 5 | Rothamsted | 16.6
2001-05-31 | 2001 | 5 | Rothamsted | 17.3
2001-06-01 | 2001 | 6 | Rothamsted | 14.4
2001-06-02 | 2001 | 6 | Rothamsted | 15.6
2001-06-03 | 2001 | 6 | Rothamsted | 18.5
2001-06-04 | 2001 | 6 | Rothamsted | 20.1
2001-06-05 | 2001 | 6 | Rothamsted | 17.9
2001-06-06 | 2001 | 6 | Rothamsted | 16.1
2001-06-07 | 2001 | 6 | Rothamsted | 15.6
2001-06-08 | 2001 | 6 | Rothamsted | 15
2001-06-09 | 2001 | 6 | Rothamsted | 12.8
2001-06-10 | 2001 | 6 | Rothamsted | 15.8
2001-06-11 | 2001 | 6 | Rothamsted | 17.4
2001-06-12 | 2001 | 6 | Rothamsted | 20.6
2001-06-13 | 2001 | 6 | Rothamsted | 20.7
2001-06-14 | 2001 | 6 | Rothamsted | 18.6
2001-06-15 | 2001 | 6 | Rothamsted | 16.2
2001-06-17 | 2001 | 6 | Rothamsted | 16.9
2001-06-18 | 2001 | 6 | Rothamsted | 21
2001-06-19 | 2001 | 6 | Rothamsted | 21.6
2001-06-20 | 2001 | 6 | Rothamsted | 19.1
2001-06-21 | 2001 | 6 | Rothamsted | 19.1
2001-06-22 | 2001 | 6 | Rothamsted | 20.9
2001-06-23 | 2001 | 6 | Rothamsted | 25
2001-06-24 | 2001 | 6 | Rothamsted | 26.4
2001-06-25 | 2001 | 6 | Rothamsted | 27
2001-06-26 | 2001 | 6 | Rothamsted | 23
2001-06-27 | 2001 | 6 | Rothamsted | 22.4
2001-06-28 | 2001 | 6 | Rothamsted | 20
2001-06-29 | 2001 | 6 | Rothamsted | 21.2
2001-06-30 | 2001 | 6 | Rothamsted | 23.9
2001-07-01 | 2001 | 7 | Rothamsted | 25.4
2001-07-02 | 2001 | 7 | Rothamsted | 25.8
2001-07-03 | 2001 | 7 | Rothamsted | 26.9
2001-07-04 | 2001 | 7 | Rothamsted | 28.5
2001-07-05 | 2001 | 7 | Rothamsted | 24.8
2001-07-07 | 2001 | 7 | Rothamsted | 18.8
2001-07-08 | 2001 | 7 | Rothamsted | 19.3
2001-07-09 | 2001 | 7 | Rothamsted | 18.3
2001-07-10 | 2001 | 7 | Rothamsted | 18.3
2001-07-11 | 2001 | 7 | Rothamsted | 19.4
2001-07-12 | 2001 | 7 | Rothamsted | 19.5
2001-07-13 | 2001 | 7 | Rothamsted | 16.9
2001-07-14 | 2001 | 7 | Rothamsted | 17.5
2001-07-15 | 2001 | 7 | Rothamsted | 19.7
2001-07-16 | 2001 | 7 | Rothamsted | 19.9
2001-07-17 | 2001 | 7 | Rothamsted | 19
2001-07-18 | 2001 | 7 | Rothamsted | 16
2001-07-19 | 2001 | 7 | Rothamsted | 19.8
2001-07-20 | 2001 | 7 | Rothamsted | 20
2001-07-21 | 2001 | 7 | Rothamsted | 20.2
2001-07-22 | 2001 | 7 | Rothamsted | 23.3
2001-07-23 | 2001 | 7 | Rothamsted | 21.4
2001-07-24 | 2001 | 7 | Rothamsted | 25.1
2001-07-25 | 2001 | 7 | Rothamsted | 26.1
2001-07-26 | 2001 | 7 | Rothamsted | 27.1
2001-07-27 | 2001 | 7 | Rothamsted | 28.5
2001-07-28 | 2001 | 7 | Rothamsted | 29.5
2001-07-29 | 2001 | 7 | Rothamsted | 26.4
2001-07-30 | 2001 | 7 | Rothamsted | 24
2001-07-31 | 2001 | 7 | Rothamsted | 24.1
2001-08-01 | 2001 | 8 | Rothamsted | 19.9
2001-08-02 | 2001 | 8 | Rothamsted | 22
2001-08-03 | 2001 | 8 | Rothamsted | 20.5
2001-08-04 | 2001 | 8 | Rothamsted | 21.8
2001-08-05 | 2001 | 8 | Rothamsted | 23
2001-08-06 | 2001 | 8 | Rothamsted | 19.4
2001-08-07 | 2001 | 8 | Rothamsted | 18.7
2001-08-08 | 2001 | 8 | Rothamsted | 16.1
2001-08-09 | 2001 | 8 | Rothamsted | 20.3
2001-08-10 | 2001 | 8 | Rothamsted | 20.2
2001-08-11 | 2001 | 8 | Rothamsted | 18.6
2001-08-12 | 2001 | 8 | Rothamsted | 24.1
2001-08-13 | 2001 | 8 | Rothamsted | 25.4
2001-08-14 | 2001 | 8 | Rothamsted | 28.6
2001-08-15 | 2001 | 8 | Rothamsted | 23.4
2001-08-16 | 2001 | 8 | Rothamsted | 21.5
2001-08-17 | 2001 | 8 | Rothamsted | 23.2
2001-08-18 | 2001 | 8 | Rothamsted | 21.1
2001-08-19 | 2001 | 8 | Rothamsted | 21.5
2001-08-20 | 2001 | 8 | Rothamsted | 23.2
2001-08-21 | 2001 | 8 | Rothamsted | 24.4
2001-08-22 | 2001 | 8 | Rothamsted | 23
2001-08-23 | 2001 | 8 | Rothamsted | 27
2001-08-24 | 2001 | 8 | Rothamsted | 28.7
2001-08-26 | 2001 | 8 | Rothamsted | 20.5
2001-08-27 | 2001 | 8 | Rothamsted | 21.1
2001-08-28 | 2001 | 8 | Rothamsted | 21.4
2001-08-29 | 2001 | 8 | Rothamsted | 17.8
2001-08-30 | 2001 | 8 | Rothamsted | 16.8
2001-08-31 | 2001 | 8 | Rothamsted | 19.1
2001-09-01 | 2001 | 9 | Rothamsted | 20.2
2001-09-02 | 2001 | 9 | Rothamsted | 18.9
2001-09-03 | 2001 | 9 | Rothamsted | 16.2
2001-09-04 | 2001 | 9 | Rothamsted | 18.2
2001-09-05 | 2001 | 9 | Rothamsted | 17.9
2001-09-06 | 2001 | 9 | Rothamsted | 18.9
2001-09-07 | 2001 | 9 | Rothamsted | 17.3
2001-09-09 | 2001 | 9 | Rothamsted | 15.5
2001-09-10 | 2001 | 9 | Rothamsted | 17.7
2001-09-11 | 2001 | 9 | Rothamsted | 17.1
2001-09-12 | 2001 | 9 | Rothamsted | 15.5
2001-09-13 | 2001 | 9 | Rothamsted | 17.4
2001-09-14 | 2001 | 9 | Rothamsted | 16.6
2001-09-15 | 2001 | 9 | Rothamsted | 15.9
2001-09-16 | 2001 | 9 | Rothamsted | 12.8
2001-09-17 | 2001 | 9 | Rothamsted | 13.6
2001-09-18 | 2001 | 9 | Rothamsted | 13.3
2001-09-19 | 2001 | 9 | Rothamsted | 16.3
2001-09-20 | 2001 | 9 | Rothamsted | 13.9
2001-09-21 | 2001 | 9 | Rothamsted | 15.9
2001-09-22 | 2001 | 9 | Rothamsted | 14
2001-09-23 | 2001 | 9 | Rothamsted | 15.9
2001-09-24 | 2001 | 9 | Rothamsted | 15.7
2001-09-25 | 2001 | 9 | Rothamsted | 16
2001-09-26 | 2001 | 9 | Rothamsted | 18.7
2001-09-27 | 2001 | 9 | Rothamsted | 21.9
2001-09-28 | 2001 | 9 | Rothamsted | 17.9
2001-09-29 | 2001 | 9 | Rothamsted | 16.5
2001-09-30 | 2001 | 9 | Rothamsted | 17.6
2002-05-01 | 2002 | 5 | Rothamsted | 13.7
2002-05-02 | 2002 | 5 | Rothamsted | 13.9
2002-05-03 | 2002 | 5 | Rothamsted | 12
2002-05-04 | 2002 | 5 | Rothamsted | 11.3
2002-05-05 | 2002 | 5 | Rothamsted | 14.6
2002-05-06 | 2002 | 5 | Rothamsted | 15.4
2002-05-07 | 2002 | 5 | Rothamsted | 15.1
2002-05-08 | 2002 | 5 | Rothamsted | 11.3
2002-05-09 | 2002 | 5 | Rothamsted | 16.3
2002-05-10 | 2002 | 5 | Rothamsted | 15.9
2002-05-11 | 2002 | 5 | Rothamsted | 16.4
2002-05-12 | 2002 | 5 | Rothamsted | 13.7
2002-05-13 | 2002 | 5 | Rothamsted | 15.5
2002-05-14 | 2002 | 5 | Rothamsted | 18.5
2002-05-15 | 2002 | 5 | Rothamsted | 22.7
2002-05-16 | 2002 | 5 | Rothamsted | 21.3
2002-05-17 | 2002 | 5 | Rothamsted | 16.8
2002-05-18 | 2002 | 5 | Rothamsted | 19.1
2002-05-19 | 2002 | 5 | Rothamsted | 17.5
2002-05-20 | 2002 | 5 | Rothamsted | 17.2
2002-05-21 | 2002 | 5 | Rothamsted | 17.1
2002-05-22 | 2002 | 5 | Rothamsted | 17.1
2002-05-23 | 2002 | 5 | Rothamsted | 16.6
2002-05-24 | 2002 | 5 | Rothamsted | 14.5
2002-05-25 | 2002 | 5 | Rothamsted | 13.1
2002-05-26 | 2002 | 5 | Rothamsted | 17.2
2002-05-27 | 2002 | 5 | Rothamsted | 14.7
2002-05-28 | 2002 | 5 | Rothamsted | 15.9
2002-05-29 | 2002 | 5 | Rothamsted | 16.4
2002-05-30 | 2002 | 5 | Rothamsted | 18
2002-05-31 | 2002 | 5 | Rothamsted | 20.3
2002-06-01 | 2002 | 6 | Rothamsted | 24.9
2002-06-03 | 2002 | 6 | Rothamsted | 15.7
2002-06-04 | 2002 | 6 | Rothamsted | 13.9
2002-06-05 | 2002 | 6 | Rothamsted | 15
2002-06-06 | 2002 | 6 | Rothamsted | 16
2002-06-07 | 2002 | 6 | Rothamsted | 17.5
2002-06-08 | 2002 | 6 | Rothamsted | 17.4
2002-06-09 | 2002 | 6 | Rothamsted | 16.4
2002-06-10 | 2002 | 6 | Rothamsted | 17.8
2002-06-11 | 2002 | 6 | Rothamsted | 16.5
2002-06-12 | 2002 | 6 | Rothamsted | 19.2
2002-06-13 | 2002 | 6 | Rothamsted | 21.1
2002-06-14 | 2002 | 6 | Rothamsted | 21.1
2002-06-15 | 2002 | 6 | Rothamsted | 22
2002-06-16 | 2002 | 6 | Rothamsted | 24.6
2002-06-17 | 2002 | 6 | Rothamsted | 20.7
2002-06-18 | 2002 | 6 | Rothamsted | 20.2
2002-06-19 | 2002 | 6 | Rothamsted | 20.6
2002-06-20 | 2002 | 6 | Rothamsted | 20.4
2002-06-21 | 2002 | 6 | Rothamsted | 18.3
2002-06-22 | 2002 | 6 | Rothamsted | 19.2
2002-06-23 | 2002 | 6 | Rothamsted | 21.1
2002-06-24 | 2002 | 6 | Rothamsted | 19
2002-06-25 | 2002 | 6 | Rothamsted | 22.6
2002-06-26 | 2002 | 6 | Rothamsted | 17.7
2002-06-27 | 2002 | 6 | Rothamsted | 17.1
2002-06-28 | 2002 | 6 | Rothamsted | 18.7
2002-06-29 | 2002 | 6 | Rothamsted | 19.5
2002-06-30 | 2002 | 6 | Rothamsted | 16.4
2002-07-01 | 2002 | 7 | Rothamsted | 17.2
2002-07-02 | 2002 | 7 | Rothamsted | 17
2002-07-03 | 2002 | 7 | Rothamsted | 18.7
2002-07-04 | 2002 | 7 | Rothamsted | 17.8
2002-07-05 | 2002 | 7 | Rothamsted | 18.7
2002-07-06 | 2002 | 7 | Rothamsted | 19
2002-07-07 | 2002 | 7 | Rothamsted | 18.1
2002-07-08 | 2002 | 7 | Rothamsted | 19.8
2002-07-09 | 2002 | 7 | Rothamsted | 18.2
2002-07-10 | 2002 | 7 | Rothamsted | 18.4
2002-07-11 | 2002 | 7 | Rothamsted | 18.4
2002-07-12 | 2002 | 7 | Rothamsted | 21.2
2002-07-13 | 2002 | 7 | Rothamsted | 23.6
2002-07-14 | 2002 | 7 | Rothamsted | 24.8
2002-07-15 | 2002 | 7 | Rothamsted | 22.9
2002-07-16 | 2002 | 7 | Rothamsted | 19.9
2002-07-17 | 2002 | 7 | Rothamsted | 21
2002-07-18 | 2002 | 7 | Rothamsted | 22.3
2002-07-19 | 2002 | 7 | Rothamsted | 20.9
2002-07-20 | 2002 | 7 | Rothamsted | 18.5
2002-07-21 | 2002 | 7 | Rothamsted | 19.9
2002-07-22 | 2002 | 7 | Rothamsted | 21.1
2002-07-23 | 2002 | 7 | Rothamsted | 18.9
2002-07-24 | 2002 | 7 | Rothamsted | 21.6
2002-07-25 | 2002 | 7 | Rothamsted | 26.7
2002-07-26 | 2002 | 7 | Rothamsted | 24.5
2002-07-27 | 2002 | 7 | Rothamsted | 28.1
2002-07-28 | 2002 | 7 | Rothamsted | 30
2002-07-29 | 2002 | 7 | Rothamsted | 25.2
2002-08-01 | 2002 | 8 | Rothamsted | 21.4
2002-08-02 | 2002 | 8 | Rothamsted | 19.3
2002-08-03 | 2002 | 8 | Rothamsted | 20.2
2002-08-04 | 2002 | 8 | Rothamsted | 19.3
2002-08-05 | 2002 | 8 | Rothamsted | 22.4
2002-08-06 | 2002 | 8 | Rothamsted | 25.3
2002-08-08 | 2002 | 8 | Rothamsted | 17.6
2002-08-09 | 2002 | 8 | Rothamsted | 21.4
2002-08-10 | 2002 | 8 | Rothamsted | 20.7
2002-08-11 | 2002 | 8 | Rothamsted | 21.3
2002-08-12 | 2002 | 8 | Rothamsted | 23.6
2002-08-13 | 2002 | 8 | Rothamsted | 24.7
2002-08-14 | 2002 | 8 | Rothamsted | 27.7
2002-08-15 | 2002 | 8 | Rothamsted | 25.9
2002-08-16 | 2002 | 8 | Rothamsted | 28.8
2002-08-17 | 2002 | 8 | Rothamsted | 25.3
2002-08-18 | 2002 | 8 | Rothamsted | 23.9
2002-08-19 | 2002 | 8 | Rothamsted | 20.5
2002-08-20 | 2002 | 8 | Rothamsted | 21
2002-08-21 | 2002 | 8 | Rothamsted | 22.4
2002-08-22 | 2002 | 8 | Rothamsted | 21.3
2002-08-23 | 2002 | 8 | Rothamsted | 22.3
2002-08-24 | 2002 | 8 | Rothamsted | 20
2002-08-26 | 2002 | 8 | Rothamsted | 20.1
2002-08-27 | 2002 | 8 | Rothamsted | 22.1
2002-08-28 | 2002 | 8 | Rothamsted | 24
2002-08-29 | 2002 | 8 | Rothamsted | 22
2002-08-30 | 2002 | 8 | Rothamsted | 18.7
2002-08-31 | 2002 | 8 | Rothamsted | 19.8
2002-09-01 | 2002 | 9 | Rothamsted | 20.9
2002-09-02 | 2002 | 9 | Rothamsted | 21.9
2002-09-03 | 2002 | 9 | Rothamsted | 21.5
2002-09-04 | 2002 | 9 | Rothamsted | 21.3
2002-09-05 | 2002 | 9 | Rothamsted | 21.6
2002-09-06 | 2002 | 9 | Rothamsted | 18.8
2002-09-07 | 2002 | 9 | Rothamsted | 19.1
2002-09-08 | 2002 | 9 | Rothamsted | 16
2002-09-09 | 2002 | 9 | Rothamsted | 19.4
2002-09-10 | 2002 | 9 | Rothamsted | 20.7
2002-09-11 | 2002 | 9 | Rothamsted | 21.9
2002-09-12 | 2002 | 9 | Rothamsted | 22.9
2002-09-15 | 2002 | 9 | Rothamsted | 16.4
2002-09-16 | 2002 | 9 | Rothamsted | 16.6
2002-09-17 | 2002 | 9 | Rothamsted | 15.8
2002-09-18 | 2002 | 9 | Rothamsted | 17.6
2002-09-19 | 2002 | 9 | Rothamsted | 17.5
2002-09-20 | 2002 | 9 | Rothamsted | 17.9
2002-09-21 | 2002 | 9 | Rothamsted | 16.6
2002-09-22 | 2002 | 9 | Rothamsted | 17.6
2002-09-23 | 2002 | 9 | Rothamsted | 16.7
2002-09-24 | 2002 | 9 | Rothamsted | 17.7
2002-09-25 | 2002 | 9 | Rothamsted | 16.8
2002-09-26 | 2002 | 9 | Rothamsted | 16.2
2002-09-27 | 2002 | 9 | Rothamsted | 18.1
2002-09-28 | 2002 | 9 | Rothamsted | 19.2
2002-09-29 | 2002 | 9 | Rothamsted | 20.4
2002-09-30 | 2002 | 9 | Rothamsted | 20.5
2003-05-01 | 2003 | 5 | Rothamsted | 13.3
2003-05-02 | 2003 | 5 | Rothamsted | 15.9
2003-05-03 | 2003 | 5 | Rothamsted | 21
2003-05-04 | 2003 | 5 | Rothamsted | 15.6
2003-05-05 | 2003 | 5 | Rothamsted | 15.9
2003-05-06 | 2003 | 5 | Rothamsted | 18.5
2003-05-07 | 2003 | 5 | Rothamsted | 18.4
2003-05-08 | 2003 | 5 | Rothamsted | 18.4
2003-05-09 | 2003 | 5 | Rothamsted | 13.7
2003-05-10 | 2003 | 5 | Rothamsted | 14.7
2003-05-11 | 2003 | 5 | Rothamsted | 14.2
2003-05-12 | 2003 | 5 | Rothamsted | 12.8
2003-05-13 | 2003 | 5 | Rothamsted | 14.4
2003-05-14 | 2003 | 5 | Rothamsted | 15.5
2003-05-15 | 2003 | 5 | Rothamsted | 11.7
2003-05-16 | 2003 | 5 | Rothamsted | 15.5
2003-05-17 | 2003 | 5 | Rothamsted | 15.7
2003-05-18 | 2003 | 5 | Rothamsted | 15.7
2003-05-19 | 2003 | 5 | Rothamsted | 14.7
2003-05-20 | 2003 | 5 | Rothamsted | 15.7
2003-05-21 | 2003 | 5 | Rothamsted | 16.8
2003-05-22 | 2003 | 5 | Rothamsted | 16.9
2003-05-23 | 2003 | 5 | Rothamsted | 17.1
2003-05-24 | 2003 | 5 | Rothamsted | 16.9
2003-05-25 | 2003 | 5 | Rothamsted | 17.9
2003-05-26 | 2003 | 5 | Rothamsted | 18.2
2003-05-27 | 2003 | 5 | Rothamsted | 21.6
2003-05-28 | 2003 | 5 | Rothamsted | 23.7
2003-05-29 | 2003 | 5 | Rothamsted | 24.8
2003-05-30 | 2003 | 5 | Rothamsted | 26.7
2003-05-31 | 2003 | 5 | Rothamsted | 22
2003-06-01 | 2003 | 6 | Rothamsted | 21.1
2003-06-02 | 2003 | 6 | Rothamsted | 20.3
2003-06-03 | 2003 | 6 | Rothamsted | 19.1
2003-06-04 | 2003 | 6 | Rothamsted | 19.8
2003-06-05 | 2003 | 6 | Rothamsted | 17.7
2003-06-06 | 2003 | 6 | Rothamsted | 21.8
2003-06-07 | 2003 | 6 | Rothamsted | 19.8
2003-06-08 | 2003 | 6 | Rothamsted | 19.8
2003-06-09 | 2003 | 6 | Rothamsted | 21
2003-06-10 | 2003 | 6 | Rothamsted | 19.7
2003-06-11 | 2003 | 6 | Rothamsted | 20.8
2003-06-12 | 2003 | 6 | Rothamsted | 21.2
2003-06-13 | 2003 | 6 | Rothamsted | 22.5
2003-06-14 | 2003 | 6 | Rothamsted | 24.4
2003-06-15 | 2003 | 6 | Rothamsted | 26.6
2003-06-16 | 2003 | 6 | Rothamsted | 23.2
2003-06-17 | 2003 | 6 | Rothamsted | 19.7
2003-06-18 | 2003 | 6 | Rothamsted | 21.6
2003-06-19 | 2003 | 6 | Rothamsted | 19.9
2003-06-20 | 2003 | 6 | Rothamsted | 23.4
2003-06-21 | 2003 | 6 | Rothamsted | 25.9
2003-06-22 | 2003 | 6 | Rothamsted | 21.5
2003-06-23 | 2003 | 6 | Rothamsted | 21.3
2003-06-24 | 2003 | 6 | Rothamsted | 21.1
2003-06-25 | 2003 | 6 | Rothamsted | 22.5
2003-06-26 | 2003 | 6 | Rothamsted | 21.5
2003-06-27 | 2003 | 6 | Rothamsted | 21.2
2003-06-28 | 2003 | 6 | Rothamsted | 24.5
2003-06-29 | 2003 | 6 | Rothamsted | 18.1
2003-06-30 | 2003 | 6 | Rothamsted | 18.8
2003-07-01 | 2003 | 7 | Rothamsted | 20.4
2003-07-02 | 2003 | 7 | Rothamsted | 17.7
2003-07-03 | 2003 | 7 | Rothamsted | 19.3
2003-07-04 | 2003 | 7 | Rothamsted | 17.4
2003-07-05 | 2003 | 7 | Rothamsted | 21.3
2003-07-06 | 2003 | 7 | Rothamsted | 21.9
2003-07-07 | 2003 | 7 | Rothamsted | 22.9
2003-07-08 | 2003 | 7 | Rothamsted | 26.6
2003-07-09 | 2003 | 7 | Rothamsted | 28.2
2003-07-10 | 2003 | 7 | Rothamsted | 21.7
2003-07-11 | 2003 | 7 | Rothamsted | 25
2003-07-12 | 2003 | 7 | Rothamsted | 26.2
2003-07-13 | 2003 | 7 | Rothamsted | 28.7
2003-07-14 | 2003 | 7 | Rothamsted | 30.9
2003-07-15 | 2003 | 7 | Rothamsted | 27
2003-07-17 | 2003 | 7 | Rothamsted | 24
2003-07-18 | 2003 | 7 | Rothamsted | 27.5
2003-07-19 | 2003 | 7 | Rothamsted | 23.7
2003-07-20 | 2003 | 7 | Rothamsted | 24
2003-07-21 | 2003 | 7 | Rothamsted | 23.9
2003-07-22 | 2003 | 7 | Rothamsted | 23.1
2003-07-23 | 2003 | 7 | Rothamsted | 23.2
2003-07-24 | 2003 | 7 | Rothamsted | 18.8
2003-07-25 | 2003 | 7 | Rothamsted | 20.6
2003-07-26 | 2003 | 7 | Rothamsted | 22.4
2003-07-27 | 2003 | 7 | Rothamsted | 22.6
2003-07-28 | 2003 | 7 | Rothamsted | 20.7
2003-07-29 | 2003 | 7 | Rothamsted | 22.9
2003-07-30 | 2003 | 7 | Rothamsted | 21.8
2003-07-31 | 2003 | 7 | Rothamsted | 17.9
2003-08-01 | 2003 | 8 | Rothamsted | 24.2
2003-08-02 | 2003 | 8 | Rothamsted | 28
2003-08-03 | 2003 | 8 | Rothamsted | 29.8
2003-08-04 | 2003 | 8 | Rothamsted | 29.9
2003-08-05 | 2003 | 8 | Rothamsted | 34.4
2003-08-06 | 2003 | 8 | Rothamsted | 28.6
2003-08-07 | 2003 | 8 | Rothamsted | 27.5
2003-08-08 | 2003 | 8 | Rothamsted | 34.1
2003-08-09 | 2003 | 8 | Rothamsted | 36
2003-08-10 | 2003 | 8 | Rothamsted | 32.4
2003-08-11 | 2003 | 8 | Rothamsted | 28.2
2003-08-12 | 2003 | 8 | Rothamsted | 27.4
2003-08-13 | 2003 | 8 | Rothamsted | 23
2003-08-14 | 2003 | 8 | Rothamsted | 23.3
2003-08-15 | 2003 | 8 | Rothamsted | 22.7
2003-08-16 | 2003 | 8 | Rothamsted | 25.1
2003-08-17 | 2003 | 8 | Rothamsted | 24.9
2003-08-18 | 2003 | 8 | Rothamsted | 22
2003-08-19 | 2003 | 8 | Rothamsted | 22.1
2003-08-20 | 2003 | 8 | Rothamsted | 22.4
2003-08-21 | 2003 | 8 | Rothamsted | 24.8
2003-08-22 | 2003 | 8 | Rothamsted | 25.9
2003-08-23 | 2003 | 8 | Rothamsted | 24
2003-08-25 | 2003 | 8 | Rothamsted | 21.9
2003-08-26 | 2003 | 8 | Rothamsted | 21
2003-08-27 | 2003 | 8 | Rothamsted | 19.3
2003-08-28 | 2003 | 8 | Rothamsted | 19.5
2003-08-29 | 2003 | 8 | Rothamsted | 18.9
2003-08-30 | 2003 | 8 | Rothamsted | 19.1
2003-08-31 | 2003 | 8 | Rothamsted | 18.3
2003-09-01 | 2003 | 9 | Rothamsted | 19.7
2003-09-02 | 2003 | 9 | Rothamsted | 21.3
2003-09-03 | 2003 | 9 | Rothamsted | 22.9
2003-09-04 | 2003 | 9 | Rothamsted | 25
2003-09-05 | 2003 | 9 | Rothamsted | 20.4
2003-09-06 | 2003 | 9 | Rothamsted | 18.3
2003-09-07 | 2003 | 9 | Rothamsted | 21.7
2003-09-08 | 2003 | 9 | Rothamsted | 20.3
2003-09-09 | 2003 | 9 | Rothamsted | 19.2
2003-09-10 | 2003 | 9 | Rothamsted | 17
2003-09-11 | 2003 | 9 | Rothamsted | 18.8
2003-09-12 | 2003 | 9 | Rothamsted | 22.8
2003-09-13 | 2003 | 9 | Rothamsted | 24.9
2003-09-14 | 2003 | 9 | Rothamsted | 24.9
2003-09-15 | 2003 | 9 | Rothamsted | 26.7
2003-09-16 | 2003 | 9 | Rothamsted | 26.9
2003-09-17 | 2003 | 9 | Rothamsted | 19
2003-09-18 | 2003 | 9 | Rothamsted | 22.3
2003-09-19 | 2003 | 9 | Rothamsted | 25.2
2003-09-20 | 2003 | 9 | Rothamsted | 24.5
2003-09-21 | 2003 | 9 | Rothamsted | 20.1
2003-09-23 | 2003 | 9 | Rothamsted | 16.4
2003-09-24 | 2003 | 9 | Rothamsted | 18.6
2003-09-25 | 2003 | 9 | Rothamsted | 19.4
2003-09-26 | 2003 | 9 | Rothamsted | 16.2
2003-09-27 | 2003 | 9 | Rothamsted | 14.9
2003-09-28 | 2003 | 9 | Rothamsted | 17.7
2003-09-29 | 2003 | 9 | Rothamsted | 19.5
2003-09-30 | 2003 | 9 | Rothamsted | 18.3
2004-05-01 | 2004 | 5 | Rothamsted | 17.5
2004-05-02 | 2004 | 5 | Rothamsted | 12.5
2004-05-04 | 2004 | 5 | Rothamsted | 11.8
2004-05-05 | 2004 | 5 | Rothamsted | 13.6
2004-05-06 | 2004 | 5 | Rothamsted | 14.3
2004-05-07 | 2004 | 5 | Rothamsted | 13
2004-05-08 | 2004 | 5 | Rothamsted | 14.3
2004-05-09 | 2004 | 5 | Rothamsted | 17.6
2004-05-12 | 2004 | 5 | Rothamsted | 16.1
2004-05-13 | 2004 | 5 | Rothamsted | 18.8
2004-05-14 | 2004 | 5 | Rothamsted | 19.1
2004-05-15 | 2004 | 5 | Rothamsted | 21.2
2004-05-16 | 2004 | 5 | Rothamsted | 22.4
2004-05-17 | 2004 | 5 | Rothamsted | 20.3
2004-05-18 | 2004 | 5 | Rothamsted | 22.1
2004-05-19 | 2004 | 5 | Rothamsted | 18.6
2004-05-21 | 2004 | 5 | Rothamsted | 14.5
2004-05-22 | 2004 | 5 | Rothamsted | 17.1
2004-05-23 | 2004 | 5 | Rothamsted | 18.9
2004-05-24 | 2004 | 5 | Rothamsted | 17.9
2004-05-25 | 2004 | 5 | Rothamsted | 14.8
2004-05-26 | 2004 | 5 | Rothamsted | 16
2004-05-27 | 2004 | 5 | Rothamsted | 18.8
2004-05-28 | 2004 | 5 | Rothamsted | 18.9
2004-05-29 | 2004 | 5 | Rothamsted | 18.5
2004-05-30 | 2004 | 5 | Rothamsted | 20.3
2004-05-31 | 2004 | 5 | Rothamsted | 15
2004-06-01 | 2004 | 6 | Rothamsted | 18.5
2004-06-02 | 2004 | 6 | Rothamsted | 18.2
2004-06-03 | 2004 | 6 | Rothamsted | 21
2004-06-04 | 2004 | 6 | Rothamsted | 20
2004-06-05 | 2004 | 6 | Rothamsted | 22.8
2004-06-06 | 2004 | 6 | Rothamsted | 25.8
2004-06-07 | 2004 | 6 | Rothamsted | 29.3
2004-06-08 | 2004 | 6 | Rothamsted | 21.9
2004-06-09 | 2004 | 6 | Rothamsted | 22.9
2004-06-10 | 2004 | 6 | Rothamsted | 18.8
2004-06-11 | 2004 | 6 | Rothamsted | 19.9
2004-06-12 | 2004 | 6 | Rothamsted | 23.8
2004-06-13 | 2004 | 6 | Rothamsted | 26.1
2004-06-14 | 2004 | 6 | Rothamsted | 24.3
2004-06-15 | 2004 | 6 | Rothamsted | 24.6
2004-06-16 | 2004 | 6 | Rothamsted | 17.8
2004-06-18 | 2004 | 6 | Rothamsted | 16.7
2004-06-19 | 2004 | 6 | Rothamsted | 16.9
2004-06-20 | 2004 | 6 | Rothamsted | 17
2004-06-21 | 2004 | 6 | Rothamsted | 19.1
2004-06-22 | 2004 | 6 | Rothamsted | 16.7
2004-06-23 | 2004 | 6 | Rothamsted | 18
2004-06-24 | 2004 | 6 | Rothamsted | 19.6
2004-06-25 | 2004 | 6 | Rothamsted | 19.2
2004-06-26 | 2004 | 6 | Rothamsted | 21.8
2004-06-27 | 2004 | 6 | Rothamsted | 19.7
2004-06-28 | 2004 | 6 | Rothamsted | 21.7
2004-06-29 | 2004 | 6 | Rothamsted | 19.7
2004-06-30 | 2004 | 6 | Rothamsted | 18.7
2004-07-01 | 2004 | 7 | Rothamsted | 19.6
2004-07-02 | 2004 | 7 | Rothamsted | 18.8
2004-07-03 | 2004 | 7 | Rothamsted | 18.4
2004-07-04 | 2004 | 7 | Rothamsted | 20.1
2004-07-05 | 2004 | 7 | Rothamsted | 22.5
2004-07-06 | 2004 | 7 | Rothamsted | 20.3
2004-07-07 | 2004 | 7 | Rothamsted | 18.5
2004-07-08 | 2004 | 7 | Rothamsted | 17.3
2004-07-09 | 2004 | 7 | Rothamsted | 17.9
2004-07-10 | 2004 | 7 | Rothamsted | 17
2004-07-11 | 2004 | 7 | Rothamsted | 18.1
2004-07-12 | 2004 | 7 | Rothamsted | 19.5
2004-07-13 | 2004 | 7 | Rothamsted | 22.2
2004-07-14 | 2004 | 7 | Rothamsted | 22.7
2004-07-15 | 2004 | 7 | Rothamsted | 23
2004-07-16 | 2004 | 7 | Rothamsted | 23.7
2004-07-17 | 2004 | 7 | Rothamsted | 20.9
2004-07-18 | 2004 | 7 | Rothamsted | 21.8
2004-07-19 | 2004 | 7 | Rothamsted | 22.7
2004-07-20 | 2004 | 7 | Rothamsted | 21.2
2004-07-21 | 2004 | 7 | Rothamsted | 24.6
2004-07-22 | 2004 | 7 | Rothamsted | 23.9
2004-07-23 | 2004 | 7 | Rothamsted | 23.2
2004-07-24 | 2004 | 7 | Rothamsted | 21.7
2004-07-25 | 2004 | 7 | Rothamsted | 22.1
2004-07-26 | 2004 | 7 | Rothamsted | 22.3
2004-07-27 | 2004 | 7 | Rothamsted | 25.6
2004-07-28 | 2004 | 7 | Rothamsted | 27.4
2004-07-29 | 2004 | 7 | Rothamsted | 24
2004-07-30 | 2004 | 7 | Rothamsted | 26.5
2004-07-31 | 2004 | 7 | Rothamsted | 23.8
2004-08-01 | 2004 | 8 | Rothamsted | 26.3
2004-08-02 | 2004 | 8 | Rothamsted | 26
2004-08-03 | 2004 | 8 | Rothamsted | 26.8
2004-08-04 | 2004 | 8 | Rothamsted | 27.1
2004-08-05 | 2004 | 8 | Rothamsted | 27.2
2004-08-06 | 2004 | 8 | Rothamsted | 28.2
2004-08-07 | 2004 | 8 | Rothamsted | 29.3
2004-08-08 | 2004 | 8 | Rothamsted | 22.9
2004-08-09 | 2004 | 8 | Rothamsted | 24.2
2004-08-10 | 2004 | 8 | Rothamsted | 23.6
2004-08-11 | 2004 | 8 | Rothamsted | 22.3
2004-08-12 | 2004 | 8 | Rothamsted | 22.3
2004-08-13 | 2004 | 8 | Rothamsted | 23.6
2004-08-14 | 2004 | 8 | Rothamsted | 22.9
2004-08-15 | 2004 | 8 | Rothamsted | 21.2
2004-08-16 | 2004 | 8 | Rothamsted | 22.7
2004-08-17 | 2004 | 8 | Rothamsted | 22.6
2004-08-18 | 2004 | 8 | Rothamsted | 21.1
2004-08-19 | 2004 | 8 | Rothamsted | 20.2
2004-08-20 | 2004 | 8 | Rothamsted | 18.8
2004-08-21 | 2004 | 8 | Rothamsted | 20.6
2004-08-22 | 2004 | 8 | Rothamsted | 20.7
2004-08-23 | 2004 | 8 | Rothamsted | 20.1
2004-08-24 | 2004 | 8 | Rothamsted | 18.7
2004-08-25 | 2004 | 8 | Rothamsted | 19.9
2004-08-26 | 2004 | 8 | Rothamsted | 20.8
2004-08-27 | 2004 | 8 | Rothamsted | 18.5
2004-08-28 | 2004 | 8 | Rothamsted | 17.9
2004-08-29 | 2004 | 8 | Rothamsted | 18.2
2004-08-30 | 2004 | 8 | Rothamsted | 19.1
2004-08-31 | 2004 | 8 | Rothamsted | 21.1
2004-09-01 | 2004 | 9 | Rothamsted | 23.4
2004-09-02 | 2004 | 9 | Rothamsted | 25.1
2004-09-03 | 2004 | 9 | Rothamsted | 25.7
2004-09-04 | 2004 | 9 | Rothamsted | 26.3
2004-09-05 | 2004 | 9 | Rothamsted | 24
2004-09-06 | 2004 | 9 | Rothamsted | 22.8
2004-09-07 | 2004 | 9 | Rothamsted | 22.7
2004-09-08 | 2004 | 9 | Rothamsted | 23.3
2004-09-09 | 2004 | 9 | Rothamsted | 21.5
2004-09-10 | 2004 | 9 | Rothamsted | 21.5
2004-09-12 | 2004 | 9 | Rothamsted | 17.8
2004-09-13 | 2004 | 9 | Rothamsted | 17.3
2004-09-14 | 2004 | 9 | Rothamsted | 16.7
2004-09-15 | 2004 | 9 | Rothamsted | 17.8
2004-09-16 | 2004 | 9 | Rothamsted | 18.5
2004-09-17 | 2004 | 9 | Rothamsted | 19
2004-09-19 | 2004 | 9 | Rothamsted | 18.2
2004-09-20 | 2004 | 9 | Rothamsted | 15.3
2004-09-21 | 2004 | 9 | Rothamsted | 17.5
2004-09-22 | 2004 | 9 | Rothamsted | 16.5
2004-09-24 | 2004 | 9 | Rothamsted | 14.5
2004-09-25 | 2004 | 9 | Rothamsted | 19.4
2004-09-26 | 2004 | 9 | Rothamsted | 19.8
2004-09-27 | 2004 | 9 | Rothamsted | 18
2004-09-29 | 2004 | 9 | Rothamsted | 18.4
2004-09-30 | 2004 | 9 | Rothamsted | 15.3
2005-05-01 | 2005 | 5 | Rothamsted | 20.4
2005-05-04 | 2005 | 5 | Rothamsted | 16.9
2005-05-05 | 2005 | 5 | Rothamsted | 15
2005-05-06 | 2005 | 5 | Rothamsted | 13.5
2005-05-07 | 2005 | 5 | Rothamsted | 13
2005-05-08 | 2005 | 5 | Rothamsted | 11
2005-05-09 | 2005 | 5 | Rothamsted | 11.7
2005-05-10 | 2005 | 5 | Rothamsted | 12.1
2005-05-11 | 2005 | 5 | Rothamsted | 13.3
2005-05-12 | 2005 | 5 | Rothamsted | 14.9
2005-05-13 | 2005 | 5 | Rothamsted | 13.6
2005-05-14 | 2005 | 5 | Rothamsted | 16.2
2005-05-15 | 2005 | 5 | Rothamsted | 12.4
2005-05-16 | 2005 | 5 | Rothamsted | 11.9
2005-05-17 | 2005 | 5 | Rothamsted | 13.9
2005-05-18 | 2005 | 5 | Rothamsted | 13.7
2005-05-19 | 2005 | 5 | Rothamsted | 17.9
2005-05-20 | 2005 | 5 | Rothamsted | 14.9
2005-05-21 | 2005 | 5 | Rothamsted | 15
2005-05-22 | 2005 | 5 | Rothamsted | 15.9
2005-05-23 | 2005 | 5 | Rothamsted | 17
2005-05-24 | 2005 | 5 | Rothamsted | 20.3
2005-05-25 | 2005 | 5 | Rothamsted | 21.7
2005-05-26 | 2005 | 5 | Rothamsted | 29.1
2005-05-27 | 2005 | 5 | Rothamsted | 18.7
2005-05-29 | 2005 | 5 | Rothamsted | 16.2
2005-05-30 | 2005 | 5 | Rothamsted | 17.9
2005-05-31 | 2005 | 5 | Rothamsted | 15.5
2005-06-01 | 2005 | 6 | Rothamsted | 17.1
2005-06-02 | 2005 | 6 | Rothamsted | 19.8
2005-06-03 | 2005 | 6 | Rothamsted | 16.9
2005-06-04 | 2005 | 6 | Rothamsted | 18.3
2005-06-05 | 2005 | 6 | Rothamsted | 15.3
2005-06-06 | 2005 | 6 | Rothamsted | 16.4
2005-06-07 | 2005 | 6 | Rothamsted | 20.3
2005-06-08 | 2005 | 6 | Rothamsted | 20.9
2005-06-09 | 2005 | 6 | Rothamsted | 15.9
2005-06-11 | 2005 | 6 | Rothamsted | 16.9
2005-06-12 | 2005 | 6 | Rothamsted | 17.2
2005-06-13 | 2005 | 6 | Rothamsted | 19.1
2005-06-14 | 2005 | 6 | Rothamsted | 20.2
2005-06-15 | 2005 | 6 | Rothamsted | 20
2005-06-16 | 2005 | 6 | Rothamsted | 25.4
2005-06-17 | 2005 | 6 | Rothamsted | 28.3
2005-06-18 | 2005 | 6 | Rothamsted | 30.8
2005-06-19 | 2005 | 6 | Rothamsted | 25.8
2005-06-21 | 2005 | 6 | Rothamsted | 27
2005-06-22 | 2005 | 6 | Rothamsted | 29.3
2005-06-23 | 2005 | 6 | Rothamsted | 21.6
2005-06-25 | 2005 | 6 | Rothamsted | 18.7
2005-06-26 | 2005 | 6 | Rothamsted | 23.9
2005-06-27 | 2005 | 6 | Rothamsted | 24.8
2005-06-28 | 2005 | 6 | Rothamsted | 22.9
2005-06-29 | 2005 | 6 | Rothamsted | 19.9
2005-06-30 | 2005 | 6 | Rothamsted | 20
2005-07-01 | 2005 | 7 | Rothamsted | 20.6
2005-07-02 | 2005 | 7 | Rothamsted | 18.8
2005-07-03 | 2005 | 7 | Rothamsted | 16.6
2005-07-04 | 2005 | 7 | Rothamsted | 16
2005-07-05 | 2005 | 7 | Rothamsted | 18.3
2005-07-06 | 2005 | 7 | Rothamsted | 19.2
2005-07-07 | 2005 | 7 | Rothamsted | 18.1
2005-07-08 | 2005 | 7 | Rothamsted | 20.1
2005-07-09 | 2005 | 7 | Rothamsted | 26.8
2005-07-10 | 2005 | 7 | Rothamsted | 25.5
2005-07-11 | 2005 | 7 | Rothamsted | 24.4
2005-07-12 | 2005 | 7 | Rothamsted | 28.1
2005-07-13 | 2005 | 7 | Rothamsted | 28.6
2005-07-14 | 2005 | 7 | Rothamsted | 24.9
2005-07-16 | 2005 | 7 | Rothamsted | 27.3
2005-07-17 | 2005 | 7 | Rothamsted | 23.2
2005-07-18 | 2005 | 7 | Rothamsted | 21.2
2005-07-19 | 2005 | 7 | Rothamsted | 21.7
2005-07-20 | 2005 | 7 | Rothamsted | 19.2
2005-07-21 | 2005 | 7 | Rothamsted | 19.5
2005-07-22 | 2005 | 7 | Rothamsted | 21.1
2005-07-23 | 2005 | 7 | Rothamsted | 20.1
2005-07-25 | 2005 | 7 | Rothamsted | 19
2005-07-26 | 2005 | 7 | Rothamsted | 16.1
2005-07-27 | 2005 | 7 | Rothamsted | 24.1
2005-07-28 | 2005 | 7 | Rothamsted | 21.4
2005-07-29 | 2005 | 7 | Rothamsted | 20.1
2005-07-30 | 2005 | 7 | Rothamsted | 18.5
2005-07-31 | 2005 | 7 | Rothamsted | 20.1
2005-08-01 | 2005 | 8 | Rothamsted | 23.7
2005-08-02 | 2005 | 8 | Rothamsted | 22.4
2005-08-03 | 2005 | 8 | Rothamsted | 21.6
2005-08-04 | 2005 | 8 | Rothamsted | 20.6
2005-08-05 | 2005 | 8 | Rothamsted | 19.3
2005-08-06 | 2005 | 8 | Rothamsted | 20.1
2005-08-07 | 2005 | 8 | Rothamsted | 21.5
2005-08-08 | 2005 | 8 | Rothamsted | 24
2005-08-09 | 2005 | 8 | Rothamsted | 23
2005-08-10 | 2005 | 8 | Rothamsted | 24.6
2005-08-11 | 2005 | 8 | Rothamsted | 21.3
2005-08-12 | 2005 | 8 | Rothamsted | 20.2
2005-08-13 | 2005 | 8 | Rothamsted | 18.5
2005-08-14 | 2005 | 8 | Rothamsted | 22.1
2005-08-15 | 2005 | 8 | Rothamsted | 23
2005-08-16 | 2005 | 8 | Rothamsted | 24.8
2005-08-17 | 2005 | 8 | Rothamsted | 27
2005-08-20 | 2005 | 8 | Rothamsted | 23.6
2005-08-21 | 2005 | 8 | Rothamsted | 17.6
2005-08-22 | 2005 | 8 | Rothamsted | 20.9
2005-08-23 | 2005 | 8 | Rothamsted | 15.7
2005-08-24 | 2005 | 8 | Rothamsted | 18.2
2005-08-25 | 2005 | 8 | Rothamsted | 18.4
2005-08-26 | 2005 | 8 | Rothamsted | 19
2005-08-27 | 2005 | 8 | Rothamsted | 23.1
2005-08-28 | 2005 | 8 | Rothamsted | 24.4
2005-08-29 | 2005 | 8 | Rothamsted | 26
2005-08-30 | 2005 | 8 | Rothamsted | 30.5
2005-08-31 | 2005 | 8 | Rothamsted | 22.4
2005-09-02 | 2005 | 9 | Rothamsted | 23.9
2005-09-03 | 2005 | 9 | Rothamsted | 27.2
2005-09-04 | 2005 | 9 | Rothamsted | 23
2005-09-06 | 2005 | 9 | Rothamsted | 23.7
2005-09-07 | 2005 | 9 | Rothamsted | 23.8
2005-09-08 | 2005 | 9 | Rothamsted | 24.8
2005-09-09 | 2005 | 9 | Rothamsted | 20.2
2005-09-11 | 2005 | 9 | Rothamsted | 20.4
2005-09-12 | 2005 | 9 | Rothamsted | 21.7
2005-09-13 | 2005 | 9 | Rothamsted | 23.9
2005-09-14 | 2005 | 9 | Rothamsted | 20.9
2005-09-16 | 2005 | 9 | Rothamsted | 15.2
2005-09-17 | 2005 | 9 | Rothamsted | 15.6
2005-09-18 | 2005 | 9 | Rothamsted | 17.1
2005-09-19 | 2005 | 9 | Rothamsted | 20.9
2005-09-20 | 2005 | 9 | Rothamsted | 20.9
2005-09-21 | 2005 | 9 | Rothamsted | 20.2
2005-09-22 | 2005 | 9 | Rothamsted | 18.3
2005-09-23 | 2005 | 9 | Rothamsted | 17
2005-09-24 | 2005 | 9 | Rothamsted | 19.2
2005-09-25 | 2005 | 9 | Rothamsted | 16.7
2005-09-26 | 2005 | 9 | Rothamsted | 18.8
2005-09-28 | 2005 | 9 | Rothamsted | 15.7
2005-09-29 | 2005 | 9 | Rothamsted | 18.7
2005-09-30 | 2005 | 9 | Rothamsted | 15.2
2006-05-01 | 2006 | 5 | Rothamsted | 15.6
2006-05-02 | 2006 | 5 | Rothamsted | 18.4
2006-05-03 | 2006 | 5 | Rothamsted | 25.5
2006-05-04 | 2006 | 5 | Rothamsted | 19.7
2006-05-05 | 2006 | 5 | Rothamsted | 16.7
2006-05-06 | 2006 | 5 | Rothamsted | 16.6
2006-05-07 | 2006 | 5 | Rothamsted | 14.3
2006-05-08 | 2006 | 5 | Rothamsted | 18.2
2006-05-09 | 2006 | 5 | Rothamsted | 21.4
2006-05-10 | 2006 | 5 | Rothamsted | 21.2
2006-05-11 | 2006 | 5 | Rothamsted | 23
2006-05-12 | 2006 | 5 | Rothamsted | 16.4
2006-05-13 | 2006 | 5 | Rothamsted | 14.6
2006-05-14 | 2006 | 5 | Rothamsted | 16.9
2006-05-15 | 2006 | 5 | Rothamsted | 15.7
2006-05-16 | 2006 | 5 | Rothamsted | 16.3
2006-05-17 | 2006 | 5 | Rothamsted | 17.5
2006-05-18 | 2006 | 5 | Rothamsted | 16.1
2006-05-19 | 2006 | 5 | Rothamsted | 15.1
2006-05-20 | 2006 | 5 | Rothamsted | 13.8
2006-05-21 | 2006 | 5 | Rothamsted | 14.8
2006-05-22 | 2006 | 5 | Rothamsted | 13.4
2006-05-23 | 2006 | 5 | Rothamsted | 12.9
2006-05-24 | 2006 | 5 | Rothamsted | 16.5
2006-05-25 | 2006 | 5 | Rothamsted | 18.7
2006-05-26 | 2006 | 5 | Rothamsted | 16
2006-05-27 | 2006 | 5 | Rothamsted | 16.8
2006-05-28 | 2006 | 5 | Rothamsted | 12.9
2006-05-29 | 2006 | 5 | Rothamsted | 12.2
2006-05-30 | 2006 | 5 | Rothamsted | 13.9
2006-05-31 | 2006 | 5 | Rothamsted | 15.1
2006-06-01 | 2006 | 6 | Rothamsted | 19.1
2006-06-02 | 2006 | 6 | Rothamsted | 22.4
2006-06-03 | 2006 | 6 | Rothamsted | 22.4
2006-06-04 | 2006 | 6 | Rothamsted | 17.9
2006-06-05 | 2006 | 6 | Rothamsted | 19.6
2006-06-06 | 2006 | 6 | Rothamsted | 24.1
2006-06-07 | 2006 | 6 | Rothamsted | 25
2006-06-08 | 2006 | 6 | Rothamsted | 24.7
2006-06-09 | 2006 | 6 | Rothamsted | 27.1
2006-06-10 | 2006 | 6 | Rothamsted | 26.5
2006-06-11 | 2006 | 6 | Rothamsted | 29.7
2006-06-12 | 2006 | 6 | Rothamsted | 23.1
2006-06-14 | 2006 | 6 | Rothamsted | 19.1
2006-06-15 | 2006 | 6 | Rothamsted | 22.4
2006-06-16 | 2006 | 6 | Rothamsted | 26.3
2006-06-17 | 2006 | 6 | Rothamsted | 23.8
2006-06-19 | 2006 | 6 | Rothamsted | 21.8
2006-06-20 | 2006 | 6 | Rothamsted | 17.8
2006-06-21 | 2006 | 6 | Rothamsted | 18.9
2006-06-22 | 2006 | 6 | Rothamsted | 20.4
2006-06-23 | 2006 | 6 | Rothamsted | 22.8
2006-06-24 | 2006 | 6 | Rothamsted | 22.7
2006-06-26 | 2006 | 6 | Rothamsted | 17.8
2006-06-27 | 2006 | 6 | Rothamsted | 20.5
2006-06-28 | 2006 | 6 | Rothamsted | 23.5
2006-06-29 | 2006 | 6 | Rothamsted | 26.4
2006-06-30 | 2006 | 6 | Rothamsted | 27.7
2006-07-01 | 2006 | 7 | Rothamsted | 29.9
2006-07-02 | 2006 | 7 | Rothamsted | 29.2
2006-07-03 | 2006 | 7 | Rothamsted | 28.5
2006-07-04 | 2006 | 7 | Rothamsted | 23
2006-07-05 | 2006 | 7 | Rothamsted | 23.6
2006-07-06 | 2006 | 7 | Rothamsted | 21.3
2006-07-07 | 2006 | 7 | Rothamsted | 21
2006-07-08 | 2006 | 7 | Rothamsted | 21.9
2006-07-09 | 2006 | 7 | Rothamsted | 20.1
2006-07-10 | 2006 | 7 | Rothamsted | 22.8
2006-07-11 | 2006 | 7 | Rothamsted | 25.8
2006-07-12 | 2006 | 7 | Rothamsted | 22.4
2006-07-13 | 2006 | 7 | Rothamsted | 22.5
2006-07-14 | 2006 | 7 | Rothamsted | 24.5
2006-07-15 | 2006 | 7 | Rothamsted | 28.3
2006-07-16 | 2006 | 7 | Rothamsted | 30.6
2006-07-17 | 2006 | 7 | Rothamsted | 31.1
2006-07-18 | 2006 | 7 | Rothamsted | 33.8
2006-07-19 | 2006 | 7 | Rothamsted | 29.8
2006-07-20 | 2006 | 7 | Rothamsted | 29.9
2006-07-21 | 2006 | 7 | Rothamsted | 29.2
2006-07-22 | 2006 | 7 | Rothamsted | 25.4
2006-07-23 | 2006 | 7 | Rothamsted | 28.4
2006-07-24 | 2006 | 7 | Rothamsted | 30.7
2006-07-25 | 2006 | 7 | Rothamsted | 31.4
2006-07-26 | 2006 | 7 | Rothamsted | 27.9
2006-07-27 | 2006 | 7 | Rothamsted | 27.2
2006-07-28 | 2006 | 7 | Rothamsted | 25.3
2006-07-29 | 2006 | 7 | Rothamsted | 24.2
2006-07-30 | 2006 | 7 | Rothamsted | 22.7
2006-07-31 | 2006 | 7 | Rothamsted | 21.1
2006-08-01 | 2006 | 8 | Rothamsted | 20
2006-08-02 | 2006 | 8 | Rothamsted | 18.8
2006-08-03 | 2006 | 8 | Rothamsted | 20.9
2006-08-04 | 2006 | 8 | Rothamsted | 26
2006-08-05 | 2006 | 8 | Rothamsted | 26.6
2006-08-06 | 2006 | 8 | Rothamsted | 23.1
2006-08-07 | 2006 | 8 | Rothamsted | 23.8
2006-08-08 | 2006 | 8 | Rothamsted | 20.6
2006-08-09 | 2006 | 8 | Rothamsted | 20.5
2006-08-10 | 2006 | 8 | Rothamsted | 19.9
2006-08-11 | 2006 | 8 | Rothamsted | 17
2006-08-12 | 2006 | 8 | Rothamsted | 19.5
2006-08-13 | 2006 | 8 | Rothamsted | 17.5
2006-08-14 | 2006 | 8 | Rothamsted | 20.6
2006-08-15 | 2006 | 8 | Rothamsted | 21.1
2006-08-16 | 2006 | 8 | Rothamsted | 21.5
2006-08-17 | 2006 | 8 | Rothamsted | 19.9
2006-08-18 | 2006 | 8 | Rothamsted | 20.1
2006-08-19 | 2006 | 8 | Rothamsted | 20.5
2006-08-20 | 2006 | 8 | Rothamsted | 19.5
2006-08-21 | 2006 | 8 | Rothamsted | 20.5
2006-08-22 | 2006 | 8 | Rothamsted | 19.6
2006-08-23 | 2006 | 8 | Rothamsted | 19.8
2006-08-24 | 2006 | 8 | Rothamsted | 21.2
2006-08-25 | 2006 | 8 | Rothamsted | 19.7
2006-08-26 | 2006 | 8 | Rothamsted | 20.4
2006-08-27 | 2006 | 8 | Rothamsted | 18.4
2006-08-28 | 2006 | 8 | Rothamsted | 17.9
2006-08-29 | 2006 | 8 | Rothamsted | 19.3
2006-08-30 | 2006 | 8 | Rothamsted | 22.3
2006-08-31 | 2006 | 8 | Rothamsted | 21.2
2006-09-01 | 2006 | 9 | Rothamsted | 20.1
2006-09-02 | 2006 | 9 | Rothamsted | 23.8
2006-09-03 | 2006 | 9 | Rothamsted | 22.8
2006-09-04 | 2006 | 9 | Rothamsted | 24.1
2006-09-05 | 2006 | 9 | Rothamsted | 25.2
2006-09-07 | 2006 | 9 | Rothamsted | 19.7
2006-09-08 | 2006 | 9 | Rothamsted | 20.2
2006-09-09 | 2006 | 9 | Rothamsted | 25.1
2006-09-10 | 2006 | 9 | Rothamsted | 28.4
2006-09-11 | 2006 | 9 | Rothamsted | 20.3
2006-09-12 | 2006 | 9 | Rothamsted | 22.6
2006-09-13 | 2006 | 9 | Rothamsted | 20.4
2006-09-14 | 2006 | 9 | Rothamsted | 20.5
2006-09-15 | 2006 | 9 | Rothamsted | 19.8
2006-09-16 | 2006 | 9 | Rothamsted | 22.8
2006-09-17 | 2006 | 9 | Rothamsted | 19.8
2006-09-19 | 2006 | 9 | Rothamsted | 21.8
2006-09-20 | 2006 | 9 | Rothamsted | 27.1
2006-09-22 | 2006 | 9 | Rothamsted | 21.5
2006-09-23 | 2006 | 9 | Rothamsted | 21.5
2006-09-24 | 2006 | 9 | Rothamsted | 18.7
2006-09-25 | 2006 | 9 | Rothamsted | 19.8
2006-09-26 | 2006 | 9 | Rothamsted | 22.5
2006-09-27 | 2006 | 9 | Rothamsted | 18.7
2006-09-28 | 2006 | 9 | Rothamsted | 19.7
2006-09-29 | 2006 | 9 | Rothamsted | 18.9
2006-09-30 | 2006 | 9 | Rothamsted | 18.1
2007-05-01 | 2007 | 5 | Rothamsted | 20.1
2007-05-03 | 2007 | 5 | Rothamsted | 14.9
2007-05-04 | 2007 | 5 | Rothamsted | 13.5
2007-05-05 | 2007 | 5 | Rothamsted | 18.2
2007-05-06 | 2007 | 5 | Rothamsted | 18.3
2007-05-07 | 2007 | 5 | Rothamsted | 17.1
2007-05-08 | 2007 | 5 | Rothamsted | 14.7
2007-05-09 | 2007 | 5 | Rothamsted | 15.3
2007-05-10 | 2007 | 5 | Rothamsted | 15.7
2007-05-11 | 2007 | 5 | Rothamsted | 15.6
2007-05-12 | 2007 | 5 | Rothamsted | 13.5
2007-05-14 | 2007 | 5 | Rothamsted | 15.3
2007-05-15 | 2007 | 5 | Rothamsted | 14.7
2007-05-16 | 2007 | 5 | Rothamsted | 17
2007-05-17 | 2007 | 5 | Rothamsted | 20
2007-05-18 | 2007 | 5 | Rothamsted | 15.8
2007-05-19 | 2007 | 5 | Rothamsted | 17.4
2007-05-20 | 2007 | 5 | Rothamsted | 15.4
2007-05-21 | 2007 | 5 | Rothamsted | 19.9
2007-05-22 | 2007 | 5 | Rothamsted | 22.4
2007-05-23 | 2007 | 5 | Rothamsted | 23.3
2007-05-24 | 2007 | 5 | Rothamsted | 20.2
2007-05-28 | 2007 | 5 | Rothamsted | 13.3
2007-05-29 | 2007 | 5 | Rothamsted | 15.8
2007-05-30 | 2007 | 5 | Rothamsted | 18.5
2007-05-31 | 2007 | 5 | Rothamsted | 20.6
2007-06-01 | 2007 | 6 | Rothamsted | 23.3
2007-06-02 | 2007 | 6 | Rothamsted | 23
2007-06-03 | 2007 | 6 | Rothamsted | 20.3
2007-06-04 | 2007 | 6 | Rothamsted | 19.5
2007-06-06 | 2007 | 6 | Rothamsted | 16.6
2007-06-07 | 2007 | 6 | Rothamsted | 18.9
2007-06-08 | 2007 | 6 | Rothamsted | 23.7
2007-06-09 | 2007 | 6 | Rothamsted | 21
2007-06-10 | 2007 | 6 | Rothamsted | 19
2007-06-11 | 2007 | 6 | Rothamsted | 20.8
2007-06-12 | 2007 | 6 | Rothamsted | 22
2007-06-13 | 2007 | 6 | Rothamsted | 20.9
2007-06-14 | 2007 | 6 | Rothamsted | 20.2
2007-06-15 | 2007 | 6 | Rothamsted | 17.9
2007-06-16 | 2007 | 6 | Rothamsted | 19.3
2007-06-17 | 2007 | 6 | Rothamsted | 19.3
2007-06-18 | 2007 | 6 | Rothamsted | 22.5
2007-06-19 | 2007 | 6 | Rothamsted | 20.1
2007-06-20 | 2007 | 6 | Rothamsted | 19.4
2007-06-21 | 2007 | 6 | Rothamsted | 18.5
2007-06-22 | 2007 | 6 | Rothamsted | 19.9
2007-06-24 | 2007 | 6 | Rothamsted | 16.4
2007-06-25 | 2007 | 6 | Rothamsted | 14.4
2007-06-26 | 2007 | 6 | Rothamsted | 16.8
2007-06-27 | 2007 | 6 | Rothamsted | 18
2007-06-28 | 2007 | 6 | Rothamsted | 21
2007-06-29 | 2007 | 6 | Rothamsted | 17.8
2007-06-30 | 2007 | 6 | Rothamsted | 19.4
2007-07-01 | 2007 | 7 | Rothamsted | 19.3
2007-07-02 | 2007 | 7 | Rothamsted | 18.3
2007-07-03 | 2007 | 7 | Rothamsted | 18
2007-07-04 | 2007 | 7 | Rothamsted | 18
2007-07-05 | 2007 | 7 | Rothamsted | 17.9
2007-07-06 | 2007 | 7 | Rothamsted | 19.8
2007-07-07 | 2007 | 7 | Rothamsted | 19.9
2007-07-08 | 2007 | 7 | Rothamsted | 20.1
2007-07-09 | 2007 | 7 | Rothamsted | 18.4
2007-07-10 | 2007 | 7 | Rothamsted | 18.7
2007-07-11 | 2007 | 7 | Rothamsted | 22.6
2007-07-12 | 2007 | 7 | Rothamsted | 21.2
2007-07-13 | 2007 | 7 | Rothamsted | 21.5
2007-07-14 | 2007 | 7 | Rothamsted | 21.7
2007-07-15 | 2007 | 7 | Rothamsted | 21.4
2007-07-16 | 2007 | 7 | Rothamsted | 19.5
2007-07-17 | 2007 | 7 | Rothamsted | 22
2007-07-18 | 2007 | 7 | Rothamsted | 23.1
2007-07-19 | 2007 | 7 | Rothamsted | 18.3
2007-07-21 | 2007 | 7 | Rothamsted | 19
2007-07-22 | 2007 | 7 | Rothamsted | 18.4
2007-07-23 | 2007 | 7 | Rothamsted | 20.7
2007-07-24 | 2007 | 7 | Rothamsted | 18.9
2007-07-25 | 2007 | 7 | Rothamsted | 18.1
2007-07-26 | 2007 | 7 | Rothamsted | 20.5
2007-07-27 | 2007 | 7 | Rothamsted | 20.9
2007-07-28 | 2007 | 7 | Rothamsted | 18.9
2007-07-29 | 2007 | 7 | Rothamsted | 18.9
2007-07-30 | 2007 | 7 | Rothamsted | 20.9
2007-07-31 | 2007 | 7 | Rothamsted | 22.4
2007-08-01 | 2007 | 8 | Rothamsted | 18.4
2007-08-02 | 2007 | 8 | Rothamsted | 23.5
2007-08-03 | 2007 | 8 | Rothamsted | 25.3
2007-08-04 | 2007 | 8 | Rothamsted | 27.7
2007-08-05 | 2007 | 8 | Rothamsted | 22.1
2007-08-07 | 2007 | 8 | Rothamsted | 19.5
2007-08-08 | 2007 | 8 | Rothamsted | 19.8
2007-08-09 | 2007 | 8 | Rothamsted | 22.8
2007-08-10 | 2007 | 8 | Rothamsted | 24.3
2007-08-11 | 2007 | 8 | Rothamsted | 20.5
2007-08-12 | 2007 | 8 | Rothamsted | 20.3
2007-08-13 | 2007 | 8 | Rothamsted | 18.7
2007-08-14 | 2007 | 8 | Rothamsted | 21.2
2007-08-15 | 2007 | 8 | Rothamsted | 17.7
2007-08-16 | 2007 | 8 | Rothamsted | 18.4
2007-08-17 | 2007 | 8 | Rothamsted | 18.8
2007-08-18 | 2007 | 8 | Rothamsted | 16.5
2007-08-20 | 2007 | 8 | Rothamsted | 15.7
2007-08-21 | 2007 | 8 | Rothamsted | 15.3
2007-08-22 | 2007 | 8 | Rothamsted | 17.7
2007-08-23 | 2007 | 8 | Rothamsted | 19.5
2007-08-24 | 2007 | 8 | Rothamsted | 24.9
2007-08-25 | 2007 | 8 | Rothamsted | 21.4
2007-08-27 | 2007 | 8 | Rothamsted | 18.4
2007-08-28 | 2007 | 8 | Rothamsted | 19.4
2007-08-29 | 2007 | 8 | Rothamsted | 18.7
2007-08-30 | 2007 | 8 | Rothamsted | 19.2
2007-08-31 | 2007 | 8 | Rothamsted | 19.7
2007-09-01 | 2007 | 9 | Rothamsted | 20.3
2007-09-02 | 2007 | 9 | Rothamsted | 18.1
2007-09-03 | 2007 | 9 | Rothamsted | 17.8
2007-09-04 | 2007 | 9 | Rothamsted | 22.5
2007-09-05 | 2007 | 9 | Rothamsted | 22.1
2007-09-06 | 2007 | 9 | Rothamsted | 22
2007-09-08 | 2007 | 9 | Rothamsted | 19.9
2007-09-09 | 2007 | 9 | Rothamsted | 19
2007-09-10 | 2007 | 9 | Rothamsted | 19.1
2007-09-11 | 2007 | 9 | Rothamsted | 19.9
2007-09-12 | 2007 | 9 | Rothamsted | 21.8
2007-09-13 | 2007 | 9 | Rothamsted | 20.3
2007-09-14 | 2007 | 9 | Rothamsted | 19.5
2007-09-15 | 2007 | 9 | Rothamsted | 19.7
2007-09-16 | 2007 | 9 | Rothamsted | 14.7
2007-09-18 | 2007 | 9 | Rothamsted | 17.6
2007-09-19 | 2007 | 9 | Rothamsted | 19
2007-09-20 | 2007 | 9 | Rothamsted | 18.2
2007-09-21 | 2007 | 9 | Rothamsted | 21
2007-09-22 | 2007 | 9 | Rothamsted | 20.7
2007-09-23 | 2007 | 9 | Rothamsted | 16.4
2007-09-26 | 2007 | 9 | Rothamsted | 12.4
2007-09-27 | 2007 | 9 | Rothamsted | 12.9
2007-09-28 | 2007 | 9 | Rothamsted | 16
2007-09-29 | 2007 | 9 | Rothamsted | 14.2
2007-09-30 | 2007 | 9 | Rothamsted | 13.6
2008-05-01 | 2008 | 5 | Rothamsted | 14.9
2008-05-02 | 2008 | 5 | Rothamsted | 19.4
2008-05-03 | 2008 | 5 | Rothamsted | 19.9
2008-05-04 | 2008 | 5 | Rothamsted | 20.7
2008-05-05 | 2008 | 5 | Rothamsted | 20.9
2008-05-06 | 2008 | 5 | Rothamsted | 23.1
2008-05-07 | 2008 | 5 | Rothamsted | 22.9
2008-05-08 | 2008 | 5 | Rothamsted | 23.9
2008-05-09 | 2008 | 5 | Rothamsted | 24.2
2008-05-10 | 2008 | 5 | Rothamsted | 24.8
2008-05-11 | 2008 | 5 | Rothamsted | 23.2
2008-05-12 | 2008 | 5 | Rothamsted | 19
2008-05-13 | 2008 | 5 | Rothamsted | 17.6
2008-05-16 | 2008 | 5 | Rothamsted | 13.5
2008-05-17 | 2008 | 5 | Rothamsted | 14.1
2008-05-18 | 2008 | 5 | Rothamsted | 12.7
2008-05-19 | 2008 | 5 | Rothamsted | 14.7
2008-05-20 | 2008 | 5 | Rothamsted | 16.9
2008-05-21 | 2008 | 5 | Rothamsted | 19.6
2008-05-22 | 2008 | 5 | Rothamsted | 20.2
2008-05-23 | 2008 | 5 | Rothamsted | 19.6
2008-05-26 | 2008 | 5 | Rothamsted | 16.7
2008-05-27 | 2008 | 5 | Rothamsted | 16.4
2008-05-28 | 2008 | 5 | Rothamsted | 20.1
2008-05-29 | 2008 | 5 | Rothamsted | 18
2008-05-30 | 2008 | 5 | Rothamsted | 19.2
2008-06-01 | 2008 | 6 | Rothamsted | 17.7
2008-06-02 | 2008 | 6 | Rothamsted | 14.4
2008-06-03 | 2008 | 6 | Rothamsted | 19.2
2008-06-04 | 2008 | 6 | Rothamsted | 19.7
2008-06-05 | 2008 | 6 | Rothamsted | 17
2008-06-06 | 2008 | 6 | Rothamsted | 17.8
2008-06-07 | 2008 | 6 | Rothamsted | 22.6
2008-06-08 | 2008 | 6 | Rothamsted | 24.5
2008-06-09 | 2008 | 6 | Rothamsted | 21.3
2008-06-10 | 2008 | 6 | Rothamsted | 19.1
2008-06-12 | 2008 | 6 | Rothamsted | 15.6
2008-06-13 | 2008 | 6 | Rothamsted | 18.1
2008-06-14 | 2008 | 6 | Rothamsted | 16.9
2008-06-15 | 2008 | 6 | Rothamsted | 18
2008-06-16 | 2008 | 6 | Rothamsted | 19.3
2008-06-17 | 2008 | 6 | Rothamsted | 17.7
2008-06-18 | 2008 | 6 | Rothamsted | 18.8
2008-06-19 | 2008 | 6 | Rothamsted | 19
2008-06-20 | 2008 | 6 | Rothamsted | 17.6
2008-06-21 | 2008 | 6 | Rothamsted | 19.5
2008-06-22 | 2008 | 6 | Rothamsted | 19.6
2008-06-23 | 2008 | 6 | Rothamsted | 20.6
2008-06-24 | 2008 | 6 | Rothamsted | 20.4
2008-06-25 | 2008 | 6 | Rothamsted | 20.5
2008-06-26 | 2008 | 6 | Rothamsted | 20.3
2008-06-27 | 2008 | 6 | Rothamsted | 20.7
2008-06-28 | 2008 | 6 | Rothamsted | 20
2008-06-29 | 2008 | 6 | Rothamsted | 21
2008-06-30 | 2008 | 6 | Rothamsted | 25.8
2008-07-01 | 2008 | 7 | Rothamsted | 18.1
2008-07-02 | 2008 | 7 | Rothamsted | 20.2
2008-07-03 | 2008 | 7 | Rothamsted | 20.8
2008-07-04 | 2008 | 7 | Rothamsted | 20.3
2008-07-06 | 2008 | 7 | Rothamsted | 17.5
2008-07-07 | 2008 | 7 | Rothamsted | 17.9
2008-07-08 | 2008 | 7 | Rothamsted | 16.6
2008-07-09 | 2008 | 7 | Rothamsted | 19.4
2008-07-10 | 2008 | 7 | Rothamsted | 19.7
2008-07-11 | 2008 | 7 | Rothamsted | 16.9
2008-07-12 | 2008 | 7 | Rothamsted | 19.9
2008-07-13 | 2008 | 7 | Rothamsted | 20.4
2008-07-14 | 2008 | 7 | Rothamsted | 24
2008-07-16 | 2008 | 7 | Rothamsted | 17.6
2008-07-17 | 2008 | 7 | Rothamsted | 17.9
2008-07-18 | 2008 | 7 | Rothamsted | 19.3
2008-07-19 | 2008 | 7 | Rothamsted | 17.3
2008-07-20 | 2008 | 7 | Rothamsted | 19.6
2008-07-21 | 2008 | 7 | Rothamsted | 21.4
2008-07-22 | 2008 | 7 | Rothamsted | 24.3
2008-07-23 | 2008 | 7 | Rothamsted | 24.9
2008-07-24 | 2008 | 7 | Rothamsted | 25.3
2008-07-25 | 2008 | 7 | Rothamsted | 25.5
2008-07-26 | 2008 | 7 | Rothamsted | 27
2008-07-27 | 2008 | 7 | Rothamsted | 27.2
2008-07-28 | 2008 | 7 | Rothamsted | 22.1
2008-07-29 | 2008 | 7 | Rothamsted | 25
2008-07-30 | 2008 | 7 | Rothamsted | 24.6
2008-07-31 | 2008 | 7 | Rothamsted | 21.8
2008-08-01 | 2008 | 8 | Rothamsted | 22.2
2008-08-02 | 2008 | 8 | Rothamsted | 19.9
2008-08-03 | 2008 | 8 | Rothamsted | 20.6
2008-08-04 | 2008 | 8 | Rothamsted | 19.8
2008-08-05 | 2008 | 8 | Rothamsted | 23.6
2008-08-06 | 2008 | 8 | Rothamsted | 23.4
2008-08-08 | 2008 | 8 | Rothamsted | 17.3
2008-08-09 | 2008 | 8 | Rothamsted | 21.3
2008-08-10 | 2008 | 8 | Rothamsted | 18.9
2008-08-11 | 2008 | 8 | Rothamsted | 19.5
2008-08-12 | 2008 | 8 | Rothamsted | 17.3
2008-08-13 | 2008 | 8 | Rothamsted | 19.6
2008-08-14 | 2008 | 8 | Rothamsted | 19.8
2008-08-15 | 2008 | 8 | Rothamsted | 20.4
2008-08-16 | 2008 | 8 | Rothamsted | 19.8
2008-08-17 | 2008 | 8 | Rothamsted | 19.1
2008-08-18 | 2008 | 8 | Rothamsted | 18.1
2008-08-19 | 2008 | 8 | Rothamsted | 20.1
2008-08-20 | 2008 | 8 | Rothamsted | 20.5
2008-08-21 | 2008 | 8 | Rothamsted | 18.8
2008-08-22 | 2008 | 8 | Rothamsted | 19.7
2008-08-23 | 2008 | 8 | Rothamsted | 20.5
2008-08-24 | 2008 | 8 | Rothamsted | 20.2
2008-08-25 | 2008 | 8 | Rothamsted | 18.6
2008-08-26 | 2008 | 8 | Rothamsted | 18.8
2008-08-27 | 2008 | 8 | Rothamsted | 21
2008-08-28 | 2008 | 8 | Rothamsted | 21.8
2008-08-29 | 2008 | 8 | Rothamsted | 24.5
2008-08-30 | 2008 | 8 | Rothamsted | 20.7
2008-08-31 | 2008 | 8 | Rothamsted | 19.4
2008-09-01 | 2008 | 9 | Rothamsted | 17.3
2008-09-02 | 2008 | 9 | Rothamsted | 17.9
2008-09-03 | 2008 | 9 | Rothamsted | 16.7
2008-09-04 | 2008 | 9 | Rothamsted | 16.1
2008-09-05 | 2008 | 9 | Rothamsted | 16.7
2008-09-06 | 2008 | 9 | Rothamsted | 16.7
2008-09-07 | 2008 | 9 | Rothamsted | 16.3
2008-09-08 | 2008 | 9 | Rothamsted | 18.6
2008-09-09 | 2008 | 9 | Rothamsted | 19.1
2008-09-10 | 2008 | 9 | Rothamsted | 18.3
2008-09-11 | 2008 | 9 | Rothamsted | 17
2008-09-12 | 2008 | 9 | Rothamsted | 18.1
2008-09-13 | 2008 | 9 | Rothamsted | 17.2
2008-09-14 | 2008 | 9 | Rothamsted | 16.8
2008-09-15 | 2008 | 9 | Rothamsted | 14.9
2008-09-16 | 2008 | 9 | Rothamsted | 16.1
2008-09-17 | 2008 | 9 | Rothamsted | 17.6
2008-09-18 | 2008 | 9 | Rothamsted | 19.6
2008-09-19 | 2008 | 9 | Rothamsted | 19.2
2008-09-20 | 2008 | 9 | Rothamsted | 18.1
2008-09-21 | 2008 | 9 | Rothamsted | 17.8
2008-09-22 | 2008 | 9 | Rothamsted | 15
2008-09-23 | 2008 | 9 | Rothamsted | 15.4
2008-09-24 | 2008 | 9 | Rothamsted | 17.7
2008-09-25 | 2008 | 9 | Rothamsted | 17.9
2008-09-26 | 2008 | 9 | Rothamsted | 19.1
2008-09-27 | 2008 | 9 | Rothamsted | 17.2
2008-09-28 | 2008 | 9 | Rothamsted | 15.5
2008-09-29 | 2008 | 9 | Rothamsted | 13.7
2008-09-30 | 2008 | 9 | Rothamsted | 14.3
2009-05-01 | 2009 | 5 | Rothamsted | 16.9
2009-05-02 | 2009 | 5 | Rothamsted | 13.2
2009-05-03 | 2009 | 5 | Rothamsted | 12.9
2009-05-04 | 2009 | 5 | Rothamsted | 18.2
2009-05-05 | 2009 | 5 | Rothamsted | 18
2009-05-06 | 2009 | 5 | Rothamsted | 15.3
2009-05-07 | 2009 | 5 | Rothamsted | 14.3
2009-05-08 | 2009 | 5 | Rothamsted | 15.1
2009-05-09 | 2009 | 5 | Rothamsted | 17.7
2009-05-10 | 2009 | 5 | Rothamsted | 14.8
2009-05-11 | 2009 | 5 | Rothamsted | 15.2
2009-05-12 | 2009 | 5 | Rothamsted | 13.4
2009-05-13 | 2009 | 5 | Rothamsted | 15.9
2009-05-14 | 2009 | 5 | Rothamsted | 14.7
2009-05-15 | 2009 | 5 | Rothamsted | 15.1
2009-05-16 | 2009 | 5 | Rothamsted | 13.4
2009-05-17 | 2009 | 5 | Rothamsted | 15.4
2009-05-18 | 2009 | 5 | Rothamsted | 16.1
2009-05-19 | 2009 | 5 | Rothamsted | 17.7
2009-05-20 | 2009 | 5 | Rothamsted | 17.5
2009-05-21 | 2009 | 5 | Rothamsted | 17.1
2009-05-22 | 2009 | 5 | Rothamsted | 19.9
2009-05-23 | 2009 | 5 | Rothamsted | 22.8
2009-05-24 | 2009 | 5 | Rothamsted | 21.6
2009-05-26 | 2009 | 5 | Rothamsted | 17.3
2009-05-27 | 2009 | 5 | Rothamsted | 21.3
2009-05-28 | 2009 | 5 | Rothamsted | 22.3
2009-05-29 | 2009 | 5 | Rothamsted | 21.1
2009-05-30 | 2009 | 5 | Rothamsted | 23.7
2009-05-31 | 2009 | 5 | Rothamsted | 23.7
2009-06-01 | 2009 | 6 | Rothamsted | 23.1
2009-06-04 | 2009 | 6 | Rothamsted | 11
2009-06-05 | 2009 | 6 | Rothamsted | 14.3
2009-06-06 | 2009 | 6 | Rothamsted | 15.5
2009-06-07 | 2009 | 6 | Rothamsted | 15.9
2009-06-08 | 2009 | 6 | Rothamsted | 14.9
2009-06-09 | 2009 | 6 | Rothamsted | 15.9
2009-06-10 | 2009 | 6 | Rothamsted | 17.5
2009-06-11 | 2009 | 6 | Rothamsted | 19
2009-06-12 | 2009 | 6 | Rothamsted | 22.5
2009-06-13 | 2009 | 6 | Rothamsted | 21.5
2009-06-14 | 2009 | 6 | Rothamsted | 21.4
2009-06-15 | 2009 | 6 | Rothamsted | 21.3
2009-06-16 | 2009 | 6 | Rothamsted | 20.9
2009-06-17 | 2009 | 6 | Rothamsted | 17.1
2009-06-18 | 2009 | 6 | Rothamsted | 18.2
2009-06-19 | 2009 | 6 | Rothamsted | 17.7
2009-06-20 | 2009 | 6 | Rothamsted | 19.1
2009-06-21 | 2009 | 6 | Rothamsted | 20.8
2009-06-22 | 2009 | 6 | Rothamsted | 22.7
2009-06-23 | 2009 | 6 | Rothamsted | 22.8
2009-06-24 | 2009 | 6 | Rothamsted | 25.4
2009-06-25 | 2009 | 6 | Rothamsted | 22.9
2009-06-26 | 2009 | 6 | Rothamsted | 24.3
2009-06-27 | 2009 | 6 | Rothamsted | 24.4
2009-06-28 | 2009 | 6 | Rothamsted | 27.8
2009-06-29 | 2009 | 6 | Rothamsted | 27.9
2009-06-30 | 2009 | 6 | Rothamsted | 27.6
2009-07-01 | 2009 | 7 | Rothamsted | 27.5
2009-07-02 | 2009 | 7 | Rothamsted | 23.8
2009-07-03 | 2009 | 7 | Rothamsted | 23.9
2009-07-04 | 2009 | 7 | Rothamsted | 22.8
2009-07-05 | 2009 | 7 | Rothamsted | 20.2
2009-07-06 | 2009 | 7 | Rothamsted | 18.7
2009-07-07 | 2009 | 7 | Rothamsted | 19.1
2009-07-08 | 2009 | 7 | Rothamsted | 17.1
2009-07-09 | 2009 | 7 | Rothamsted | 19.4
2009-07-10 | 2009 | 7 | Rothamsted | 20.2
2009-07-11 | 2009 | 7 | Rothamsted | 22.2
2009-07-12 | 2009 | 7 | Rothamsted | 20.6
2009-07-13 | 2009 | 7 | Rothamsted | 22.1
2009-07-14 | 2009 | 7 | Rothamsted | 21.9
2009-07-15 | 2009 | 7 | Rothamsted | 22.2
2009-07-16 | 2009 | 7 | Rothamsted | 17.9
2009-07-17 | 2009 | 7 | Rothamsted | 19.5
2009-07-18 | 2009 | 7 | Rothamsted | 18.8
2009-07-19 | 2009 | 7 | Rothamsted | 19.5
2009-07-20 | 2009 | 7 | Rothamsted | 19.9
2009-07-21 | 2009 | 7 | Rothamsted | 20.9
2009-07-22 | 2009 | 7 | Rothamsted | 21.3
2009-07-23 | 2009 | 7 | Rothamsted | 19
2009-07-24 | 2009 | 7 | Rothamsted | 22.8
2009-07-25 | 2009 | 7 | Rothamsted | 19.5
2009-07-26 | 2009 | 7 | Rothamsted | 21
2009-07-27 | 2009 | 7 | Rothamsted | 20.1
2009-07-28 | 2009 | 7 | Rothamsted | 18.7
2009-07-29 | 2009 | 7 | Rothamsted | 19.2
2009-07-30 | 2009 | 7 | Rothamsted | 20.8
2009-07-31 | 2009 | 7 | Rothamsted | 19.7
2009-08-01 | 2009 | 8 | Rothamsted | 19.8
2009-08-02 | 2009 | 8 | Rothamsted | 20.6
2009-08-03 | 2009 | 8 | Rothamsted | 23
2009-08-04 | 2009 | 8 | Rothamsted | 25.8
2009-08-05 | 2009 | 8 | Rothamsted | 22.6
2009-08-06 | 2009 | 8 | Rothamsted | 21
2009-08-07 | 2009 | 8 | Rothamsted | 23.3
2009-08-08 | 2009 | 8 | Rothamsted | 24.2
2009-08-09 | 2009 | 8 | Rothamsted | 19.9
2009-08-10 | 2009 | 8 | Rothamsted | 23.3
2009-08-11 | 2009 | 8 | Rothamsted | 21.7
2009-08-12 | 2009 | 8 | Rothamsted | 21.5
2009-08-13 | 2009 | 8 | Rothamsted | 22.3
2009-08-14 | 2009 | 8 | Rothamsted | 22.7
2009-08-15 | 2009 | 8 | Rothamsted | 23.1
2009-08-16 | 2009 | 8 | Rothamsted | 22.1
2009-08-17 | 2009 | 8 | Rothamsted | 22.9
2009-08-18 | 2009 | 8 | Rothamsted | 27.5
2009-08-19 | 2009 | 8 | Rothamsted | 22
2009-08-21 | 2009 | 8 | Rothamsted | 21.1
2009-08-22 | 2009 | 8 | Rothamsted | 26.2
2009-08-23 | 2009 | 8 | Rothamsted | 23.7
2009-08-24 | 2009 | 8 | Rothamsted | 20.1
2009-08-25 | 2009 | 8 | Rothamsted | 21.6
2009-08-26 | 2009 | 8 | Rothamsted | 22.4
2009-08-27 | 2009 | 8 | Rothamsted | 19.1
2009-08-28 | 2009 | 8 | Rothamsted | 19.1
2009-08-29 | 2009 | 8 | Rothamsted | 18.6
2009-08-30 | 2009 | 8 | Rothamsted | 24
2009-08-31 | 2009 | 8 | Rothamsted | 20.6
2009-09-01 | 2009 | 9 | Rothamsted | 18.1
2009-09-02 | 2009 | 9 | Rothamsted | 17.5
2009-09-03 | 2009 | 9 | Rothamsted | 17.5
2009-09-04 | 2009 | 9 | Rothamsted | 18.6
2009-09-05 | 2009 | 9 | Rothamsted | 18.7
2009-09-06 | 2009 | 9 | Rothamsted | 19.1
2009-09-07 | 2009 | 9 | Rothamsted | 26.3
2009-09-08 | 2009 | 9 | Rothamsted | 18.9
2009-09-10 | 2009 | 9 | Rothamsted | 19.3
2009-09-11 | 2009 | 9 | Rothamsted | 20.4
2009-09-12 | 2009 | 9 | Rothamsted | 16.2
2009-09-13 | 2009 | 9 | Rothamsted | 18.3
2009-09-14 | 2009 | 9 | Rothamsted | 16.7
2009-09-15 | 2009 | 9 | Rothamsted | 18.4
2009-09-16 | 2009 | 9 | Rothamsted | 15.7
2009-09-17 | 2009 | 9 | Rothamsted | 19.2
2009-09-18 | 2009 | 9 | Rothamsted | 21.9
2009-09-19 | 2009 | 9 | Rothamsted | 19
2009-09-20 | 2009 | 9 | Rothamsted | 19.6
2009-09-21 | 2009 | 9 | Rothamsted | 20.4
2009-09-22 | 2009 | 9 | Rothamsted | 17.7
2009-09-23 | 2009 | 9 | Rothamsted | 18.1
2009-09-24 | 2009 | 9 | Rothamsted | 18.5
2009-09-25 | 2009 | 9 | Rothamsted | 18.7
2009-09-26 | 2009 | 9 | Rothamsted | 20.1
2009-09-27 | 2009 | 9 | Rothamsted | 17.4
2009-09-28 | 2009 | 9 | Rothamsted | 20.8
2009-09-29 | 2009 | 9 | Rothamsted | 17.3
2010-05-03 | 2010 | 5 | Rothamsted | 10.9
2010-05-04 | 2010 | 5 | Rothamsted | 13.5
2010-05-05 | 2010 | 5 | Rothamsted | 13.2
2010-05-06 | 2010 | 5 | Rothamsted | 12.3
2010-05-08 | 2010 | 5 | Rothamsted | 10.6
2010-05-09 | 2010 | 5 | Rothamsted | 10.9
2010-05-10 | 2010 | 5 | Rothamsted | 9.3
2010-05-11 | 2010 | 5 | Rothamsted | 10.5
2010-05-12 | 2010 | 5 | Rothamsted | 12.2
2010-05-13 | 2010 | 5 | Rothamsted | 13.3
2010-05-14 | 2010 | 5 | Rothamsted | 15.9
2010-05-15 | 2010 | 5 | Rothamsted | 14.8
2010-05-16 | 2010 | 5 | Rothamsted | 15.9
2010-05-17 | 2010 | 5 | Rothamsted | 17.1
2010-05-18 | 2010 | 5 | Rothamsted | 19.2
2010-05-19 | 2010 | 5 | Rothamsted | 21.6
2010-05-20 | 2010 | 5 | Rothamsted | 23
2010-05-21 | 2010 | 5 | Rothamsted | 22.7
2010-05-22 | 2010 | 5 | Rothamsted | 26.4
2010-05-23 | 2010 | 5 | Rothamsted | 25.3
2010-05-26 | 2010 | 5 | Rothamsted | 15.6
2010-05-27 | 2010 | 5 | Rothamsted | 17.4
2010-05-28 | 2010 | 5 | Rothamsted | 14.5
2010-05-29 | 2010 | 5 | Rothamsted | 17.1
2010-05-30 | 2010 | 5 | Rothamsted | 15
2010-05-31 | 2010 | 5 | Rothamsted | 13.5
2010-06-01 | 2010 | 6 | Rothamsted | 19.9
2010-06-02 | 2010 | 6 | Rothamsted | 21.1
2010-06-03 | 2010 | 6 | Rothamsted | 24.6
2010-06-04 | 2010 | 6 | Rothamsted | 25.2
2010-06-05 | 2010 | 6 | Rothamsted | 21.5
2010-06-07 | 2010 | 6 | Rothamsted | 18
2010-06-08 | 2010 | 6 | Rothamsted | 18.6
2010-06-09 | 2010 | 6 | Rothamsted | 17.7
2010-06-10 | 2010 | 6 | Rothamsted | 18.9
2010-06-11 | 2010 | 6 | Rothamsted | 17.4
2010-06-12 | 2010 | 6 | Rothamsted | 20.2
2010-06-13 | 2010 | 6 | Rothamsted | 18
2010-06-14 | 2010 | 6 | Rothamsted | 16.1
2010-06-15 | 2010 | 6 | Rothamsted | 17.8
2010-06-16 | 2010 | 6 | Rothamsted | 20.7
2010-06-17 | 2010 | 6 | Rothamsted | 16.7
2010-06-19 | 2010 | 6 | Rothamsted | 18.8
2010-06-20 | 2010 | 6 | Rothamsted | 22.5
2010-06-21 | 2010 | 6 | Rothamsted | 24.8
2010-06-22 | 2010 | 6 | Rothamsted | 25
2010-06-23 | 2010 | 6 | Rothamsted | 23.1
2010-06-24 | 2010 | 6 | Rothamsted | 24.5
2010-06-25 | 2010 | 6 | Rothamsted | 25.5
2010-06-26 | 2010 | 6 | Rothamsted | 27.6
2010-06-27 | 2010 | 6 | Rothamsted | 25.9
2010-06-28 | 2010 | 6 | Rothamsted | 25.9
2010-06-29 | 2010 | 6 | Rothamsted | 23.6
2010-06-30 | 2010 | 6 | Rothamsted | 24.9
2010-07-01 | 2010 | 7 | Rothamsted | 23.7
2010-07-02 | 2010 | 7 | Rothamsted | 23.8
2010-07-03 | 2010 | 7 | Rothamsted | 22.9
2010-07-04 | 2010 | 7 | Rothamsted | 22.1
2010-07-05 | 2010 | 7 | Rothamsted | 22.1
2010-07-06 | 2010 | 7 | Rothamsted | 21.6
2010-07-07 | 2010 | 7 | Rothamsted | 24.9
2010-07-08 | 2010 | 7 | Rothamsted | 29.1
2010-07-09 | 2010 | 7 | Rothamsted | 27.4
2010-07-10 | 2010 | 7 | Rothamsted | 25.1
2010-07-11 | 2010 | 7 | Rothamsted | 22
2010-07-13 | 2010 | 7 | Rothamsted | 20.5
2010-07-14 | 2010 | 7 | Rothamsted | 19.6
2010-07-15 | 2010 | 7 | Rothamsted | 20.9
2010-07-16 | 2010 | 7 | Rothamsted | 20.2
2010-07-17 | 2010 | 7 | Rothamsted | 22.8
2010-07-18 | 2010 | 7 | Rothamsted | 27.4
2010-07-19 | 2010 | 7 | Rothamsted | 27.7
2010-07-20 | 2010 | 7 | Rothamsted | 23.5
2010-07-22 | 2010 | 7 | Rothamsted | 18.9
2010-07-23 | 2010 | 7 | Rothamsted | 22.8
2010-07-24 | 2010 | 7 | Rothamsted | 25.5
2010-07-25 | 2010 | 7 | Rothamsted | 21.3
2010-07-26 | 2010 | 7 | Rothamsted | 23.3
2010-07-27 | 2010 | 7 | Rothamsted | 22.4
2010-07-28 | 2010 | 7 | Rothamsted | 19.7
2010-07-29 | 2010 | 7 | Rothamsted | 21.3
2010-07-30 | 2010 | 7 | Rothamsted | 23.1
2010-07-31 | 2010 | 7 | Rothamsted | 21
2010-08-01 | 2010 | 8 | Rothamsted | 20.7
2010-08-02 | 2010 | 8 | Rothamsted | 21.9
2010-08-03 | 2010 | 8 | Rothamsted | 17.3
2010-08-04 | 2010 | 8 | Rothamsted | 20.5
2010-08-05 | 2010 | 8 | Rothamsted | 20
2010-08-06 | 2010 | 8 | Rothamsted | 20.6
2010-08-07 | 2010 | 8 | Rothamsted | 22.2
2010-08-08 | 2010 | 8 | Rothamsted | 23.7
2010-08-09 | 2010 | 8 | Rothamsted | 16.8
2010-08-10 | 2010 | 8 | Rothamsted | 21.5
2010-08-11 | 2010 | 8 | Rothamsted | 18.5
2010-08-12 | 2010 | 8 | Rothamsted | 17.4
2010-08-13 | 2010 | 8 | Rothamsted | 17.6
2010-08-14 | 2010 | 8 | Rothamsted | 20.8
2010-08-15 | 2010 | 8 | Rothamsted | 22.9
2010-08-16 | 2010 | 8 | Rothamsted | 20.9
2010-08-17 | 2010 | 8 | Rothamsted | 20.6
2010-08-18 | 2010 | 8 | Rothamsted | 19.9
2010-08-19 | 2010 | 8 | Rothamsted | 22
2010-08-20 | 2010 | 8 | Rothamsted | 22.7
2010-08-21 | 2010 | 8 | Rothamsted | 22.9
2010-08-23 | 2010 | 8 | Rothamsted | 20.2
2010-08-24 | 2010 | 8 | Rothamsted | 17.6
2010-08-25 | 2010 | 8 | Rothamsted | 18.5
2010-08-26 | 2010 | 8 | Rothamsted | 17.1
2010-08-27 | 2010 | 8 | Rothamsted | 19.5
2010-08-28 | 2010 | 8 | Rothamsted | 17.3
2010-08-29 | 2010 | 8 | Rothamsted | 18
2010-08-30 | 2010 | 8 | Rothamsted | 19.5
2010-08-31 | 2010 | 8 | Rothamsted | 19.9
2010-09-01 | 2010 | 9 | Rothamsted | 19.6
2010-09-02 | 2010 | 9 | Rothamsted | 20.4
2010-09-03 | 2010 | 9 | Rothamsted | 19.3
2010-09-04 | 2010 | 9 | Rothamsted | 19.6
2010-09-05 | 2010 | 9 | Rothamsted | 19.6
2010-09-06 | 2010 | 9 | Rothamsted | 18.3
2010-09-07 | 2010 | 9 | Rothamsted | 18.7
2010-09-08 | 2010 | 9 | Rothamsted | 19.7
2010-09-09 | 2010 | 9 | Rothamsted | 20.4
2010-09-10 | 2010 | 9 | Rothamsted | 21.3
2010-09-11 | 2010 | 9 | Rothamsted | 19.3
2010-09-12 | 2010 | 9 | Rothamsted | 16.9
2010-09-13 | 2010 | 9 | Rothamsted | 18.4
2010-09-14 | 2010 | 9 | Rothamsted | 15.8
2010-09-15 | 2010 | 9 | Rothamsted | 16.6
2010-09-16 | 2010 | 9 | Rothamsted | 15.1
2010-09-17 | 2010 | 9 | Rothamsted | 16.1
2010-09-18 | 2010 | 9 | Rothamsted | 16.4
2010-09-19 | 2010 | 9 | Rothamsted | 19.7
2010-09-20 | 2010 | 9 | Rothamsted | 20.5
2010-09-21 | 2010 | 9 | Rothamsted | 22.2
2010-09-22 | 2010 | 9 | Rothamsted | 17.9
2010-09-25 | 2010 | 9 | Rothamsted | 12.3
2010-09-26 | 2010 | 9 | Rothamsted | 14
2010-09-27 | 2010 | 9 | Rothamsted | 16.2
2010-09-28 | 2010 | 9 | Rothamsted | 16.7
2010-09-29 | 2010 | 9 | Rothamsted | 15.4
2010-09-30 | 2010 | 9 | Rothamsted | 14.7
2011-05-01 | 2011 | 5 | Rothamsted | 15.1
2011-05-02 | 2011 | 5 | Rothamsted | 13.6
2011-05-03 | 2011 | 5 | Rothamsted | 15.9
2011-05-04 | 2011 | 5 | Rothamsted | 19.1
2011-05-05 | 2011 | 5 | Rothamsted | 23.3
2011-05-06 | 2011 | 5 | Rothamsted | 22.1
2011-05-07 | 2011 | 5 | Rothamsted | 18.4
2011-05-08 | 2011 | 5 | Rothamsted | 19
2011-05-09 | 2011 | 5 | Rothamsted | 19.6
2011-05-10 | 2011 | 5 | Rothamsted | 16.3
2011-05-11 | 2011 | 5 | Rothamsted | 16.4
2011-05-12 | 2011 | 5 | Rothamsted | 16.1
2011-05-13 | 2011 | 5 | Rothamsted | 15.4
2011-05-14 | 2011 | 5 | Rothamsted | 14.1
2011-05-15 | 2011 | 5 | Rothamsted | 17.9
2011-05-16 | 2011 | 5 | Rothamsted | 16.9
2011-05-17 | 2011 | 5 | Rothamsted | 17
2011-05-18 | 2011 | 5 | Rothamsted | 17.6
2011-05-19 | 2011 | 5 | Rothamsted | 17.2
2011-05-20 | 2011 | 5 | Rothamsted | 20
2011-05-21 | 2011 | 5 | Rothamsted | 17
2011-05-22 | 2011 | 5 | Rothamsted | 17.4
2011-05-23 | 2011 | 5 | Rothamsted | 17.6
2011-05-24 | 2011 | 5 | Rothamsted | 19.6
2011-05-25 | 2011 | 5 | Rothamsted | 15
2011-05-26 | 2011 | 5 | Rothamsted | 15
2011-05-27 | 2011 | 5 | Rothamsted | 15.7
2011-05-28 | 2011 | 5 | Rothamsted | 18.9
2011-05-29 | 2011 | 5 | Rothamsted | 18.7
2011-05-30 | 2011 | 5 | Rothamsted | 16.8
2011-05-31 | 2011 | 5 | Rothamsted | 18.7
2011-06-01 | 2011 | 6 | Rothamsted | 22
2011-06-02 | 2011 | 6 | Rothamsted | 23.4
2011-06-03 | 2011 | 6 | Rothamsted | 23.7
2011-06-06 | 2011 | 6 | Rothamsted | 17.3
2011-06-07 | 2011 | 6 | Rothamsted | 16.4
2011-06-08 | 2011 | 6 | Rothamsted | 16.9
2011-06-09 | 2011 | 6 | Rothamsted | 14.7
2011-06-10 | 2011 | 6 | Rothamsted | 17.1
2011-06-11 | 2011 | 6 | Rothamsted | 15.2
2011-06-12 | 2011 | 6 | Rothamsted | 19
2011-06-13 | 2011 | 6 | Rothamsted | 21.4
2011-06-14 | 2011 | 6 | Rothamsted | 19.2
2011-06-15 | 2011 | 6 | Rothamsted | 17.8
2011-06-17 | 2011 | 6 | Rothamsted | 16.7
2011-06-18 | 2011 | 6 | Rothamsted | 17.1
2011-06-19 | 2011 | 6 | Rothamsted | 20
2011-06-20 | 2011 | 6 | Rothamsted | 20.3
2011-06-21 | 2011 | 6 | Rothamsted | 18.4
2011-06-22 | 2011 | 6 | Rothamsted | 18.1
2011-06-23 | 2011 | 6 | Rothamsted | 17.7
2011-06-24 | 2011 | 6 | Rothamsted | 21.3
2011-06-25 | 2011 | 6 | Rothamsted | 27.3
2011-06-26 | 2011 | 6 | Rothamsted | 29.3
2011-06-29 | 2011 | 6 | Rothamsted | 18
2011-06-30 | 2011 | 6 | Rothamsted | 18.6
2011-07-01 | 2011 | 7 | Rothamsted | 20.9
2011-07-02 | 2011 | 7 | Rothamsted | 21.8
2011-07-03 | 2011 | 7 | Rothamsted | 23.5
2011-07-04 | 2011 | 7 | Rothamsted | 24.3
2011-07-05 | 2011 | 7 | Rothamsted | 19.3
2011-07-07 | 2011 | 7 | Rothamsted | 18.7
2011-07-08 | 2011 | 7 | Rothamsted | 19.9
2011-07-09 | 2011 | 7 | Rothamsted | 21.5
2011-07-10 | 2011 | 7 | Rothamsted | 21.6
2011-07-11 | 2011 | 7 | Rothamsted | 17.9
2011-07-13 | 2011 | 7 | Rothamsted | 22.2
2011-07-14 | 2011 | 7 | Rothamsted | 23.1
2011-07-15 | 2011 | 7 | Rothamsted | 19.1
2011-07-16 | 2011 | 7 | Rothamsted | 19.4
2011-07-17 | 2011 | 7 | Rothamsted | 17.6
2011-07-18 | 2011 | 7 | Rothamsted | 19.3
2011-07-19 | 2011 | 7 | Rothamsted | 17.4
2011-07-20 | 2011 | 7 | Rothamsted | 18.2
2011-07-21 | 2011 | 7 | Rothamsted | 18.9
2011-07-22 | 2011 | 7 | Rothamsted | 17.3
2011-07-23 | 2011 | 7 | Rothamsted | 21.8
2011-07-24 | 2011 | 7 | Rothamsted | 21.1
2011-07-25 | 2011 | 7 | Rothamsted | 18.7
2011-07-26 | 2011 | 7 | Rothamsted | 19.7
2011-07-27 | 2011 | 7 | Rothamsted | 22.6
2011-07-28 | 2011 | 7 | Rothamsted | 17.6
2011-07-29 | 2011 | 7 | Rothamsted | 20.4
2011-07-30 | 2011 | 7 | Rothamsted | 23.6
2011-07-31 | 2011 | 7 | Rothamsted | 27.3
2011-08-01 | 2011 | 8 | Rothamsted | 26.8
2011-08-02 | 2011 | 8 | Rothamsted | 27.9
2011-08-04 | 2011 | 8 | Rothamsted | 23
2011-08-05 | 2011 | 8 | Rothamsted | 18.4
2011-08-07 | 2011 | 8 | Rothamsted | 19.9
2011-08-08 | 2011 | 8 | Rothamsted | 20.1
2011-08-09 | 2011 | 8 | Rothamsted | 23.1
2011-08-10 | 2011 | 8 | Rothamsted | 22.7
2011-08-11 | 2011 | 8 | Rothamsted | 20.7
2011-08-12 | 2011 | 8 | Rothamsted | 19.1
2011-08-13 | 2011 | 8 | Rothamsted | 21.2
2011-08-14 | 2011 | 8 | Rothamsted | 20.7
2011-08-15 | 2011 | 8 | Rothamsted | 21.9
2011-08-16 | 2011 | 8 | Rothamsted | 18.4
2011-08-18 | 2011 | 8 | Rothamsted | 20.3
2011-08-19 | 2011 | 8 | Rothamsted | 20
2011-08-20 | 2011 | 8 | Rothamsted | 22.5
2011-08-21 | 2011 | 8 | Rothamsted | 21.6
2011-08-23 | 2011 | 8 | Rothamsted | 20.6
2011-08-24 | 2011 | 8 | Rothamsted | 18.9
2011-08-26 | 2011 | 8 | Rothamsted | 17.3
2011-08-27 | 2011 | 8 | Rothamsted | 18.5
2011-08-28 | 2011 | 8 | Rothamsted | 15.4
2011-08-29 | 2011 | 8 | Rothamsted | 15.3
2011-08-30 | 2011 | 8 | Rothamsted | 16.3
2011-08-31 | 2011 | 8 | Rothamsted | 19.3
2011-09-01 | 2011 | 9 | Rothamsted | 25.3
2011-09-02 | 2011 | 9 | Rothamsted | 21.5
2011-09-04 | 2011 | 9 | Rothamsted | 18.2
2011-09-05 | 2011 | 9 | Rothamsted | 17.6
2011-09-06 | 2011 | 9 | Rothamsted | 16.2
2011-09-07 | 2011 | 9 | Rothamsted | 18.7
2011-09-08 | 2011 | 9 | Rothamsted | 20.8
2011-09-09 | 2011 | 9 | Rothamsted | 21.6
2011-09-10 | 2011 | 9 | Rothamsted | 19.9
2011-09-11 | 2011 | 9 | Rothamsted | 20.7
2011-09-12 | 2011 | 9 | Rothamsted | 17.1
2011-09-13 | 2011 | 9 | Rothamsted | 18.1
2011-09-14 | 2011 | 9 | Rothamsted | 18.6
2011-09-15 | 2011 | 9 | Rothamsted | 20.9
2011-09-16 | 2011 | 9 | Rothamsted | 16.9
2011-09-18 | 2011 | 9 | Rothamsted | 18.1
2011-09-19 | 2011 | 9 | Rothamsted | 18.2
2011-09-20 | 2011 | 9 | Rothamsted | 16.1
2011-09-21 | 2011 | 9 | Rothamsted | 16.9
2011-09-22 | 2011 | 9 | Rothamsted | 17.7
2011-09-23 | 2011 | 9 | Rothamsted | 18.9
2011-09-24 | 2011 | 9 | Rothamsted | 20.2
2011-09-25 | 2011 | 9 | Rothamsted | 19.9
2011-09-26 | 2011 | 9 | Rothamsted | 19.8
2011-09-27 | 2011 | 9 | Rothamsted | 24.7
2011-09-28 | 2011 | 9 | Rothamsted | 26.7
2011-09-29 | 2011 | 9 | Rothamsted | 27.4
2011-09-30 | 2011 | 9 | Rothamsted | 26.9
2012-05-01 | 2012 | 5 | Rothamsted | 13.5
2012-05-04 | 2012 | 5 | Rothamsted | 9.6
2012-05-05 | 2012 | 5 | Rothamsted | 9.6
2012-05-06 | 2012 | 5 | Rothamsted | 13.9
2012-05-07 | 2012 | 5 | Rothamsted | 17.1
2012-05-08 | 2012 | 5 | Rothamsted | 15.6
2012-05-09 | 2012 | 5 | Rothamsted | 17.2
2012-05-10 | 2012 | 5 | Rothamsted | 14.3
2012-05-11 | 2012 | 5 | Rothamsted | 13.4
2012-05-12 | 2012 | 5 | Rothamsted | 15.3
2012-05-13 | 2012 | 5 | Rothamsted | 11.6
2012-05-14 | 2012 | 5 | Rothamsted | 10.5
2012-05-15 | 2012 | 5 | Rothamsted | 12.9
2012-05-16 | 2012 | 5 | Rothamsted | 13.6
2012-05-17 | 2012 | 5 | Rothamsted | 15.7
2012-05-18 | 2012 | 5 | Rothamsted | 14.9
2012-05-20 | 2012 | 5 | Rothamsted | 14.8
2012-05-21 | 2012 | 5 | Rothamsted | 23.9
2012-05-22 | 2012 | 5 | Rothamsted | 23.4
2012-05-23 | 2012 | 5 | Rothamsted | 24.7
2012-05-24 | 2012 | 5 | Rothamsted | 23.9
2012-05-25 | 2012 | 5 | Rothamsted | 24.7
2012-05-26 | 2012 | 5 | Rothamsted | 25.6
2012-05-27 | 2012 | 5 | Rothamsted | 24.9
2012-05-28 | 2012 | 5 | Rothamsted | 19.5
2012-05-29 | 2012 | 5 | Rothamsted | 23
2012-05-30 | 2012 | 5 | Rothamsted | 18.7
2012-05-31 | 2012 | 5 | Rothamsted | 19.8
2012-06-01 | 2012 | 6 | Rothamsted | 16.9
2012-06-03 | 2012 | 6 | Rothamsted | 13.5
2012-06-04 | 2012 | 6 | Rothamsted | 15.4
2012-06-05 | 2012 | 6 | Rothamsted | 18.8
2012-06-06 | 2012 | 6 | Rothamsted | 17.8
2012-06-08 | 2012 | 6 | Rothamsted | 16.9
2012-06-09 | 2012 | 6 | Rothamsted | 19.4
2012-06-10 | 2012 | 6 | Rothamsted | 13.5
2012-06-11 | 2012 | 6 | Rothamsted | 15.5
2012-06-12 | 2012 | 6 | Rothamsted | 17
2012-06-13 | 2012 | 6 | Rothamsted | 17.3
2012-06-14 | 2012 | 6 | Rothamsted | 17.5
2012-06-15 | 2012 | 6 | Rothamsted | 17.2
2012-06-16 | 2012 | 6 | Rothamsted | 18.9
2012-06-17 | 2012 | 6 | Rothamsted | 18.1
2012-06-18 | 2012 | 6 | Rothamsted | 19.5
2012-06-19 | 2012 | 6 | Rothamsted | 20.9
2012-06-20 | 2012 | 6 | Rothamsted | 19.2
2012-06-21 | 2012 | 6 | Rothamsted | 16.9
2012-06-22 | 2012 | 6 | Rothamsted | 17.7
2012-06-23 | 2012 | 6 | Rothamsted | 18.8
2012-06-24 | 2012 | 6 | Rothamsted | 20.5
2012-06-25 | 2012 | 6 | Rothamsted | 20.9
2012-06-26 | 2012 | 6 | Rothamsted | 23.5
2012-06-27 | 2012 | 6 | Rothamsted | 26.3
2012-06-28 | 2012 | 6 | Rothamsted | 19.8
2012-06-29 | 2012 | 6 | Rothamsted | 19.7
2012-06-30 | 2012 | 6 | Rothamsted | 17.6
2012-07-01 | 2012 | 7 | Rothamsted | 17
2012-07-02 | 2012 | 7 | Rothamsted | 18.2
2012-07-03 | 2012 | 7 | Rothamsted | 21.3
2012-07-04 | 2012 | 7 | Rothamsted | 22.9
2012-07-05 | 2012 | 7 | Rothamsted | 18
2012-07-07 | 2012 | 7 | Rothamsted | 18.2
2012-07-08 | 2012 | 7 | Rothamsted | 17.9
2012-07-09 | 2012 | 7 | Rothamsted | 17.5
2012-07-10 | 2012 | 7 | Rothamsted | 18.1
2012-07-11 | 2012 | 7 | Rothamsted | 18.2
2012-07-12 | 2012 | 7 | Rothamsted | 18.8
2012-07-13 | 2012 | 7 | Rothamsted | 17.5
2012-07-14 | 2012 | 7 | Rothamsted | 17.9
2012-07-15 | 2012 | 7 | Rothamsted | 18.6
2012-07-16 | 2012 | 7 | Rothamsted | 22.4
2012-07-17 | 2012 | 7 | Rothamsted | 19.5
2012-07-18 | 2012 | 7 | Rothamsted | 20
2012-07-19 | 2012 | 7 | Rothamsted | 17.8
2012-07-20 | 2012 | 7 | Rothamsted | 21.7
2012-07-21 | 2012 | 7 | Rothamsted | 23
2012-07-22 | 2012 | 7 | Rothamsted | 27.7
2012-07-23 | 2012 | 7 | Rothamsted | 29.8
2012-07-24 | 2012 | 7 | Rothamsted | 29.2
2012-07-25 | 2012 | 7 | Rothamsted | 26.7
2012-07-26 | 2012 | 7 | Rothamsted | 23.7
2012-07-27 | 2012 | 7 | Rothamsted | 20.2
2012-07-28 | 2012 | 7 | Rothamsted | 18.7
2012-07-29 | 2012 | 7 | Rothamsted | 19.2
2012-07-30 | 2012 | 7 | Rothamsted | 19.5
2012-07-31 | 2012 | 7 | Rothamsted | 22.1
2012-08-01 | 2012 | 8 | Rothamsted | 20.9
2012-08-02 | 2012 | 8 | Rothamsted | 21.4
2012-08-03 | 2012 | 8 | Rothamsted | 20.7
2012-08-04 | 2012 | 8 | Rothamsted | 20.7
2012-08-05 | 2012 | 8 | Rothamsted | 21
2012-08-06 | 2012 | 8 | Rothamsted | 19.6
2012-08-07 | 2012 | 8 | Rothamsted | 22.8
2012-08-08 | 2012 | 8 | Rothamsted | 24.7
2012-08-09 | 2012 | 8 | Rothamsted | 25.5
2012-08-10 | 2012 | 8 | Rothamsted | 22
2012-08-11 | 2012 | 8 | Rothamsted | 25.6
2012-08-12 | 2012 | 8 | Rothamsted | 22
2012-08-13 | 2012 | 8 | Rothamsted | 24
2012-08-14 | 2012 | 8 | Rothamsted | 22.1
2012-08-15 | 2012 | 8 | Rothamsted | 21.4
2012-08-16 | 2012 | 8 | Rothamsted | 26.2
2012-08-17 | 2012 | 8 | Rothamsted | 28.3
2012-08-18 | 2012 | 8 | Rothamsted | 28.7
2012-08-19 | 2012 | 8 | Rothamsted | 23.9
2012-08-21 | 2012 | 8 | Rothamsted | 21.6
2012-08-22 | 2012 | 8 | Rothamsted | 20.2
2012-08-23 | 2012 | 8 | Rothamsted | 19.6
2012-08-24 | 2012 | 8 | Rothamsted | 21.7
2012-08-25 | 2012 | 8 | Rothamsted | 20.3
2012-08-26 | 2012 | 8 | Rothamsted | 20.1
2012-08-27 | 2012 | 8 | Rothamsted | 21.9
2012-08-28 | 2012 | 8 | Rothamsted | 19.3
2012-08-30 | 2012 | 8 | Rothamsted | 18.1
2012-08-31 | 2012 | 8 | Rothamsted | 22.4
2012-09-01 | 2012 | 9 | Rothamsted | 19.5
2012-09-02 | 2012 | 9 | Rothamsted | 23.7
2012-09-03 | 2012 | 9 | Rothamsted | 23.2
2012-09-04 | 2012 | 9 | Rothamsted | 18.8
2012-09-05 | 2012 | 9 | Rothamsted | 20.7
2012-09-06 | 2012 | 9 | Rothamsted | 25.1
2012-09-07 | 2012 | 9 | Rothamsted | 25.5
2012-09-08 | 2012 | 9 | Rothamsted | 26.6
2012-09-09 | 2012 | 9 | Rothamsted | 19.8
2012-09-11 | 2012 | 9 | Rothamsted | 18.1
2012-09-12 | 2012 | 9 | Rothamsted | 17.9
2012-09-13 | 2012 | 9 | Rothamsted | 19.2
2012-09-14 | 2012 | 9 | Rothamsted | 20.5
2012-09-15 | 2012 | 9 | Rothamsted | 18.5
2012-09-16 | 2012 | 9 | Rothamsted | 17.7
2012-09-17 | 2012 | 9 | Rothamsted | 16.5
2012-09-18 | 2012 | 9 | Rothamsted | 16.2
2012-09-19 | 2012 | 9 | Rothamsted | 16.7
2012-09-20 | 2012 | 9 | Rothamsted | 16.1
2012-09-21 | 2012 | 9 | Rothamsted | 14.5
2012-09-22 | 2012 | 9 | Rothamsted | 13.7
2012-09-23 | 2012 | 9 | Rothamsted | 14.9
2012-09-24 | 2012 | 9 | Rothamsted | 16
2012-09-25 | 2012 | 9 | Rothamsted | 14.8
2012-09-26 | 2012 | 9 | Rothamsted | 15.9
2012-09-27 | 2012 | 9 | Rothamsted | 15.8
2012-09-28 | 2012 | 9 | Rothamsted | 15.2
2012-09-29 | 2012 | 9 | Rothamsted | 16.4
2012-09-30 | 2012 | 9 | Rothamsted | 16.7
2013-05-01 | 2013 | 5 | Rothamsted | 16.1
2013-05-02 | 2013 | 5 | Rothamsted | 18.7
2013-05-03 | 2013 | 5 | Rothamsted | 16.7
2013-05-04 | 2013 | 5 | Rothamsted | 18
2013-05-05 | 2013 | 5 | Rothamsted | 21
2013-05-06 | 2013 | 5 | Rothamsted | 20.1
2013-05-07 | 2013 | 5 | Rothamsted | 17.1
2013-05-09 | 2013 | 5 | Rothamsted | 16.2
2013-05-10 | 2013 | 5 | Rothamsted | 13.4
2013-05-11 | 2013 | 5 | Rothamsted | 14.1
2013-05-12 | 2013 | 5 | Rothamsted | 13.5
2013-05-14 | 2013 | 5 | Rothamsted | 12.8
2013-05-15 | 2013 | 5 | Rothamsted | 15.5
2013-05-16 | 2013 | 5 | Rothamsted | 10.6
2013-05-17 | 2013 | 5 | Rothamsted | 13.8
2013-05-18 | 2013 | 5 | Rothamsted | 17.9
2013-05-19 | 2013 | 5 | Rothamsted | 16.5
2013-05-24 | 2013 | 5 | Rothamsted | 14.2
2013-05-25 | 2013 | 5 | Rothamsted | 17.8
2013-05-26 | 2013 | 5 | Rothamsted | 16.8
2013-05-27 | 2013 | 5 | Rothamsted | 12.4
2013-05-29 | 2013 | 5 | Rothamsted | 13.3
2013-05-30 | 2013 | 5 | Rothamsted | 19.9
2013-05-31 | 2013 | 5 | Rothamsted | 16.6
2013-06-01 | 2013 | 6 | Rothamsted | 16.6
2013-06-02 | 2013 | 6 | Rothamsted | 17.4
2013-06-03 | 2013 | 6 | Rothamsted | 18.6
2013-06-04 | 2013 | 6 | Rothamsted | 17.4
2013-06-05 | 2013 | 6 | Rothamsted | 19.9
2013-06-06 | 2013 | 6 | Rothamsted | 20.3
2013-06-07 | 2013 | 6 | Rothamsted | 15.4
2013-06-08 | 2013 | 6 | Rothamsted | 14.9
2013-06-09 | 2013 | 6 | Rothamsted | 13.5
2013-06-10 | 2013 | 6 | Rothamsted | 17.1
2013-06-11 | 2013 | 6 | Rothamsted | 16.6
2013-06-12 | 2013 | 6 | Rothamsted | 16.7
2013-06-13 | 2013 | 6 | Rothamsted | 18.1
2013-06-14 | 2013 | 6 | Rothamsted | 15.5
2013-06-15 | 2013 | 6 | Rothamsted | 16.3
2013-06-16 | 2013 | 6 | Rothamsted | 18.7
2013-06-17 | 2013 | 6 | Rothamsted | 20
2013-06-18 | 2013 | 6 | Rothamsted | 24.3
2013-06-19 | 2013 | 6 | Rothamsted | 20.1
2013-06-20 | 2013 | 6 | Rothamsted | 20
2013-06-21 | 2013 | 6 | Rothamsted | 16.4
2013-06-22 | 2013 | 6 | Rothamsted | 16.5
2013-06-23 | 2013 | 6 | Rothamsted | 15.9
2013-06-24 | 2013 | 6 | Rothamsted | 18.2
2013-06-25 | 2013 | 6 | Rothamsted | 19.9
2013-06-26 | 2013 | 6 | Rothamsted | 17.2
2013-06-27 | 2013 | 6 | Rothamsted | 19.5
2013-06-28 | 2013 | 6 | Rothamsted | 19.5
2013-06-29 | 2013 | 6 | Rothamsted | 23.7
2013-06-30 | 2013 | 6 | Rothamsted | 18.2
2013-07-02 | 2013 | 7 | Rothamsted | 19.9
2013-07-03 | 2013 | 7 | Rothamsted | 22.5
2013-07-04 | 2013 | 7 | Rothamsted | 23.7
2013-07-05 | 2013 | 7 | Rothamsted | 26
2013-07-06 | 2013 | 7 | Rothamsted | 27
2013-07-07 | 2013 | 7 | Rothamsted | 24.6
2013-07-08 | 2013 | 7 | Rothamsted | 24.4
2013-07-09 | 2013 | 7 | Rothamsted | 21
2013-07-10 | 2013 | 7 | Rothamsted | 20.1
2013-07-11 | 2013 | 7 | Rothamsted | 23.6
2013-07-12 | 2013 | 7 | Rothamsted | 28.5
2013-07-13 | 2013 | 7 | Rothamsted | 26.5
2013-07-14 | 2013 | 7 | Rothamsted | 27.7
2013-07-15 | 2013 | 7 | Rothamsted | 28.4
2013-07-16 | 2013 | 7 | Rothamsted | 28.9
2013-07-17 | 2013 | 7 | Rothamsted | 26.7
2013-07-18 | 2013 | 7 | Rothamsted | 27.9
2013-07-19 | 2013 | 7 | Rothamsted | 22.1
2013-07-20 | 2013 | 7 | Rothamsted | 24.2
2013-07-21 | 2013 | 7 | Rothamsted | 31.5
2013-07-22 | 2013 | 7 | Rothamsted | 27.5
2013-07-23 | 2013 | 7 | Rothamsted | 25.6
2013-07-24 | 2013 | 7 | Rothamsted | 24.7
2013-07-25 | 2013 | 7 | Rothamsted | 24.9
2013-07-26 | 2013 | 7 | Rothamsted | 26.8
2013-07-27 | 2013 | 7 | Rothamsted | 23.3
2013-07-28 | 2013 | 7 | Rothamsted | 21.5
2013-07-29 | 2013 | 7 | Rothamsted | 21.4
2013-07-30 | 2013 | 7 | Rothamsted | 23.3
2013-07-31 | 2013 | 7 | Rothamsted | 31.3
2013-08-01 | 2013 | 8 | Rothamsted | 24
2013-08-03 | 2013 | 8 | Rothamsted | 22.2
2013-08-04 | 2013 | 8 | Rothamsted | 22.1
2013-08-05 | 2013 | 8 | Rothamsted | 20.2
2013-08-06 | 2013 | 8 | Rothamsted | 20.9
2013-08-07 | 2013 | 8 | Rothamsted | 23.2
2013-08-08 | 2013 | 8 | Rothamsted | 22
2013-08-09 | 2013 | 8 | Rothamsted | 20.7
2013-08-10 | 2013 | 8 | Rothamsted | 21.2
2013-08-11 | 2013 | 8 | Rothamsted | 20.3
2013-08-12 | 2013 | 8 | Rothamsted | 18.1
2013-08-13 | 2013 | 8 | Rothamsted | 21
2013-08-14 | 2013 | 8 | Rothamsted | 21.9
2013-08-15 | 2013 | 8 | Rothamsted | 23.4
2013-08-16 | 2013 | 8 | Rothamsted | 18.9
2013-08-17 | 2013 | 8 | Rothamsted | 22.9
2013-08-18 | 2013 | 8 | Rothamsted | 22.1
2013-08-19 | 2013 | 8 | Rothamsted | 23.3
2013-08-20 | 2013 | 8 | Rothamsted | 25
2013-08-21 | 2013 | 8 | Rothamsted | 20.3
2013-08-22 | 2013 | 8 | Rothamsted | 24.7
2013-08-23 | 2013 | 8 | Rothamsted | 18
2013-08-24 | 2013 | 8 | Rothamsted | 22.7
2013-08-25 | 2013 | 8 | Rothamsted | 24.2
2013-08-26 | 2013 | 8 | Rothamsted | 21.5
2013-08-27 | 2013 | 8 | Rothamsted | 22.7
2013-08-28 | 2013 | 8 | Rothamsted | 23.6
2013-08-29 | 2013 | 8 | Rothamsted | 22.9
2013-08-30 | 2013 | 8 | Rothamsted | 18.5
2013-08-31 | 2013 | 8 | Rothamsted | 20.7
2013-09-01 | 2013 | 9 | Rothamsted | 23.9
2013-09-02 | 2013 | 9 | Rothamsted | 23.6
2013-09-03 | 2013 | 9 | Rothamsted | 25.7
2013-09-04 | 2013 | 9 | Rothamsted | 27.1
2013-09-07 | 2013 | 9 | Rothamsted | 15.7
2013-09-08 | 2013 | 9 | Rothamsted | 13
2013-09-09 | 2013 | 9 | Rothamsted | 15.4
2013-09-10 | 2013 | 9 | Rothamsted | 15.4
2013-09-11 | 2013 | 9 | Rothamsted | 18.2
2013-09-12 | 2013 | 9 | Rothamsted | 15.9
2013-09-14 | 2013 | 9 | Rothamsted | 14.8
2013-09-15 | 2013 | 9 | Rothamsted | 14.1
2013-09-16 | 2013 | 9 | Rothamsted | 12
2013-09-17 | 2013 | 9 | Rothamsted | 14.7
2013-09-18 | 2013 | 9 | Rothamsted | 15.8
2013-09-19 | 2013 | 9 | Rothamsted | 17
2013-09-20 | 2013 | 9 | Rothamsted | 17.6
2013-09-21 | 2013 | 9 | Rothamsted | 20.5
2013-09-22 | 2013 | 9 | Rothamsted | 17.3
2013-09-23 | 2013 | 9 | Rothamsted | 20.1
2013-09-24 | 2013 | 9 | Rothamsted | 19.2
2013-09-25 | 2013 | 9 | Rothamsted | 17.4
2013-09-26 | 2013 | 9 | Rothamsted | 16.7
2013-09-27 | 2013 | 9 | Rothamsted | 17.5
2013-09-28 | 2013 | 9 | Rothamsted | 18
2013-09-29 | 2013 | 9 | Rothamsted | 18.5
2013-09-30 | 2013 | 9 | Rothamsted | 16.4
2014-05-02 | 2014 | 5 | Rothamsted | 11.8
2014-05-03 | 2014 | 5 | Rothamsted | 16.1
2014-05-04 | 2014 | 5 | Rothamsted | 17.6
2014-05-05 | 2014 | 5 | Rothamsted | 17.5
2014-05-06 | 2014 | 5 | Rothamsted | 15.6
2014-05-07 | 2014 | 5 | Rothamsted | 14.7
2014-05-08 | 2014 | 5 | Rothamsted | 15.8
2014-05-09 | 2014 | 5 | Rothamsted | 16.3
2014-05-10 | 2014 | 5 | Rothamsted | 13.1
2014-05-11 | 2014 | 5 | Rothamsted | 15.5
2014-05-12 | 2014 | 5 | Rothamsted | 13.9
2014-05-13 | 2014 | 5 | Rothamsted | 17.1
2014-05-14 | 2014 | 5 | Rothamsted | 19.1
2014-05-15 | 2014 | 5 | Rothamsted | 20.3
2014-05-16 | 2014 | 5 | Rothamsted | 22.1
2014-05-17 | 2014 | 5 | Rothamsted | 22.7
2014-05-18 | 2014 | 5 | Rothamsted | 23.8
2014-05-19 | 2014 | 5 | Rothamsted | 19
2014-05-21 | 2014 | 5 | Rothamsted | 16.9
2014-05-22 | 2014 | 5 | Rothamsted | 16.6
2014-05-23 | 2014 | 5 | Rothamsted | 15.8
2014-05-24 | 2014 | 5 | Rothamsted | 17.1
2014-05-25 | 2014 | 5 | Rothamsted | 12.9
2014-05-26 | 2014 | 5 | Rothamsted | 11.7
2014-05-27 | 2014 | 5 | Rothamsted | 15.3
2014-05-28 | 2014 | 5 | Rothamsted | 18.4
2014-05-29 | 2014 | 5 | Rothamsted | 15
2014-05-30 | 2014 | 5 | Rothamsted | 16.9
2014-05-31 | 2014 | 5 | Rothamsted | 20.3
2014-06-01 | 2014 | 6 | Rothamsted | 19.3
2014-06-02 | 2014 | 6 | Rothamsted | 18.5
2014-06-04 | 2014 | 6 | Rothamsted | 17.8
2014-06-05 | 2014 | 6 | Rothamsted | 21.2
2014-06-06 | 2014 | 6 | Rothamsted | 20.7
2014-06-07 | 2014 | 6 | Rothamsted | 22.5
2014-06-08 | 2014 | 6 | Rothamsted | 24.2
2014-06-09 | 2014 | 6 | Rothamsted | 20.9
2014-06-10 | 2014 | 6 | Rothamsted | 20.2
2014-06-11 | 2014 | 6 | Rothamsted | 23.1
2014-06-12 | 2014 | 6 | Rothamsted | 23.5
2014-06-13 | 2014 | 6 | Rothamsted | 20
2014-06-16 | 2014 | 6 | Rothamsted | 19
2014-06-17 | 2014 | 6 | Rothamsted | 19.9
2014-06-18 | 2014 | 6 | Rothamsted | 17.9
2014-06-19 | 2014 | 6 | Rothamsted | 21.5
2014-06-20 | 2014 | 6 | Rothamsted | 22.2
2014-06-21 | 2014 | 6 | Rothamsted | 23.1
2014-06-22 | 2014 | 6 | Rothamsted | 23.2
2014-06-23 | 2014 | 6 | Rothamsted | 22.4
2014-06-24 | 2014 | 6 | Rothamsted | 19.4
2014-06-25 | 2014 | 6 | Rothamsted | 19.8
2014-06-26 | 2014 | 6 | Rothamsted | 20.6
2014-06-27 | 2014 | 6 | Rothamsted | 18.2
2014-06-28 | 2014 | 6 | Rothamsted | 17
2014-06-29 | 2014 | 6 | Rothamsted | 20.6
2014-06-30 | 2014 | 6 | Rothamsted | 21.4
2014-07-01 | 2014 | 7 | Rothamsted | 22.9
2014-07-02 | 2014 | 7 | Rothamsted | 25
2014-07-03 | 2014 | 7 | Rothamsted | 25.1
2014-07-04 | 2014 | 7 | Rothamsted | 19.5
2014-07-05 | 2014 | 7 | Rothamsted | 21.1
2014-07-06 | 2014 | 7 | Rothamsted | 20.9
2014-07-07 | 2014 | 7 | Rothamsted | 19.7
2014-07-08 | 2014 | 7 | Rothamsted | 21.9
2014-07-09 | 2014 | 7 | Rothamsted | 18.7
2014-07-10 | 2014 | 7 | Rothamsted | 20.1
2014-07-11 | 2014 | 7 | Rothamsted | 25.1
2014-07-12 | 2014 | 7 | Rothamsted | 22.1
2014-07-13 | 2014 | 7 | Rothamsted | 22.9
2014-07-14 | 2014 | 7 | Rothamsted | 23.5
2014-07-15 | 2014 | 7 | Rothamsted | 24
2014-07-16 | 2014 | 7 | Rothamsted | 26.4
2014-07-17 | 2014 | 7 | Rothamsted | 30.1
2014-07-18 | 2014 | 7 | Rothamsted | 26.9
2014-07-19 | 2014 | 7 | Rothamsted | 25
2014-07-20 | 2014 | 7 | Rothamsted | 25
2014-07-21 | 2014 | 7 | Rothamsted | 24.9
2014-07-22 | 2014 | 7 | Rothamsted | 27.9
2014-07-23 | 2014 | 7 | Rothamsted | 27.7
2014-07-24 | 2014 | 7 | Rothamsted | 25.9
2014-07-25 | 2014 | 7 | Rothamsted | 27.6
2014-07-26 | 2014 | 7 | Rothamsted | 23.8
2014-07-27 | 2014 | 7 | Rothamsted | 22.2
2014-07-28 | 2014 | 7 | Rothamsted | 25.9
2014-07-29 | 2014 | 7 | Rothamsted | 24.6
2014-07-30 | 2014 | 7 | Rothamsted | 24.2
2014-07-31 | 2014 | 7 | Rothamsted | 23.6
2014-08-01 | 2014 | 8 | Rothamsted | 22.8
2014-08-02 | 2014 | 8 | Rothamsted | 23
2014-08-03 | 2014 | 8 | Rothamsted | 23.6
2014-08-04 | 2014 | 8 | Rothamsted | 22.6
2014-08-05 | 2014 | 8 | Rothamsted | 24.5
2014-08-06 | 2014 | 8 | Rothamsted | 24.4
2014-08-07 | 2014 | 8 | Rothamsted | 22.5
2014-08-08 | 2014 | 8 | Rothamsted | 21.6
2014-08-09 | 2014 | 8 | Rothamsted | 21.6
2014-08-10 | 2014 | 8 | Rothamsted | 19.2
2014-08-11 | 2014 | 8 | Rothamsted | 19.2
2014-08-12 | 2014 | 8 | Rothamsted | 21.4
2014-08-13 | 2014 | 8 | Rothamsted | 19.1
2014-08-14 | 2014 | 8 | Rothamsted | 18.3
2014-08-15 | 2014 | 8 | Rothamsted | 18.9
2014-08-16 | 2014 | 8 | Rothamsted | 19.8
2014-08-17 | 2014 | 8 | Rothamsted | 19.1
2014-08-18 | 2014 | 8 | Rothamsted | 17
2014-08-19 | 2014 | 8 | Rothamsted | 17.8
2014-08-20 | 2014 | 8 | Rothamsted | 16.7
2014-08-21 | 2014 | 8 | Rothamsted | 18.5
2014-08-22 | 2014 | 8 | Rothamsted | 17.3
2014-08-23 | 2014 | 8 | Rothamsted | 17.8
2014-08-24 | 2014 | 8 | Rothamsted | 15.9
2014-08-25 | 2014 | 8 | Rothamsted | 16.6
2014-08-26 | 2014 | 8 | Rothamsted | 18.6
2014-08-27 | 2014 | 8 | Rothamsted | 21.3
2014-08-28 | 2014 | 8 | Rothamsted | 19.6
2014-08-29 | 2014 | 8 | Rothamsted | 17.8
2014-08-30 | 2014 | 8 | Rothamsted | 20.9
2014-08-31 | 2014 | 8 | Rothamsted | 19.7
2014-09-01 | 2014 | 9 | Rothamsted | 20.7
2014-09-02 | 2014 | 9 | Rothamsted | 21.6
2014-09-03 | 2014 | 9 | Rothamsted | 19.7
2014-09-04 | 2014 | 9 | Rothamsted | 18.2
2014-09-05 | 2014 | 9 | Rothamsted | 20.1
2014-09-06 | 2014 | 9 | Rothamsted | 20
2014-09-07 | 2014 | 9 | Rothamsted | 21
2014-09-08 | 2014 | 9 | Rothamsted | 20.8
2014-09-09 | 2014 | 9 | Rothamsted | 19.5
2014-09-10 | 2014 | 9 | Rothamsted | 17
2014-09-11 | 2014 | 9 | Rothamsted | 21.7
2014-09-12 | 2014 | 9 | Rothamsted | 20.3
2014-09-13 | 2014 | 9 | Rothamsted | 20.2
2014-09-14 | 2014 | 9 | Rothamsted | 19.8
2014-09-15 | 2014 | 9 | Rothamsted | 22
2014-09-16 | 2014 | 9 | Rothamsted | 19.8
2014-09-17 | 2014 | 9 | Rothamsted | 23.9
2014-09-18 | 2014 | 9 | Rothamsted | 22.2
2014-09-21 | 2014 | 9 | Rothamsted | 18
2014-09-22 | 2014 | 9 | Rothamsted | 17.8
2014-09-23 | 2014 | 9 | Rothamsted | 17.6
2014-09-24 | 2014 | 9 | Rothamsted | 18.3
2014-09-25 | 2014 | 9 | Rothamsted | 20.3
2014-09-26 | 2014 | 9 | Rothamsted | 20.5
2014-09-27 | 2014 | 9 | Rothamsted | 22.5
2014-09-28 | 2014 | 9 | Rothamsted | 18.3
2014-09-29 | 2014 | 9 | Rothamsted | 21.2
2014-09-30 | 2014 | 9 | Rothamsted | 19.5
2015-05-01 | 2015 | 5 | Rothamsted | 13.4
2015-05-02 | 2015 | 5 | Rothamsted | 19.3
2015-05-03 | 2015 | 5 | Rothamsted | 17.4
2015-05-04 | 2015 | 5 | Rothamsted | 14.8
2015-05-06 | 2015 | 5 | Rothamsted | 15.2
2015-05-07 | 2015 | 5 | Rothamsted | 15.1
2015-05-08 | 2015 | 5 | Rothamsted | 15.7
2015-05-09 | 2015 | 5 | Rothamsted | 18.2
2015-05-10 | 2015 | 5 | Rothamsted | 20.1
2015-05-11 | 2015 | 5 | Rothamsted | 15.9
2015-05-12 | 2015 | 5 | Rothamsted | 17
2015-05-13 | 2015 | 5 | Rothamsted | 9.6
2015-05-14 | 2015 | 5 | Rothamsted | 13.8
2015-05-15 | 2015 | 5 | Rothamsted | 15.9
2015-05-16 | 2015 | 5 | Rothamsted | 14.6
2015-05-17 | 2015 | 5 | Rothamsted | 13.6
2015-05-18 | 2015 | 5 | Rothamsted | 12.9
2015-05-19 | 2015 | 5 | Rothamsted | 13.7
2015-05-20 | 2015 | 5 | Rothamsted | 17.9
2015-05-21 | 2015 | 5 | Rothamsted | 19.1
2015-05-22 | 2015 | 5 | Rothamsted | 15.2
2015-05-23 | 2015 | 5 | Rothamsted | 17.1
2015-05-24 | 2015 | 5 | Rothamsted | 14.6
2015-05-25 | 2015 | 5 | Rothamsted | 17.2
2015-05-26 | 2015 | 5 | Rothamsted | 17.8
2015-05-27 | 2015 | 5 | Rothamsted | 15.8
2015-05-29 | 2015 | 5 | Rothamsted | 15.9
2015-05-30 | 2015 | 5 | Rothamsted | 16.8
2015-05-31 | 2015 | 5 | Rothamsted | 14.6
2015-06-01 | 2015 | 6 | Rothamsted | 17.8
2015-06-02 | 2015 | 6 | Rothamsted | 17.5
2015-06-03 | 2015 | 6 | Rothamsted | 21
2015-06-04 | 2015 | 6 | Rothamsted | 22.3
2015-06-05 | 2015 | 6 | Rothamsted | 17.3
2015-06-06 | 2015 | 6 | Rothamsted | 17.8
2015-06-07 | 2015 | 6 | Rothamsted | 16.7
2015-06-08 | 2015 | 6 | Rothamsted | 13.3
2015-06-09 | 2015 | 6 | Rothamsted | 17.1
2015-06-10 | 2015 | 6 | Rothamsted | 22.1
2015-06-11 | 2015 | 6 | Rothamsted | 23.9
2015-06-14 | 2015 | 6 | Rothamsted | 17.5
2015-06-15 | 2015 | 6 | Rothamsted | 22
2015-06-16 | 2015 | 6 | Rothamsted | 22.8
2015-06-17 | 2015 | 6 | Rothamsted | 18.7
2015-06-18 | 2015 | 6 | Rothamsted | 18.9
2015-06-19 | 2015 | 6 | Rothamsted | 17.4
2015-06-20 | 2015 | 6 | Rothamsted | 18.1
2015-06-21 | 2015 | 6 | Rothamsted | 16.7
2015-06-22 | 2015 | 6 | Rothamsted | 18.8
2015-06-23 | 2015 | 6 | Rothamsted | 22.4
2015-06-24 | 2015 | 6 | Rothamsted | 23.6
2015-06-25 | 2015 | 6 | Rothamsted | 24.8
2015-06-26 | 2015 | 6 | Rothamsted | 22.4
2015-06-27 | 2015 | 6 | Rothamsted | 18.8
2015-06-28 | 2015 | 6 | Rothamsted | 23.7
2015-06-29 | 2015 | 6 | Rothamsted | 28.8
2015-06-30 | 2015 | 6 | Rothamsted | 33.7
2015-07-01 | 2015 | 7 | Rothamsted | 24.4
2015-07-02 | 2015 | 7 | Rothamsted | 25.9
2015-07-03 | 2015 | 7 | Rothamsted | 25
2015-07-04 | 2015 | 7 | Rothamsted | 22.2
2015-07-05 | 2015 | 7 | Rothamsted | 22
2015-07-06 | 2015 | 7 | Rothamsted | 21.1
2015-07-07 | 2015 | 7 | Rothamsted | 18.8
2015-07-08 | 2015 | 7 | Rothamsted | 20.4
2015-07-09 | 2015 | 7 | Rothamsted | 25.7
2015-07-10 | 2015 | 7 | Rothamsted | 23.7
2015-07-11 | 2015 | 7 | Rothamsted | 21.5
2015-07-13 | 2015 | 7 | Rothamsted | 20.1
2015-07-14 | 2015 | 7 | Rothamsted | 20.8
2015-07-15 | 2015 | 7 | Rothamsted | 23.2
2015-07-16 | 2015 | 7 | Rothamsted | 23.1
2015-07-17 | 2015 | 7 | Rothamsted | 21.3
2015-07-18 | 2015 | 7 | Rothamsted | 22.8
2015-07-19 | 2015 | 7 | Rothamsted | 23
2015-07-20 | 2015 | 7 | Rothamsted | 24.1
2015-07-21 | 2015 | 7 | Rothamsted | 21.4
2015-07-22 | 2015 | 7 | Rothamsted | 19.8
2015-07-23 | 2015 | 7 | Rothamsted | 14.8
2015-07-24 | 2015 | 7 | Rothamsted | 19.5
2015-07-25 | 2015 | 7 | Rothamsted | 16.2
2015-07-26 | 2015 | 7 | Rothamsted | 19
2015-07-27 | 2015 | 7 | Rothamsted | 18.3
2015-07-28 | 2015 | 7 | Rothamsted | 17.9
2015-07-29 | 2015 | 7 | Rothamsted | 18.7
2015-07-30 | 2015 | 7 | Rothamsted | 21.5
2015-07-31 | 2015 | 7 | Rothamsted | 19.5
2015-08-01 | 2015 | 8 | Rothamsted | 23.6
2015-08-02 | 2015 | 8 | Rothamsted | 22.2
2015-08-03 | 2015 | 8 | Rothamsted | 20
2015-08-04 | 2015 | 8 | Rothamsted | 19.5
2015-08-05 | 2015 | 8 | Rothamsted | 22.8
2015-08-06 | 2015 | 8 | Rothamsted | 22.6
2015-08-07 | 2015 | 8 | Rothamsted | 24.9
2015-08-08 | 2015 | 8 | Rothamsted | 24.6
2015-08-09 | 2015 | 8 | Rothamsted | 22.1
2015-08-10 | 2015 | 8 | Rothamsted | 20.6
2015-08-11 | 2015 | 8 | Rothamsted | 21.3
2015-08-12 | 2015 | 8 | Rothamsted | 19.4
2015-08-13 | 2015 | 8 | Rothamsted | 18.9
2015-08-14 | 2015 | 8 | Rothamsted | 19.5
2015-08-15 | 2015 | 8 | Rothamsted | 19.6
2015-08-16 | 2015 | 8 | Rothamsted | 20
2015-08-17 | 2015 | 8 | Rothamsted | 18.4
2015-08-18 | 2015 | 8 | Rothamsted | 19.1
2015-08-19 | 2015 | 8 | Rothamsted | 20.2
2015-08-20 | 2015 | 8 | Rothamsted | 25.3
2015-08-21 | 2015 | 8 | Rothamsted | 28.8
2015-08-22 | 2015 | 8 | Rothamsted | 21.9
2015-08-24 | 2015 | 8 | Rothamsted | 17.3
2015-08-25 | 2015 | 8 | Rothamsted | 19.6
2015-08-26 | 2015 | 8 | Rothamsted | 18.8
2015-08-27 | 2015 | 8 | Rothamsted | 20.5
2015-08-28 | 2015 | 8 | Rothamsted | 20.6
2015-08-29 | 2015 | 8 | Rothamsted | 18.6
2015-08-31 | 2015 | 8 | Rothamsted | 18.1
2015-09-01 | 2015 | 9 | Rothamsted | 17.6
2015-09-02 | 2015 | 9 | Rothamsted | 15
2015-09-03 | 2015 | 9 | Rothamsted | 14.8
2015-09-04 | 2015 | 9 | Rothamsted | 15.4
2015-09-05 | 2015 | 9 | Rothamsted | 18.7
2015-09-06 | 2015 | 9 | Rothamsted | 16.5
2015-09-07 | 2015 | 9 | Rothamsted | 16.1
2015-09-08 | 2015 | 9 | Rothamsted | 18.2
2015-09-09 | 2015 | 9 | Rothamsted | 19.9
2015-09-10 | 2015 | 9 | Rothamsted | 20.1
2015-09-11 | 2015 | 9 | Rothamsted | 20.2
2015-09-12 | 2015 | 9 | Rothamsted | 17.4
2015-09-13 | 2015 | 9 | Rothamsted | 18.3
2015-09-14 | 2015 | 9 | Rothamsted | 17.6
2015-09-15 | 2015 | 9 | Rothamsted | 14
2015-09-16 | 2015 | 9 | Rothamsted | 17
2015-09-17 | 2015 | 9 | Rothamsted | 17.7
2015-09-18 | 2015 | 9 | Rothamsted | 17.6
2015-09-19 | 2015 | 9 | Rothamsted | 17.9
2015-09-20 | 2015 | 9 | Rothamsted | 13.9
2015-09-22 | 2015 | 9 | Rothamsted | 16.5
2015-09-23 | 2015 | 9 | Rothamsted | 16.2
2015-09-24 | 2015 | 9 | Rothamsted | 16.5
2015-09-25 | 2015 | 9 | Rothamsted | 16.4
2015-09-26 | 2015 | 9 | Rothamsted | 17.7
2015-09-27 | 2015 | 9 | Rothamsted | 17.4
2015-09-28 | 2015 | 9 | Rothamsted | 17.7
2015-09-29 | 2015 | 9 | Rothamsted | 17.2
2015-09-30 | 2015 | 9 | Rothamsted | 17.5
2016-05-01 | 2016 | 5 | Rothamsted | 17.3
2016-05-02 | 2016 | 5 | Rothamsted | 13.6
2016-05-03 | 2016 | 5 | Rothamsted | 16.8
2016-05-04 | 2016 | 5 | Rothamsted | 19.5
2016-05-05 | 2016 | 5 | Rothamsted | 21.4
2016-05-06 | 2016 | 5 | Rothamsted | 23.3
2016-05-07 | 2016 | 5 | Rothamsted | 25.2
2016-05-08 | 2016 | 5 | Rothamsted | 22.9
2016-05-10 | 2016 | 5 | Rothamsted | 18.6
2016-05-11 | 2016 | 5 | Rothamsted | 22.8
2016-05-13 | 2016 | 5 | Rothamsted | 12.5
2016-05-14 | 2016 | 5 | Rothamsted | 15.5
2016-05-15 | 2016 | 5 | Rothamsted | 15.9
2016-05-16 | 2016 | 5 | Rothamsted | 17.3
2016-05-17 | 2016 | 5 | Rothamsted | 14.1
2016-05-18 | 2016 | 5 | Rothamsted | 17.1
2016-05-19 | 2016 | 5 | Rothamsted | 17.9
2016-05-20 | 2016 | 5 | Rothamsted | 16.6
2016-05-21 | 2016 | 5 | Rothamsted | 16.9
2016-05-22 | 2016 | 5 | Rothamsted | 17.7
2016-05-23 | 2016 | 5 | Rothamsted | 15.6
2016-05-24 | 2016 | 5 | Rothamsted | 12.1
2016-05-25 | 2016 | 5 | Rothamsted | 19.3
2016-05-26 | 2016 | 5 | Rothamsted | 19.1
2016-05-27 | 2016 | 5 | Rothamsted | 19
2016-05-28 | 2016 | 5 | Rothamsted | 17.7
2016-05-29 | 2016 | 5 | Rothamsted | 16.5
2016-05-31 | 2016 | 5 | Rothamsted | 12.3
2016-06-02 | 2016 | 6 | Rothamsted | 12.8
2016-06-03 | 2016 | 6 | Rothamsted | 17.6
2016-06-04 | 2016 | 6 | Rothamsted | 21.2
2016-06-05 | 2016 | 6 | Rothamsted | 23.7
2016-06-06 | 2016 | 6 | Rothamsted | 23.9
2016-06-07 | 2016 | 6 | Rothamsted | 23.3
2016-06-08 | 2016 | 6 | Rothamsted | 21.8
2016-06-09 | 2016 | 6 | Rothamsted | 23.1
2016-06-10 | 2016 | 6 | Rothamsted | 20.5
2016-06-11 | 2016 | 6 | Rothamsted | 19.3
2016-06-12 | 2016 | 6 | Rothamsted | 16.9
2016-06-13 | 2016 | 6 | Rothamsted | 17.9
2016-06-14 | 2016 | 6 | Rothamsted | 20.4
2016-06-15 | 2016 | 6 | Rothamsted | 18.4
2016-06-16 | 2016 | 6 | Rothamsted | 18.1
2016-06-17 | 2016 | 6 | Rothamsted | 16.8
2016-06-18 | 2016 | 6 | Rothamsted | 19.3
2016-06-19 | 2016 | 6 | Rothamsted | 21.1
2016-06-20 | 2016 | 6 | Rothamsted | 19.2
2016-06-21 | 2016 | 6 | Rothamsted | 20.7
2016-06-22 | 2016 | 6 | Rothamsted | 21.4
2016-06-23 | 2016 | 6 | Rothamsted | 20.4
2016-06-24 | 2016 | 6 | Rothamsted | 18.6
2016-06-25 | 2016 | 6 | Rothamsted | 19.4
2016-06-26 | 2016 | 6 | Rothamsted | 20.1
2016-06-27 | 2016 | 6 | Rothamsted | 19.6
2016-06-28 | 2016 | 6 | Rothamsted | 16
2016-06-29 | 2016 | 6 | Rothamsted | 20
2016-06-30 | 2016 | 6 | Rothamsted | 18.3
2016-07-01 | 2016 | 7 | Rothamsted | 18.9
2016-07-02 | 2016 | 7 | Rothamsted | 20.4
2016-07-03 | 2016 | 7 | Rothamsted | 20.1
2016-07-04 | 2016 | 7 | Rothamsted | 20.1
2016-07-05 | 2016 | 7 | Rothamsted | 20.2
2016-07-06 | 2016 | 7 | Rothamsted | 21.9
2016-07-07 | 2016 | 7 | Rothamsted | 22.3
2016-07-08 | 2016 | 7 | Rothamsted | 22.1
2016-07-09 | 2016 | 7 | Rothamsted | 22
2016-07-10 | 2016 | 7 | Rothamsted | 22
2016-07-12 | 2016 | 7 | Rothamsted | 18.7
2016-07-13 | 2016 | 7 | Rothamsted | 20.5
2016-07-14 | 2016 | 7 | Rothamsted | 21
2016-07-15 | 2016 | 7 | Rothamsted | 25.1
2016-07-16 | 2016 | 7 | Rothamsted | 26.5
2016-07-17 | 2016 | 7 | Rothamsted | 28.4
2016-07-18 | 2016 | 7 | Rothamsted | 31.2
2016-07-19 | 2016 | 7 | Rothamsted | 29.4
2016-07-21 | 2016 | 7 | Rothamsted | 22.6
2016-07-22 | 2016 | 7 | Rothamsted | 27.1
2016-07-23 | 2016 | 7 | Rothamsted | 24.1
2016-07-24 | 2016 | 7 | Rothamsted | 23
2016-07-25 | 2016 | 7 | Rothamsted | 20.6
2016-07-26 | 2016 | 7 | Rothamsted | 23.9
2016-07-27 | 2016 | 7 | Rothamsted | 20.1
2016-07-28 | 2016 | 7 | Rothamsted | 21.6
2016-07-29 | 2016 | 7 | Rothamsted | 21.7
2016-07-30 | 2016 | 7 | Rothamsted | 19.8
2016-07-31 | 2016 | 7 | Rothamsted | 18.2
2016-08-01 | 2016 | 8 | Rothamsted | 20.5
2016-08-02 | 2016 | 8 | Rothamsted | 23.6
2016-08-03 | 2016 | 8 | Rothamsted | 21.7
2016-08-04 | 2016 | 8 | Rothamsted | 22.7
2016-08-05 | 2016 | 8 | Rothamsted | 25
2016-08-06 | 2016 | 8 | Rothamsted | 23.7
2016-08-07 | 2016 | 8 | Rothamsted | 20
2016-08-08 | 2016 | 8 | Rothamsted | 19.5
2016-08-09 | 2016 | 8 | Rothamsted | 19.2
2016-08-10 | 2016 | 8 | Rothamsted | 21.6
2016-08-11 | 2016 | 8 | Rothamsted | 25.9
2016-08-12 | 2016 | 8 | Rothamsted | 24.7
2016-08-13 | 2016 | 8 | Rothamsted | 21.2
2016-08-14 | 2016 | 8 | Rothamsted | 23
2016-08-15 | 2016 | 8 | Rothamsted | 23.4
2016-08-16 | 2016 | 8 | Rothamsted | 24.8
2016-08-17 | 2016 | 8 | Rothamsted | 24.4
2016-08-18 | 2016 | 8 | Rothamsted | 18.2
2016-08-19 | 2016 | 8 | Rothamsted | 20.2
2016-08-20 | 2016 | 8 | Rothamsted | 21
2016-08-21 | 2016 | 8 | Rothamsted | 23.3
2016-08-22 | 2016 | 8 | Rothamsted | 29.1
2016-08-23 | 2016 | 8 | Rothamsted | 31.5
2016-08-24 | 2016 | 8 | Rothamsted | 25.3
2016-08-25 | 2016 | 8 | Rothamsted | 25
2016-08-26 | 2016 | 8 | Rothamsted | 25.2
2016-08-27 | 2016 | 8 | Rothamsted | 20.7
2016-08-28 | 2016 | 8 | Rothamsted | 22.1
2016-08-29 | 2016 | 8 | Rothamsted | 25.1
2016-08-30 | 2016 | 8 | Rothamsted | 22.7
2016-08-31 | 2016 | 8 | Rothamsted | 23
2016-09-01 | 2016 | 9 | Rothamsted | 20.3
2016-09-02 | 2016 | 9 | Rothamsted | 19.6
2016-09-03 | 2016 | 9 | Rothamsted | 18.9
2016-09-04 | 2016 | 9 | Rothamsted | 20.8
2016-09-05 | 2016 | 9 | Rothamsted | 22.2
2016-09-06 | 2016 | 9 | Rothamsted | 25.8
2016-09-07 | 2016 | 9 | Rothamsted | 22
2016-09-08 | 2016 | 9 | Rothamsted | 22.1
2016-09-10 | 2016 | 9 | Rothamsted | 20
2016-09-11 | 2016 | 9 | Rothamsted | 23.9
2016-09-12 | 2016 | 9 | Rothamsted | 31
2016-09-13 | 2016 | 9 | Rothamsted | 28.1
2016-09-14 | 2016 | 9 | Rothamsted | 25.4
2016-09-17 | 2016 | 9 | Rothamsted | 18
2016-09-18 | 2016 | 9 | Rothamsted | 18.9
2016-09-19 | 2016 | 9 | Rothamsted | 17.9
2016-09-20 | 2016 | 9 | Rothamsted | 21.3
2016-09-21 | 2016 | 9 | Rothamsted | 19.8
2016-09-22 | 2016 | 9 | Rothamsted | 18.6
2016-09-23 | 2016 | 9 | Rothamsted | 21.1
2016-09-24 | 2016 | 9 | Rothamsted | 17.7
2016-09-25 | 2016 | 9 | Rothamsted | 16.5
2016-09-26 | 2016 | 9 | Rothamsted | 17.9
2016-09-27 | 2016 | 9 | Rothamsted | 21.1
2016-09-28 | 2016 | 9 | Rothamsted | 18.1
2016-09-29 | 2016 | 9 | Rothamsted | 17.8
2016-09-30 | 2016 | 9 | Rothamsted | 14.7
2017-05-01 | 2017 | 5 | Rothamsted | 15.7
2017-05-02 | 2017 | 5 | Rothamsted | 10.7
2017-05-03 | 2017 | 5 | Rothamsted | 13.8
2017-05-04 | 2017 | 5 | Rothamsted | 15.4
2017-05-05 | 2017 | 5 | Rothamsted | 12.5
2017-05-06 | 2017 | 5 | Rothamsted | 16.3
2017-05-08 | 2017 | 5 | Rothamsted | 10.5
2017-05-09 | 2017 | 5 | Rothamsted | 16.5
2017-05-10 | 2017 | 5 | Rothamsted | 21.5
2017-05-11 | 2017 | 5 | Rothamsted | 17.6
2017-05-12 | 2017 | 5 | Rothamsted | 16.8
2017-05-13 | 2017 | 5 | Rothamsted | 18.6
2017-05-14 | 2017 | 5 | Rothamsted | 18.6
2017-05-15 | 2017 | 5 | Rothamsted | 22.2
2017-05-17 | 2017 | 5 | Rothamsted | 15.5
2017-05-18 | 2017 | 5 | Rothamsted | 14
2017-05-19 | 2017 | 5 | Rothamsted | 15.2
2017-05-20 | 2017 | 5 | Rothamsted | 19
2017-05-21 | 2017 | 5 | Rothamsted | 23
2017-05-22 | 2017 | 5 | Rothamsted | 20
2017-05-23 | 2017 | 5 | Rothamsted | 23.8
2017-05-24 | 2017 | 5 | Rothamsted | 24.9
2017-05-25 | 2017 | 5 | Rothamsted | 24.8
2017-05-26 | 2017 | 5 | Rothamsted | 23.8
2017-05-27 | 2017 | 5 | Rothamsted | 22.8
2017-05-28 | 2017 | 5 | Rothamsted | 19.5
2017-05-29 | 2017 | 5 | Rothamsted | 19.5
2017-05-30 | 2017 | 5 | Rothamsted | 21.2
2017-05-31 | 2017 | 5 | Rothamsted | 23.1
2017-06-01 | 2017 | 6 | Rothamsted | 22.3
2017-06-02 | 2017 | 6 | Rothamsted | 18.9
2017-06-03 | 2017 | 6 | Rothamsted | 17.6
2017-06-04 | 2017 | 6 | Rothamsted | 16.2
2017-06-05 | 2017 | 6 | Rothamsted | 15.9
2017-06-06 | 2017 | 6 | Rothamsted | 18.2
2017-06-07 | 2017 | 6 | Rothamsted | 16.4
2017-06-08 | 2017 | 6 | Rothamsted | 19.6
2017-06-09 | 2017 | 6 | Rothamsted | 22.7
2017-06-10 | 2017 | 6 | Rothamsted | 21.2
2017-06-11 | 2017 | 6 | Rothamsted | 18.9
2017-06-12 | 2017 | 6 | Rothamsted | 21.4
2017-06-13 | 2017 | 6 | Rothamsted | 24.7
2017-06-14 | 2017 | 6 | Rothamsted | 21.8
2017-06-15 | 2017 | 6 | Rothamsted | 22.1
2017-06-16 | 2017 | 6 | Rothamsted | 27.6
2017-06-17 | 2017 | 6 | Rothamsted | 29.7
2017-06-18 | 2017 | 6 | Rothamsted | 30.3
2017-06-19 | 2017 | 6 | Rothamsted | 29.2
2017-06-20 | 2017 | 6 | Rothamsted | 31.5
2017-06-22 | 2017 | 6 | Rothamsted | 21.3
2017-06-23 | 2017 | 6 | Rothamsted | 22.5
2017-06-24 | 2017 | 6 | Rothamsted | 22.1
2017-06-25 | 2017 | 6 | Rothamsted | 22.3
2017-06-26 | 2017 | 6 | Rothamsted | 18.4
2017-06-28 | 2017 | 6 | Rothamsted | 17.2
2017-06-29 | 2017 | 6 | Rothamsted | 19.8
2017-06-30 | 2017 | 6 | Rothamsted | 21.4
2017-07-01 | 2017 | 7 | Rothamsted | 21.9
2017-07-02 | 2017 | 7 | Rothamsted | 23.4
2017-07-03 | 2017 | 7 | Rothamsted | 23.2
2017-07-04 | 2017 | 7 | Rothamsted | 27.2
2017-07-05 | 2017 | 7 | Rothamsted | 30.1
2017-07-06 | 2017 | 7 | Rothamsted | 26.9
2017-07-07 | 2017 | 7 | Rothamsted | 24.8
2017-07-08 | 2017 | 7 | Rothamsted | 26
2017-07-09 | 2017 | 7 | Rothamsted | 24.1
2017-07-11 | 2017 | 7 | Rothamsted | 19.7
2017-07-12 | 2017 | 7 | Rothamsted | 21.4
2017-07-13 | 2017 | 7 | Rothamsted | 19.9
2017-07-14 | 2017 | 7 | Rothamsted | 20.4
2017-07-15 | 2017 | 7 | Rothamsted | 24.2
2017-07-16 | 2017 | 7 | Rothamsted | 24.9
2017-07-17 | 2017 | 7 | Rothamsted | 25.9
2017-07-18 | 2017 | 7 | Rothamsted | 21.2
2017-07-19 | 2017 | 7 | Rothamsted | 19.8
2017-07-20 | 2017 | 7 | Rothamsted | 21.4
2017-07-21 | 2017 | 7 | Rothamsted | 17.7
2017-07-22 | 2017 | 7 | Rothamsted | 19.3
2017-07-23 | 2017 | 7 | Rothamsted | 17
2017-07-24 | 2017 | 7 | Rothamsted | 21.4
2017-07-25 | 2017 | 7 | Rothamsted | 20.5
2017-07-26 | 2017 | 7 | Rothamsted | 20.3
2017-07-27 | 2017 | 7 | Rothamsted | 20.2
2017-07-28 | 2017 | 7 | Rothamsted | 18.8
2017-07-29 | 2017 | 7 | Rothamsted | 20
2017-07-30 | 2017 | 7 | Rothamsted | 20.4
2017-07-31 | 2017 | 7 | Rothamsted | 21
2017-08-01 | 2017 | 8 | Rothamsted | 17.7
2017-08-02 | 2017 | 8 | Rothamsted | 20.5
2017-08-03 | 2017 | 8 | Rothamsted | 20.5
2017-08-04 | 2017 | 8 | Rothamsted | 19.1
2017-08-05 | 2017 | 8 | Rothamsted | 20.6
2017-08-06 | 2017 | 8 | Rothamsted | 19.6
2017-08-08 | 2017 | 8 | Rothamsted | 14.8
2017-08-09 | 2017 | 8 | Rothamsted | 19.2
2017-08-10 | 2017 | 8 | Rothamsted | 20.9
2017-08-11 | 2017 | 8 | Rothamsted | 21
2017-08-12 | 2017 | 8 | Rothamsted | 21.6
2017-08-13 | 2017 | 8 | Rothamsted | 22
2017-08-14 | 2017 | 8 | Rothamsted | 22.8
2017-08-15 | 2017 | 8 | Rothamsted | 21.3
2017-08-16 | 2017 | 8 | Rothamsted | 23.8
2017-08-18 | 2017 | 8 | Rothamsted | 19.5
2017-08-19 | 2017 | 8 | Rothamsted | 19.8
2017-08-20 | 2017 | 8 | Rothamsted | 17.7
2017-08-21 | 2017 | 8 | Rothamsted | 21.4
2017-08-22 | 2017 | 8 | Rothamsted | 20.6
2017-08-23 | 2017 | 8 | Rothamsted | 19.1
2017-08-24 | 2017 | 8 | Rothamsted | 22.8
2017-08-25 | 2017 | 8 | Rothamsted | 22.6
2017-08-26 | 2017 | 8 | Rothamsted | 24.6
2017-08-27 | 2017 | 8 | Rothamsted | 26.4
2017-08-28 | 2017 | 8 | Rothamsted | 24.8
2017-08-30 | 2017 | 8 | Rothamsted | 19.2
2017-08-31 | 2017 | 8 | Rothamsted | 19.9
2017-09-01 | 2017 | 9 | Rothamsted | 19.3
2017-09-02 | 2017 | 9 | Rothamsted | 17.2
2017-09-03 | 2017 | 9 | Rothamsted | 21.6
2017-09-04 | 2017 | 9 | Rothamsted | 19.9
2017-09-05 | 2017 | 9 | Rothamsted | 17.7
2017-09-06 | 2017 | 9 | Rothamsted | 18.6
2017-09-07 | 2017 | 9 | Rothamsted | 16.5
2017-09-08 | 2017 | 9 | Rothamsted | 17
2017-09-09 | 2017 | 9 | Rothamsted | 15.8
2017-09-10 | 2017 | 9 | Rothamsted | 17.6
2017-09-11 | 2017 | 9 | Rothamsted | 17.3
2017-09-12 | 2017 | 9 | Rothamsted | 16.8
2017-09-13 | 2017 | 9 | Rothamsted | 15.8
2017-09-14 | 2017 | 9 | Rothamsted | 14.4
2017-09-15 | 2017 | 9 | Rothamsted | 13.2
2017-09-16 | 2017 | 9 | Rothamsted | 16.1
2017-09-17 | 2017 | 9 | Rothamsted | 15.4
2017-09-18 | 2017 | 9 | Rothamsted | 14.3
2017-09-19 | 2017 | 9 | Rothamsted | 17.7
2017-09-20 | 2017 | 9 | Rothamsted | 16.7
2017-09-21 | 2017 | 9 | Rothamsted | 17.3
2017-09-22 | 2017 | 9 | Rothamsted | 18.4
2017-09-23 | 2017 | 9 | Rothamsted | 21.1
2017-09-24 | 2017 | 9 | Rothamsted | 17
2017-09-25 | 2017 | 9 | Rothamsted | 19.4
2017-09-26 | 2017 | 9 | Rothamsted | 19.7
2017-09-27 | 2017 | 9 | Rothamsted | 18.9
2017-09-28 | 2017 | 9 | Rothamsted | 17.3
2017-09-29 | 2017 | 9 | Rothamsted | 16.4
2017-09-30 | 2017 | 9 | Rothamsted | 16.6
2018-05-01 | 2018 | 5 | Rothamsted | 13
2018-05-02 | 2018 | 5 | Rothamsted | 15.4
2018-05-03 | 2018 | 5 | Rothamsted | 18.2
2018-05-04 | 2018 | 5 | Rothamsted | 21
2018-05-05 | 2018 | 5 | Rothamsted | 23.4
2018-05-06 | 2018 | 5 | Rothamsted | 25.9
2018-05-07 | 2018 | 5 | Rothamsted | 23.8
2018-05-08 | 2018 | 5 | Rothamsted | 18.7
2018-05-09 | 2018 | 5 | Rothamsted | 15.9
2018-05-10 | 2018 | 5 | Rothamsted | 16.5
2018-05-11 | 2018 | 5 | Rothamsted | 14.5
2018-05-12 | 2018 | 5 | Rothamsted | 16.4
2018-05-13 | 2018 | 5 | Rothamsted | 18.7
2018-05-14 | 2018 | 5 | Rothamsted | 20.8
2018-05-16 | 2018 | 5 | Rothamsted | 14.7
2018-05-17 | 2018 | 5 | Rothamsted | 16.2
2018-05-18 | 2018 | 5 | Rothamsted | 19.5
2018-05-19 | 2018 | 5 | Rothamsted | 20.3
2018-05-20 | 2018 | 5 | Rothamsted | 21.4
2018-05-21 | 2018 | 5 | Rothamsted | 20
2018-05-22 | 2018 | 5 | Rothamsted | 17
2018-05-23 | 2018 | 5 | Rothamsted | 21.9
2018-05-24 | 2018 | 5 | Rothamsted | 17
2018-05-25 | 2018 | 5 | Rothamsted | 23.7
2018-05-26 | 2018 | 5 | Rothamsted | 25.7
2018-05-27 | 2018 | 5 | Rothamsted | 22.7
2018-05-29 | 2018 | 5 | Rothamsted | 17.4
2018-05-30 | 2018 | 5 | Rothamsted | 22.3
2018-05-31 | 2018 | 5 | Rothamsted | 22
2018-06-01 | 2018 | 6 | Rothamsted | 22.3
2018-06-02 | 2018 | 6 | Rothamsted | 23.8
2018-06-04 | 2018 | 6 | Rothamsted | 15.6
2018-06-05 | 2018 | 6 | Rothamsted | 20.2
2018-06-06 | 2018 | 6 | Rothamsted | 18.8
2018-06-07 | 2018 | 6 | Rothamsted | 19.9
2018-06-08 | 2018 | 6 | Rothamsted | 19.6
2018-06-09 | 2018 | 6 | Rothamsted | 20.2
2018-06-10 | 2018 | 6 | Rothamsted | 23.3
2018-06-11 | 2018 | 6 | Rothamsted | 17.2
2018-06-12 | 2018 | 6 | Rothamsted | 21.2
2018-06-13 | 2018 | 6 | Rothamsted | 21.1
2018-06-14 | 2018 | 6 | Rothamsted | 20.4
2018-06-15 | 2018 | 6 | Rothamsted | 19.2
2018-06-16 | 2018 | 6 | Rothamsted | 17.3
2018-06-17 | 2018 | 6 | Rothamsted | 23.6
2018-06-18 | 2018 | 6 | Rothamsted | 23.1
2018-06-19 | 2018 | 6 | Rothamsted | 23.1
2018-06-21 | 2018 | 6 | Rothamsted | 20.6
2018-06-22 | 2018 | 6 | Rothamsted | 21.2
2018-06-23 | 2018 | 6 | Rothamsted | 24
2018-06-24 | 2018 | 6 | Rothamsted | 27.5
2018-06-25 | 2018 | 6 | Rothamsted | 27.3
2018-06-26 | 2018 | 6 | Rothamsted | 26.1
2018-06-27 | 2018 | 6 | Rothamsted | 25.6
2018-06-28 | 2018 | 6 | Rothamsted | 26.4
2018-06-29 | 2018 | 6 | Rothamsted | 26.8
2018-06-30 | 2018 | 6 | Rothamsted | 29.3
2018-07-01 | 2018 | 7 | Rothamsted | 27.5
2018-07-02 | 2018 | 7 | Rothamsted | 25.8
2018-07-03 | 2018 | 7 | Rothamsted | 25.2
2018-07-04 | 2018 | 7 | Rothamsted | 28.5
2018-07-05 | 2018 | 7 | Rothamsted | 28.1
2018-07-06 | 2018 | 7 | Rothamsted | 28.4
2018-07-07 | 2018 | 7 | Rothamsted | 28.4
2018-07-08 | 2018 | 7 | Rothamsted | 27.4
2018-07-09 | 2018 | 7 | Rothamsted | 20.6
2018-07-10 | 2018 | 7 | Rothamsted | 21.5
2018-07-11 | 2018 | 7 | Rothamsted | 22.6
2018-07-12 | 2018 | 7 | Rothamsted | 25.1
2018-07-13 | 2018 | 7 | Rothamsted | 27.1
2018-07-14 | 2018 | 7 | Rothamsted | 28.7
2018-07-15 | 2018 | 7 | Rothamsted | 27.7
2018-07-16 | 2018 | 7 | Rothamsted | 23.2
2018-07-17 | 2018 | 7 | Rothamsted | 24.6
2018-07-18 | 2018 | 7 | Rothamsted | 26.1
2018-07-19 | 2018 | 7 | Rothamsted | 25
2018-07-20 | 2018 | 7 | Rothamsted | 26.5
2018-07-21 | 2018 | 7 | Rothamsted | 26.8
2018-07-22 | 2018 | 7 | Rothamsted | 31
2018-07-23 | 2018 | 7 | Rothamsted | 28.9
2018-07-24 | 2018 | 7 | Rothamsted | 29.1
2018-07-25 | 2018 | 7 | Rothamsted | 32.6
2018-07-26 | 2018 | 7 | Rothamsted | 30.9
2018-07-28 | 2018 | 7 | Rothamsted | 19.9
2018-07-29 | 2018 | 7 | Rothamsted | 22.7
2018-07-30 | 2018 | 7 | Rothamsted | 24.4
2018-07-31 | 2018 | 7 | Rothamsted | 25.1
2018-08-01 | 2018 | 8 | Rothamsted | 28.9
2018-08-02 | 2018 | 8 | Rothamsted | 30.8
2018-08-03 | 2018 | 8 | Rothamsted | 26.6
2018-08-04 | 2018 | 8 | Rothamsted | 28.4
2018-08-05 | 2018 | 8 | Rothamsted | 30.4
2018-08-06 | 2018 | 8 | Rothamsted | 29.4
2018-08-07 | 2018 | 8 | Rothamsted | 23.5
2018-08-09 | 2018 | 8 | Rothamsted | 18.1
2018-08-10 | 2018 | 8 | Rothamsted | 21
2018-08-11 | 2018 | 8 | Rothamsted | 20.2
2018-08-12 | 2018 | 8 | Rothamsted | 23.3
2018-08-13 | 2018 | 8 | Rothamsted | 23.7
2018-08-14 | 2018 | 8 | Rothamsted | 23.3
2018-08-15 | 2018 | 8 | Rothamsted | 20
2018-08-16 | 2018 | 8 | Rothamsted | 21.4
2018-08-17 | 2018 | 8 | Rothamsted | 21.6
2018-08-18 | 2018 | 8 | Rothamsted | 24.8
2018-08-19 | 2018 | 8 | Rothamsted | 23.9
2018-08-20 | 2018 | 8 | Rothamsted | 25.9
2018-08-21 | 2018 | 8 | Rothamsted | 22.1
2018-08-22 | 2018 | 8 | Rothamsted | 20.7
2018-08-23 | 2018 | 8 | Rothamsted | 18.2
2018-08-24 | 2018 | 8 | Rothamsted | 17.4
2018-08-25 | 2018 | 8 | Rothamsted | 17
2018-08-26 | 2018 | 8 | Rothamsted | 17.9
2018-08-27 | 2018 | 8 | Rothamsted | 19.3
2018-08-28 | 2018 | 8 | Rothamsted | 19.4
2018-08-29 | 2018 | 8 | Rothamsted | 19.5
2018-08-30 | 2018 | 8 | Rothamsted | 20.4
2018-08-31 | 2018 | 8 | Rothamsted | 23.5
2018-09-01 | 2018 | 9 | Rothamsted | 23
2018-09-02 | 2018 | 9 | Rothamsted | 23.4
2018-09-03 | 2018 | 9 | Rothamsted | 17.9
2018-09-04 | 2018 | 9 | Rothamsted | 20.7
2018-09-05 | 2018 | 9 | Rothamsted | 20.9
2018-09-06 | 2018 | 9 | Rothamsted | 18.3
2018-09-07 | 2018 | 9 | Rothamsted | 19.1
2018-09-08 | 2018 | 9 | Rothamsted | 22.3
2018-09-09 | 2018 | 9 | Rothamsted | 20.6
2018-09-10 | 2018 | 9 | Rothamsted | 21.1
2018-09-12 | 2018 | 9 | Rothamsted | 18.8
2018-09-13 | 2018 | 9 | Rothamsted | 17.5
2018-09-14 | 2018 | 9 | Rothamsted | 19.9
2018-09-15 | 2018 | 9 | Rothamsted | 22.7
2018-09-16 | 2018 | 9 | Rothamsted | 24.2
2018-09-17 | 2018 | 9 | Rothamsted | 22.1
2018-09-18 | 2018 | 9 | Rothamsted | 22.7
2018-09-19 | 2018 | 9 | Rothamsted | 19.6
2018-09-22 | 2018 | 9 | Rothamsted | 13
2018-09-23 | 2018 | 9 | Rothamsted | 14.3
2018-09-24 | 2018 | 9 | Rothamsted | 16.3
2018-09-25 | 2018 | 9 | Rothamsted | 21.9
2018-09-26 | 2018 | 9 | Rothamsted | 21.7
2018-09-27 | 2018 | 9 | Rothamsted | 15.8
2018-09-28 | 2018 | 9 | Rothamsted | 16.5
2018-09-29 | 2018 | 9 | Rothamsted | 13.7
2018-09-30 | 2018 | 9 | Rothamsted | 15.2
2019-05-01 | 2019 | 5 | Rothamsted | 14.3
2019-05-02 | 2019 | 5 | Rothamsted | 13.1
2019-05-03 | 2019 | 5 | Rothamsted | 10
2019-05-04 | 2019 | 5 | Rothamsted | 10.8
2019-05-05 | 2019 | 5 | Rothamsted | 11.6
2019-05-06 | 2019 | 5 | Rothamsted | 14.5
2019-05-07 | 2019 | 5 | Rothamsted | 13.9
2019-05-08 | 2019 | 5 | Rothamsted | 12.2
2019-05-09 | 2019 | 5 | Rothamsted | 15.3
2019-05-10 | 2019 | 5 | Rothamsted | 14.7
2019-05-11 | 2019 | 5 | Rothamsted | 16
2019-05-12 | 2019 | 5 | Rothamsted | 16.2
2019-05-13 | 2019 | 5 | Rothamsted | 17.1
2019-05-14 | 2019 | 5 | Rothamsted | 17.9
2019-05-15 | 2019 | 5 | Rothamsted | 16.7
2019-05-16 | 2019 | 5 | Rothamsted | 13.5
2019-05-17 | 2019 | 5 | Rothamsted | 16.1
2019-05-18 | 2019 | 5 | Rothamsted | 17.4
2019-05-19 | 2019 | 5 | Rothamsted | 18.7
2019-05-20 | 2019 | 5 | Rothamsted | 18.8
2019-05-21 | 2019 | 5 | Rothamsted | 19.9
2019-05-22 | 2019 | 5 | Rothamsted | 22
2019-05-23 | 2019 | 5 | Rothamsted | 20.2
2019-05-24 | 2019 | 5 | Rothamsted | 20.7
2019-05-25 | 2019 | 5 | Rothamsted | 19.2
2019-05-26 | 2019 | 5 | Rothamsted | 16.9
2019-05-27 | 2019 | 5 | Rothamsted | 15.4
2019-05-28 | 2019 | 5 | Rothamsted | 18.2
2019-05-29 | 2019 | 5 | Rothamsted | 22.5
2019-05-30 | 2019 | 5 | Rothamsted | 19.2
2019-05-31 | 2019 | 5 | Rothamsted | 24.8
2019-06-01 | 2019 | 6 | Rothamsted | 24.7
2019-06-02 | 2019 | 6 | Rothamsted | 19.5
2019-06-03 | 2019 | 6 | Rothamsted | 16.1
2019-06-04 | 2019 | 6 | Rothamsted | 16.8
2019-06-05 | 2019 | 6 | Rothamsted | 18.3
2019-06-06 | 2019 | 6 | Rothamsted | 15.3
2019-06-07 | 2019 | 6 | Rothamsted | 17.2
2019-06-08 | 2019 | 6 | Rothamsted | 18.6
2019-06-09 | 2019 | 6 | Rothamsted | 12.1
2019-06-10 | 2019 | 6 | Rothamsted | 13.1
2019-06-11 | 2019 | 6 | Rothamsted | 13.2
2019-06-12 | 2019 | 6 | Rothamsted | 14.5
2019-06-13 | 2019 | 6 | Rothamsted | 18.1
2019-06-14 | 2019 | 6 | Rothamsted | 17.5
2019-06-15 | 2019 | 6 | Rothamsted | 19.3
2019-06-16 | 2019 | 6 | Rothamsted | 19.8
2019-06-17 | 2019 | 6 | Rothamsted | 18.8
2019-06-18 | 2019 | 6 | Rothamsted | 19
2019-06-19 | 2019 | 6 | Rothamsted | 18.9
2019-06-20 | 2019 | 6 | Rothamsted | 19.4
2019-06-21 | 2019 | 6 | Rothamsted | 21.6
2019-06-22 | 2019 | 6 | Rothamsted | 23.2
2019-06-23 | 2019 | 6 | Rothamsted | 23.1
2019-06-24 | 2019 | 6 | Rothamsted | 19.7
2019-06-26 | 2019 | 6 | Rothamsted | 22.2
2019-06-27 | 2019 | 6 | Rothamsted | 22.7
2019-06-28 | 2019 | 6 | Rothamsted | 32.6
2019-06-30 | 2019 | 6 | Rothamsted | 19.9
2019-07-01 | 2019 | 7 | Rothamsted | 20.3
2019-07-02 | 2019 | 7 | Rothamsted | 21.7
2019-07-03 | 2019 | 7 | Rothamsted | 24
2019-07-04 | 2019 | 7 | Rothamsted | 24.8
2019-07-05 | 2019 | 7 | Rothamsted | 19.7
2019-07-06 | 2019 | 7 | Rothamsted | 20.9
2019-07-07 | 2019 | 7 | Rothamsted | 22
2019-07-08 | 2019 | 7 | Rothamsted | 21.8
2019-07-09 | 2019 | 7 | Rothamsted | 24.6
2019-07-10 | 2019 | 7 | Rothamsted | 23.9
2019-07-11 | 2019 | 7 | Rothamsted | 23.2
2019-07-12 | 2019 | 7 | Rothamsted | 19.9
2019-07-13 | 2019 | 7 | Rothamsted | 20.9
2019-07-14 | 2019 | 7 | Rothamsted | 20.6
2019-07-15 | 2019 | 7 | Rothamsted | 25.4
2019-07-16 | 2019 | 7 | Rothamsted | 24.6
2019-07-17 | 2019 | 7 | Rothamsted | 22.5
2019-07-18 | 2019 | 7 | Rothamsted | 18.8
2019-07-19 | 2019 | 7 | Rothamsted | 22.6
2019-07-20 | 2019 | 7 | Rothamsted | 22.3
2019-07-21 | 2019 | 7 | Rothamsted | 27.5
2019-07-22 | 2019 | 7 | Rothamsted | 31.7
2019-07-23 | 2019 | 7 | Rothamsted | 30.6
2019-07-24 | 2019 | 7 | Rothamsted | 36.6
2019-07-27 | 2019 | 7 | Rothamsted | 20.5
2019-07-28 | 2019 | 7 | Rothamsted | 24.2
2019-07-29 | 2019 | 7 | Rothamsted | 19.3
2019-07-30 | 2019 | 7 | Rothamsted | 22.2
2019-07-31 | 2019 | 7 | Rothamsted | 24
2019-08-01 | 2019 | 8 | Rothamsted | 23.6
2019-08-02 | 2019 | 8 | Rothamsted | 23.4
2019-08-03 | 2019 | 8 | Rothamsted | 24.7
2019-08-04 | 2019 | 8 | Rothamsted | 24.4
2019-08-05 | 2019 | 8 | Rothamsted | 22.8
2019-08-06 | 2019 | 8 | Rothamsted | 22.2
2019-08-07 | 2019 | 8 | Rothamsted | 23.8
2019-08-08 | 2019 | 8 | Rothamsted | 23.7
2019-08-09 | 2019 | 8 | Rothamsted | 21.4
2019-08-10 | 2019 | 8 | Rothamsted | 20.9
2019-08-11 | 2019 | 8 | Rothamsted | 18.8
2019-08-12 | 2019 | 8 | Rothamsted | 20.8
2019-08-13 | 2019 | 8 | Rothamsted | 17.6
2019-08-14 | 2019 | 8 | Rothamsted | 21.3
2019-08-15 | 2019 | 8 | Rothamsted | 17.3
2019-08-16 | 2019 | 8 | Rothamsted | 21.8
2019-08-17 | 2019 | 8 | Rothamsted | 20.8
2019-08-18 | 2019 | 8 | Rothamsted | 20.6
2019-08-19 | 2019 | 8 | Rothamsted | 19.9
2019-08-20 | 2019 | 8 | Rothamsted | 21.4
2019-08-21 | 2019 | 8 | Rothamsted | 22.6
2019-08-22 | 2019 | 8 | Rothamsted | 25.7
2019-08-23 | 2019 | 8 | Rothamsted | 28.2
2019-08-24 | 2019 | 8 | Rothamsted | 31.2
2019-08-25 | 2019 | 8 | Rothamsted | 31.3
2019-08-26 | 2019 | 8 | Rothamsted | 31.2
2019-08-27 | 2019 | 8 | Rothamsted | 24.3
2019-08-28 | 2019 | 8 | Rothamsted | 21.7
2019-08-29 | 2019 | 8 | Rothamsted | 23.4
2019-08-30 | 2019 | 8 | Rothamsted | 21.7
2019-08-31 | 2019 | 8 | Rothamsted | 19.6
2019-09-01 | 2019 | 9 | Rothamsted | 20.8
2019-09-02 | 2019 | 9 | Rothamsted | 21.4
2019-09-03 | 2019 | 9 | Rothamsted | 18.9
2019-09-04 | 2019 | 9 | Rothamsted | 17.5
2019-09-05 | 2019 | 9 | Rothamsted | 17.1
2019-09-06 | 2019 | 9 | Rothamsted | 16.9
2019-09-07 | 2019 | 9 | Rothamsted | 17.1
2019-09-08 | 2019 | 9 | Rothamsted | 14.8
2019-09-09 | 2019 | 9 | Rothamsted | 17.8
2019-09-10 | 2019 | 9 | Rothamsted | 22.2
2019-09-11 | 2019 | 9 | Rothamsted | 24.1
2019-09-12 | 2019 | 9 | Rothamsted | 19.8
2019-09-13 | 2019 | 9 | Rothamsted | 22.3
2019-09-14 | 2019 | 9 | Rothamsted | 24.2
2019-09-15 | 2019 | 9 | Rothamsted | 17.6
2019-09-16 | 2019 | 9 | Rothamsted | 17.7
2019-09-17 | 2019 | 9 | Rothamsted | 18.1
2019-09-18 | 2019 | 9 | Rothamsted | 20.5
2019-09-19 | 2019 | 9 | Rothamsted | 20.4
2019-09-20 | 2019 | 9 | Rothamsted | 23.9
2019-09-21 | 2019 | 9 | Rothamsted | 21.4
2019-09-22 | 2019 | 9 | Rothamsted | 19.9
2019-09-23 | 2019 | 9 | Rothamsted | 19
2019-09-24 | 2019 | 9 | Rothamsted | 18.5
2019-09-25 | 2019 | 9 | Rothamsted | 19.3
2019-09-26 | 2019 | 9 | Rothamsted | 18.3
2019-09-27 | 2019 | 9 | Rothamsted | 18.2
2019-09-28 | 2019 | 9 | Rothamsted | 19.1
2019-09-29 | 2019 | 9 | Rothamsted | 16.5
2019-09-30 | 2019 | 9 | Rothamsted | 16.8
2020-05-01 | 2020 | 5 | Rothamsted | 15
2020-05-02 | 2020 | 5 | Rothamsted | 14
2020-05-03 | 2020 | 5 | Rothamsted | 16.1
2020-05-04 | 2020 | 5 | Rothamsted | 13.6
2020-05-05 | 2020 | 5 | Rothamsted | 16.8
2020-05-06 | 2020 | 5 | Rothamsted | 21.3
2020-05-07 | 2020 | 5 | Rothamsted | 22.6
2020-05-08 | 2020 | 5 | Rothamsted | 22.7
2020-05-11 | 2020 | 5 | Rothamsted | 13.7
2020-05-12 | 2020 | 5 | Rothamsted | 11.3
2020-05-13 | 2020 | 5 | Rothamsted | 12.7
2020-05-14 | 2020 | 5 | Rothamsted | 16.8
2020-05-15 | 2020 | 5 | Rothamsted | 16.3
2020-05-16 | 2020 | 5 | Rothamsted | 18.4
2020-05-17 | 2020 | 5 | Rothamsted | 21.5
2020-05-18 | 2020 | 5 | Rothamsted | 23.7
2020-05-19 | 2020 | 5 | Rothamsted | 25.9
2020-05-20 | 2020 | 5 | Rothamsted | 24.5
2020-05-21 | 2020 | 5 | Rothamsted | 20.5
2020-05-23 | 2020 | 5 | Rothamsted | 20.7
2020-05-24 | 2020 | 5 | Rothamsted | 23.4
2020-05-25 | 2020 | 5 | Rothamsted | 23.9
2020-05-26 | 2020 | 5 | Rothamsted | 23.3
2020-05-27 | 2020 | 5 | Rothamsted | 20.2
2020-05-28 | 2020 | 5 | Rothamsted | 22
2020-05-29 | 2020 | 5 | Rothamsted | 23.4
2020-05-30 | 2020 | 5 | Rothamsted | 23
2020-05-31 | 2020 | 5 | Rothamsted | 24.8
2020-06-01 | 2020 | 6 | Rothamsted | 22.7
2020-06-02 | 2020 | 6 | Rothamsted | 17.5
2020-06-03 | 2020 | 6 | Rothamsted | 14.5
2020-06-04 | 2020 | 6 | Rothamsted | 15.8
2020-06-05 | 2020 | 6 | Rothamsted | 13.5
2020-06-06 | 2020 | 6 | Rothamsted | 16.6
2020-06-07 | 2020 | 6 | Rothamsted | 14.2
2020-06-08 | 2020 | 6 | Rothamsted | 18.1
2020-06-09 | 2020 | 6 | Rothamsted | 15
2020-06-10 | 2020 | 6 | Rothamsted | 19
2020-06-11 | 2020 | 6 | Rothamsted | 20.4
2020-06-12 | 2020 | 6 | Rothamsted | 23.5
2020-06-13 | 2020 | 6 | Rothamsted | 21.7
2020-06-14 | 2020 | 6 | Rothamsted | 22.6
2020-06-15 | 2020 | 6 | Rothamsted | 23.4
2020-06-16 | 2020 | 6 | Rothamsted | 21
2020-06-17 | 2020 | 6 | Rothamsted | 17.9
2020-06-18 | 2020 | 6 | Rothamsted | 18.1
2020-06-19 | 2020 | 6 | Rothamsted | 21.2
2020-06-20 | 2020 | 6 | Rothamsted | 20.9
2020-06-21 | 2020 | 6 | Rothamsted | 21.8
2020-06-22 | 2020 | 6 | Rothamsted | 26.9
2020-06-23 | 2020 | 6 | Rothamsted | 29
2020-06-24 | 2020 | 6 | Rothamsted | 29.4
2020-06-25 | 2020 | 6 | Rothamsted | 28.8
2020-06-27 | 2020 | 6 | Rothamsted | 18
2020-06-28 | 2020 | 6 | Rothamsted | 18.4
2020-06-29 | 2020 | 6 | Rothamsted | 17.7
2020-06-30 | 2020 | 6 | Rothamsted | 21.2
2020-07-01 | 2020 | 7 | Rothamsted | 20.7
2020-07-02 | 2020 | 7 | Rothamsted | 19.5
2020-07-03 | 2020 | 7 | Rothamsted | 19.1
2020-07-04 | 2020 | 7 | Rothamsted | 19.5
2020-07-05 | 2020 | 7 | Rothamsted | 19.2
2020-07-06 | 2020 | 7 | Rothamsted | 18.6
2020-07-07 | 2020 | 7 | Rothamsted | 19.9
2020-07-08 | 2020 | 7 | Rothamsted | 18.2
2020-07-09 | 2020 | 7 | Rothamsted | 17.5
2020-07-10 | 2020 | 7 | Rothamsted | 19.6
2020-07-11 | 2020 | 7 | Rothamsted | 22.2
2020-07-12 | 2020 | 7 | Rothamsted | 22.7
2020-07-13 | 2020 | 7 | Rothamsted | 19.5
2020-07-14 | 2020 | 7 | Rothamsted | 17.2
2020-07-15 | 2020 | 7 | Rothamsted | 21.5
2020-07-16 | 2020 | 7 | Rothamsted | 25.1
2020-07-17 | 2020 | 7 | Rothamsted | 22.8
2020-07-18 | 2020 | 7 | Rothamsted | 19.8
2020-07-19 | 2020 | 7 | Rothamsted | 19.9
2020-07-20 | 2020 | 7 | Rothamsted | 20.4
2020-07-21 | 2020 | 7 | Rothamsted | 24.2
2020-07-22 | 2020 | 7 | Rothamsted | 25
2020-07-23 | 2020 | 7 | Rothamsted | 23.6
2020-07-24 | 2020 | 7 | Rothamsted | 23
2020-07-25 | 2020 | 7 | Rothamsted | 20.8
2020-07-26 | 2020 | 7 | Rothamsted | 19.7
2020-07-27 | 2020 | 7 | Rothamsted | 19.6
2020-07-28 | 2020 | 7 | Rothamsted | 21.8
2020-07-29 | 2020 | 7 | Rothamsted | 27.2
2020-07-30 | 2020 | 7 | Rothamsted | 34.5
2020-08-01 | 2020 | 8 | Rothamsted | 22.6
2020-08-02 | 2020 | 8 | Rothamsted | 21.1
2020-08-03 | 2020 | 8 | Rothamsted | 21.5
2020-08-04 | 2020 | 8 | Rothamsted | 24.9
2020-08-05 | 2020 | 8 | Rothamsted | 27.4
2020-08-06 | 2020 | 8 | Rothamsted | 33.6
2020-08-07 | 2020 | 8 | Rothamsted | 27.1
2020-08-08 | 2020 | 8 | Rothamsted | 31.3
2020-08-09 | 2020 | 8 | Rothamsted | 32.5
2020-08-10 | 2020 | 8 | Rothamsted | 32.3
2020-08-11 | 2020 | 8 | Rothamsted | 33.2
2020-08-14 | 2020 | 8 | Rothamsted | 19.1
2020-08-15 | 2020 | 8 | Rothamsted | 22.8
2020-08-16 | 2020 | 8 | Rothamsted | 21.6
2020-08-17 | 2020 | 8 | Rothamsted | 22.8
2020-08-18 | 2020 | 8 | Rothamsted | 19.8
2020-08-19 | 2020 | 8 | Rothamsted | 23.4
2020-08-20 | 2020 | 8 | Rothamsted | 22
2020-08-21 | 2020 | 8 | Rothamsted | 21.2
2020-08-22 | 2020 | 8 | Rothamsted | 20.8
2020-08-23 | 2020 | 8 | Rothamsted | 21.4
2020-08-24 | 2020 | 8 | Rothamsted | 20.9
2020-08-25 | 2020 | 8 | Rothamsted | 20.9
2020-08-27 | 2020 | 8 | Rothamsted | 17.7
2020-08-29 | 2020 | 8 | Rothamsted | 16.3
2020-08-30 | 2020 | 8 | Rothamsted | 16.6
2020-08-31 | 2020 | 8 | Rothamsted | 19
2020-09-01 | 2020 | 9 | Rothamsted | 18.8
2020-09-02 | 2020 | 9 | Rothamsted | 20.4
2020-09-03 | 2020 | 9 | Rothamsted | 18.2
2020-09-04 | 2020 | 9 | Rothamsted | 17.7
2020-09-05 | 2020 | 9 | Rothamsted | 18.4
2020-09-06 | 2020 | 9 | Rothamsted | 18.5
2020-09-07 | 2020 | 9 | Rothamsted | 23.9
2020-09-08 | 2020 | 9 | Rothamsted | 20.7
2020-09-09 | 2020 | 9 | Rothamsted | 17.9
2020-09-10 | 2020 | 9 | Rothamsted | 18
2020-09-11 | 2020 | 9 | Rothamsted | 19.9
2020-09-12 | 2020 | 9 | Rothamsted | 23.6
2020-09-13 | 2020 | 9 | Rothamsted | 26.2
2020-09-14 | 2020 | 9 | Rothamsted | 28.3
2020-09-15 | 2020 | 9 | Rothamsted | 23.5
2020-09-16 | 2020 | 9 | Rothamsted | 20.1
2020-09-17 | 2020 | 9 | Rothamsted | 20.1
2020-09-18 | 2020 | 9 | Rothamsted | 22.3
2020-09-19 | 2020 | 9 | Rothamsted | 21.9
2020-09-20 | 2020 | 9 | Rothamsted | 23.4
2020-09-21 | 2020 | 9 | Rothamsted | 23.8
2020-09-23 | 2020 | 9 | Rothamsted | 15.2
2020-09-24 | 2020 | 9 | Rothamsted | 13.2
2020-09-25 | 2020 | 9 | Rothamsted | 11.2
2020-09-26 | 2020 | 9 | Rothamsted | 13.2
2020-09-27 | 2020 | 9 | Rothamsted | 16.1
2020-09-28 | 2020 | 9 | Rothamsted | 16
2020-09-29 | 2020 | 9 | Rothamsted | 16.7
2020-09-30 | 2020 | 9 | Rothamsted | 14.2
2021-05-01 | 2021 | 5 | Rothamsted | 12.4
2021-05-02 | 2021 | 5 | Rothamsted | 12.1
2021-05-03 | 2021 | 5 | Rothamsted | 11.9
2021-05-04 | 2021 | 5 | Rothamsted | 11.5
2021-05-05 | 2021 | 5 | Rothamsted | 11
2021-05-06 | 2021 | 5 | Rothamsted | 12.8
2021-05-07 | 2021 | 5 | Rothamsted | 16
2021-05-08 | 2021 | 5 | Rothamsted | 19.3
2021-05-09 | 2021 | 5 | Rothamsted | 16
2021-05-10 | 2021 | 5 | Rothamsted | 17
2021-05-11 | 2021 | 5 | Rothamsted | 15.3
2021-05-12 | 2021 | 5 | Rothamsted | 11.9
2021-05-13 | 2021 | 5 | Rothamsted | 10.9
2021-05-14 | 2021 | 5 | Rothamsted | 12.8
2021-05-15 | 2021 | 5 | Rothamsted | 14.3
2021-05-16 | 2021 | 5 | Rothamsted | 14.6
2021-05-17 | 2021 | 5 | Rothamsted | 15.4
2021-05-18 | 2021 | 5 | Rothamsted | 15.6
2021-05-19 | 2021 | 5 | Rothamsted | 13.3
2021-05-20 | 2021 | 5 | Rothamsted | 11
2021-05-21 | 2021 | 5 | Rothamsted | 12.9
2021-05-22 | 2021 | 5 | Rothamsted | 12.7
2021-05-23 | 2021 | 5 | Rothamsted | 12.7
2021-05-24 | 2021 | 5 | Rothamsted | 15.1
2021-05-25 | 2021 | 5 | Rothamsted | 14.5
2021-05-26 | 2021 | 5 | Rothamsted | 18.5
2021-05-27 | 2021 | 5 | Rothamsted | 18
2021-05-28 | 2021 | 5 | Rothamsted | 20.3
2021-05-29 | 2021 | 5 | Rothamsted | 19.5
2021-05-30 | 2021 | 5 | Rothamsted | 22.2
2021-05-31 | 2021 | 5 | Rothamsted | 23.6
2021-06-01 | 2021 | 6 | Rothamsted | 25.8
2021-06-02 | 2021 | 6 | Rothamsted | 21.6
2021-06-04 | 2021 | 6 | Rothamsted | 21.5
2021-06-05 | 2021 | 6 | Rothamsted | 21.3
2021-06-06 | 2021 | 6 | Rothamsted | 21.9
2021-06-07 | 2021 | 6 | Rothamsted | 22.7
2021-06-08 | 2021 | 6 | Rothamsted | 24
2021-06-09 | 2021 | 6 | Rothamsted | 21.9
2021-06-10 | 2021 | 6 | Rothamsted | 23.1
2021-06-11 | 2021 | 6 | Rothamsted | 21.7
2021-06-12 | 2021 | 6 | Rothamsted | 26
2021-06-13 | 2021 | 6 | Rothamsted | 25.5
2021-06-14 | 2021 | 6 | Rothamsted | 23.9
2021-06-15 | 2021 | 6 | Rothamsted | 25.8
2021-06-16 | 2021 | 6 | Rothamsted | 19.4
2021-06-18 | 2021 | 6 | Rothamsted | 14.9
2021-06-19 | 2021 | 6 | Rothamsted | 14.8
2021-06-20 | 2021 | 6 | Rothamsted | 13.5
2021-06-21 | 2021 | 6 | Rothamsted | 15.5
2021-06-22 | 2021 | 6 | Rothamsted | 19.6
2021-06-23 | 2021 | 6 | Rothamsted | 17.8
2021-06-24 | 2021 | 6 | Rothamsted | 18.9
2021-06-25 | 2021 | 6 | Rothamsted | 21.1
2021-06-26 | 2021 | 6 | Rothamsted | 19.8
2021-06-28 | 2021 | 6 | Rothamsted | 15.9
2021-06-29 | 2021 | 6 | Rothamsted | 16.4
2021-06-30 | 2021 | 6 | Rothamsted | 19.9
2021-07-01 | 2021 | 7 | Rothamsted | 22.2
2021-07-02 | 2021 | 7 | Rothamsted | 21.1
2021-07-03 | 2021 | 7 | Rothamsted | 20.7
2021-07-04 | 2021 | 7 | Rothamsted | 19.7
2021-07-05 | 2021 | 7 | Rothamsted | 17.6
2021-07-06 | 2021 | 7 | Rothamsted | 19.6
2021-07-07 | 2021 | 7 | Rothamsted | 20.2
2021-07-08 | 2021 | 7 | Rothamsted | 22.2
2021-07-09 | 2021 | 7 | Rothamsted | 18.3
2021-07-10 | 2021 | 7 | Rothamsted | 20
2021-07-11 | 2021 | 7 | Rothamsted | 20.9
2021-07-12 | 2021 | 7 | Rothamsted | 20.9
2021-07-13 | 2021 | 7 | Rothamsted | 23.1
2021-07-14 | 2021 | 7 | Rothamsted | 20
2021-07-15 | 2021 | 7 | Rothamsted | 24.8
2021-07-16 | 2021 | 7 | Rothamsted | 26.7
2021-07-17 | 2021 | 7 | Rothamsted | 29.2
2021-07-18 | 2021 | 7 | Rothamsted | 28.4
2021-07-19 | 2021 | 7 | Rothamsted | 29.3
2021-07-20 | 2021 | 7 | Rothamsted | 28.1
2021-07-21 | 2021 | 7 | Rothamsted | 27.3
2021-07-22 | 2021 | 7 | Rothamsted | 23
2021-07-23 | 2021 | 7 | Rothamsted | 21.6
2021-07-24 | 2021 | 7 | Rothamsted | 19.9
2021-07-25 | 2021 | 7 | Rothamsted | 23.9
2021-07-26 | 2021 | 7 | Rothamsted | 22
2021-07-27 | 2021 | 7 | Rothamsted | 19.5
2021-07-28 | 2021 | 7 | Rothamsted | 21
2021-07-29 | 2021 | 7 | Rothamsted | 16.3
2021-07-30 | 2021 | 7 | Rothamsted | 20.2
2021-07-31 | 2021 | 7 | Rothamsted | 18.1
2021-08-01 | 2021 | 8 | Rothamsted | 19.5
2021-08-02 | 2021 | 8 | Rothamsted | 20.4
2021-08-03 | 2021 | 8 | Rothamsted | 21.5
2021-08-04 | 2021 | 8 | Rothamsted | 20
2021-08-05 | 2021 | 8 | Rothamsted | 21.1
2021-08-06 | 2021 | 8 | Rothamsted | 19.4
2021-08-07 | 2021 | 8 | Rothamsted | 19.4
2021-08-08 | 2021 | 8 | Rothamsted | 20.6
2021-08-09 | 2021 | 8 | Rothamsted | 22.1
2021-08-10 | 2021 | 8 | Rothamsted | 22.5
2021-08-11 | 2021 | 8 | Rothamsted | 20.6
2021-08-12 | 2021 | 8 | Rothamsted | 21.1
2021-08-13 | 2021 | 8 | Rothamsted | 23.2
2021-08-14 | 2021 | 8 | Rothamsted | 22.6
2021-08-15 | 2021 | 8 | Rothamsted | 17.5
2021-08-16 | 2021 | 8 | Rothamsted | 17.9
2021-08-17 | 2021 | 8 | Rothamsted | 21.8
2021-08-18 | 2021 | 8 | Rothamsted | 21.2
2021-08-19 | 2021 | 8 | Rothamsted | 20.1
2021-08-20 | 2021 | 8 | Rothamsted | 18.7
2021-08-21 | 2021 | 8 | Rothamsted | 21.3
2021-08-22 | 2021 | 8 | Rothamsted | 20.2
2021-08-23 | 2021 | 8 | Rothamsted | 22
2021-08-24 | 2021 | 8 | Rothamsted | 19.4
2021-08-25 | 2021 | 8 | Rothamsted | 17.4
2021-08-26 | 2021 | 8 | Rothamsted | 17
2021-08-27 | 2021 | 8 | Rothamsted | 19.7
2021-08-28 | 2021 | 8 | Rothamsted | 17.5
2021-08-29 | 2021 | 8 | Rothamsted | 15.8
2021-08-30 | 2021 | 8 | Rothamsted | 16.9
2021-08-31 | 2021 | 8 | Rothamsted | 17.1
2021-09-01 | 2021 | 9 | Rothamsted | 18.5
2021-09-02 | 2021 | 9 | Rothamsted | 20.2
2021-09-03 | 2021 | 9 | Rothamsted | 17.8
2021-09-04 | 2021 | 9 | Rothamsted | 24.4
2021-09-05 | 2021 | 9 | Rothamsted | 26.6
2021-09-06 | 2021 | 9 | Rothamsted | 27.7
2021-09-07 | 2021 | 9 | Rothamsted | 27.9
2021-09-08 | 2021 | 9 | Rothamsted | 21.9
2021-09-09 | 2021 | 9 | Rothamsted | 21.6
2021-09-10 | 2021 | 9 | Rothamsted | 21.9
2021-09-11 | 2021 | 9 | Rothamsted | 20.3
2021-09-12 | 2021 | 9 | Rothamsted | 19.4
2021-09-13 | 2021 | 9 | Rothamsted | 18.3
2021-09-14 | 2021 | 9 | Rothamsted | 20.4
2021-09-15 | 2021 | 9 | Rothamsted | 22.2
2021-09-16 | 2021 | 9 | Rothamsted | 20.1
2021-09-17 | 2021 | 9 | Rothamsted | 22.7
2021-09-18 | 2021 | 9 | Rothamsted | 17.6
2021-09-19 | 2021 | 9 | Rothamsted | 19.1
2021-09-20 | 2021 | 9 | Rothamsted | 20.9
2021-09-21 | 2021 | 9 | Rothamsted | 20.8
2021-09-22 | 2021 | 9 | Rothamsted | 22
2021-09-23 | 2021 | 9 | Rothamsted | 23.5
2021-09-24 | 2021 | 9 | Rothamsted | 17.5
2021-09-25 | 2021 | 9 | Rothamsted | 22
2021-09-26 | 2021 | 9 | Rothamsted | 17.3
2021-09-27 | 2021 | 9 | Rothamsted | 17.2
2021-09-28 | 2021 | 9 | Rothamsted | 14.3
2021-09-29 | 2021 | 9 | Rothamsted | 15.4
2021-09-30 | 2021 | 9 | Rothamsted | 17
2022-05-01 | 2022 | 5 | Rothamsted | 16.2
2022-05-02 | 2022 | 5 | Rothamsted | 13.7
2022-05-03 | 2022 | 5 | Rothamsted | 16.2
2022-05-04 | 2022 | 5 | Rothamsted | 17.9
2022-05-05 | 2022 | 5 | Rothamsted | 20.2
2022-05-06 | 2022 | 5 | Rothamsted | 18.3
2022-05-07 | 2022 | 5 | Rothamsted | 18.1
2022-05-08 | 2022 | 5 | Rothamsted | 20.8
2022-05-09 | 2022 | 5 | Rothamsted | 18.5
2022-05-11 | 2022 | 5 | Rothamsted | 16.9
2022-05-12 | 2022 | 5 | Rothamsted | 19
2022-05-13 | 2022 | 5 | Rothamsted | 21.7
2022-05-14 | 2022 | 5 | Rothamsted | 18.4
2022-05-15 | 2022 | 5 | Rothamsted | 21
2022-05-16 | 2022 | 5 | Rothamsted | 24.6
2022-05-17 | 2022 | 5 | Rothamsted | 21.9
2022-05-18 | 2022 | 5 | Rothamsted | 19.8
2022-05-19 | 2022 | 5 | Rothamsted | 17
2022-05-20 | 2022 | 5 | Rothamsted | 18.5
2022-05-21 | 2022 | 5 | Rothamsted | 21.9
2022-05-22 | 2022 | 5 | Rothamsted | 18.2
2022-05-23 | 2022 | 5 | Rothamsted | 16.5
2022-05-24 | 2022 | 5 | Rothamsted | 19
2022-05-25 | 2022 | 5 | Rothamsted | 18.9
2022-05-26 | 2022 | 5 | Rothamsted | 18.6
2022-05-27 | 2022 | 5 | Rothamsted | 16.8
2022-05-28 | 2022 | 5 | Rothamsted | 15.2
2022-05-29 | 2022 | 5 | Rothamsted | 13.1
2022-05-30 | 2022 | 5 | Rothamsted | 14.1
2022-05-31 | 2022 | 5 | Rothamsted | 16.9
2022-06-01 | 2022 | 6 | Rothamsted | 18.9
2022-06-02 | 2022 | 6 | Rothamsted | 21.6
2022-06-03 | 2022 | 6 | Rothamsted | 18.8
2022-06-05 | 2022 | 6 | Rothamsted | 16.8
2022-06-06 | 2022 | 6 | Rothamsted | 21.6
2022-06-07 | 2022 | 6 | Rothamsted | 20.1
2022-06-08 | 2022 | 6 | Rothamsted | 19.3
2022-06-09 | 2022 | 6 | Rothamsted | 22.1
2022-06-10 | 2022 | 6 | Rothamsted | 21.7
2022-06-11 | 2022 | 6 | Rothamsted | 20.5
2022-06-12 | 2022 | 6 | Rothamsted | 18.8
2022-06-13 | 2022 | 6 | Rothamsted | 23.2
2022-06-14 | 2022 | 6 | Rothamsted | 25.5
2022-06-15 | 2022 | 6 | Rothamsted | 27.2
2022-06-16 | 2022 | 6 | Rothamsted | 30.7
2022-06-19 | 2022 | 6 | Rothamsted | 20.1
2022-06-20 | 2022 | 6 | Rothamsted | 24.5
2022-06-21 | 2022 | 6 | Rothamsted | 25.8
2022-06-22 | 2022 | 6 | Rothamsted | 23.3
2022-06-23 | 2022 | 6 | Rothamsted | 20.7
2022-06-24 | 2022 | 6 | Rothamsted | 20
2022-06-25 | 2022 | 6 | Rothamsted | 20.8
2022-06-26 | 2022 | 6 | Rothamsted | 17.9
2022-06-27 | 2022 | 6 | Rothamsted | 20.7
2022-06-28 | 2022 | 6 | Rothamsted | 20.6
2022-06-29 | 2022 | 6 | Rothamsted | 17.8
2022-06-30 | 2022 | 6 | Rothamsted | 18.4
2022-07-01 | 2022 | 7 | Rothamsted | 20.5
2022-07-02 | 2022 | 7 | Rothamsted | 20.7
2022-07-03 | 2022 | 7 | Rothamsted | 20.2
2022-07-04 | 2022 | 7 | Rothamsted | 21
2022-07-05 | 2022 | 7 | Rothamsted | 22.5
2022-07-06 | 2022 | 7 | Rothamsted | 23.3
2022-07-07 | 2022 | 7 | Rothamsted | 26.9
2022-07-08 | 2022 | 7 | Rothamsted | 25.3
2022-07-09 | 2022 | 7 | Rothamsted | 27.7
2022-07-10 | 2022 | 7 | Rothamsted | 30.2
2022-07-11 | 2022 | 7 | Rothamsted | 28.4
2022-07-12 | 2022 | 7 | Rothamsted | 26.2
2022-07-13 | 2022 | 7 | Rothamsted | 23.4
2022-07-14 | 2022 | 7 | Rothamsted | 24.4
2022-07-15 | 2022 | 7 | Rothamsted | 27.4
2022-07-16 | 2022 | 7 | Rothamsted | 29.5
2022-07-17 | 2022 | 7 | Rothamsted | 35.9
2022-07-18 | 2022 | 7 | Rothamsted | 38.5
2022-07-20 | 2022 | 7 | Rothamsted | 22.9
2022-07-21 | 2022 | 7 | Rothamsted | 22.1
2022-07-22 | 2022 | 7 | Rothamsted | 25.3
2022-07-23 | 2022 | 7 | Rothamsted | 27.7
2022-07-25 | 2022 | 7 | Rothamsted | 20.8
2022-07-26 | 2022 | 7 | Rothamsted | 23.1
2022-07-27 | 2022 | 7 | Rothamsted | 22.2
2022-07-28 | 2022 | 7 | Rothamsted | 25.2
2022-07-29 | 2022 | 7 | Rothamsted | 24.2
2022-07-30 | 2022 | 7 | Rothamsted | 25.6
2022-07-31 | 2022 | 7 | Rothamsted | 26.1
2022-08-01 | 2022 | 8 | Rothamsted | 26.8
2022-08-02 | 2022 | 8 | Rothamsted | 25.5
2022-08-03 | 2022 | 8 | Rothamsted | 22.7
2022-08-04 | 2022 | 8 | Rothamsted | 22.1
2022-08-05 | 2022 | 8 | Rothamsted | 22.7
2022-08-06 | 2022 | 8 | Rothamsted | 25.7
2022-08-07 | 2022 | 8 | Rothamsted | 27.1
2022-08-08 | 2022 | 8 | Rothamsted | 27.9
2022-08-09 | 2022 | 8 | Rothamsted | 29
2022-08-10 | 2022 | 8 | Rothamsted | 31.6
2022-08-11 | 2022 | 8 | Rothamsted | 32
2022-08-12 | 2022 | 8 | Rothamsted | 32.3
2022-08-13 | 2022 | 8 | Rothamsted | 31.6
2022-08-14 | 2022 | 8 | Rothamsted | 29.1
2022-08-15 | 2022 | 8 | Rothamsted | 23.7
2022-08-16 | 2022 | 8 | Rothamsted | 23.1
2022-08-17 | 2022 | 8 | Rothamsted | 25
2022-08-18 | 2022 | 8 | Rothamsted | 23
2022-08-19 | 2022 | 8 | Rothamsted | 23.8
2022-08-20 | 2022 | 8 | Rothamsted | 23.5
2022-08-21 | 2022 | 8 | Rothamsted | 22.3
2022-08-22 | 2022 | 8 | Rothamsted | 24.6
2022-08-23 | 2022 | 8 | Rothamsted | 27.9
2022-08-25 | 2022 | 8 | Rothamsted | 22.8
2022-08-26 | 2022 | 8 | Rothamsted | 23.4
2022-08-27 | 2022 | 8 | Rothamsted | 23
2022-08-28 | 2022 | 8 | Rothamsted | 21.7
2022-08-29 | 2022 | 8 | Rothamsted | 22.7
2022-08-30 | 2022 | 8 | Rothamsted | 22.5
2022-08-31 | 2022 | 8 | Rothamsted | 22.7
2022-09-01 | 2022 | 9 | Rothamsted | 24.3
2022-09-02 | 2022 | 9 | Rothamsted | 22.5
2022-09-03 | 2022 | 9 | Rothamsted | 23
2022-09-04 | 2022 | 9 | Rothamsted | 22.6
2022-09-05 | 2022 | 9 | Rothamsted | 21
2022-09-06 | 2022 | 9 | Rothamsted | 20.3
2022-09-07 | 2022 | 9 | Rothamsted | 17.3
2022-09-08 | 2022 | 9 | Rothamsted | 18.5
2022-09-09 | 2022 | 9 | Rothamsted | 20.3
2022-09-10 | 2022 | 9 | Rothamsted | 22
2022-09-11 | 2022 | 9 | Rothamsted | 24.8
2022-09-13 | 2022 | 9 | Rothamsted | 20.9
2022-09-14 | 2022 | 9 | Rothamsted | 17.3
2022-09-15 | 2022 | 9 | Rothamsted | 15.7
2022-09-16 | 2022 | 9 | Rothamsted | 16.2
2022-09-17 | 2022 | 9 | Rothamsted | 16.7
2022-09-18 | 2022 | 9 | Rothamsted | 16.8
2022-09-19 | 2022 | 9 | Rothamsted | 17.5
2022-09-20 | 2022 | 9 | Rothamsted | 18.8
2022-09-21 | 2022 | 9 | Rothamsted | 19.3
2022-09-22 | 2022 | 9 | Rothamsted | 17.8
2022-09-23 | 2022 | 9 | Rothamsted | 17.7
2022-09-24 | 2022 | 9 | Rothamsted | 15.2
2022-09-25 | 2022 | 9 | Rothamsted | 13.9
2022-09-26 | 2022 | 9 | Rothamsted | 13.4
2022-09-27 | 2022 | 9 | Rothamsted | 13.8
2022-09-28 | 2022 | 9 | Rothamsted | 15.3
2022-09-29 | 2022 | 9 | Rothamsted | 15
2022-09-30 | 2022 | 9 | Rothamsted | 18
2023-05-01 | 2023 | 5 | Rothamsted | 13.7
2023-05-02 | 2023 | 5 | Rothamsted | 13.5
2023-05-03 | 2023 | 5 | Rothamsted | 17.6
2023-05-04 | 2023 | 5 | Rothamsted | 18.5
2023-05-06 | 2023 | 5 | Rothamsted | 19.6
2023-05-08 | 2023 | 5 | Rothamsted | 17.2
2023-05-09 | 2023 | 5 | Rothamsted | 17.1
2023-05-10 | 2023 | 5 | Rothamsted | 17.5
2023-05-12 | 2023 | 5 | Rothamsted | 11.2
2023-05-13 | 2023 | 5 | Rothamsted | 19.3
2023-05-14 | 2023 | 5 | Rothamsted | 14.7
2023-05-15 | 2023 | 5 | Rothamsted | 16
2023-05-16 | 2023 | 5 | Rothamsted | 16.6
2023-05-17 | 2023 | 5 | Rothamsted | 18.5
2023-05-18 | 2023 | 5 | Rothamsted | 15.4
2023-05-19 | 2023 | 5 | Rothamsted | 18.1
2023-05-20 | 2023 | 5 | Rothamsted | 17.8
2023-05-21 | 2023 | 5 | Rothamsted | 18
2023-05-22 | 2023 | 5 | Rothamsted | 16.7
2023-05-23 | 2023 | 5 | Rothamsted | 19.7
2023-05-24 | 2023 | 5 | Rothamsted | 16.3
2023-05-25 | 2023 | 5 | Rothamsted | 18.2
2023-05-26 | 2023 | 5 | Rothamsted | 19.4
2023-05-27 | 2023 | 5 | Rothamsted | 20.8
2023-05-28 | 2023 | 5 | Rothamsted | 16.9
2023-05-29 | 2023 | 5 | Rothamsted | 15.7
2023-05-30 | 2023 | 5 | Rothamsted | 15.4
2023-05-31 | 2023 | 5 | Rothamsted | 16.6
2023-06-01 | 2023 | 6 | Rothamsted | 17
2023-06-02 | 2023 | 6 | Rothamsted | 20.6
2023-06-03 | 2023 | 6 | Rothamsted | 20.5
2023-06-04 | 2023 | 6 | Rothamsted | 15.5
2023-06-05 | 2023 | 6 | Rothamsted | 14.7
2023-06-06 | 2023 | 6 | Rothamsted | 20.2
2023-06-07 | 2023 | 6 | Rothamsted | 20.9
2023-06-08 | 2023 | 6 | Rothamsted | 24.3
2023-06-09 | 2023 | 6 | Rothamsted | 29.2
2023-06-10 | 2023 | 6 | Rothamsted | 29.8
2023-06-11 | 2023 | 6 | Rothamsted | 28
2023-06-12 | 2023 | 6 | Rothamsted | 27.8
2023-06-13 | 2023 | 6 | Rothamsted | 27.2
2023-06-14 | 2023 | 6 | Rothamsted | 26.1
2023-06-15 | 2023 | 6 | Rothamsted | 25.4
2023-06-16 | 2023 | 6 | Rothamsted | 24.6
2023-06-17 | 2023 | 6 | Rothamsted | 26.4
2023-06-18 | 2023 | 6 | Rothamsted | 24.2
2023-06-19 | 2023 | 6 | Rothamsted | 22.2
2023-06-20 | 2023 | 6 | Rothamsted | 24.8
2023-06-21 | 2023 | 6 | Rothamsted | 26.8
2023-06-22 | 2023 | 6 | Rothamsted | 26.2
2023-06-23 | 2023 | 6 | Rothamsted | 26.9
2023-06-24 | 2023 | 6 | Rothamsted | 29.8
2023-06-25 | 2023 | 6 | Rothamsted | 21.9
2023-06-26 | 2023 | 6 | Rothamsted | 21.4
2023-06-27 | 2023 | 6 | Rothamsted | 24.4
2023-06-28 | 2023 | 6 | Rothamsted | 21.7
2023-06-29 | 2023 | 6 | Rothamsted | 18.1
2023-06-30 | 2023 | 6 | Rothamsted | 22
2023-07-01 | 2023 | 7 | Rothamsted | 19.9
2023-07-02 | 2023 | 7 | Rothamsted | 18.7
2023-07-03 | 2023 | 7 | Rothamsted | 16.4
2023-07-04 | 2023 | 7 | Rothamsted | 19.6
2023-07-05 | 2023 | 7 | Rothamsted | 21.5
2023-07-06 | 2023 | 7 | Rothamsted | 28.4
2023-07-07 | 2023 | 7 | Rothamsted | 24.7
2023-07-08 | 2023 | 7 | Rothamsted | 23
2023-07-09 | 2023 | 7 | Rothamsted | 23.3
2023-07-10 | 2023 | 7 | Rothamsted | 22
2023-07-11 | 2023 | 7 | Rothamsted | 21.4
2023-07-12 | 2023 | 7 | Rothamsted | 21.7
2023-07-13 | 2023 | 7 | Rothamsted | 18.3
2023-07-14 | 2023 | 7 | Rothamsted | 20.3
2023-07-15 | 2023 | 7 | Rothamsted | 20.6
2023-07-16 | 2023 | 7 | Rothamsted | 22.6
2023-07-17 | 2023 | 7 | Rothamsted | 21.6
2023-07-18 | 2023 | 7 | Rothamsted | 22
2023-07-19 | 2023 | 7 | Rothamsted | 22.1
2023-07-20 | 2023 | 7 | Rothamsted | 19.7
2023-07-21 | 2023 | 7 | Rothamsted | 18.2
2023-07-22 | 2023 | 7 | Rothamsted | 22.2
2023-07-24 | 2023 | 7 | Rothamsted | 19.5
2023-07-25 | 2023 | 7 | Rothamsted | 21
2023-07-26 | 2023 | 7 | Rothamsted | 22.6
2023-07-27 | 2023 | 7 | Rothamsted | 21.7
2023-07-28 | 2023 | 7 | Rothamsted | 22.4
2023-07-29 | 2023 | 7 | Rothamsted | 20
2023-07-30 | 2023 | 7 | Rothamsted | 18.6
2023-07-31 | 2023 | 7 | Rothamsted | 21.8
2023-08-01 | 2023 | 8 | Rothamsted | 18.8
2023-08-02 | 2023 | 8 | Rothamsted | 20.7
2023-08-03 | 2023 | 8 | Rothamsted | 18.1
2023-08-04 | 2023 | 8 | Rothamsted | 17.6
2023-08-05 | 2023 | 8 | Rothamsted | 18.8
2023-08-06 | 2023 | 8 | Rothamsted | 20.6
2023-08-07 | 2023 | 8 | Rothamsted | 16.9
2023-08-08 | 2023 | 8 | Rothamsted | 23.3
2023-08-09 | 2023 | 8 | Rothamsted | 25.4
2023-08-10 | 2023 | 8 | Rothamsted | 24.5
2023-08-11 | 2023 | 8 | Rothamsted | 21.6
2023-08-12 | 2023 | 8 | Rothamsted | 21
2023-08-13 | 2023 | 8 | Rothamsted | 20.7
2023-08-14 | 2023 | 8 | Rothamsted | 23.4
2023-08-15 | 2023 | 8 | Rothamsted | 24.7
2023-08-16 | 2023 | 8 | Rothamsted | 23.2
2023-08-17 | 2023 | 8 | Rothamsted | 22.8
2023-08-18 | 2023 | 8 | Rothamsted | 23.4
2023-08-19 | 2023 | 8 | Rothamsted | 23.3
2023-08-20 | 2023 | 8 | Rothamsted | 23.7
2023-08-21 | 2023 | 8 | Rothamsted | 24.1
2023-08-22 | 2023 | 8 | Rothamsted | 25.2
2023-08-23 | 2023 | 8 | Rothamsted | 25
2023-08-24 | 2023 | 8 | Rothamsted | 19.8
2023-08-25 | 2023 | 8 | Rothamsted | 19.1
2023-08-26 | 2023 | 8 | Rothamsted | 17.9
2023-08-27 | 2023 | 8 | Rothamsted | 19.3
2023-08-28 | 2023 | 8 | Rothamsted | 19.5
2023-08-29 | 2023 | 8 | Rothamsted | 19.2
2023-08-30 | 2023 | 8 | Rothamsted | 17.4
2023-08-31 | 2023 | 8 | Rothamsted | 20.8
2023-09-01 | 2023 | 9 | Rothamsted | 22.9
2023-09-02 | 2023 | 9 | Rothamsted | 24.5
2023-09-03 | 2023 | 9 | Rothamsted | 27.8
2023-09-04 | 2023 | 9 | Rothamsted | 28.7
2023-09-05 | 2023 | 9 | Rothamsted | 29.4
2023-09-06 | 2023 | 9 | Rothamsted | 30.3
2023-09-07 | 2023 | 9 | Rothamsted | 29
2023-09-08 | 2023 | 9 | Rothamsted | 30.9
2023-09-09 | 2023 | 9 | Rothamsted | 29.9
2023-09-10 | 2023 | 9 | Rothamsted | 24.1
2023-09-11 | 2023 | 9 | Rothamsted | 22.6
2023-09-12 | 2023 | 9 | Rothamsted | 20.2
2023-09-13 | 2023 | 9 | Rothamsted | 22.7
2023-09-14 | 2023 | 9 | Rothamsted | 24.9
2023-09-15 | 2023 | 9 | Rothamsted | 25.2
2023-09-16 | 2023 | 9 | Rothamsted | 19.8
2023-09-17 | 2023 | 9 | Rothamsted | 18.7
2023-09-18 | 2023 | 9 | Rothamsted | 18.2
2023-09-19 | 2023 | 9 | Rothamsted | 18.5
2023-09-20 | 2023 | 9 | Rothamsted | 17.4
2023-09-21 | 2023 | 9 | Rothamsted | 16.9
2023-09-22 | 2023 | 9 | Rothamsted | 17.1
2023-09-23 | 2023 | 9 | Rothamsted | 20.3
2023-09-24 | 2023 | 9 | Rothamsted | 21
2023-09-25 | 2023 | 9 | Rothamsted | 21.3
2023-09-26 | 2023 | 9 | Rothamsted | 20.2
2023-09-27 | 2023 | 9 | Rothamsted | 17.9
2023-09-28 | 2023 | 9 | Rothamsted | 18.1
2023-09-29 | 2023 | 9 | Rothamsted | 18.2
2023-09-30 | 2023 | 9 | Rothamsted | 21.4
2024-05-01 | 2024 | 5 | Rothamsted | 14.6
2024-05-03 | 2024 | 5 | Rothamsted | 16.9
2024-05-04 | 2024 | 5 | Rothamsted | 18.6
2024-05-05 | 2024 | 5 | Rothamsted | 14
2024-05-06 | 2024 | 5 | Rothamsted | 17.1
2024-05-07 | 2024 | 5 | Rothamsted | 19.5
2024-05-08 | 2024 | 5 | Rothamsted | 22.1
2024-05-09 | 2024 | 5 | Rothamsted | 22.5
2024-05-10 | 2024 | 5 | Rothamsted | 21.6
2024-05-11 | 2024 | 5 | Rothamsted | 24.8
2024-05-12 | 2024 | 5 | Rothamsted | 17.7
2024-05-13 | 2024 | 5 | Rothamsted | 16.4
2024-05-14 | 2024 | 5 | Rothamsted | 20.3
2024-05-15 | 2024 | 5 | Rothamsted | 18.1
2024-05-16 | 2024 | 5 | Rothamsted | 20.6
2024-05-17 | 2024 | 5 | Rothamsted | 18.1
2024-05-18 | 2024 | 5 | Rothamsted | 20.7
2024-05-19 | 2024 | 5 | Rothamsted | 19
2024-05-20 | 2024 | 5 | Rothamsted | 14.5
2024-05-21 | 2024 | 5 | Rothamsted | 15
2024-05-22 | 2024 | 5 | Rothamsted | 16.8
2024-05-23 | 2024 | 5 | Rothamsted | 16.9
2024-05-24 | 2024 | 5 | Rothamsted | 19.4
2024-05-25 | 2024 | 5 | Rothamsted | 18.4
2024-05-26 | 2024 | 5 | Rothamsted | 16.3
2024-05-27 | 2024 | 5 | Rothamsted | 16.7
2024-05-28 | 2024 | 5 | Rothamsted | 18.8
2024-05-29 | 2024 | 5 | Rothamsted | 17.2
2024-05-31 | 2024 | 5 | Rothamsted | 15.8
2024-06-01 | 2024 | 6 | Rothamsted | 21.8
2024-06-02 | 2024 | 6 | Rothamsted | 19
2024-06-03 | 2024 | 6 | Rothamsted | 17.4
2024-06-04 | 2024 | 6 | Rothamsted | 15.6
2024-06-05 | 2024 | 6 | Rothamsted | 17.5
2024-06-06 | 2024 | 6 | Rothamsted | 18.4
2024-06-07 | 2024 | 6 | Rothamsted | 18.1
2024-06-08 | 2024 | 6 | Rothamsted | 14.5
2024-06-09 | 2024 | 6 | Rothamsted | 14.8
2024-06-10 | 2024 | 6 | Rothamsted | 14.4
2024-06-11 | 2024 | 6 | Rothamsted | 15.4
2024-06-12 | 2024 | 6 | Rothamsted | 15.4
2024-06-13 | 2024 | 6 | Rothamsted | 17.4
2024-06-14 | 2024 | 6 | Rothamsted | 17.2
2024-06-15 | 2024 | 6 | Rothamsted | 19.4
2024-06-16 | 2024 | 6 | Rothamsted | 21.5
2024-06-17 | 2024 | 6 | Rothamsted | 20.1
2024-06-18 | 2024 | 6 | Rothamsted | 19.3
2024-06-19 | 2024 | 6 | Rothamsted | 21
2024-06-20 | 2024 | 6 | Rothamsted | 22.8
2024-06-21 | 2024 | 6 | Rothamsted | 21.5
2024-06-22 | 2024 | 6 | Rothamsted | 24
2024-06-23 | 2024 | 6 | Rothamsted | 26.4
2024-06-24 | 2024 | 6 | Rothamsted | 27.3
2024-06-25 | 2024 | 6 | Rothamsted | 27.6
2024-06-26 | 2024 | 6 | Rothamsted | 22.3
2024-06-27 | 2024 | 6 | Rothamsted | 19.5
2024-06-28 | 2024 | 6 | Rothamsted | 23
2024-06-29 | 2024 | 6 | Rothamsted | 18.4
2024-06-30 | 2024 | 6 | Rothamsted | 18.3
2024-07-01 | 2024 | 7 | Rothamsted | 18.4
2024-07-02 | 2024 | 7 | Rothamsted | 17.4
2024-07-03 | 2024 | 7 | Rothamsted | 19
2024-07-04 | 2024 | 7 | Rothamsted | 20.1
2024-07-05 | 2024 | 7 | Rothamsted | 15.9
2024-07-06 | 2024 | 7 | Rothamsted | 17.7
2024-07-07 | 2024 | 7 | Rothamsted | 19.4
2024-07-08 | 2024 | 7 | Rothamsted | 18.9
2024-07-09 | 2024 | 7 | Rothamsted | 20.9
2024-07-10 | 2024 | 7 | Rothamsted | 21.8
2024-07-12 | 2024 | 7 | Rothamsted | 17.8
2024-07-13 | 2024 | 7 | Rothamsted | 20.4
2024-07-14 | 2024 | 7 | Rothamsted | 19.6
2024-07-15 | 2024 | 7 | Rothamsted | 20.7
2024-07-16 | 2024 | 7 | Rothamsted | 22.5
2024-07-17 | 2024 | 7 | Rothamsted | 26.1
2024-07-18 | 2024 | 7 | Rothamsted | 29.6
2024-07-19 | 2024 | 7 | Rothamsted | 22.4
2024-07-20 | 2024 | 7 | Rothamsted | 21.8
2024-07-21 | 2024 | 7 | Rothamsted | 24.6
2024-07-22 | 2024 | 7 | Rothamsted | 22.9
2024-07-23 | 2024 | 7 | Rothamsted | 23.3
2024-07-24 | 2024 | 7 | Rothamsted | 20.5
2024-07-25 | 2024 | 7 | Rothamsted | 22.2
2024-07-26 | 2024 | 7 | Rothamsted | 22.2
2024-07-27 | 2024 | 7 | Rothamsted | 24.7
2024-07-28 | 2024 | 7 | Rothamsted | 27.1
2024-07-29 | 2024 | 7 | Rothamsted | 29.4
2024-07-30 | 2024 | 7 | Rothamsted | 27.8
2024-07-31 | 2024 | 7 | Rothamsted | 27.6
2024-08-01 | 2024 | 8 | Rothamsted | 26.4
2024-08-02 | 2024 | 8 | Rothamsted | 22.5
2024-08-03 | 2024 | 8 | Rothamsted | 22.2
2024-08-04 | 2024 | 8 | Rothamsted | 24.4
2024-08-05 | 2024 | 8 | Rothamsted | 20.8
2024-08-06 | 2024 | 8 | Rothamsted | 20.7
2024-08-07 | 2024 | 8 | Rothamsted | 20
2024-08-08 | 2024 | 8 | Rothamsted | 23.3
2024-08-09 | 2024 | 8 | Rothamsted | 23.5
2024-08-10 | 2024 | 8 | Rothamsted | 26.9
2024-08-11 | 2024 | 8 | Rothamsted | 31.9
2024-08-12 | 2024 | 8 | Rothamsted | 25.5
2024-08-13 | 2024 | 8 | Rothamsted | 22
2024-08-14 | 2024 | 8 | Rothamsted | 23.1
2024-08-15 | 2024 | 8 | Rothamsted | 23.6
2024-08-16 | 2024 | 8 | Rothamsted | 21.9
2024-08-17 | 2024 | 8 | Rothamsted | 22.2
2024-08-18 | 2024 | 8 | Rothamsted | 19.3
2024-08-19 | 2024 | 8 | Rothamsted | 21.9
2024-08-20 | 2024 | 8 | Rothamsted | 19.4
2024-08-21 | 2024 | 8 | Rothamsted | 19.2
2024-08-22 | 2024 | 8 | Rothamsted | 21.7
2024-08-24 | 2024 | 8 | Rothamsted | 19.5
2024-08-25 | 2024 | 8 | Rothamsted | 21.1
2024-08-26 | 2024 | 8 | Rothamsted | 23.8
2024-08-27 | 2024 | 8 | Rothamsted | 27.6
2024-08-28 | 2024 | 8 | Rothamsted | 21.2
2024-08-29 | 2024 | 8 | Rothamsted | 21.4
2024-08-30 | 2024 | 8 | Rothamsted | 19
2024-08-31 | 2024 | 8 | Rothamsted | 28.3
2024-09-02 | 2024 | 9 | Rothamsted | 21.4
2024-09-03 | 2024 | 9 | Rothamsted | 19.1
2024-09-04 | 2024 | 9 | Rothamsted | 18.3
2024-09-05 | 2024 | 9 | Rothamsted | 23.5
2024-09-06 | 2024 | 9 | Rothamsted | 21.1
2024-09-07 | 2024 | 9 | Rothamsted | 20.6
2024-09-08 | 2024 | 9 | Rothamsted | 16.3
2024-09-09 | 2024 | 9 | Rothamsted | 17.2
2024-09-10 | 2024 | 9 | Rothamsted | 15.3
2024-09-11 | 2024 | 9 | Rothamsted | 13.5
2024-09-12 | 2024 | 9 | Rothamsted | 16
2024-09-13 | 2024 | 9 | Rothamsted | 18.3
2024-09-14 | 2024 | 9 | Rothamsted | 18.6
2024-09-15 | 2024 | 9 | Rothamsted | 18.7
2024-09-16 | 2024 | 9 | Rothamsted | 19.5
2024-09-17 | 2024 | 9 | Rothamsted | 22.2
2024-09-18 | 2024 | 9 | Rothamsted | 23.2
2024-09-19 | 2024 | 9 | Rothamsted | 22.6
2024-09-20 | 2024 | 9 | Rothamsted | 22.9
2024-09-21 | 2024 | 9 | Rothamsted | 19.4
2024-09-23 | 2024 | 9 | Rothamsted | 15.7
2024-09-24 | 2024 | 9 | Rothamsted | 15.6
2024-09-25 | 2024 | 9 | Rothamsted | 17.1
2024-09-27 | 2024 | 9 | Rothamsted | 14.3
2024-09-28 | 2024 | 9 | Rothamsted | 14.1
2024-09-29 | 2024 | 9 | Rothamsted | 16.5
2024-09-30 | 2024 | 9 | Rothamsted | 13.6
2025-05-01 | 2025 | 5 | Rothamsted | 21.1
2025-05-02 | 2025 | 5 | Rothamsted | 18.2
2025-05-04 | 2025 | 5 | Rothamsted | 14
2025-05-05 | 2025 | 5 | Rothamsted | 13.6
2025-05-06 | 2025 | 5 | Rothamsted | 15
2025-05-07 | 2025 | 5 | Rothamsted | 14.4
2025-05-08 | 2025 | 5 | Rothamsted | 18.3
2025-05-09 | 2025 | 5 | Rothamsted | 20.4
2025-05-10 | 2025 | 5 | Rothamsted | 23
2025-05-11 | 2025 | 5 | Rothamsted | 24
2025-05-12 | 2025 | 5 | Rothamsted | 23.2
2025-05-13 | 2025 | 5 | Rothamsted | 21
2025-05-15 | 2025 | 5 | Rothamsted | 16.8
2025-05-16 | 2025 | 5 | Rothamsted | 16.1
2025-05-17 | 2025 | 5 | Rothamsted | 15.5
2025-05-18 | 2025 | 5 | Rothamsted | 19.8
2025-05-19 | 2025 | 5 | Rothamsted | 20.4
2025-05-20 | 2025 | 5 | Rothamsted | 18.2
2025-05-22 | 2025 | 5 | Rothamsted | 20.2
2025-05-23 | 2025 | 5 | Rothamsted | 19.3
2025-05-24 | 2025 | 5 | Rothamsted | 18.2
2025-05-25 | 2025 | 5 | Rothamsted | 17.6
2025-05-26 | 2025 | 5 | Rothamsted | 16.1
2025-05-27 | 2025 | 5 | Rothamsted | 19.5
2025-05-28 | 2025 | 5 | Rothamsted | 23.4
2025-05-29 | 2025 | 5 | Rothamsted | 23.2
2025-05-30 | 2025 | 5 | Rothamsted | 23.9
2025-05-31 | 2025 | 5 | Rothamsted | 19.7
2025-06-01 | 2025 | 6 | Rothamsted | 19.5
2025-06-02 | 2025 | 6 | Rothamsted | 17.9
2025-06-03 | 2025 | 6 | Rothamsted | 17.9
2025-06-04 | 2025 | 6 | Rothamsted | 14.7
2025-06-05 | 2025 | 6 | Rothamsted | 18
2025-06-06 | 2025 | 6 | Rothamsted | 16.6
2025-06-07 | 2025 | 6 | Rothamsted | 17.4
2025-06-08 | 2025 | 6 | Rothamsted | 19.4
2025-06-09 | 2025 | 6 | Rothamsted | 21.4
2025-06-10 | 2025 | 6 | Rothamsted | 21.9
2025-06-11 | 2025 | 6 | Rothamsted | 24.6
2025-06-12 | 2025 | 6 | Rothamsted | 27.5
2025-06-13 | 2025 | 6 | Rothamsted | 23.7
2025-06-14 | 2025 | 6 | Rothamsted | 23.3
2025-06-15 | 2025 | 6 | Rothamsted | 24.7
2025-06-16 | 2025 | 6 | Rothamsted | 25.9
2025-06-17 | 2025 | 6 | Rothamsted | 27
2025-06-18 | 2025 | 6 | Rothamsted | 29
2025-06-19 | 2025 | 6 | Rothamsted | 27.9
2025-06-20 | 2025 | 6 | Rothamsted | 30
2025-06-21 | 2025 | 6 | Rothamsted | 23.7
2025-06-22 | 2025 | 6 | Rothamsted | 21.4
2025-06-23 | 2025 | 6 | Rothamsted | 25.4
2025-06-24 | 2025 | 6 | Rothamsted | 25.3
2025-06-25 | 2025 | 6 | Rothamsted | 23.2
2025-06-26 | 2025 | 6 | Rothamsted | 26.5
2025-06-27 | 2025 | 6 | Rothamsted | 29.1
2025-06-28 | 2025 | 6 | Rothamsted | 27.8
2025-06-29 | 2025 | 6 | Rothamsted | 31.2
2025-06-30 | 2025 | 6 | Rothamsted | 31.7
2025-07-02 | 2025 | 7 | Rothamsted | 23.7
2025-07-03 | 2025 | 7 | Rothamsted | 26.3
2025-07-04 | 2025 | 7 | Rothamsted | 21.7
2025-07-05 | 2025 | 7 | Rothamsted | 21
2025-07-06 | 2025 | 7 | Rothamsted | 20.7
2025-07-07 | 2025 | 7 | Rothamsted | 23
2025-07-08 | 2025 | 7 | Rothamsted | 25.9
2025-07-09 | 2025 | 7 | Rothamsted | 29.3
2025-07-10 | 2025 | 7 | Rothamsted | 31.1
2025-07-11 | 2025 | 7 | Rothamsted | 29.6
2025-07-12 | 2025 | 7 | Rothamsted | 27.5
2025-07-13 | 2025 | 7 | Rothamsted | 24.6
2025-07-14 | 2025 | 7 | Rothamsted | 21.8
2025-07-15 | 2025 | 7 | Rothamsted | 23
2025-07-16 | 2025 | 7 | Rothamsted | 25
2025-07-17 | 2025 | 7 | Rothamsted | 28.5
2025-07-19 | 2025 | 7 | Rothamsted | 21
2025-07-20 | 2025 | 7 | Rothamsted | 23.4
2025-07-21 | 2025 | 7 | Rothamsted | 21.5
2025-07-22 | 2025 | 7 | Rothamsted | 21.8
2025-07-23 | 2025 | 7 | Rothamsted | 20.5
2025-07-24 | 2025 | 7 | Rothamsted | 25.8
2025-07-25 | 2025 | 7 | Rothamsted | 22.6
2025-07-26 | 2025 | 7 | Rothamsted | 20.2
2025-07-27 | 2025 | 7 | Rothamsted | 23.1
2025-07-28 | 2025 | 7 | Rothamsted | 19
2025-07-29 | 2025 | 7 | Rothamsted | 23.6
2025-07-30 | 2025 | 7 | Rothamsted | 24.2
2025-08-01 | 2025 | 8 | Rothamsted | 21.2
2025-08-02 | 2025 | 8 | Rothamsted | 23.5
2025-08-03 | 2025 | 8 | Rothamsted | 21.5
2025-08-04 | 2025 | 8 | Rothamsted | 20.9
2025-08-05 | 2025 | 8 | Rothamsted | 22.6
2025-08-06 | 2025 | 8 | Rothamsted | 23.6
2025-08-07 | 2025 | 8 | Rothamsted | 24.1
2025-08-08 | 2025 | 8 | Rothamsted | 24.3
2025-08-09 | 2025 | 8 | Rothamsted | 25.7
2025-08-10 | 2025 | 8 | Rothamsted | 29.1
2025-08-11 | 2025 | 8 | Rothamsted | 31.4
2025-08-12 | 2025 | 8 | Rothamsted | 27
2025-08-13 | 2025 | 8 | Rothamsted | 27
2025-08-14 | 2025 | 8 | Rothamsted | 28.2
2025-08-16 | 2025 | 8 | Rothamsted | 25.5
2025-08-17 | 2025 | 8 | Rothamsted | 21.3
2025-08-18 | 2025 | 8 | Rothamsted | 23.4
2025-08-19 | 2025 | 8 | Rothamsted | 19.5
2025-08-20 | 2025 | 8 | Rothamsted | 19.1
2025-08-21 | 2025 | 8 | Rothamsted | 21.6
2025-08-22 | 2025 | 8 | Rothamsted | 20.8
2025-08-23 | 2025 | 8 | Rothamsted | 23.9
2025-08-24 | 2025 | 8 | Rothamsted | 26.9
2025-08-25 | 2025 | 8 | Rothamsted | 25.1
2025-08-26 | 2025 | 8 | Rothamsted | 22.9
2025-08-27 | 2025 | 8 | Rothamsted | 21.1
2025-08-28 | 2025 | 8 | Rothamsted | 20.3
2025-08-29 | 2025 | 8 | Rothamsted | 20.6
2025-08-30 | 2025 | 8 | Rothamsted | 20.8
2025-08-31 | 2025 | 8 | Rothamsted | 20
2025-09-01 | 2025 | 9 | Rothamsted | 18.1
2025-09-02 | 2025 | 9 | Rothamsted | 20.2
2025-09-03 | 2025 | 9 | Rothamsted | 18.7
2025-09-04 | 2025 | 9 | Rothamsted | 21
2025-09-05 | 2025 | 9 | Rothamsted | 22.2
2025-09-06 | 2025 | 9 | Rothamsted | 24.3
2025-09-07 | 2025 | 9 | Rothamsted | 20.8
2025-09-08 | 2025 | 9 | Rothamsted | 20.6
2025-09-09 | 2025 | 9 | Rothamsted | 17.6
2025-09-10 | 2025 | 9 | Rothamsted | 18
2025-09-11 | 2025 | 9 | Rothamsted | 18.4
2025-09-12 | 2025 | 9 | Rothamsted | 16.7
2025-09-13 | 2025 | 9 | Rothamsted | 17.3
2025-09-14 | 2025 | 9 | Rothamsted | 18.1
2025-09-15 | 2025 | 9 | Rothamsted | 18.2
2025-09-16 | 2025 | 9 | Rothamsted | 19
2025-09-17 | 2025 | 9 | Rothamsted | 21.2
2025-09-18 | 2025 | 9 | Rothamsted | 25.9
2025-09-19 | 2025 | 9 | Rothamsted | 20
2025-09-21 | 2025 | 9 | Rothamsted | 15.2
2025-09-22 | 2025 | 9 | Rothamsted | 17
2025-09-23 | 2025 | 9 | Rothamsted | 17.4
2025-09-24 | 2025 | 9 | Rothamsted | 17.7
2025-09-25 | 2025 | 9 | Rothamsted | 14.4
2025-09-26 | 2025 | 9 | Rothamsted | 17.4
2025-09-27 | 2025 | 9 | Rothamsted | 15.2
2025-09-28 | 2025 | 9 | Rothamsted | 17.5
2025-09-29 | 2025 | 9 | Rothamsted | 18.8
2025-09-30 | 2025 | 9 | Rothamsted | 17.6
2026-05-01 | 2026 | 5 | Rothamsted | 21.4
2026-05-02 | 2026 | 5 | Rothamsted | 18
2026-05-04 | 2026 | 5 | Rothamsted | 15.7
2026-05-06 | 2026 | 5 | Rothamsted | 14.9
2026-05-07 | 2026 | 5 | Rothamsted | 17.2
2026-05-08 | 2026 | 5 | Rothamsted | 20.4
2026-05-09 | 2026 | 5 | Rothamsted | 12.8
2026-05-10 | 2026 | 5 | Rothamsted | 11.8
2026-05-11 | 2026 | 5 | Rothamsted | 14.3
2026-05-12 | 2026 | 5 | Rothamsted | 12.4
2026-05-13 | 2026 | 5 | Rothamsted | 12.9
2026-05-14 | 2026 | 5 | Rothamsted | 14
2026-05-15 | 2026 | 5 | Rothamsted | 12.9
2026-05-16 | 2026 | 5 | Rothamsted | 16.1
2026-05-17 | 2026 | 5 | Rothamsted | 13.7
2026-05-18 | 2026 | 5 | Rothamsted | 16.8
2026-05-19 | 2026 | 5 | Rothamsted | 20.1
2026-05-20 | 2026 | 5 | Rothamsted | 22.3
2026-05-21 | 2026 | 5 | Rothamsted | 26.9
2026-05-22 | 2026 | 5 | Rothamsted | 26.5
2026-05-23 | 2026 | 5 | Rothamsted | 29.7
2026-05-24 | 2026 | 5 | Rothamsted | 32
2026-05-25 | 2026 | 5 | Rothamsted | 32.5
2026-05-26 | 2026 | 5 | Rothamsted | 26.1
2026-05-27 | 2026 | 5 | Rothamsted | 30.1
2026-05-28 | 2026 | 5 | Rothamsted | 23.2
2026-05-29 | 2026 | 5 | Rothamsted | 27.9
2026-05-30 | 2026 | 5 | Rothamsted | 21.3
2026-05-31 | 2026 | 5 | Rothamsted | 21.8
2026-06-01 | 2026 | 6 | Rothamsted | 20.7
2026-06-02 | 2026 | 6 | Rothamsted | 19.4
2026-06-03 | 2026 | 6 | Rothamsted | 19
2026-06-04 | 2026 | 6 | Rothamsted | 17.5
2026-06-05 | 2026 | 6 | Rothamsted | 16.4
2026-06-06 | 2026 | 6 | Rothamsted | 18.4
2026-06-07 | 2026 | 6 | Rothamsted | 17.2
2026-06-08 | 2026 | 6 | Rothamsted | 17.5
2026-06-09 | 2026 | 6 | Rothamsted | 16.5
2026-06-10 | 2026 | 6 | Rothamsted | 16.2
2026-06-11 | 2026 | 6 | Rothamsted | 20.9
2026-06-12 | 2026 | 6 | Rothamsted | 19.9
2026-06-13 | 2026 | 6 | Rothamsted | 19.4
2026-06-14 | 2026 | 6 | Rothamsted | 20.7
2026-06-15 | 2026 | 6 | Rothamsted | 24.7
2026-06-16 | 2026 | 6 | Rothamsted | 23
2026-06-17 | 2026 | 6 | Rothamsted | 24.4
2026-06-18 | 2026 | 6 | Rothamsted | 28.2
2026-06-19 | 2026 | 6 | Rothamsted | 25.3
2026-06-20 | 2026 | 6 | Rothamsted | 27.2
2026-06-21 | 2026 | 6 | Rothamsted | 28.2
2026-06-22 | 2026 | 6 | Rothamsted | 32.6
2026-06-23 | 2026 | 6 | Rothamsted | 32.2
2026-06-24 | 2026 | 6 | Rothamsted | 31.9
2026-06-25 | 2026 | 6 | Rothamsted | 34.3
2026-06-26 | 2026 | 6 | Rothamsted | 30.1
2026-06-27 | 2026 | 6 | Rothamsted | 24.5
2026-06-28 | 2026 | 6 | Rothamsted | 22.3
2026-06-29 | 2026 | 6 | Rothamsted | 23.9
2026-06-30 | 2026 | 6 | Rothamsted | 25.1
2026-07-01 | 2026 | 7 | Rothamsted | 24.1
2026-07-02 | 2026 | 7 | Rothamsted | 25.8
2026-07-03 | 2026 | 7 | Rothamsted | 27.2
2026-07-04 | 2026 | 7 | Rothamsted | 27.2
2026-07-05 | 2026 | 7 | Rothamsted | 31.1
2026-07-06 | 2026 | 7 | Rothamsted | 30.1
2026-07-07 | 2026 | 7 | Rothamsted | 31.6
2026-07-08 | 2026 | 7 | Rothamsted | 33.1
2026-07-09 | 2026 | 7 | Rothamsted | 31.3
2026-07-10 | 2026 | 7 | Rothamsted | 28.8
2026-07-11 | 2026 | 7 | Rothamsted | 29
2026-07-12 | 2026 | 7 | Rothamsted | 26.5
2026-07-13 | 2026 | 7 | Rothamsted | 26.3
2026-07-14 | 2026 | 7 | Rothamsted | 27.3
2026-07-15 | 2026 | 7 | Rothamsted | 28
2026-07-16 | 2026 | 7 | Rothamsted | 26.5
2026-07-17 | 2026 | 7 | Rothamsted | 21.2
2026-07-18 | 2026 | 7 | Rothamsted | 21.2
2026-07-19 | 2026 | 7 | Rothamsted | 25
2026-07-20 | 2026 | 7 | Rothamsted | 22.7
2026-07-21 | 2026 | 7 | Rothamsted | 25.4
2026-07-22 | 2026 | 7 | Rothamsted | 26.1
2026-07-23 | 2026 | 7 | Rothamsted | 27.5
2026-07-24 | 2026 | 7 | Rothamsted | 27.3
2026-07-25 | 2026 | 7 | Rothamsted | 25.7
2026-07-26 | 2026 | 7 | Rothamsted | 25.3
2026-07-27 | 2026 | 7 | Rothamsted | 28.8
2026-07-28 | 2026 | 7 | Rothamsted | 33.1
2026-07-29 | 2026 | 7 | Rothamsted | 27.3
2026-07-30 | 2026 | 7 | Rothamsted | 24.3
2026-07-31 | 2026 | 7 | Rothamsted | 24.8
2026-08-01 | 2026 | 8 | Rothamsted | 26.8
2026-08-02 | 2026 | 8 | Rothamsted | 31.1
2026-08-03 | 2026 | 8 | Rothamsted | 28.4
2026-08-04 | 2026 | 8 | Rothamsted | 24.6
2026-08-05 | 2026 | 8 | Rothamsted | 22.3
2026-08-06 | 2026 | 8 | Rothamsted | 24.7
2026-08-07 | 2026 | 8 | Rothamsted | 27.1
2026-08-08 | 2026 | 8 | Rothamsted | 30.3
2026-08-09 | 2026 | 8 | Rothamsted | 24.9
2026-08-10 | 2026 | 8 | Rothamsted | 25.2
2026-08-11 | 2026 | 8 | Rothamsted | 31.8
2026-08-12 | 2026 | 8 | Rothamsted | 35.5
2026-08-13 | 2026 | 8 | Rothamsted | 32.6
2026-08-15 | 2026 | 8 | Rothamsted | 25.1
2026-08-16 | 2026 | 8 | Rothamsted | 26.3
2026-08-17 | 2026 | 8 | Rothamsted | 23.5
2026-08-18 | 2026 | 8 | Rothamsted | 24.6
2026-08-19 | 2026 | 8 | Rothamsted | 23.6
2026-08-20 | 2026 | 8 | Rothamsted | 20.9
2026-08-21 | 2026 | 8 | Rothamsted | 21.3
2026-08-22 | 2026 | 8 | Rothamsted | 23.5
2026-08-23 | 2026 | 8 | Rothamsted | 22.7
2026-08-24 | 2026 | 8 | Rothamsted | 25.2
2026-08-25 | 2026 | 8 | Rothamsted | 25.7
2026-08-26 | 2026 | 8 | Rothamsted | 23.1
2026-08-27 | 2026 | 8 | Rothamsted | 22.6
2026-08-28 | 2026 | 8 | Rothamsted | 19.2
2026-08-29 | 2026 | 8 | Rothamsted | 22.9
2026-08-30 | 2026 | 8 | Rothamsted | 22.3
2026-08-31 | 2026 | 8 | Rothamsted | 22.5
2026-09-01 | 2026 | 9 | Rothamsted | 20.7
2026-09-02 | 2026 | 9 | Rothamsted | 25.4
2026-09-04 | 2026 | 9 | Rothamsted | 22
2026-09-05 | 2026 | 9 | Rothamsted | 26.9
2026-09-06 | 2026 | 9 | Rothamsted | 24.2
2026-09-08 | 2026 | 9 | Rothamsted | 19.1
2026-09-09 | 2026 | 9 | Rothamsted | 19.7
2026-09-10 | 2026 | 9 | Rothamsted | 20.4
2026-09-11 | 2026 | 9 | Rothamsted | 23
2026-09-12 | 2026 | 9 | Rothamsted | 22.1
2026-09-13 | 2026 | 9 | Rothamsted | 24.6
2026-09-14 | 2026 | 9 | Rothamsted | 22
2026-09-15 | 2026 | 9 | Rothamsted | 19.7
2026-09-16 | 2026 | 9 | Rothamsted | 20.2
2026-09-17 | 2026 | 9 | Rothamsted | 19.3
2026-09-18 | 2026 | 9 | Rothamsted | 23.5
2026-09-19 | 2026 | 9 | Rothamsted | 19.6
2026-09-20 | 2026 | 9 | Rothamsted | 22.7
2026-09-21 | 2026 | 9 | Rothamsted | 23.7
2026-09-22 | 2026 | 9 | Rothamsted | 22.5
2026-09-23 | 2026 | 9 | Rothamsted | 20.8
2026-09-24 | 2026 | 9 | Rothamsted | 22.7
2026-09-25 | 2026 | 9 | Rothamsted | 20.9
2026-09-26 | 2026 | 9 | Rothamsted | 22.1
2026-09-27 | 2026 | 9 | Rothamsted | 19.1
2026-09-28 | 2026 | 9 | Rothamsted | 25
2026-09-29 | 2026 | 9 | Rothamsted | 23.9
1979-05-01 | 1979 | 5 | Heathrow | 8
1979-05-02 | 1979 | 5 | Heathrow | 10
1979-05-03 | 1979 | 5 | Heathrow | 9.1
1979-05-04 | 1979 | 5 | Heathrow | 11.1
1979-05-05 | 1979 | 5 | Heathrow | 12.4
1979-05-06 | 1979 | 5 | Heathrow | 15
1979-05-07 | 1979 | 5 | Heathrow | 16
1979-05-08 | 1979 | 5 | Heathrow | 15.6
1979-05-09 | 1979 | 5 | Heathrow | 13.6
1979-05-10 | 1979 | 5 | Heathrow | 16.1
1979-05-11 | 1979 | 5 | Heathrow | 20.8
1979-05-12 | 1979 | 5 | Heathrow | 23.4
1979-05-13 | 1979 | 5 | Heathrow | 26.1
1979-05-14 | 1979 | 5 | Heathrow | 26.2
1979-05-15 | 1979 | 5 | Heathrow | 22.5
1979-05-17 | 1979 | 5 | Heathrow | 16
1979-05-18 | 1979 | 5 | Heathrow | 17.2
1979-05-19 | 1979 | 5 | Heathrow | 14
1979-05-20 | 1979 | 5 | Heathrow | 15.1
1979-05-21 | 1979 | 5 | Heathrow | 15.8
1979-05-22 | 1979 | 5 | Heathrow | 14.3
1979-05-23 | 1979 | 5 | Heathrow | 14.6
1979-05-24 | 1979 | 5 | Heathrow | 13.4
1979-05-25 | 1979 | 5 | Heathrow | 15.5
1979-05-26 | 1979 | 5 | Heathrow | 15.9
1979-05-27 | 1979 | 5 | Heathrow | 15.9
1979-05-28 | 1979 | 5 | Heathrow | 18.6
1979-05-29 | 1979 | 5 | Heathrow | 20.1
1979-05-30 | 1979 | 5 | Heathrow | 16.2
1979-05-31 | 1979 | 5 | Heathrow | 18.7
1979-06-01 | 1979 | 6 | Heathrow | 21.2
1979-06-02 | 1979 | 6 | Heathrow | 19.2
1979-06-03 | 1979 | 6 | Heathrow | 19.3
1979-06-04 | 1979 | 6 | Heathrow | 20.4
1979-06-05 | 1979 | 6 | Heathrow | 16.7
1979-06-06 | 1979 | 6 | Heathrow | 14.4
1979-06-07 | 1979 | 6 | Heathrow | 17.2
1979-06-08 | 1979 | 6 | Heathrow | 18.7
1979-06-09 | 1979 | 6 | Heathrow | 17.9
1979-06-10 | 1979 | 6 | Heathrow | 16.2
1979-06-11 | 1979 | 6 | Heathrow | 15.4
1979-06-12 | 1979 | 6 | Heathrow | 18.1
1979-06-13 | 1979 | 6 | Heathrow | 16.4
1979-06-14 | 1979 | 6 | Heathrow | 16.1
1979-06-15 | 1979 | 6 | Heathrow | 19.2
1979-06-16 | 1979 | 6 | Heathrow | 20.7
1979-06-17 | 1979 | 6 | Heathrow | 22.6
1979-06-18 | 1979 | 6 | Heathrow | 25.5
1979-06-19 | 1979 | 6 | Heathrow | 25.8
1979-06-20 | 1979 | 6 | Heathrow | 19.4
1979-06-21 | 1979 | 6 | Heathrow | 20.1
1979-06-22 | 1979 | 6 | Heathrow | 19.5
1979-06-23 | 1979 | 6 | Heathrow | 16.6
1979-06-24 | 1979 | 6 | Heathrow | 18.5
1979-06-25 | 1979 | 6 | Heathrow | 19.9
1979-06-26 | 1979 | 6 | Heathrow | 21.4
1979-06-27 | 1979 | 6 | Heathrow | 20.8
1979-06-28 | 1979 | 6 | Heathrow | 17.6
1979-06-29 | 1979 | 6 | Heathrow | 16.6
1979-06-30 | 1979 | 6 | Heathrow | 18.5
1979-07-01 | 1979 | 7 | Heathrow | 18.7
1979-07-02 | 1979 | 7 | Heathrow | 22.1
1979-07-03 | 1979 | 7 | Heathrow | 23.4
1979-07-04 | 1979 | 7 | Heathrow | 25.5
1979-07-05 | 1979 | 7 | Heathrow | 25.1
1979-07-06 | 1979 | 7 | Heathrow | 21.9
1979-07-07 | 1979 | 7 | Heathrow | 23.1
1979-07-08 | 1979 | 7 | Heathrow | 20.8
1979-07-09 | 1979 | 7 | Heathrow | 22
1979-07-10 | 1979 | 7 | Heathrow | 20.8
1979-07-11 | 1979 | 7 | Heathrow | 25.1
1979-07-12 | 1979 | 7 | Heathrow | 26.2
1979-07-13 | 1979 | 7 | Heathrow | 22.1
1979-07-14 | 1979 | 7 | Heathrow | 21.1
1979-07-15 | 1979 | 7 | Heathrow | 23.6
1979-07-16 | 1979 | 7 | Heathrow | 26.7
1979-07-17 | 1979 | 7 | Heathrow | 21.8
1979-07-19 | 1979 | 7 | Heathrow | 21.5
1979-07-20 | 1979 | 7 | Heathrow | 19.5
1979-07-21 | 1979 | 7 | Heathrow | 18.1
1979-07-22 | 1979 | 7 | Heathrow | 18.7
1979-07-23 | 1979 | 7 | Heathrow | 21.1
1979-07-24 | 1979 | 7 | Heathrow | 25.2
1979-07-25 | 1979 | 7 | Heathrow | 27.1
1979-07-26 | 1979 | 7 | Heathrow | 29.9
1979-07-27 | 1979 | 7 | Heathrow | 27.4
1979-07-29 | 1979 | 7 | Heathrow | 21.5
1979-07-30 | 1979 | 7 | Heathrow | 20.8
1979-07-31 | 1979 | 7 | Heathrow | 23.1
1979-08-01 | 1979 | 8 | Heathrow | 21.6
1979-08-02 | 1979 | 8 | Heathrow | 20
1979-08-03 | 1979 | 8 | Heathrow | 21.6
1979-08-04 | 1979 | 8 | Heathrow | 22.5
1979-08-05 | 1979 | 8 | Heathrow | 24.8
1979-08-06 | 1979 | 8 | Heathrow | 23.1
1979-08-07 | 1979 | 8 | Heathrow | 20.1
1979-08-08 | 1979 | 8 | Heathrow | 20.1
1979-08-09 | 1979 | 8 | Heathrow | 20
1979-08-10 | 1979 | 8 | Heathrow | 23.6
1979-08-11 | 1979 | 8 | Heathrow | 25
1979-08-12 | 1979 | 8 | Heathrow | 21.5
1979-08-13 | 1979 | 8 | Heathrow | 20.4
1979-08-14 | 1979 | 8 | Heathrow | 21.3
1979-08-15 | 1979 | 8 | Heathrow | 21
1979-08-16 | 1979 | 8 | Heathrow | 18.3
1979-08-17 | 1979 | 8 | Heathrow | 18.2
1979-08-18 | 1979 | 8 | Heathrow | 19.8
1979-08-19 | 1979 | 8 | Heathrow | 22.8
1979-08-20 | 1979 | 8 | Heathrow | 19.8
1979-08-21 | 1979 | 8 | Heathrow | 19.6
1979-08-22 | 1979 | 8 | Heathrow | 16.1
1979-08-23 | 1979 | 8 | Heathrow | 16.9
1979-08-24 | 1979 | 8 | Heathrow | 18.3
1979-08-25 | 1979 | 8 | Heathrow | 18.7
1979-08-26 | 1979 | 8 | Heathrow | 17.4
1979-08-27 | 1979 | 8 | Heathrow | 21.8
1979-08-28 | 1979 | 8 | Heathrow | 23.9
1979-08-29 | 1979 | 8 | Heathrow | 26
1979-08-30 | 1979 | 8 | Heathrow | 23.1
1979-08-31 | 1979 | 8 | Heathrow | 22.8
1979-09-01 | 1979 | 9 | Heathrow | 21.6
1979-09-02 | 1979 | 9 | Heathrow | 19.4
1979-09-03 | 1979 | 9 | Heathrow | 21.7
1979-09-04 | 1979 | 9 | Heathrow | 23.6
1979-09-05 | 1979 | 9 | Heathrow | 25.9
1979-09-06 | 1979 | 9 | Heathrow | 21.9
1979-09-07 | 1979 | 9 | Heathrow | 24.3
1979-09-08 | 1979 | 9 | Heathrow | 21.8
1979-09-09 | 1979 | 9 | Heathrow | 21.2
1979-09-10 | 1979 | 9 | Heathrow | 23.2
1979-09-11 | 1979 | 9 | Heathrow | 17.4
1979-09-12 | 1979 | 9 | Heathrow | 18.5
1979-09-13 | 1979 | 9 | Heathrow | 18.2
1979-09-14 | 1979 | 9 | Heathrow | 17.4
1979-09-15 | 1979 | 9 | Heathrow | 20.2
1979-09-16 | 1979 | 9 | Heathrow | 21.2
1979-09-17 | 1979 | 9 | Heathrow | 20.4
1979-09-18 | 1979 | 9 | Heathrow | 18.3
1979-09-19 | 1979 | 9 | Heathrow | 17.6
1979-09-20 | 1979 | 9 | Heathrow | 15.5
1979-09-21 | 1979 | 9 | Heathrow | 14.2
1979-09-22 | 1979 | 9 | Heathrow | 14.7
1979-09-23 | 1979 | 9 | Heathrow | 16.6
1979-09-24 | 1979 | 9 | Heathrow | 18.6
1979-09-25 | 1979 | 9 | Heathrow | 21
1979-09-26 | 1979 | 9 | Heathrow | 17.7
1979-09-27 | 1979 | 9 | Heathrow | 17.4
1979-09-28 | 1979 | 9 | Heathrow | 17.1
1979-09-29 | 1979 | 9 | Heathrow | 18.7
1979-09-30 | 1979 | 9 | Heathrow | 19
1980-05-01 | 1980 | 5 | Heathrow | 14
1980-05-02 | 1980 | 5 | Heathrow | 12.5
1980-05-03 | 1980 | 5 | Heathrow | 16.2
1980-05-04 | 1980 | 5 | Heathrow | 12.3
1980-05-05 | 1980 | 5 | Heathrow | 13.4
1980-05-06 | 1980 | 5 | Heathrow | 11.1
1980-05-07 | 1980 | 5 | Heathrow | 11.6
1980-05-08 | 1980 | 5 | Heathrow | 13.6
1980-05-09 | 1980 | 5 | Heathrow | 19.3
1980-05-10 | 1980 | 5 | Heathrow | 21.1
1980-05-11 | 1980 | 5 | Heathrow | 26.2
1980-05-12 | 1980 | 5 | Heathrow | 23.6
1980-05-13 | 1980 | 5 | Heathrow | 20.9
1980-05-14 | 1980 | 5 | Heathrow | 18.9
1980-05-15 | 1980 | 5 | Heathrow | 21.1
1980-05-16 | 1980 | 5 | Heathrow | 21.2
1980-05-17 | 1980 | 5 | Heathrow | 22.5
1980-05-18 | 1980 | 5 | Heathrow | 24.2
1980-05-20 | 1980 | 5 | Heathrow | 21.1
1980-05-21 | 1980 | 5 | Heathrow | 15.9
1980-05-22 | 1980 | 5 | Heathrow | 12.9
1980-05-23 | 1980 | 5 | Heathrow | 14.1
1980-05-24 | 1980 | 5 | Heathrow | 16.6
1980-05-25 | 1980 | 5 | Heathrow | 18.7
1980-05-26 | 1980 | 5 | Heathrow | 19.5
1980-05-27 | 1980 | 5 | Heathrow | 18.4
1980-05-28 | 1980 | 5 | Heathrow | 14.9
1980-05-29 | 1980 | 5 | Heathrow | 16.6
1980-05-30 | 1980 | 5 | Heathrow | 12.2
1980-05-31 | 1980 | 5 | Heathrow | 17.9
1980-06-01 | 1980 | 6 | Heathrow | 18
1980-06-02 | 1980 | 6 | Heathrow | 25.6
1980-06-03 | 1980 | 6 | Heathrow | 29
1980-06-04 | 1980 | 6 | Heathrow | 27
1980-06-06 | 1980 | 6 | Heathrow | 19.7
1980-06-07 | 1980 | 6 | Heathrow | 19.1
1980-06-08 | 1980 | 6 | Heathrow | 20.8
1980-06-09 | 1980 | 6 | Heathrow | 18.3
1980-06-10 | 1980 | 6 | Heathrow | 18.5
1980-06-11 | 1980 | 6 | Heathrow | 23.2
1980-06-12 | 1980 | 6 | Heathrow | 23.5
1980-06-13 | 1980 | 6 | Heathrow | 19.4
1980-06-14 | 1980 | 6 | Heathrow | 20.1
1980-06-15 | 1980 | 6 | Heathrow | 18.3
1980-06-16 | 1980 | 6 | Heathrow | 17
1980-06-17 | 1980 | 6 | Heathrow | 20.2
1980-06-18 | 1980 | 6 | Heathrow | 17.7
1980-06-19 | 1980 | 6 | Heathrow | 17
1980-06-20 | 1980 | 6 | Heathrow | 18.6
1980-06-21 | 1980 | 6 | Heathrow | 15.5
1980-06-22 | 1980 | 6 | Heathrow | 15.1
1980-06-23 | 1980 | 6 | Heathrow | 17
1980-06-24 | 1980 | 6 | Heathrow | 19.2
1980-06-25 | 1980 | 6 | Heathrow | 19.4
1980-06-26 | 1980 | 6 | Heathrow | 18.1
1980-06-27 | 1980 | 6 | Heathrow | 18.7
1980-06-28 | 1980 | 6 | Heathrow | 20
1980-06-29 | 1980 | 6 | Heathrow | 19.4
1980-06-30 | 1980 | 6 | Heathrow | 16
1980-07-01 | 1980 | 7 | Heathrow | 21.1
1980-07-02 | 1980 | 7 | Heathrow | 21.8
1980-07-03 | 1980 | 7 | Heathrow | 18.5
1980-07-04 | 1980 | 7 | Heathrow | 19.3
1980-07-05 | 1980 | 7 | Heathrow | 18.2
1980-07-06 | 1980 | 7 | Heathrow | 17.5
1980-07-07 | 1980 | 7 | Heathrow | 15.6
1980-07-08 | 1980 | 7 | Heathrow | 14.9
1980-07-09 | 1980 | 7 | Heathrow | 15.3
1980-07-10 | 1980 | 7 | Heathrow | 19.4
1980-07-11 | 1980 | 7 | Heathrow | 17.6
1980-07-12 | 1980 | 7 | Heathrow | 17.7
1980-07-13 | 1980 | 7 | Heathrow | 15.3
1980-07-14 | 1980 | 7 | Heathrow | 16.9
1980-07-15 | 1980 | 7 | Heathrow | 19
1980-07-16 | 1980 | 7 | Heathrow | 16.8
1980-07-17 | 1980 | 7 | Heathrow | 18.3
1980-07-18 | 1980 | 7 | Heathrow | 20
1980-07-19 | 1980 | 7 | Heathrow | 17.3
1980-07-20 | 1980 | 7 | Heathrow | 19.8
1980-07-21 | 1980 | 7 | Heathrow | 21.7
1980-07-22 | 1980 | 7 | Heathrow | 24.8
1980-07-23 | 1980 | 7 | Heathrow | 24.2
1980-07-24 | 1980 | 7 | Heathrow | 27.8
1980-07-26 | 1980 | 7 | Heathrow | 21.2
1980-07-27 | 1980 | 7 | Heathrow | 25
1980-07-28 | 1980 | 7 | Heathrow | 25.7
1980-07-30 | 1980 | 7 | Heathrow | 22
1980-07-31 | 1980 | 7 | Heathrow | 23
1980-08-01 | 1980 | 8 | Heathrow | 25.2
1980-08-02 | 1980 | 8 | Heathrow | 23.3
1980-08-03 | 1980 | 8 | Heathrow | 21.6
1980-08-04 | 1980 | 8 | Heathrow | 21
1980-08-05 | 1980 | 8 | Heathrow | 21.9
1980-08-06 | 1980 | 8 | Heathrow | 25.2
1980-08-08 | 1980 | 8 | Heathrow | 22.1
1980-08-09 | 1980 | 8 | Heathrow | 24.4
1980-08-10 | 1980 | 8 | Heathrow | 20.3
1980-08-11 | 1980 | 8 | Heathrow | 19.8
1980-08-12 | 1980 | 8 | Heathrow | 24.6
1980-08-13 | 1980 | 8 | Heathrow | 24.8
1980-08-14 | 1980 | 8 | Heathrow | 23.3
1980-08-15 | 1980 | 8 | Heathrow | 23.9
1980-08-16 | 1980 | 8 | Heathrow | 22.4
1980-08-17 | 1980 | 8 | Heathrow | 22.3
1980-08-18 | 1980 | 8 | Heathrow | 20.2
1980-08-19 | 1980 | 8 | Heathrow | 24.5
1980-08-20 | 1980 | 8 | Heathrow | 21
1980-08-22 | 1980 | 8 | Heathrow | 18.3
1980-08-23 | 1980 | 8 | Heathrow | 19.8
1980-08-24 | 1980 | 8 | Heathrow | 21
1980-08-25 | 1980 | 8 | Heathrow | 22.6
1980-08-26 | 1980 | 8 | Heathrow | 24.3
1980-08-27 | 1980 | 8 | Heathrow | 23
1980-08-28 | 1980 | 8 | Heathrow | 19.6
1980-08-29 | 1980 | 8 | Heathrow | 20.4
1980-08-30 | 1980 | 8 | Heathrow | 19.9
1980-08-31 | 1980 | 8 | Heathrow | 22
1980-09-01 | 1980 | 9 | Heathrow | 22.4
1980-09-02 | 1980 | 9 | Heathrow | 25
1980-09-03 | 1980 | 9 | Heathrow | 20.3
1980-09-04 | 1980 | 9 | Heathrow | 18.9
1980-09-05 | 1980 | 9 | Heathrow | 21.8
1980-09-06 | 1980 | 9 | Heathrow | 23.1
1980-09-07 | 1980 | 9 | Heathrow | 22.1
1980-09-08 | 1980 | 9 | Heathrow | 17.7
1980-09-09 | 1980 | 9 | Heathrow | 20.1
1980-09-10 | 1980 | 9 | Heathrow | 19.3
1980-09-11 | 1980 | 9 | Heathrow | 20.4
1980-09-12 | 1980 | 9 | Heathrow | 19.2
1980-09-13 | 1980 | 9 | Heathrow | 21.5
1980-09-14 | 1980 | 9 | Heathrow | 20
1980-09-15 | 1980 | 9 | Heathrow | 20.2
1980-09-16 | 1980 | 9 | Heathrow | 19
1980-09-17 | 1980 | 9 | Heathrow | 18.7
1980-09-18 | 1980 | 9 | Heathrow | 21.5
1980-09-19 | 1980 | 9 | Heathrow | 19.7
1980-09-20 | 1980 | 9 | Heathrow | 19.6
1980-09-21 | 1980 | 9 | Heathrow | 19.7
1980-09-22 | 1980 | 9 | Heathrow | 20.1
1980-09-23 | 1980 | 9 | Heathrow | 18.9
1980-09-24 | 1980 | 9 | Heathrow | 19.8
1980-09-25 | 1980 | 9 | Heathrow | 20.3
1980-09-26 | 1980 | 9 | Heathrow | 18.2
1980-09-27 | 1980 | 9 | Heathrow | 16.6
1980-09-28 | 1980 | 9 | Heathrow | 17.8
1980-09-29 | 1980 | 9 | Heathrow | 19.1
1980-09-30 | 1980 | 9 | Heathrow | 18.4
1981-05-01 | 1981 | 5 | Heathrow | 10.6
1981-05-02 | 1981 | 5 | Heathrow | 9.2
1981-05-03 | 1981 | 5 | Heathrow | 12.2
1981-05-04 | 1981 | 5 | Heathrow | 13.3
1981-05-05 | 1981 | 5 | Heathrow | 16.2
1981-05-06 | 1981 | 5 | Heathrow | 19.7
1981-05-07 | 1981 | 5 | Heathrow | 18.5
1981-05-08 | 1981 | 5 | Heathrow | 16.5
1981-05-09 | 1981 | 5 | Heathrow | 15.3
1981-05-10 | 1981 | 5 | Heathrow | 21.6
1981-05-11 | 1981 | 5 | Heathrow | 18.6
1981-05-12 | 1981 | 5 | Heathrow | 16.2
1981-05-13 | 1981 | 5 | Heathrow | 16.4
1981-05-14 | 1981 | 5 | Heathrow | 18.2
1981-05-15 | 1981 | 5 | Heathrow | 15.1
1981-05-16 | 1981 | 5 | Heathrow | 14
1981-05-17 | 1981 | 5 | Heathrow | 15.6
1981-05-18 | 1981 | 5 | Heathrow | 18.5
1981-05-19 | 1981 | 5 | Heathrow | 21.7
1981-05-20 | 1981 | 5 | Heathrow | 17.7
1981-05-21 | 1981 | 5 | Heathrow | 16.6
1981-05-22 | 1981 | 5 | Heathrow | 14.6
1981-05-23 | 1981 | 5 | Heathrow | 15.2
1981-05-24 | 1981 | 5 | Heathrow | 13
1981-05-25 | 1981 | 5 | Heathrow | 15.4
1981-05-26 | 1981 | 5 | Heathrow | 16.4
1981-05-27 | 1981 | 5 | Heathrow | 15.7
1981-05-28 | 1981 | 5 | Heathrow | 16.8
1981-05-29 | 1981 | 5 | Heathrow | 19.2
1981-05-30 | 1981 | 5 | Heathrow | 21.8
1981-05-31 | 1981 | 5 | Heathrow | 22.4
1981-06-01 | 1981 | 6 | Heathrow | 19.2
1981-06-02 | 1981 | 6 | Heathrow | 19.7
1981-06-03 | 1981 | 6 | Heathrow | 17.2
1981-06-04 | 1981 | 6 | Heathrow | 17.2
1981-06-05 | 1981 | 6 | Heathrow | 18.4
1981-06-06 | 1981 | 6 | Heathrow | 16.4
1981-06-07 | 1981 | 6 | Heathrow | 18.5
1981-06-08 | 1981 | 6 | Heathrow | 17.2
1981-06-09 | 1981 | 6 | Heathrow | 17.8
1981-06-10 | 1981 | 6 | Heathrow | 18.7
1981-06-11 | 1981 | 6 | Heathrow | 17.3
1981-06-12 | 1981 | 6 | Heathrow | 21.9
1981-06-13 | 1981 | 6 | Heathrow | 27
1981-06-14 | 1981 | 6 | Heathrow | 21.1
1981-06-16 | 1981 | 6 | Heathrow | 14
1981-06-17 | 1981 | 6 | Heathrow | 17.9
1981-06-18 | 1981 | 6 | Heathrow | 15.7
1981-06-19 | 1981 | 6 | Heathrow | 18.6
1981-06-20 | 1981 | 6 | Heathrow | 18
1981-06-21 | 1981 | 6 | Heathrow | 22.8
1981-06-22 | 1981 | 6 | Heathrow | 21.6
1981-06-23 | 1981 | 6 | Heathrow | 18
1981-06-24 | 1981 | 6 | Heathrow | 16
1981-06-25 | 1981 | 6 | Heathrow | 14.4
1981-06-26 | 1981 | 6 | Heathrow | 15.6
1981-06-27 | 1981 | 6 | Heathrow | 14.4
1981-06-28 | 1981 | 6 | Heathrow | 19.1
1981-06-29 | 1981 | 6 | Heathrow | 21.8
1981-06-30 | 1981 | 6 | Heathrow | 21
1981-07-01 | 1981 | 7 | Heathrow | 18.2
1981-07-02 | 1981 | 7 | Heathrow | 18
1981-07-03 | 1981 | 7 | Heathrow | 19.4
1981-07-04 | 1981 | 7 | Heathrow | 21.6
1981-07-05 | 1981 | 7 | Heathrow | 22.6
1981-07-06 | 1981 | 7 | Heathrow | 24.6
1981-07-07 | 1981 | 7 | Heathrow | 27.8
1981-07-08 | 1981 | 7 | Heathrow | 27.4
1981-07-10 | 1981 | 7 | Heathrow | 23.1
1981-07-11 | 1981 | 7 | Heathrow | 20.9
1981-07-12 | 1981 | 7 | Heathrow | 22.9
1981-07-13 | 1981 | 7 | Heathrow | 23
1981-07-14 | 1981 | 7 | Heathrow | 22.6
1981-07-15 | 1981 | 7 | Heathrow | 21.5
1981-07-16 | 1981 | 7 | Heathrow | 18
1981-07-17 | 1981 | 7 | Heathrow | 20.1
1981-07-18 | 1981 | 7 | Heathrow | 22.9
1981-07-19 | 1981 | 7 | Heathrow | 24.3
1981-07-20 | 1981 | 7 | Heathrow | 25.2
1981-07-22 | 1981 | 7 | Heathrow | 17.6
1981-07-23 | 1981 | 7 | Heathrow | 16
1981-07-24 | 1981 | 7 | Heathrow | 17.5
1981-07-25 | 1981 | 7 | Heathrow | 24.6
1981-07-26 | 1981 | 7 | Heathrow | 24.8
1981-07-27 | 1981 | 7 | Heathrow | 26.4
1981-07-28 | 1981 | 7 | Heathrow | 24
1981-07-29 | 1981 | 7 | Heathrow | 23.4
1981-07-30 | 1981 | 7 | Heathrow | 21.6
1981-07-31 | 1981 | 7 | Heathrow | 17.4
1981-08-01 | 1981 | 8 | Heathrow | 21.2
1981-08-02 | 1981 | 8 | Heathrow | 25.9
1981-08-03 | 1981 | 8 | Heathrow | 27
1981-08-04 | 1981 | 8 | Heathrow | 28.8
1981-08-06 | 1981 | 8 | Heathrow | 18.2
1981-08-07 | 1981 | 8 | Heathrow | 19.8
1981-08-08 | 1981 | 8 | Heathrow | 17.8
1981-08-09 | 1981 | 8 | Heathrow | 20.3
1981-08-10 | 1981 | 8 | Heathrow | 23.7
1981-08-11 | 1981 | 8 | Heathrow | 25.6
1981-08-12 | 1981 | 8 | Heathrow | 24.4
1981-08-13 | 1981 | 8 | Heathrow | 26.2
1981-08-14 | 1981 | 8 | Heathrow | 26.3
1981-08-16 | 1981 | 8 | Heathrow | 22.2
1981-08-17 | 1981 | 8 | Heathrow | 23.6
1981-08-18 | 1981 | 8 | Heathrow | 21.6
1981-08-19 | 1981 | 8 | Heathrow | 19.9
1981-08-20 | 1981 | 8 | Heathrow | 20
1981-08-21 | 1981 | 8 | Heathrow | 22.8
1981-08-22 | 1981 | 8 | Heathrow | 20.5
1981-08-23 | 1981 | 8 | Heathrow | 22.5
1981-08-24 | 1981 | 8 | Heathrow | 24.9
1981-08-25 | 1981 | 8 | Heathrow | 26.6
1981-08-26 | 1981 | 8 | Heathrow | 27.9
1981-08-27 | 1981 | 8 | Heathrow | 27
1981-08-28 | 1981 | 8 | Heathrow | 22
1981-08-29 | 1981 | 8 | Heathrow | 22.7
1981-08-30 | 1981 | 8 | Heathrow | 21.1
1981-08-31 | 1981 | 8 | Heathrow | 19.2
1981-09-01 | 1981 | 9 | Heathrow | 21
1981-09-02 | 1981 | 9 | Heathrow | 22.1
1981-09-03 | 1981 | 9 | Heathrow | 23
1981-09-04 | 1981 | 9 | Heathrow | 24.3
1981-09-05 | 1981 | 9 | Heathrow | 24.8
1981-09-06 | 1981 | 9 | Heathrow | 22
1981-09-07 | 1981 | 9 | Heathrow | 24.5
1981-09-08 | 1981 | 9 | Heathrow | 24
1981-09-09 | 1981 | 9 | Heathrow | 25.5
1981-09-10 | 1981 | 9 | Heathrow | 22.2
1981-09-11 | 1981 | 9 | Heathrow | 18.1
1981-09-12 | 1981 | 9 | Heathrow | 19.1
1981-09-13 | 1981 | 9 | Heathrow | 18.2
1981-09-14 | 1981 | 9 | Heathrow | 21.2
1981-09-15 | 1981 | 9 | Heathrow | 18.6
1981-09-16 | 1981 | 9 | Heathrow | 20.4
1981-09-17 | 1981 | 9 | Heathrow | 19.8
1981-09-18 | 1981 | 9 | Heathrow | 19
1981-09-19 | 1981 | 9 | Heathrow | 18.2
1981-09-20 | 1981 | 9 | Heathrow | 20.3
1981-09-21 | 1981 | 9 | Heathrow | 19.7
1981-09-22 | 1981 | 9 | Heathrow | 18.8
1981-09-23 | 1981 | 9 | Heathrow | 17.7
1981-09-24 | 1981 | 9 | Heathrow | 18.1
1981-09-25 | 1981 | 9 | Heathrow | 15.5
1981-09-26 | 1981 | 9 | Heathrow | 17.9
1981-09-27 | 1981 | 9 | Heathrow | 17.6
1981-09-28 | 1981 | 9 | Heathrow | 17.2
1981-09-29 | 1981 | 9 | Heathrow | 19.6
1981-09-30 | 1981 | 9 | Heathrow | 20
1982-05-01 | 1982 | 5 | Heathrow | 13.5
1982-05-02 | 1982 | 5 | Heathrow | 12.6
1982-05-03 | 1982 | 5 | Heathrow | 12.2
1982-05-04 | 1982 | 5 | Heathrow | 11.1
1982-05-05 | 1982 | 5 | Heathrow | 9.7
1982-05-06 | 1982 | 5 | Heathrow | 11.8
1982-05-07 | 1982 | 5 | Heathrow | 13.7
1982-05-08 | 1982 | 5 | Heathrow | 15.6
1982-05-09 | 1982 | 5 | Heathrow | 16.7
1982-05-10 | 1982 | 5 | Heathrow | 18.9
1982-05-11 | 1982 | 5 | Heathrow | 20.6
1982-05-12 | 1982 | 5 | Heathrow | 23.1
1982-05-13 | 1982 | 5 | Heathrow | 23
1982-05-14 | 1982 | 5 | Heathrow | 25.3
1982-05-15 | 1982 | 5 | Heathrow | 22.5
1982-05-16 | 1982 | 5 | Heathrow | 18.6
1982-05-17 | 1982 | 5 | Heathrow | 20.4
1982-05-18 | 1982 | 5 | Heathrow | 18.6
1982-05-19 | 1982 | 5 | Heathrow | 16.8
1982-05-20 | 1982 | 5 | Heathrow | 18.8
1982-05-21 | 1982 | 5 | Heathrow | 17.1
1982-05-22 | 1982 | 5 | Heathrow | 14.7
1982-05-23 | 1982 | 5 | Heathrow | 17.5
1982-05-24 | 1982 | 5 | Heathrow | 19.8
1982-05-25 | 1982 | 5 | Heathrow | 24.1
1982-05-26 | 1982 | 5 | Heathrow | 24.1
1982-05-27 | 1982 | 5 | Heathrow | 20.7
1982-05-28 | 1982 | 5 | Heathrow | 23.4
1982-05-29 | 1982 | 5 | Heathrow | 21.7
1982-05-30 | 1982 | 5 | Heathrow | 26.6
1982-05-31 | 1982 | 5 | Heathrow | 26.3
1982-06-01 | 1982 | 6 | Heathrow | 26.8
1982-06-02 | 1982 | 6 | Heathrow | 24.6
1982-06-03 | 1982 | 6 | Heathrow | 28.9
1982-06-04 | 1982 | 6 | Heathrow | 29.3
1982-06-05 | 1982 | 6 | Heathrow | 26.1
1982-06-06 | 1982 | 6 | Heathrow | 25.3
1982-06-07 | 1982 | 6 | Heathrow | 25.5
1982-06-08 | 1982 | 6 | Heathrow | 22.8
1982-06-09 | 1982 | 6 | Heathrow | 19.2
1982-06-10 | 1982 | 6 | Heathrow | 20.3
1982-06-11 | 1982 | 6 | Heathrow | 18.8
1982-06-12 | 1982 | 6 | Heathrow | 15.5
1982-06-13 | 1982 | 6 | Heathrow | 17.1
1982-06-14 | 1982 | 6 | Heathrow | 18.3
1982-06-15 | 1982 | 6 | Heathrow | 20.6
1982-06-16 | 1982 | 6 | Heathrow | 23.7
1982-06-17 | 1982 | 6 | Heathrow | 18.3
1982-06-18 | 1982 | 6 | Heathrow | 19.9
1982-06-19 | 1982 | 6 | Heathrow | 21.6
1982-06-20 | 1982 | 6 | Heathrow | 18.9
1982-06-21 | 1982 | 6 | Heathrow | 18.7
1982-06-22 | 1982 | 6 | Heathrow | 17.9
1982-06-23 | 1982 | 6 | Heathrow | 20.7
1982-06-24 | 1982 | 6 | Heathrow | 17.6
1982-06-25 | 1982 | 6 | Heathrow | 18.5
1982-06-26 | 1982 | 6 | Heathrow | 21.1
1982-06-27 | 1982 | 6 | Heathrow | 19.3
1982-06-28 | 1982 | 6 | Heathrow | 20.5
1982-06-29 | 1982 | 6 | Heathrow | 21.8
1982-06-30 | 1982 | 6 | Heathrow | 18.7
1982-07-01 | 1982 | 7 | Heathrow | 22.4
1982-07-02 | 1982 | 7 | Heathrow | 20.4
1982-07-03 | 1982 | 7 | Heathrow | 19.3
1982-07-04 | 1982 | 7 | Heathrow | 22.6
1982-07-05 | 1982 | 7 | Heathrow | 24
1982-07-06 | 1982 | 7 | Heathrow | 24.2
1982-07-07 | 1982 | 7 | Heathrow | 28.4
1982-07-08 | 1982 | 7 | Heathrow | 27.6
1982-07-09 | 1982 | 7 | Heathrow | 23
1982-07-10 | 1982 | 7 | Heathrow | 26
1982-07-11 | 1982 | 7 | Heathrow | 26.1
1982-07-12 | 1982 | 7 | Heathrow | 27.1
1982-07-13 | 1982 | 7 | Heathrow | 22.6
1982-07-14 | 1982 | 7 | Heathrow | 22.2
1982-07-15 | 1982 | 7 | Heathrow | 20.6
1982-07-16 | 1982 | 7 | Heathrow | 23
1982-07-17 | 1982 | 7 | Heathrow | 23.8
1982-07-18 | 1982 | 7 | Heathrow | 23.4
1982-07-19 | 1982 | 7 | Heathrow | 22.7
1982-07-20 | 1982 | 7 | Heathrow | 19.8
1982-07-21 | 1982 | 7 | Heathrow | 21.6
1982-07-22 | 1982 | 7 | Heathrow | 17.6
1982-07-23 | 1982 | 7 | Heathrow | 18.6
1982-07-24 | 1982 | 7 | Heathrow | 25.2
1982-07-25 | 1982 | 7 | Heathrow | 21.7
1982-07-26 | 1982 | 7 | Heathrow | 18.2
1982-07-27 | 1982 | 7 | Heathrow | 22.7
1982-07-28 | 1982 | 7 | Heathrow | 24.3
1982-07-29 | 1982 | 7 | Heathrow | 26.9
1982-07-30 | 1982 | 7 | Heathrow | 25.9
1982-07-31 | 1982 | 7 | Heathrow | 26.5
1982-08-01 | 1982 | 8 | Heathrow | 27.6
1982-08-02 | 1982 | 8 | Heathrow | 27.3
1982-08-03 | 1982 | 8 | Heathrow | 24.8
1982-08-04 | 1982 | 8 | Heathrow | 23.6
1982-08-05 | 1982 | 8 | Heathrow | 25.1
1982-08-06 | 1982 | 8 | Heathrow | 20.4
1982-08-07 | 1982 | 8 | Heathrow | 26.1
1982-08-08 | 1982 | 8 | Heathrow | 25.6
1982-08-09 | 1982 | 8 | Heathrow | 25.9
1982-08-10 | 1982 | 8 | Heathrow | 25.4
1982-08-11 | 1982 | 8 | Heathrow | 23.7
1982-08-12 | 1982 | 8 | Heathrow | 20.6
1982-08-13 | 1982 | 8 | Heathrow | 21
1982-08-14 | 1982 | 8 | Heathrow | 23.4
1982-08-15 | 1982 | 8 | Heathrow | 21
1982-08-16 | 1982 | 8 | Heathrow | 21.1
1982-08-17 | 1982 | 8 | Heathrow | 19.5
1982-08-18 | 1982 | 8 | Heathrow | 20.1
1982-08-19 | 1982 | 8 | Heathrow | 19.4
1982-08-20 | 1982 | 8 | Heathrow | 20.5
1982-08-21 | 1982 | 8 | Heathrow | 21.9
1982-08-22 | 1982 | 8 | Heathrow | 19.9
1982-08-23 | 1982 | 8 | Heathrow | 18
1982-08-24 | 1982 | 8 | Heathrow | 19
1982-08-25 | 1982 | 8 | Heathrow | 19
1982-08-26 | 1982 | 8 | Heathrow | 20.4
1982-08-27 | 1982 | 8 | Heathrow | 20.6
1982-08-28 | 1982 | 8 | Heathrow | 22.3
1982-08-29 | 1982 | 8 | Heathrow | 20.6
1982-08-30 | 1982 | 8 | Heathrow | 20.6
1982-08-31 | 1982 | 8 | Heathrow | 17.7
1982-09-01 | 1982 | 9 | Heathrow | 21.3
1982-09-02 | 1982 | 9 | Heathrow | 23.5
1982-09-03 | 1982 | 9 | Heathrow | 23.9
1982-09-04 | 1982 | 9 | Heathrow | 24.7
1982-09-05 | 1982 | 9 | Heathrow | 24.7
1982-09-06 | 1982 | 9 | Heathrow | 23.4
1982-09-07 | 1982 | 9 | Heathrow | 20
1982-09-08 | 1982 | 9 | Heathrow | 22
1982-09-09 | 1982 | 9 | Heathrow | 24.6
1982-09-10 | 1982 | 9 | Heathrow | 20.6
1982-09-11 | 1982 | 9 | Heathrow | 23
1982-09-12 | 1982 | 9 | Heathrow | 21.8
1982-09-13 | 1982 | 9 | Heathrow | 22.3
1982-09-14 | 1982 | 9 | Heathrow | 26.1
1982-09-15 | 1982 | 9 | Heathrow | 25.7
1982-09-16 | 1982 | 9 | Heathrow | 26.1
1982-09-17 | 1982 | 9 | Heathrow | 28.3
1982-09-18 | 1982 | 9 | Heathrow | 28.4
1982-09-19 | 1982 | 9 | Heathrow | 20.8
1982-09-20 | 1982 | 9 | Heathrow | 20.9
1982-09-21 | 1982 | 9 | Heathrow | 16.3
1982-09-22 | 1982 | 9 | Heathrow | 17.3
1982-09-23 | 1982 | 9 | Heathrow | 17.1
1982-09-24 | 1982 | 9 | Heathrow | 20
1982-09-25 | 1982 | 9 | Heathrow | 18.1
1982-09-26 | 1982 | 9 | Heathrow | 15.7
1982-09-27 | 1982 | 9 | Heathrow | 18.4
1982-09-28 | 1982 | 9 | Heathrow | 18.5
1982-09-29 | 1982 | 9 | Heathrow | 17.5
1982-09-30 | 1982 | 9 | Heathrow | 18.1
1983-05-01 | 1983 | 5 | Heathrow | 12
1983-05-02 | 1983 | 5 | Heathrow | 14
1983-05-03 | 1983 | 5 | Heathrow | 15.3
1983-05-04 | 1983 | 5 | Heathrow | 19.1
1983-05-05 | 1983 | 5 | Heathrow | 18.2
1983-05-06 | 1983 | 5 | Heathrow | 15.4
1983-05-07 | 1983 | 5 | Heathrow | 17.5
1983-05-08 | 1983 | 5 | Heathrow | 13.9
1983-05-09 | 1983 | 5 | Heathrow | 13.5
1983-05-10 | 1983 | 5 | Heathrow | 13
1983-05-11 | 1983 | 5 | Heathrow | 14
1983-05-12 | 1983 | 5 | Heathrow | 15.9
1983-05-13 | 1983 | 5 | Heathrow | 16.3
1983-05-14 | 1983 | 5 | Heathrow | 16
1983-05-15 | 1983 | 5 | Heathrow | 18.5
1983-05-16 | 1983 | 5 | Heathrow | 15.8
1983-05-17 | 1983 | 5 | Heathrow | 15.4
1983-05-18 | 1983 | 5 | Heathrow | 13.5
1983-05-19 | 1983 | 5 | Heathrow | 14.1
1983-05-20 | 1983 | 5 | Heathrow | 14
1983-05-21 | 1983 | 5 | Heathrow | 15.4
1983-05-22 | 1983 | 5 | Heathrow | 16.2
1983-05-23 | 1983 | 5 | Heathrow | 17.2
1983-05-24 | 1983 | 5 | Heathrow | 18.9
1983-05-25 | 1983 | 5 | Heathrow | 14.1
1983-05-26 | 1983 | 5 | Heathrow | 15
1983-05-27 | 1983 | 5 | Heathrow | 12
1983-05-28 | 1983 | 5 | Heathrow | 14.2
1983-05-29 | 1983 | 5 | Heathrow | 17.5
1983-05-30 | 1983 | 5 | Heathrow | 22.6
1983-05-31 | 1983 | 5 | Heathrow | 21
1983-06-01 | 1983 | 6 | Heathrow | 18.1
1983-06-02 | 1983 | 6 | Heathrow | 20.1
1983-06-03 | 1983 | 6 | Heathrow | 21.8
1983-06-04 | 1983 | 6 | Heathrow | 21.4
1983-06-05 | 1983 | 6 | Heathrow | 20
1983-06-06 | 1983 | 6 | Heathrow | 24.8
1983-06-07 | 1983 | 6 | Heathrow | 24.4
1983-06-08 | 1983 | 6 | Heathrow | 24.5
1983-06-09 | 1983 | 6 | Heathrow | 20
1983-06-10 | 1983 | 6 | Heathrow | 20
1983-06-11 | 1983 | 6 | Heathrow | 20.4
1983-06-12 | 1983 | 6 | Heathrow | 18.2
1983-06-13 | 1983 | 6 | Heathrow | 18.9
1983-06-14 | 1983 | 6 | Heathrow | 17.3
1983-06-15 | 1983 | 6 | Heathrow | 17.9
1983-06-16 | 1983 | 6 | Heathrow | 17.7
1983-06-17 | 1983 | 6 | Heathrow | 21
1983-06-18 | 1983 | 6 | Heathrow | 23.3
1983-06-19 | 1983 | 6 | Heathrow | 24.5
1983-06-20 | 1983 | 6 | Heathrow | 24.2
1983-06-21 | 1983 | 6 | Heathrow | 23.8
1983-06-22 | 1983 | 6 | Heathrow | 23
1983-06-23 | 1983 | 6 | Heathrow | 23.1
1983-06-24 | 1983 | 6 | Heathrow | 22.6
1983-06-25 | 1983 | 6 | Heathrow | 25.4
1983-06-26 | 1983 | 6 | Heathrow | 25.5
1983-06-27 | 1983 | 6 | Heathrow | 20.7
1983-06-28 | 1983 | 6 | Heathrow | 21.7
1983-06-29 | 1983 | 6 | Heathrow | 18.7
1983-06-30 | 1983 | 6 | Heathrow | 22.3
1983-07-01 | 1983 | 7 | Heathrow | 25.3
1983-07-02 | 1983 | 7 | Heathrow | 26.2
1983-07-03 | 1983 | 7 | Heathrow | 28.4
1983-07-04 | 1983 | 7 | Heathrow | 28.8
1983-07-05 | 1983 | 7 | Heathrow | 26.6
1983-07-06 | 1983 | 7 | Heathrow | 26.1
1983-07-07 | 1983 | 7 | Heathrow | 28.2
1983-07-08 | 1983 | 7 | Heathrow | 27.2
1983-07-09 | 1983 | 7 | Heathrow | 27.5
1983-07-10 | 1983 | 7 | Heathrow | 30.6
1983-07-11 | 1983 | 7 | Heathrow | 30.6
1983-07-12 | 1983 | 7 | Heathrow | 31.6
1983-07-13 | 1983 | 7 | Heathrow | 31.4
1983-07-14 | 1983 | 7 | Heathrow | 32.6
1983-07-15 | 1983 | 7 | Heathrow | 32.8
1983-07-16 | 1983 | 7 | Heathrow | 28.5
1983-07-17 | 1983 | 7 | Heathrow | 28.5
1983-07-18 | 1983 | 7 | Heathrow | 25.6
1983-07-19 | 1983 | 7 | Heathrow | 21.2
1983-07-20 | 1983 | 7 | Heathrow | 23.8
1983-07-21 | 1983 | 7 | Heathrow | 27.3
1983-07-22 | 1983 | 7 | Heathrow | 24.6
1983-07-23 | 1983 | 7 | Heathrow | 22.7
1983-07-24 | 1983 | 7 | Heathrow | 25.3
1983-07-25 | 1983 | 7 | Heathrow | 28.2
1983-07-26 | 1983 | 7 | Heathrow | 27
1983-07-27 | 1983 | 7 | Heathrow | 26.8
1983-07-28 | 1983 | 7 | Heathrow | 31.4
1983-07-29 | 1983 | 7 | Heathrow | 30
1983-07-30 | 1983 | 7 | Heathrow | 28.9
1983-07-31 | 1983 | 7 | Heathrow | 29
1983-08-01 | 1983 | 8 | Heathrow | 19.4
1983-08-02 | 1983 | 8 | Heathrow | 22.5
1983-08-03 | 1983 | 8 | Heathrow | 23.9
1983-08-04 | 1983 | 8 | Heathrow | 24.6
1983-08-05 | 1983 | 8 | Heathrow | 21.2
1983-08-06 | 1983 | 8 | Heathrow | 22.7
1983-08-07 | 1983 | 8 | Heathrow | 26.4
1983-08-08 | 1983 | 8 | Heathrow | 28
1983-08-09 | 1983 | 8 | Heathrow | 25.3
1983-08-10 | 1983 | 8 | Heathrow | 21.5
1983-08-11 | 1983 | 8 | Heathrow | 25.3
1983-08-12 | 1983 | 8 | Heathrow | 23.7
1983-08-13 | 1983 | 8 | Heathrow | 28.8
1983-08-14 | 1983 | 8 | Heathrow | 27.2
1983-08-15 | 1983 | 8 | Heathrow | 25.6
1983-08-16 | 1983 | 8 | Heathrow | 25.9
1983-08-17 | 1983 | 8 | Heathrow | 26.7
1983-08-18 | 1983 | 8 | Heathrow | 30.2
1983-08-19 | 1983 | 8 | Heathrow | 24.2
1983-08-20 | 1983 | 8 | Heathrow | 24.2
1983-08-21 | 1983 | 8 | Heathrow | 26.3
1983-08-22 | 1983 | 8 | Heathrow | 26.1
1983-08-23 | 1983 | 8 | Heathrow | 22.4
1983-08-24 | 1983 | 8 | Heathrow | 26.1
1983-08-25 | 1983 | 8 | Heathrow | 26.7
1983-08-26 | 1983 | 8 | Heathrow | 25.9
1983-08-27 | 1983 | 8 | Heathrow | 21
1983-08-28 | 1983 | 8 | Heathrow | 19.4
1983-08-29 | 1983 | 8 | Heathrow | 21.7
1983-08-30 | 1983 | 8 | Heathrow | 26.9
1983-08-31 | 1983 | 8 | Heathrow | 22.4
1983-09-01 | 1983 | 9 | Heathrow | 20.6
1983-09-02 | 1983 | 9 | Heathrow | 19.3
1983-09-03 | 1983 | 9 | Heathrow | 23.4
1983-09-04 | 1983 | 9 | Heathrow | 21.6
1983-09-05 | 1983 | 9 | Heathrow | 21
1983-09-06 | 1983 | 9 | Heathrow | 21.2
1983-09-07 | 1983 | 9 | Heathrow | 19.5
1983-09-08 | 1983 | 9 | Heathrow | 18.7
1983-09-09 | 1983 | 9 | Heathrow | 18.1
1983-09-10 | 1983 | 9 | Heathrow | 18.1
1983-09-11 | 1983 | 9 | Heathrow | 15.9
1983-09-12 | 1983 | 9 | Heathrow | 16
1983-09-13 | 1983 | 9 | Heathrow | 19
1983-09-14 | 1983 | 9 | Heathrow | 18.2
1983-09-15 | 1983 | 9 | Heathrow | 17.8
1983-09-16 | 1983 | 9 | Heathrow | 19
1983-09-17 | 1983 | 9 | Heathrow | 17.6
1983-09-18 | 1983 | 9 | Heathrow | 19.1
1983-09-19 | 1983 | 9 | Heathrow | 17
1983-09-20 | 1983 | 9 | Heathrow | 14.9
1983-09-21 | 1983 | 9 | Heathrow | 17.6
1983-09-22 | 1983 | 9 | Heathrow | 23
1983-09-23 | 1983 | 9 | Heathrow | 22.4
1983-09-24 | 1983 | 9 | Heathrow | 20.4
1983-09-25 | 1983 | 9 | Heathrow | 24.4
1983-09-26 | 1983 | 9 | Heathrow | 19.3
1983-09-27 | 1983 | 9 | Heathrow | 19.6
1983-09-28 | 1983 | 9 | Heathrow | 19.7
1983-09-29 | 1983 | 9 | Heathrow | 18.6
1983-09-30 | 1983 | 9 | Heathrow | 16.7
1984-05-01 | 1984 | 5 | Heathrow | 17.1
1984-05-02 | 1984 | 5 | Heathrow | 13.5
1984-05-03 | 1984 | 5 | Heathrow | 17.1
1984-05-04 | 1984 | 5 | Heathrow | 14.8
1984-05-05 | 1984 | 5 | Heathrow | 12.6
1984-05-06 | 1984 | 5 | Heathrow | 12.7
1984-05-07 | 1984 | 5 | Heathrow | 11.1
1984-05-08 | 1984 | 5 | Heathrow | 16.2
1984-05-09 | 1984 | 5 | Heathrow | 12.5
1984-05-10 | 1984 | 5 | Heathrow | 13.9
1984-05-11 | 1984 | 5 | Heathrow | 14.4
1984-05-12 | 1984 | 5 | Heathrow | 16.6
1984-05-13 | 1984 | 5 | Heathrow | 16.5
1984-05-14 | 1984 | 5 | Heathrow | 13.1
1984-05-15 | 1984 | 5 | Heathrow | 17
1984-05-16 | 1984 | 5 | Heathrow | 12.9
1984-05-17 | 1984 | 5 | Heathrow | 14.4
1984-05-18 | 1984 | 5 | Heathrow | 16
1984-05-19 | 1984 | 5 | Heathrow | 11.9
1984-05-20 | 1984 | 5 | Heathrow | 13.7
1984-05-21 | 1984 | 5 | Heathrow | 13.2
1984-05-22 | 1984 | 5 | Heathrow | 18.3
1984-05-23 | 1984 | 5 | Heathrow | 23
1984-05-24 | 1984 | 5 | Heathrow | 23.1
1984-05-25 | 1984 | 5 | Heathrow | 10.9
1984-05-26 | 1984 | 5 | Heathrow | 10.4
1984-05-27 | 1984 | 5 | Heathrow | 10.9
1984-05-28 | 1984 | 5 | Heathrow | 17.2
1984-05-29 | 1984 | 5 | Heathrow | 20.3
1984-05-30 | 1984 | 5 | Heathrow | 19.4
1984-05-31 | 1984 | 5 | Heathrow | 15
1984-06-01 | 1984 | 6 | Heathrow | 16.7
1984-06-02 | 1984 | 6 | Heathrow | 16.5
1984-06-03 | 1984 | 6 | Heathrow | 18
1984-06-04 | 1984 | 6 | Heathrow | 16.1
1984-06-05 | 1984 | 6 | Heathrow | 18.1
1984-06-06 | 1984 | 6 | Heathrow | 21.8
1984-06-07 | 1984 | 6 | Heathrow | 21.9
1984-06-08 | 1984 | 6 | Heathrow | 23.3
1984-06-09 | 1984 | 6 | Heathrow | 24.6
1984-06-10 | 1984 | 6 | Heathrow | 18.7
1984-06-11 | 1984 | 6 | Heathrow | 18.8
1984-06-12 | 1984 | 6 | Heathrow | 21.5
1984-06-13 | 1984 | 6 | Heathrow | 23.7
1984-06-14 | 1984 | 6 | Heathrow | 23.7
1984-06-15 | 1984 | 6 | Heathrow | 23.2
1984-06-16 | 1984 | 6 | Heathrow | 25.3
1984-06-17 | 1984 | 6 | Heathrow | 26
1984-06-18 | 1984 | 6 | Heathrow | 26.2
1984-06-19 | 1984 | 6 | Heathrow | 27
1984-06-20 | 1984 | 6 | Heathrow | 27.1
1984-06-21 | 1984 | 6 | Heathrow | 20.9
1984-06-22 | 1984 | 6 | Heathrow | 19.7
1984-06-23 | 1984 | 6 | Heathrow | 20.5
1984-06-24 | 1984 | 6 | Heathrow | 22.9
1984-06-25 | 1984 | 6 | Heathrow | 25.8
1984-06-26 | 1984 | 6 | Heathrow | 24.4
1984-06-27 | 1984 | 6 | Heathrow | 24.5
1984-06-28 | 1984 | 6 | Heathrow | 18.8
1984-06-29 | 1984 | 6 | Heathrow | 19.4
1984-06-30 | 1984 | 6 | Heathrow | 21.9
1984-07-01 | 1984 | 7 | Heathrow | 18.1
1984-07-02 | 1984 | 7 | Heathrow | 22
1984-07-03 | 1984 | 7 | Heathrow | 22.5
1984-07-04 | 1984 | 7 | Heathrow | 26.1
1984-07-05 | 1984 | 7 | Heathrow | 27.7
1984-07-06 | 1984 | 7 | Heathrow | 28.2
1984-07-07 | 1984 | 7 | Heathrow | 31.7
1984-07-08 | 1984 | 7 | Heathrow | 31.7
1984-07-09 | 1984 | 7 | Heathrow | 24.4
1984-07-10 | 1984 | 7 | Heathrow | 23.3
1984-07-11 | 1984 | 7 | Heathrow | 20.1
1984-07-12 | 1984 | 7 | Heathrow | 21.9
1984-07-13 | 1984 | 7 | Heathrow | 19.9
1984-07-14 | 1984 | 7 | Heathrow | 18.9
1984-07-15 | 1984 | 7 | Heathrow | 21.2
1984-07-16 | 1984 | 7 | Heathrow | 23.4
1984-07-17 | 1984 | 7 | Heathrow | 24.5
1984-07-18 | 1984 | 7 | Heathrow | 21.2
1984-07-19 | 1984 | 7 | Heathrow | 20.2
1984-07-20 | 1984 | 7 | Heathrow | 27.3
1984-07-21 | 1984 | 7 | Heathrow | 25.8
1984-07-22 | 1984 | 7 | Heathrow | 26.8
1984-07-23 | 1984 | 7 | Heathrow | 23.5
1984-07-24 | 1984 | 7 | Heathrow | 19.3
1984-07-25 | 1984 | 7 | Heathrow | 24.3
1984-07-26 | 1984 | 7 | Heathrow | 30.6
1984-07-27 | 1984 | 7 | Heathrow | 30.6
1984-07-28 | 1984 | 7 | Heathrow | 28.4
1984-07-29 | 1984 | 7 | Heathrow | 28.9
1984-07-30 | 1984 | 7 | Heathrow | 25.5
1984-07-31 | 1984 | 7 | Heathrow | 25.3
1984-08-01 | 1984 | 8 | Heathrow | 22.2
1984-08-02 | 1984 | 8 | Heathrow | 22.8
1984-08-03 | 1984 | 8 | Heathrow | 19.8
1984-08-04 | 1984 | 8 | Heathrow | 19.8
1984-08-05 | 1984 | 8 | Heathrow | 22.8
1984-08-06 | 1984 | 8 | Heathrow | 19.5
1984-08-07 | 1984 | 8 | Heathrow | 21.5
1984-08-08 | 1984 | 8 | Heathrow | 24
1984-08-09 | 1984 | 8 | Heathrow | 19.8
1984-08-10 | 1984 | 8 | Heathrow | 23.1
1984-08-11 | 1984 | 8 | Heathrow | 23.6
1984-08-12 | 1984 | 8 | Heathrow | 24.5
1984-08-13 | 1984 | 8 | Heathrow | 26.5
1984-08-14 | 1984 | 8 | Heathrow | 26.2
1984-08-15 | 1984 | 8 | Heathrow | 24.9
1984-08-16 | 1984 | 8 | Heathrow | 24.3
1984-08-17 | 1984 | 8 | Heathrow | 25.9
1984-08-18 | 1984 | 8 | Heathrow | 28.8
1984-08-19 | 1984 | 8 | Heathrow | 29.7
1984-08-20 | 1984 | 8 | Heathrow | 29.8
1984-08-21 | 1984 | 8 | Heathrow | 23.9
1984-08-22 | 1984 | 8 | Heathrow | 27
1984-08-23 | 1984 | 8 | Heathrow | 23.9
1984-08-24 | 1984 | 8 | Heathrow | 23.7
1984-08-25 | 1984 | 8 | Heathrow | 23.5
1984-08-26 | 1984 | 8 | Heathrow | 26.5
1984-08-27 | 1984 | 8 | Heathrow | 26.2
1984-08-28 | 1984 | 8 | Heathrow | 26.3
1984-08-29 | 1984 | 8 | Heathrow | 26.9
1984-08-30 | 1984 | 8 | Heathrow | 25
1984-08-31 | 1984 | 8 | Heathrow | 24.4
1984-09-01 | 1984 | 9 | Heathrow | 25.3
1984-09-02 | 1984 | 9 | Heathrow | 25.4
1984-09-03 | 1984 | 9 | Heathrow | 25.5
1984-09-04 | 1984 | 9 | Heathrow | 16.6
1984-09-05 | 1984 | 9 | Heathrow | 17.4
1984-09-06 | 1984 | 9 | Heathrow | 16.6
1984-09-07 | 1984 | 9 | Heathrow | 19.4
1984-09-08 | 1984 | 9 | Heathrow | 21.2
1984-09-09 | 1984 | 9 | Heathrow | 21.2
1984-09-10 | 1984 | 9 | Heathrow | 22.1
1984-09-11 | 1984 | 9 | Heathrow | 22.4
1984-09-12 | 1984 | 9 | Heathrow | 21.5
1984-09-13 | 1984 | 9 | Heathrow | 19
1984-09-14 | 1984 | 9 | Heathrow | 17.2
1984-09-15 | 1984 | 9 | Heathrow | 18.6
1984-09-16 | 1984 | 9 | Heathrow | 16
1984-09-17 | 1984 | 9 | Heathrow | 18.1
1984-09-18 | 1984 | 9 | Heathrow | 18.4
1984-09-19 | 1984 | 9 | Heathrow | 17.6
1984-09-20 | 1984 | 9 | Heathrow | 15.2
1984-09-21 | 1984 | 9 | Heathrow | 16.7
1984-09-22 | 1984 | 9 | Heathrow | 16.7
1984-09-23 | 1984 | 9 | Heathrow | 13.6
1984-09-24 | 1984 | 9 | Heathrow | 16
1984-09-25 | 1984 | 9 | Heathrow | 17.6
1984-09-26 | 1984 | 9 | Heathrow | 18.1
1984-09-27 | 1984 | 9 | Heathrow | 20.5
1984-09-28 | 1984 | 9 | Heathrow | 19.2
1984-09-29 | 1984 | 9 | Heathrow | 17
1984-09-30 | 1984 | 9 | Heathrow | 16.4
1985-05-01 | 1985 | 5 | Heathrow | 13.5
1985-05-02 | 1985 | 5 | Heathrow | 10.4
1985-05-03 | 1985 | 5 | Heathrow | 13.3
1985-05-04 | 1985 | 5 | Heathrow | 12.9
1985-05-05 | 1985 | 5 | Heathrow | 17
1985-05-06 | 1985 | 5 | Heathrow | 19.1
1985-05-07 | 1985 | 5 | Heathrow | 15.1
1985-05-08 | 1985 | 5 | Heathrow | 15.9
1985-05-09 | 1985 | 5 | Heathrow | 13
1985-05-10 | 1985 | 5 | Heathrow | 9.6
1985-05-11 | 1985 | 5 | Heathrow | 12.7
1985-05-12 | 1985 | 5 | Heathrow | 14.5
1985-05-13 | 1985 | 5 | Heathrow | 11.8
1985-05-14 | 1985 | 5 | Heathrow | 16.3
1985-05-15 | 1985 | 5 | Heathrow | 20.8
1985-05-16 | 1985 | 5 | Heathrow | 21.4
1985-05-17 | 1985 | 5 | Heathrow | 21.3
1985-05-18 | 1985 | 5 | Heathrow | 15.8
1985-05-19 | 1985 | 5 | Heathrow | 19.8
1985-05-20 | 1985 | 5 | Heathrow | 16.4
1985-05-21 | 1985 | 5 | Heathrow | 15
1985-05-22 | 1985 | 5 | Heathrow | 15.8
1985-05-23 | 1985 | 5 | Heathrow | 16.9
1985-05-24 | 1985 | 5 | Heathrow | 19.6
1985-05-25 | 1985 | 5 | Heathrow | 20.8
1985-05-26 | 1985 | 5 | Heathrow | 18.1
1985-05-27 | 1985 | 5 | Heathrow | 18.6
1985-05-28 | 1985 | 5 | Heathrow | 19.6
1985-05-29 | 1985 | 5 | Heathrow | 19.1
1985-05-30 | 1985 | 5 | Heathrow | 19.7
1985-05-31 | 1985 | 5 | Heathrow | 22
1985-06-01 | 1985 | 6 | Heathrow | 23.5
1985-06-02 | 1985 | 6 | Heathrow | 25
1985-06-03 | 1985 | 6 | Heathrow | 24.3
1985-06-04 | 1985 | 6 | Heathrow | 20.4
1985-06-05 | 1985 | 6 | Heathrow | 20.5
1985-06-06 | 1985 | 6 | Heathrow | 14.2
1985-06-07 | 1985 | 6 | Heathrow | 15.7
1985-06-08 | 1985 | 6 | Heathrow | 18
1985-06-09 | 1985 | 6 | Heathrow | 17
1985-06-10 | 1985 | 6 | Heathrow | 16.4
1985-06-11 | 1985 | 6 | Heathrow | 16.6
1985-06-12 | 1985 | 6 | Heathrow | 16.7
1985-06-13 | 1985 | 6 | Heathrow | 16.4
1985-06-14 | 1985 | 6 | Heathrow | 17.8
1985-06-15 | 1985 | 6 | Heathrow | 17.9
1985-06-16 | 1985 | 6 | Heathrow | 19.5
1985-06-17 | 1985 | 6 | Heathrow | 17.5
1985-06-18 | 1985 | 6 | Heathrow | 19.7
1985-06-19 | 1985 | 6 | Heathrow | 20.1
1985-06-20 | 1985 | 6 | Heathrow | 16
1985-06-21 | 1985 | 6 | Heathrow | 16.6
1985-06-22 | 1985 | 6 | Heathrow | 19.1
1985-06-23 | 1985 | 6 | Heathrow | 18.2
1985-06-24 | 1985 | 6 | Heathrow | 15.9
1985-06-25 | 1985 | 6 | Heathrow | 18.2
1985-06-26 | 1985 | 6 | Heathrow | 18.8
1985-06-27 | 1985 | 6 | Heathrow | 17.9
1985-06-28 | 1985 | 6 | Heathrow | 21.1
1985-06-29 | 1985 | 6 | Heathrow | 21.7
1985-06-30 | 1985 | 6 | Heathrow | 22.9
1985-07-01 | 1985 | 7 | Heathrow | 23.9
1985-07-02 | 1985 | 7 | Heathrow | 24.5
1985-07-03 | 1985 | 7 | Heathrow | 27.1
1985-07-04 | 1985 | 7 | Heathrow | 26.5
1985-07-05 | 1985 | 7 | Heathrow | 26.6
1985-07-06 | 1985 | 7 | Heathrow | 22
1985-07-07 | 1985 | 7 | Heathrow | 25.6
1985-07-08 | 1985 | 7 | Heathrow | 21.7
1985-07-09 | 1985 | 7 | Heathrow | 22.1
1985-07-10 | 1985 | 7 | Heathrow | 20.5
1985-07-11 | 1985 | 7 | Heathrow | 24.4
1985-07-12 | 1985 | 7 | Heathrow | 28.9
1985-07-13 | 1985 | 7 | Heathrow | 24.4
1985-07-14 | 1985 | 7 | Heathrow | 24.5
1985-07-15 | 1985 | 7 | Heathrow | 22.2
1985-07-16 | 1985 | 7 | Heathrow | 21.3
1985-07-17 | 1985 | 7 | Heathrow | 19.4
1985-07-18 | 1985 | 7 | Heathrow | 19.9
1985-07-19 | 1985 | 7 | Heathrow | 19.9
1985-07-20 | 1985 | 7 | Heathrow | 21.2
1985-07-21 | 1985 | 7 | Heathrow | 20.8
1985-07-22 | 1985 | 7 | Heathrow | 24.8
1985-07-23 | 1985 | 7 | Heathrow | 26.7
1985-07-24 | 1985 | 7 | Heathrow | 29.8
1985-07-25 | 1985 | 7 | Heathrow | 29.9
1985-07-26 | 1985 | 7 | Heathrow | 23.4
1985-07-27 | 1985 | 7 | Heathrow | 19.5
1985-07-28 | 1985 | 7 | Heathrow | 18.5
1985-07-29 | 1985 | 7 | Heathrow | 19.3
1985-07-30 | 1985 | 7 | Heathrow | 23.7
1985-07-31 | 1985 | 7 | Heathrow | 20.8
1985-08-01 | 1985 | 8 | Heathrow | 17.8
1985-08-02 | 1985 | 8 | Heathrow | 19.2
1985-08-03 | 1985 | 8 | Heathrow | 17.4
1985-08-04 | 1985 | 8 | Heathrow | 19
1985-08-05 | 1985 | 8 | Heathrow | 19.7
1985-08-06 | 1985 | 8 | Heathrow | 17.2
1985-08-07 | 1985 | 8 | Heathrow | 20.8
1985-08-08 | 1985 | 8 | Heathrow | 18.6
1985-08-09 | 1985 | 8 | Heathrow | 20
1985-08-10 | 1985 | 8 | Heathrow | 19.5
1985-08-11 | 1985 | 8 | Heathrow | 19.8
1985-08-12 | 1985 | 8 | Heathrow | 20.6
1985-08-13 | 1985 | 8 | Heathrow | 20.7
1985-08-14 | 1985 | 8 | Heathrow | 19.6
1985-08-15 | 1985 | 8 | Heathrow | 19.1
1985-08-16 | 1985 | 8 | Heathrow | 21.8
1985-08-17 | 1985 | 8 | Heathrow | 20.3
1985-08-18 | 1985 | 8 | Heathrow | 21.5
1985-08-19 | 1985 | 8 | Heathrow | 19.6
1985-08-20 | 1985 | 8 | Heathrow | 22.9
1985-08-21 | 1985 | 8 | Heathrow | 20.5
1985-08-22 | 1985 | 8 | Heathrow | 19.3
1985-08-23 | 1985 | 8 | Heathrow | 18.7
1985-08-24 | 1985 | 8 | Heathrow | 19.4
1985-08-25 | 1985 | 8 | Heathrow | 18.5
1985-08-26 | 1985 | 8 | Heathrow | 21.2
1985-08-27 | 1985 | 8 | Heathrow | 23.1
1985-08-28 | 1985 | 8 | Heathrow | 26
1985-08-29 | 1985 | 8 | Heathrow | 25.9
1985-08-30 | 1985 | 8 | Heathrow | 20.6
1985-08-31 | 1985 | 8 | Heathrow | 17.6
1985-09-01 | 1985 | 9 | Heathrow | 16.4
1985-09-02 | 1985 | 9 | Heathrow | 19.6
1985-09-03 | 1985 | 9 | Heathrow | 17
1985-09-04 | 1985 | 9 | Heathrow | 18.8
1985-09-05 | 1985 | 9 | Heathrow | 17.9
1985-09-06 | 1985 | 9 | Heathrow | 20.1
1985-09-07 | 1985 | 9 | Heathrow | 20.5
1985-09-08 | 1985 | 9 | Heathrow | 20.9
1985-09-09 | 1985 | 9 | Heathrow | 22.7
1985-09-10 | 1985 | 9 | Heathrow | 25.2
1985-09-11 | 1985 | 9 | Heathrow | 26.9
1985-09-12 | 1985 | 9 | Heathrow | 27
1985-09-13 | 1985 | 9 | Heathrow | 16.2
1985-09-14 | 1985 | 9 | Heathrow | 17.5
1985-09-15 | 1985 | 9 | Heathrow | 19.3
1985-09-16 | 1985 | 9 | Heathrow | 22.8
1985-09-17 | 1985 | 9 | Heathrow | 20.7
1985-09-18 | 1985 | 9 | Heathrow | 20.6
1985-09-19 | 1985 | 9 | Heathrow | 18.9
1985-09-20 | 1985 | 9 | Heathrow | 19.7
1985-09-21 | 1985 | 9 | Heathrow | 23
1985-09-22 | 1985 | 9 | Heathrow | 21.1
1985-09-23 | 1985 | 9 | Heathrow | 18.9
1985-09-24 | 1985 | 9 | Heathrow | 19.8
1985-09-25 | 1985 | 9 | Heathrow | 24.1
1985-09-26 | 1985 | 9 | Heathrow | 22.9
1985-09-27 | 1985 | 9 | Heathrow | 22.1
1985-09-28 | 1985 | 9 | Heathrow | 24
1985-09-29 | 1985 | 9 | Heathrow | 25
1985-09-30 | 1985 | 9 | Heathrow | 27
1986-05-01 | 1986 | 5 | Heathrow | 22
1986-05-02 | 1986 | 5 | Heathrow | 22.1
1986-05-03 | 1986 | 5 | Heathrow | 14.1
1986-05-04 | 1986 | 5 | Heathrow | 14.5
1986-05-05 | 1986 | 5 | Heathrow | 16.8
1986-05-06 | 1986 | 5 | Heathrow | 13.1
1986-05-07 | 1986 | 5 | Heathrow | 13.9
1986-05-08 | 1986 | 5 | Heathrow | 15.6
1986-05-09 | 1986 | 5 | Heathrow | 17.9
1986-05-10 | 1986 | 5 | Heathrow | 17
1986-05-11 | 1986 | 5 | Heathrow | 15.1
1986-05-12 | 1986 | 5 | Heathrow | 15.5
1986-05-13 | 1986 | 5 | Heathrow | 15.2
1986-05-14 | 1986 | 5 | Heathrow | 15
1986-05-15 | 1986 | 5 | Heathrow | 17
1986-05-16 | 1986 | 5 | Heathrow | 15.4
1986-05-17 | 1986 | 5 | Heathrow | 17.2
1986-05-18 | 1986 | 5 | Heathrow | 21.2
1986-05-19 | 1986 | 5 | Heathrow | 18.2
1986-05-20 | 1986 | 5 | Heathrow | 18.2
1986-05-21 | 1986 | 5 | Heathrow | 16.7
1986-05-22 | 1986 | 5 | Heathrow | 16.3
1986-05-23 | 1986 | 5 | Heathrow | 17.1
1986-05-24 | 1986 | 5 | Heathrow | 16.1
1986-05-25 | 1986 | 5 | Heathrow | 18.8
1986-05-26 | 1986 | 5 | Heathrow | 17
1986-05-27 | 1986 | 5 | Heathrow | 15
1986-05-28 | 1986 | 5 | Heathrow | 15.6
1986-05-29 | 1986 | 5 | Heathrow | 16.1
1986-05-30 | 1986 | 5 | Heathrow | 13.9
1986-05-31 | 1986 | 5 | Heathrow | 17.6
1986-06-01 | 1986 | 6 | Heathrow | 20.4
1986-06-02 | 1986 | 6 | Heathrow | 20.5
1986-06-03 | 1986 | 6 | Heathrow | 15
1986-06-04 | 1986 | 6 | Heathrow | 14.7
1986-06-05 | 1986 | 6 | Heathrow | 15.3
1986-06-06 | 1986 | 6 | Heathrow | 19.4
1986-06-07 | 1986 | 6 | Heathrow | 17.6
1986-06-08 | 1986 | 6 | Heathrow | 18
1986-06-09 | 1986 | 6 | Heathrow | 18.4
1986-06-10 | 1986 | 6 | Heathrow | 16.4
1986-06-11 | 1986 | 6 | Heathrow | 20.1
1986-06-12 | 1986 | 6 | Heathrow | 23.6
1986-06-13 | 1986 | 6 | Heathrow | 25
1986-06-14 | 1986 | 6 | Heathrow | 26.3
1986-06-15 | 1986 | 6 | Heathrow | 28.6
1986-06-16 | 1986 | 6 | Heathrow | 22.4
1986-06-17 | 1986 | 6 | Heathrow | 20.6
1986-06-18 | 1986 | 6 | Heathrow | 23.6
1986-06-19 | 1986 | 6 | Heathrow | 20.4
1986-06-20 | 1986 | 6 | Heathrow | 23
1986-06-21 | 1986 | 6 | Heathrow | 18.5
1986-06-22 | 1986 | 6 | Heathrow | 17.6
1986-06-23 | 1986 | 6 | Heathrow | 20.6
1986-06-24 | 1986 | 6 | Heathrow | 26.6
1986-06-25 | 1986 | 6 | Heathrow | 27.1
1986-06-26 | 1986 | 6 | Heathrow | 30.3
1986-06-27 | 1986 | 6 | Heathrow | 30.2
1986-06-28 | 1986 | 6 | Heathrow | 28.8
1986-06-29 | 1986 | 6 | Heathrow | 30.6
1986-06-30 | 1986 | 6 | Heathrow | 26.5
1986-07-01 | 1986 | 7 | Heathrow | 27.1
1986-07-02 | 1986 | 7 | Heathrow | 25
1986-07-03 | 1986 | 7 | Heathrow | 25.6
1986-07-04 | 1986 | 7 | Heathrow | 25.6
1986-07-05 | 1986 | 7 | Heathrow | 21.3
1986-07-06 | 1986 | 7 | Heathrow | 20.5
1986-07-07 | 1986 | 7 | Heathrow | 22.3
1986-07-08 | 1986 | 7 | Heathrow | 20.7
1986-07-09 | 1986 | 7 | Heathrow | 23.3
1986-07-10 | 1986 | 7 | Heathrow | 21.5
1986-07-11 | 1986 | 7 | Heathrow | 20
1986-07-12 | 1986 | 7 | Heathrow | 21.9
1986-07-13 | 1986 | 7 | Heathrow | 25.3
1986-07-14 | 1986 | 7 | Heathrow | 29.1
1986-07-15 | 1986 | 7 | Heathrow | 28
1986-07-16 | 1986 | 7 | Heathrow | 28.1
1986-07-17 | 1986 | 7 | Heathrow | 19.6
1986-07-18 | 1986 | 7 | Heathrow | 20.4
1986-07-19 | 1986 | 7 | Heathrow | 23.8
1986-07-20 | 1986 | 7 | Heathrow | 22.1
1986-07-21 | 1986 | 7 | Heathrow | 20.6
1986-07-22 | 1986 | 7 | Heathrow | 17.4
1986-07-23 | 1986 | 7 | Heathrow | 22.5
1986-07-24 | 1986 | 7 | Heathrow | 21.9
1986-07-25 | 1986 | 7 | Heathrow | 23.3
1986-07-26 | 1986 | 7 | Heathrow | 23
1986-07-27 | 1986 | 7 | Heathrow | 21.2
1986-07-28 | 1986 | 7 | Heathrow | 22
1986-07-29 | 1986 | 7 | Heathrow | 20.6
1986-07-30 | 1986 | 7 | Heathrow | 21.6
1986-07-31 | 1986 | 7 | Heathrow | 21.5
1986-08-01 | 1986 | 8 | Heathrow | 22.6
1986-08-02 | 1986 | 8 | Heathrow | 22.6
1986-08-03 | 1986 | 8 | Heathrow | 19.3
1986-08-04 | 1986 | 8 | Heathrow | 21.2
1986-08-05 | 1986 | 8 | Heathrow | 24.5
1986-08-06 | 1986 | 8 | Heathrow | 20.6
1986-08-07 | 1986 | 8 | Heathrow | 22.4
1986-08-08 | 1986 | 8 | Heathrow | 22.3
1986-08-09 | 1986 | 8 | Heathrow | 25
1986-08-10 | 1986 | 8 | Heathrow | 20.9
1986-08-11 | 1986 | 8 | Heathrow | 20
1986-08-12 | 1986 | 8 | Heathrow | 22.9
1986-08-13 | 1986 | 8 | Heathrow | 22.6
1986-08-14 | 1986 | 8 | Heathrow | 22.3
1986-08-15 | 1986 | 8 | Heathrow | 21.7
1986-08-16 | 1986 | 8 | Heathrow | 21.2
1986-08-17 | 1986 | 8 | Heathrow | 17
1986-08-18 | 1986 | 8 | Heathrow | 18.8
1986-08-19 | 1986 | 8 | Heathrow | 20.5
1986-08-20 | 1986 | 8 | Heathrow | 19.4
1986-08-21 | 1986 | 8 | Heathrow | 19.7
1986-08-22 | 1986 | 8 | Heathrow | 17.9
1986-08-23 | 1986 | 8 | Heathrow | 19.1
1986-08-24 | 1986 | 8 | Heathrow | 16.6
1986-08-25 | 1986 | 8 | Heathrow | 16.6
1986-08-26 | 1986 | 8 | Heathrow | 17.9
1986-08-27 | 1986 | 8 | Heathrow | 17.4
1986-08-28 | 1986 | 8 | Heathrow | 17.6
1986-08-29 | 1986 | 8 | Heathrow | 15.8
1986-08-30 | 1986 | 8 | Heathrow | 18.4
1986-08-31 | 1986 | 8 | Heathrow | 16.9
1986-09-01 | 1986 | 9 | Heathrow | 21.5
1986-09-02 | 1986 | 9 | Heathrow | 16.5
1986-09-03 | 1986 | 9 | Heathrow | 19.6
1986-09-04 | 1986 | 9 | Heathrow | 19.3
1986-09-05 | 1986 | 9 | Heathrow | 17.3
1986-09-06 | 1986 | 9 | Heathrow | 19.8
1986-09-07 | 1986 | 9 | Heathrow | 16.5
1986-09-08 | 1986 | 9 | Heathrow | 17.2
1986-09-09 | 1986 | 9 | Heathrow | 17
1986-09-10 | 1986 | 9 | Heathrow | 18
1986-09-11 | 1986 | 9 | Heathrow | 16.4
1986-09-12 | 1986 | 9 | Heathrow | 14.9
1986-09-13 | 1986 | 9 | Heathrow | 16
1986-09-14 | 1986 | 9 | Heathrow | 16.1
1986-09-15 | 1986 | 9 | Heathrow | 15
1986-09-16 | 1986 | 9 | Heathrow | 14
1986-09-17 | 1986 | 9 | Heathrow | 16
1986-09-18 | 1986 | 9 | Heathrow | 16.9
1986-09-19 | 1986 | 9 | Heathrow | 20.2
1986-09-20 | 1986 | 9 | Heathrow | 20.5
1986-09-21 | 1986 | 9 | Heathrow | 20.3
1986-09-22 | 1986 | 9 | Heathrow | 20.1
1986-09-23 | 1986 | 9 | Heathrow | 14.9
1986-09-24 | 1986 | 9 | Heathrow | 16.9
1986-09-25 | 1986 | 9 | Heathrow | 17
1986-09-26 | 1986 | 9 | Heathrow | 19.2
1986-09-27 | 1986 | 9 | Heathrow | 19.6
1986-09-28 | 1986 | 9 | Heathrow | 16.7
1986-09-29 | 1986 | 9 | Heathrow | 15.8
1986-09-30 | 1986 | 9 | Heathrow | 15.7
1987-05-01 | 1987 | 5 | Heathrow | 17.2
1987-05-02 | 1987 | 5 | Heathrow | 10.1
1987-05-03 | 1987 | 5 | Heathrow | 12.3
1987-05-04 | 1987 | 5 | Heathrow | 14.2
1987-05-05 | 1987 | 5 | Heathrow | 17.7
1987-05-06 | 1987 | 5 | Heathrow | 17.6
1987-05-07 | 1987 | 5 | Heathrow | 20.4
1987-05-08 | 1987 | 5 | Heathrow | 23.7
1987-05-09 | 1987 | 5 | Heathrow | 23.7
1987-05-10 | 1987 | 5 | Heathrow | 15.2
1987-05-11 | 1987 | 5 | Heathrow | 14.8
1987-05-12 | 1987 | 5 | Heathrow | 13.8
1987-05-13 | 1987 | 5 | Heathrow | 14.5
1987-05-14 | 1987 | 5 | Heathrow | 12.3
1987-05-15 | 1987 | 5 | Heathrow | 14.6
1987-05-16 | 1987 | 5 | Heathrow | 13.8
1987-05-17 | 1987 | 5 | Heathrow | 13.2
1987-05-18 | 1987 | 5 | Heathrow | 17.2
1987-05-19 | 1987 | 5 | Heathrow | 13.6
1987-05-20 | 1987 | 5 | Heathrow | 14.6
1987-05-21 | 1987 | 5 | Heathrow | 13.1
1987-05-22 | 1987 | 5 | Heathrow | 11.7
1987-05-23 | 1987 | 5 | Heathrow | 18.9
1987-05-24 | 1987 | 5 | Heathrow | 17.5
1987-05-25 | 1987 | 5 | Heathrow | 22.6
1987-05-26 | 1987 | 5 | Heathrow | 19.9
1987-05-27 | 1987 | 5 | Heathrow | 18.8
1987-05-28 | 1987 | 5 | Heathrow | 19.9
1987-05-29 | 1987 | 5 | Heathrow | 20.6
1987-05-30 | 1987 | 5 | Heathrow | 20.9
1987-05-31 | 1987 | 5 | Heathrow | 20.5
1987-06-01 | 1987 | 6 | Heathrow | 15.5
1987-06-02 | 1987 | 6 | Heathrow | 19
1987-06-03 | 1987 | 6 | Heathrow | 19.1
1987-06-04 | 1987 | 6 | Heathrow | 15.6
1987-06-05 | 1987 | 6 | Heathrow | 18.3
1987-06-06 | 1987 | 6 | Heathrow | 16.7
1987-06-07 | 1987 | 6 | Heathrow | 14.2
1987-06-08 | 1987 | 6 | Heathrow | 13.4
1987-06-09 | 1987 | 6 | Heathrow | 17.3
1987-06-10 | 1987 | 6 | Heathrow | 17.2
1987-06-11 | 1987 | 6 | Heathrow | 18.2
1987-06-12 | 1987 | 6 | Heathrow | 17.1
1987-06-13 | 1987 | 6 | Heathrow | 17.9
1987-06-14 | 1987 | 6 | Heathrow | 18
1987-06-15 | 1987 | 6 | Heathrow | 16.5
1987-06-16 | 1987 | 6 | Heathrow | 16.2
1987-06-17 | 1987 | 6 | Heathrow | 18.2
1987-06-18 | 1987 | 6 | Heathrow | 16.2
1987-06-19 | 1987 | 6 | Heathrow | 20
1987-06-20 | 1987 | 6 | Heathrow | 19.7
1987-06-21 | 1987 | 6 | Heathrow | 15.9
1987-06-22 | 1987 | 6 | Heathrow | 19.6
1987-06-23 | 1987 | 6 | Heathrow | 19.1
1987-06-24 | 1987 | 6 | Heathrow | 17.6
1987-06-25 | 1987 | 6 | Heathrow | 21.3
1987-06-26 | 1987 | 6 | Heathrow | 22.1
1987-06-27 | 1987 | 6 | Heathrow | 25.1
1987-06-28 | 1987 | 6 | Heathrow | 28.5
1987-06-29 | 1987 | 6 | Heathrow | 24.4
1987-06-30 | 1987 | 6 | Heathrow | 21
1987-07-01 | 1987 | 7 | Heathrow | 22
1987-07-02 | 1987 | 7 | Heathrow | 23.4
1987-07-03 | 1987 | 7 | Heathrow | 26
1987-07-04 | 1987 | 7 | Heathrow | 27.8
1987-07-05 | 1987 | 7 | Heathrow | 28.3
1987-07-06 | 1987 | 7 | Heathrow | 25.3
1987-07-07 | 1987 | 7 | Heathrow | 23.1
1987-07-08 | 1987 | 7 | Heathrow | 22.4
1987-07-09 | 1987 | 7 | Heathrow | 26.6
1987-07-10 | 1987 | 7 | Heathrow | 25.9
1987-07-11 | 1987 | 7 | Heathrow | 23.2
1987-07-12 | 1987 | 7 | Heathrow | 25.8
1987-07-13 | 1987 | 7 | Heathrow | 24.9
1987-07-14 | 1987 | 7 | Heathrow | 22.7
1987-07-15 | 1987 | 7 | Heathrow | 22.7
1987-07-16 | 1987 | 7 | Heathrow | 19.5
1987-07-17 | 1987 | 7 | Heathrow | 17.4
1987-07-18 | 1987 | 7 | Heathrow | 17.8
1987-07-19 | 1987 | 7 | Heathrow | 20.3
1987-07-20 | 1987 | 7 | Heathrow | 20.4
1987-07-21 | 1987 | 7 | Heathrow | 17.7
1987-07-22 | 1987 | 7 | Heathrow | 17.7
1987-07-23 | 1987 | 7 | Heathrow | 19.9
1987-07-24 | 1987 | 7 | Heathrow | 18.1
1987-07-25 | 1987 | 7 | Heathrow | 20.8
1987-07-26 | 1987 | 7 | Heathrow | 21.3
1987-07-27 | 1987 | 7 | Heathrow | 22.7
1987-07-28 | 1987 | 7 | Heathrow | 21.9
1987-07-29 | 1987 | 7 | Heathrow | 19.3
1987-07-30 | 1987 | 7 | Heathrow | 25.1
1987-07-31 | 1987 | 7 | Heathrow | 21.6
1987-08-01 | 1987 | 8 | Heathrow | 20.9
1987-08-02 | 1987 | 8 | Heathrow | 21.2
1987-08-03 | 1987 | 8 | Heathrow | 18.5
1987-08-04 | 1987 | 8 | Heathrow | 19.1
1987-08-05 | 1987 | 8 | Heathrow | 19.9
1987-08-06 | 1987 | 8 | Heathrow | 19.5
1987-08-07 | 1987 | 8 | Heathrow | 17.2
1987-08-08 | 1987 | 8 | Heathrow | 19.6
1987-08-09 | 1987 | 8 | Heathrow | 20.8
1987-08-10 | 1987 | 8 | Heathrow | 19.1
1987-08-11 | 1987 | 8 | Heathrow | 21.4
1987-08-12 | 1987 | 8 | Heathrow | 22.6
1987-08-13 | 1987 | 8 | Heathrow | 23.5
1987-08-14 | 1987 | 8 | Heathrow | 26.2
1987-08-15 | 1987 | 8 | Heathrow | 28.1
1987-08-16 | 1987 | 8 | Heathrow | 24.2
1987-08-17 | 1987 | 8 | Heathrow | 23.7
1987-08-18 | 1987 | 8 | Heathrow | 25.3
1987-08-19 | 1987 | 8 | Heathrow | 29.1
1987-08-20 | 1987 | 8 | Heathrow | 29.2
1987-08-21 | 1987 | 8 | Heathrow | 24.4
1987-08-22 | 1987 | 8 | Heathrow | 22.1
1987-08-23 | 1987 | 8 | Heathrow | 19.3
1987-08-24 | 1987 | 8 | Heathrow | 19.4
1987-08-25 | 1987 | 8 | Heathrow | 18.1
1987-08-26 | 1987 | 8 | Heathrow | 16.3
1987-08-27 | 1987 | 8 | Heathrow | 25.1
1987-08-28 | 1987 | 8 | Heathrow | 21.1
1987-08-29 | 1987 | 8 | Heathrow | 22.8
1987-08-30 | 1987 | 8 | Heathrow | 19.3
1987-08-31 | 1987 | 8 | Heathrow | 24.4
1987-09-01 | 1987 | 9 | Heathrow | 20.5
1987-09-02 | 1987 | 9 | Heathrow | 22.2
1987-09-03 | 1987 | 9 | Heathrow | 21
1987-09-04 | 1987 | 9 | Heathrow | 19.8
1987-09-05 | 1987 | 9 | Heathrow | 19.5
1987-09-06 | 1987 | 9 | Heathrow | 18.9
1987-09-07 | 1987 | 9 | Heathrow | 20.2
1987-09-08 | 1987 | 9 | Heathrow | 20.4
1987-09-09 | 1987 | 9 | Heathrow | 20.1
1987-09-10 | 1987 | 9 | Heathrow | 19.6
1987-09-11 | 1987 | 9 | Heathrow | 21.6
1987-09-12 | 1987 | 9 | Heathrow | 21.6
1987-09-13 | 1987 | 9 | Heathrow | 20.9
1987-09-14 | 1987 | 9 | Heathrow | 19.7
1987-09-15 | 1987 | 9 | Heathrow | 19.2
1987-09-16 | 1987 | 9 | Heathrow | 24.7
1987-09-17 | 1987 | 9 | Heathrow | 20.6
1987-09-18 | 1987 | 9 | Heathrow | 20.6
1987-09-19 | 1987 | 9 | Heathrow | 23.1
1987-09-20 | 1987 | 9 | Heathrow | 21.6
1987-09-21 | 1987 | 9 | Heathrow | 19
1987-09-22 | 1987 | 9 | Heathrow | 19.9
1987-09-23 | 1987 | 9 | Heathrow | 16.9
1987-09-24 | 1987 | 9 | Heathrow | 16
1987-09-25 | 1987 | 9 | Heathrow | 15.4
1987-09-26 | 1987 | 9 | Heathrow | 14.5
1987-09-27 | 1987 | 9 | Heathrow | 13.8
1987-09-28 | 1987 | 9 | Heathrow | 15.1
1987-09-29 | 1987 | 9 | Heathrow | 16.6
1987-09-30 | 1987 | 9 | Heathrow | 17.5
1988-05-01 | 1988 | 5 | Heathrow | 15.8
1988-05-02 | 1988 | 5 | Heathrow | 14.7
1988-05-03 | 1988 | 5 | Heathrow | 16.1
1988-05-04 | 1988 | 5 | Heathrow | 17.1
1988-05-05 | 1988 | 5 | Heathrow | 20.3
1988-05-06 | 1988 | 5 | Heathrow | 19.1
1988-05-07 | 1988 | 5 | Heathrow | 22.7
1988-05-08 | 1988 | 5 | Heathrow | 22.7
1988-05-09 | 1988 | 5 | Heathrow | 16.8
1988-05-10 | 1988 | 5 | Heathrow | 16.9
1988-05-11 | 1988 | 5 | Heathrow | 18.7
1988-05-12 | 1988 | 5 | Heathrow | 21.2
1988-05-13 | 1988 | 5 | Heathrow | 23.9
1988-05-14 | 1988 | 5 | Heathrow | 23.4
1988-05-15 | 1988 | 5 | Heathrow | 22.4
1988-05-16 | 1988 | 5 | Heathrow | 21
1988-05-17 | 1988 | 5 | Heathrow | 21.1
1988-05-18 | 1988 | 5 | Heathrow | 13.7
1988-05-19 | 1988 | 5 | Heathrow | 16.1
1988-05-20 | 1988 | 5 | Heathrow | 17.8
1988-05-21 | 1988 | 5 | Heathrow | 18.6
1988-05-22 | 1988 | 5 | Heathrow | 17.1
1988-05-23 | 1988 | 5 | Heathrow | 18.9
1988-05-24 | 1988 | 5 | Heathrow | 21
1988-05-25 | 1988 | 5 | Heathrow | 18.1
1988-05-26 | 1988 | 5 | Heathrow | 19.8
1988-05-27 | 1988 | 5 | Heathrow | 19.5
1988-05-28 | 1988 | 5 | Heathrow | 16.4
1988-05-29 | 1988 | 5 | Heathrow | 15.5
1988-05-30 | 1988 | 5 | Heathrow | 17.8
1988-05-31 | 1988 | 5 | Heathrow | 19.4
1988-06-01 | 1988 | 6 | Heathrow | 17.6
1988-06-02 | 1988 | 6 | Heathrow | 17.4
1988-06-03 | 1988 | 6 | Heathrow | 15.8
1988-06-04 | 1988 | 6 | Heathrow | 16.1
1988-06-05 | 1988 | 6 | Heathrow | 17.5
1988-06-06 | 1988 | 6 | Heathrow | 18.6
1988-06-07 | 1988 | 6 | Heathrow | 16.9
1988-06-08 | 1988 | 6 | Heathrow | 13.6
1988-06-09 | 1988 | 6 | Heathrow | 14.1
1988-06-10 | 1988 | 6 | Heathrow | 16.3
1988-06-11 | 1988 | 6 | Heathrow | 19.5
1988-06-12 | 1988 | 6 | Heathrow | 23.3
1988-06-13 | 1988 | 6 | Heathrow | 23.2
1988-06-14 | 1988 | 6 | Heathrow | 20.8
1988-06-15 | 1988 | 6 | Heathrow | 20.2
1988-06-16 | 1988 | 6 | Heathrow | 16.4
1988-06-17 | 1988 | 6 | Heathrow | 19.8
1988-06-18 | 1988 | 6 | Heathrow | 25.1
1988-06-19 | 1988 | 6 | Heathrow | 23.7
1988-06-20 | 1988 | 6 | Heathrow | 23.5
1988-06-21 | 1988 | 6 | Heathrow | 21.2
1988-06-22 | 1988 | 6 | Heathrow | 24.7
1988-06-23 | 1988 | 6 | Heathrow | 21.3
1988-06-24 | 1988 | 6 | Heathrow | 23.5
1988-06-25 | 1988 | 6 | Heathrow | 20.3
1988-06-26 | 1988 | 6 | Heathrow | 20.4
1988-06-27 | 1988 | 6 | Heathrow | 17.3
1988-06-28 | 1988 | 6 | Heathrow | 21.9
1988-06-29 | 1988 | 6 | Heathrow | 25.2
1988-06-30 | 1988 | 6 | Heathrow | 20.1
1988-07-01 | 1988 | 7 | Heathrow | 19
1988-07-02 | 1988 | 7 | Heathrow | 16.5
1988-07-03 | 1988 | 7 | Heathrow | 17.1
1988-07-04 | 1988 | 7 | Heathrow | 21.4
1988-07-05 | 1988 | 7 | Heathrow | 19.5
1988-07-06 | 1988 | 7 | Heathrow | 19.4
1988-07-07 | 1988 | 7 | Heathrow | 20.2
1988-07-08 | 1988 | 7 | Heathrow | 19.9
1988-07-09 | 1988 | 7 | Heathrow | 18.6
1988-07-10 | 1988 | 7 | Heathrow | 20.7
1988-07-11 | 1988 | 7 | Heathrow | 20.5
1988-07-12 | 1988 | 7 | Heathrow | 19.5
1988-07-13 | 1988 | 7 | Heathrow | 17.6
1988-07-14 | 1988 | 7 | Heathrow | 20.3
1988-07-15 | 1988 | 7 | Heathrow | 18.1
1988-07-16 | 1988 | 7 | Heathrow | 19.9
1988-07-17 | 1988 | 7 | Heathrow | 22.6
1988-07-18 | 1988 | 7 | Heathrow | 20.7
1988-07-19 | 1988 | 7 | Heathrow | 21.7
1988-07-20 | 1988 | 7 | Heathrow | 23
1988-07-21 | 1988 | 7 | Heathrow | 21
1988-07-22 | 1988 | 7 | Heathrow | 21.7
1988-07-23 | 1988 | 7 | Heathrow | 20.8
1988-07-24 | 1988 | 7 | Heathrow | 21
1988-07-25 | 1988 | 7 | Heathrow | 21.2
1988-07-26 | 1988 | 7 | Heathrow | 21
1988-07-27 | 1988 | 7 | Heathrow | 17.5
1988-07-28 | 1988 | 7 | Heathrow | 18.9
1988-07-29 | 1988 | 7 | Heathrow | 19.5
1988-07-30 | 1988 | 7 | Heathrow | 20.3
1988-07-31 | 1988 | 7 | Heathrow | 19.7
1988-08-01 | 1988 | 8 | Heathrow | 19.5
1988-08-02 | 1988 | 8 | Heathrow | 20.9
1988-08-03 | 1988 | 8 | Heathrow | 21.1
1988-08-04 | 1988 | 8 | Heathrow | 22.5
1988-08-05 | 1988 | 8 | Heathrow | 27.4
1988-08-06 | 1988 | 8 | Heathrow | 29.1
1988-08-07 | 1988 | 8 | Heathrow | 26.6
1988-08-08 | 1988 | 8 | Heathrow | 23.8
1988-08-09 | 1988 | 8 | Heathrow | 20.2
1988-08-10 | 1988 | 8 | Heathrow | 20.1
1988-08-11 | 1988 | 8 | Heathrow | 22.1
1988-08-12 | 1988 | 8 | Heathrow | 20
1988-08-13 | 1988 | 8 | Heathrow | 22.6
1988-08-14 | 1988 | 8 | Heathrow | 22.6
1988-08-15 | 1988 | 8 | Heathrow | 24
1988-08-16 | 1988 | 8 | Heathrow | 26.9
1988-08-17 | 1988 | 8 | Heathrow | 25.7
1988-08-18 | 1988 | 8 | Heathrow | 21.7
1988-08-19 | 1988 | 8 | Heathrow | 21.2
1988-08-20 | 1988 | 8 | Heathrow | 21.2
1988-08-21 | 1988 | 8 | Heathrow | 19.5
1988-08-22 | 1988 | 8 | Heathrow | 19.1
1988-08-23 | 1988 | 8 | Heathrow | 20.8
1988-08-24 | 1988 | 8 | Heathrow | 19
1988-08-25 | 1988 | 8 | Heathrow | 19.3
1988-08-26 | 1988 | 8 | Heathrow | 22.1
1988-08-27 | 1988 | 8 | Heathrow | 18.7
1988-08-28 | 1988 | 8 | Heathrow | 20.6
1988-08-29 | 1988 | 8 | Heathrow | 21
1988-08-30 | 1988 | 8 | Heathrow | 20.1
1988-08-31 | 1988 | 8 | Heathrow | 18.9
1988-09-01 | 1988 | 9 | Heathrow | 17.2
1988-09-02 | 1988 | 9 | Heathrow | 19.2
1988-09-03 | 1988 | 9 | Heathrow | 20
1988-09-04 | 1988 | 9 | Heathrow | 22.1
1988-09-05 | 1988 | 9 | Heathrow | 24.1
1988-09-06 | 1988 | 9 | Heathrow | 26.2
1988-09-07 | 1988 | 9 | Heathrow | 25.7
1988-09-08 | 1988 | 9 | Heathrow | 22.8
1988-09-09 | 1988 | 9 | Heathrow | 23
1988-09-10 | 1988 | 9 | Heathrow | 19.1
1988-09-11 | 1988 | 9 | Heathrow | 18.6
1988-09-12 | 1988 | 9 | Heathrow | 14.9
1988-09-13 | 1988 | 9 | Heathrow | 14.7
1988-09-14 | 1988 | 9 | Heathrow | 16.1
1988-09-15 | 1988 | 9 | Heathrow | 19.6
1988-09-16 | 1988 | 9 | Heathrow | 18.4
1988-09-17 | 1988 | 9 | Heathrow | 18.3
1988-09-18 | 1988 | 9 | Heathrow | 17.4
1988-09-19 | 1988 | 9 | Heathrow | 13.4
1988-09-20 | 1988 | 9 | Heathrow | 17.6
1988-09-21 | 1988 | 9 | Heathrow | 19.6
1988-09-22 | 1988 | 9 | Heathrow | 17
1988-09-23 | 1988 | 9 | Heathrow | 16.5
1988-09-24 | 1988 | 9 | Heathrow | 20.5
1988-09-25 | 1988 | 9 | Heathrow | 19.1
1988-09-26 | 1988 | 9 | Heathrow | 17.2
1988-09-27 | 1988 | 9 | Heathrow | 16.7
1988-09-28 | 1988 | 9 | Heathrow | 15.7
1988-09-29 | 1988 | 9 | Heathrow | 15
1988-09-30 | 1988 | 9 | Heathrow | 16
1989-05-01 | 1989 | 5 | Heathrow | 20.6
1989-05-02 | 1989 | 5 | Heathrow | 22.9
1989-05-03 | 1989 | 5 | Heathrow | 23.6
1989-05-04 | 1989 | 5 | Heathrow | 25
1989-05-05 | 1989 | 5 | Heathrow | 25.1
1989-05-06 | 1989 | 5 | Heathrow | 19.1
1989-05-07 | 1989 | 5 | Heathrow | 21.9
1989-05-08 | 1989 | 5 | Heathrow | 19.6
1989-05-09 | 1989 | 5 | Heathrow | 18.3
1989-05-10 | 1989 | 5 | Heathrow | 18.1
1989-05-12 | 1989 | 5 | Heathrow | 15.9
1989-05-13 | 1989 | 5 | Heathrow | 17.9
1989-05-14 | 1989 | 5 | Heathrow | 21
1989-05-15 | 1989 | 5 | Heathrow | 20.9
1989-05-16 | 1989 | 5 | Heathrow | 22
1989-05-17 | 1989 | 5 | Heathrow | 24.1
1989-05-18 | 1989 | 5 | Heathrow | 24.5
1989-05-19 | 1989 | 5 | Heathrow | 25.2
1989-05-20 | 1989 | 5 | Heathrow | 27
1989-05-21 | 1989 | 5 | Heathrow | 25.9
1989-05-22 | 1989 | 5 | Heathrow | 29.4
1989-05-23 | 1989 | 5 | Heathrow | 28.2
1989-05-24 | 1989 | 5 | Heathrow | 28.2
1989-05-25 | 1989 | 5 | Heathrow | 19.7
1989-05-26 | 1989 | 5 | Heathrow | 19.2
1989-05-27 | 1989 | 5 | Heathrow | 21.3
1989-05-28 | 1989 | 5 | Heathrow | 22.6
1989-05-29 | 1989 | 5 | Heathrow | 22.6
1989-05-30 | 1989 | 5 | Heathrow | 16.2
1989-05-31 | 1989 | 5 | Heathrow | 13.4
1989-06-01 | 1989 | 6 | Heathrow | 15.9
1989-06-02 | 1989 | 6 | Heathrow | 15.3
1989-06-03 | 1989 | 6 | Heathrow | 16.2
1989-06-04 | 1989 | 6 | Heathrow | 17.9
1989-06-05 | 1989 | 6 | Heathrow | 12.4
1989-06-06 | 1989 | 6 | Heathrow | 16.6
1989-06-07 | 1989 | 6 | Heathrow | 16.3
1989-06-08 | 1989 | 6 | Heathrow | 19.3
1989-06-09 | 1989 | 6 | Heathrow | 22.2
1989-06-10 | 1989 | 6 | Heathrow | 23.4
1989-06-11 | 1989 | 6 | Heathrow | 28.6
1989-06-12 | 1989 | 6 | Heathrow | 27.8
1989-06-13 | 1989 | 6 | Heathrow | 27.7
1989-06-14 | 1989 | 6 | Heathrow | 27.7
1989-06-15 | 1989 | 6 | Heathrow | 27
1989-06-16 | 1989 | 6 | Heathrow | 27.6
1989-06-17 | 1989 | 6 | Heathrow | 26.6
1989-06-18 | 1989 | 6 | Heathrow | 29.1
1989-06-19 | 1989 | 6 | Heathrow | 30.2
1989-06-20 | 1989 | 6 | Heathrow | 23
1989-06-21 | 1989 | 6 | Heathrow | 19.6
1989-06-22 | 1989 | 6 | Heathrow | 25.3
1989-06-23 | 1989 | 6 | Heathrow | 25
1989-06-24 | 1989 | 6 | Heathrow | 26.9
1989-06-25 | 1989 | 6 | Heathrow | 23.5
1989-06-26 | 1989 | 6 | Heathrow | 19.7
1989-06-27 | 1989 | 6 | Heathrow | 18.7
1989-06-28 | 1989 | 6 | Heathrow | 19
1989-06-29 | 1989 | 6 | Heathrow | 21.3
1989-06-30 | 1989 | 6 | Heathrow | 22.3
1989-07-01 | 1989 | 7 | Heathrow | 20.1
1989-07-02 | 1989 | 7 | Heathrow | 24.4
1989-07-03 | 1989 | 7 | Heathrow | 25.5
1989-07-04 | 1989 | 7 | Heathrow | 28.6
1989-07-05 | 1989 | 7 | Heathrow | 31
1989-07-06 | 1989 | 7 | Heathrow | 31.1
1989-07-07 | 1989 | 7 | Heathrow | 24.6
1989-07-08 | 1989 | 7 | Heathrow | 24.6
1989-07-09 | 1989 | 7 | Heathrow | 24
1989-07-10 | 1989 | 7 | Heathrow | 26
1989-07-11 | 1989 | 7 | Heathrow | 22.6
1989-07-12 | 1989 | 7 | Heathrow | 25
1989-07-13 | 1989 | 7 | Heathrow | 22.5
1989-07-14 | 1989 | 7 | Heathrow | 28.1
1989-07-15 | 1989 | 7 | Heathrow | 25
1989-07-16 | 1989 | 7 | Heathrow | 28.5
1989-07-17 | 1989 | 7 | Heathrow | 25
1989-07-18 | 1989 | 7 | Heathrow | 26.9
1989-07-19 | 1989 | 7 | Heathrow | 29.8
1989-07-20 | 1989 | 7 | Heathrow | 32.1
1989-07-21 | 1989 | 7 | Heathrow | 34.2
1989-07-22 | 1989 | 7 | Heathrow | 31.8
1989-07-23 | 1989 | 7 | Heathrow | 30
1989-07-24 | 1989 | 7 | Heathrow | 29.9
1989-07-25 | 1989 | 7 | Heathrow | 27.4
1989-07-26 | 1989 | 7 | Heathrow | 25.6
1989-07-27 | 1989 | 7 | Heathrow | 25.7
1989-07-28 | 1989 | 7 | Heathrow | 26.5
1989-07-29 | 1989 | 7 | Heathrow | 26.6
1989-07-30 | 1989 | 7 | Heathrow | 19.4
1989-07-31 | 1989 | 7 | Heathrow | 22.1
1989-08-01 | 1989 | 8 | Heathrow | 23
1989-08-02 | 1989 | 8 | Heathrow | 26.4
1989-08-03 | 1989 | 8 | Heathrow | 25.1
1989-08-04 | 1989 | 8 | Heathrow | 26.9
1989-08-05 | 1989 | 8 | Heathrow | 29.3
1989-08-06 | 1989 | 8 | Heathrow | 27
1989-08-07 | 1989 | 8 | Heathrow | 26.6
1989-08-08 | 1989 | 8 | Heathrow | 26.1
1989-08-09 | 1989 | 8 | Heathrow | 26.1
1989-08-10 | 1989 | 8 | Heathrow | 24.2
1989-08-11 | 1989 | 8 | Heathrow | 24.6
1989-08-12 | 1989 | 8 | Heathrow | 22.2
1989-08-13 | 1989 | 8 | Heathrow | 24.4
1989-08-14 | 1989 | 8 | Heathrow | 24.2
1989-08-15 | 1989 | 8 | Heathrow | 23.9
1989-08-16 | 1989 | 8 | Heathrow | 22.4
1989-08-17 | 1989 | 8 | Heathrow | 23
1989-08-18 | 1989 | 8 | Heathrow | 27
1989-08-19 | 1989 | 8 | Heathrow | 28.7
1989-08-20 | 1989 | 8 | Heathrow | 25.8
1989-08-21 | 1989 | 8 | Heathrow | 24.3
1989-08-22 | 1989 | 8 | Heathrow | 24.9
1989-08-23 | 1989 | 8 | Heathrow | 26.4
1989-08-24 | 1989 | 8 | Heathrow | 21.5
1989-08-25 | 1989 | 8 | Heathrow | 23.3
1989-08-26 | 1989 | 8 | Heathrow | 19.1
1989-08-27 | 1989 | 8 | Heathrow | 19.7
1989-08-28 | 1989 | 8 | Heathrow | 19.7
1989-08-29 | 1989 | 8 | Heathrow | 26.2
1989-08-30 | 1989 | 8 | Heathrow | 26.2
1989-08-31 | 1989 | 8 | Heathrow | 20.7
1989-09-01 | 1989 | 9 | Heathrow | 18.4
1989-09-02 | 1989 | 9 | Heathrow | 18.7
1989-09-03 | 1989 | 9 | Heathrow | 21.2
1989-09-04 | 1989 | 9 | Heathrow | 22.9
1989-09-05 | 1989 | 9 | Heathrow | 25.7
1989-09-06 | 1989 | 9 | Heathrow | 26.7
1989-09-07 | 1989 | 9 | Heathrow | 22.6
1989-09-08 | 1989 | 9 | Heathrow | 22.6
1989-09-09 | 1989 | 9 | Heathrow | 19.7
1989-09-10 | 1989 | 9 | Heathrow | 19.4
1989-09-11 | 1989 | 9 | Heathrow | 21.2
1989-09-12 | 1989 | 9 | Heathrow | 19.4
1989-09-13 | 1989 | 9 | Heathrow | 16.7
1989-09-14 | 1989 | 9 | Heathrow | 21.5
1989-09-15 | 1989 | 9 | Heathrow | 22.2
1989-09-16 | 1989 | 9 | Heathrow | 21.1
1989-09-17 | 1989 | 9 | Heathrow | 23.9
1989-09-18 | 1989 | 9 | Heathrow | 21
1989-09-19 | 1989 | 9 | Heathrow | 22.4
1989-09-20 | 1989 | 9 | Heathrow | 26.7
1989-09-21 | 1989 | 9 | Heathrow | 19.4
1989-09-22 | 1989 | 9 | Heathrow | 18.7
1989-09-23 | 1989 | 9 | Heathrow | 22.1
1989-09-24 | 1989 | 9 | Heathrow | 22.7
1989-09-25 | 1989 | 9 | Heathrow | 20.4
1989-09-26 | 1989 | 9 | Heathrow | 18.4
1989-09-27 | 1989 | 9 | Heathrow | 16.9
1989-09-28 | 1989 | 9 | Heathrow | 18.2
1989-09-29 | 1989 | 9 | Heathrow | 15.6
1989-09-30 | 1989 | 9 | Heathrow | 15.5
1990-05-01 | 1990 | 5 | Heathrow | 26.2
1990-05-02 | 1990 | 5 | Heathrow | 28.1
1990-05-03 | 1990 | 5 | Heathrow | 26.9
1990-05-04 | 1990 | 5 | Heathrow | 27.2
1990-05-05 | 1990 | 5 | Heathrow | 26
1990-05-06 | 1990 | 5 | Heathrow | 26.1
1990-05-07 | 1990 | 5 | Heathrow | 19.4
1990-05-08 | 1990 | 5 | Heathrow | 15.8
1990-05-09 | 1990 | 5 | Heathrow | 15.4
1990-05-10 | 1990 | 5 | Heathrow | 14
1990-05-11 | 1990 | 5 | Heathrow | 15.9
1990-05-12 | 1990 | 5 | Heathrow | 17.2
1990-05-13 | 1990 | 5 | Heathrow | 20.2
1990-05-14 | 1990 | 5 | Heathrow | 22.1
1990-05-15 | 1990 | 5 | Heathrow | 21
1990-05-16 | 1990 | 5 | Heathrow | 21.5
1990-05-17 | 1990 | 5 | Heathrow | 21.6
1990-05-18 | 1990 | 5 | Heathrow | 16.9
1990-05-19 | 1990 | 5 | Heathrow | 19.5
1990-05-20 | 1990 | 5 | Heathrow | 20.8
1990-05-21 | 1990 | 5 | Heathrow | 18.7
1990-05-22 | 1990 | 5 | Heathrow | 21.8
1990-05-23 | 1990 | 5 | Heathrow | 19
1990-05-24 | 1990 | 5 | Heathrow | 17.5
1990-05-25 | 1990 | 5 | Heathrow | 18.3
1990-05-26 | 1990 | 5 | Heathrow | 21.6
1990-05-27 | 1990 | 5 | Heathrow | 22
1990-05-28 | 1990 | 5 | Heathrow | 21.5
1990-05-29 | 1990 | 5 | Heathrow | 19
1990-05-30 | 1990 | 5 | Heathrow | 24.4
1990-05-31 | 1990 | 5 | Heathrow | 23.6
1990-06-01 | 1990 | 6 | Heathrow | 18.8
1990-06-02 | 1990 | 6 | Heathrow | 16.9
1990-06-03 | 1990 | 6 | Heathrow | 19.2
1990-06-04 | 1990 | 6 | Heathrow | 16
1990-06-05 | 1990 | 6 | Heathrow | 16.9
1990-06-06 | 1990 | 6 | Heathrow | 18.5
1990-06-07 | 1990 | 6 | Heathrow | 15.1
1990-06-08 | 1990 | 6 | Heathrow | 19.4
1990-06-09 | 1990 | 6 | Heathrow | 19.6
1990-06-11 | 1990 | 6 | Heathrow | 14.5
1990-06-12 | 1990 | 6 | Heathrow | 14.8
1990-06-13 | 1990 | 6 | Heathrow | 17.4
1990-06-14 | 1990 | 6 | Heathrow | 20
1990-06-15 | 1990 | 6 | Heathrow | 21.3
1990-06-16 | 1990 | 6 | Heathrow | 24.1
1990-06-17 | 1990 | 6 | Heathrow | 20.3
1990-06-18 | 1990 | 6 | Heathrow | 22
1990-06-19 | 1990 | 6 | Heathrow | 21.1
1990-06-20 | 1990 | 6 | Heathrow | 16.1
1990-06-21 | 1990 | 6 | Heathrow | 20.8
1990-06-22 | 1990 | 6 | Heathrow | 19.4
1990-06-23 | 1990 | 6 | Heathrow | 18.4
1990-06-24 | 1990 | 6 | Heathrow | 23.3
1990-06-25 | 1990 | 6 | Heathrow | 23.2
1990-06-26 | 1990 | 6 | Heathrow | 25.1
1990-06-28 | 1990 | 6 | Heathrow | 23.5
1990-06-29 | 1990 | 6 | Heathrow | 21.7
1990-06-30 | 1990 | 6 | Heathrow | 18.9
1990-07-01 | 1990 | 7 | Heathrow | 19.6
1990-07-02 | 1990 | 7 | Heathrow | 20.2
1990-07-03 | 1990 | 7 | Heathrow | 18
1990-07-04 | 1990 | 7 | Heathrow | 18.8
1990-07-05 | 1990 | 7 | Heathrow | 20.2
1990-07-06 | 1990 | 7 | Heathrow | 23.3
1990-07-07 | 1990 | 7 | Heathrow | 26.8
1990-07-09 | 1990 | 7 | Heathrow | 20.1
1990-07-10 | 1990 | 7 | Heathrow | 27.3
1990-07-11 | 1990 | 7 | Heathrow | 27.7
1990-07-12 | 1990 | 7 | Heathrow | 26.8
1990-07-13 | 1990 | 7 | Heathrow | 24
1990-07-14 | 1990 | 7 | Heathrow | 31.3
1990-07-15 | 1990 | 7 | Heathrow | 24.9
1990-07-16 | 1990 | 7 | Heathrow | 26.4
1990-07-17 | 1990 | 7 | Heathrow | 27.6
1990-07-18 | 1990 | 7 | Heathrow | 30.1
1990-07-19 | 1990 | 7 | Heathrow | 31.8
1990-07-20 | 1990 | 7 | Heathrow | 32.5
1990-07-21 | 1990 | 7 | Heathrow | 32.5
1990-07-22 | 1990 | 7 | Heathrow | 24.1
1990-07-23 | 1990 | 7 | Heathrow | 23.9
1990-07-24 | 1990 | 7 | Heathrow | 25.9
1990-07-25 | 1990 | 7 | Heathrow | 24.4
1990-07-26 | 1990 | 7 | Heathrow | 26.1
1990-07-27 | 1990 | 7 | Heathrow | 26
1990-07-28 | 1990 | 7 | Heathrow | 25.3
1990-07-29 | 1990 | 7 | Heathrow | 23.9
1990-07-30 | 1990 | 7 | Heathrow | 27.3
1990-07-31 | 1990 | 7 | Heathrow | 32.5
1990-08-01 | 1990 | 8 | Heathrow | 34
1990-08-02 | 1990 | 8 | Heathrow | 36.5
1990-08-03 | 1990 | 8 | Heathrow | 34.4
1990-08-04 | 1990 | 8 | Heathrow | 34.4
1990-08-05 | 1990 | 8 | Heathrow | 21.5
1990-08-06 | 1990 | 8 | Heathrow | 21.3
1990-08-07 | 1990 | 8 | Heathrow | 25.8
1990-08-08 | 1990 | 8 | Heathrow | 27.6
1990-08-09 | 1990 | 8 | Heathrow | 28.2
1990-08-10 | 1990 | 8 | Heathrow | 27.5
1990-08-11 | 1990 | 8 | Heathrow | 29.4
1990-08-12 | 1990 | 8 | Heathrow | 26
1990-08-13 | 1990 | 8 | Heathrow | 23.9
1990-08-14 | 1990 | 8 | Heathrow | 23.6
1990-08-15 | 1990 | 8 | Heathrow | 22
1990-08-16 | 1990 | 8 | Heathrow | 20.5
1990-08-17 | 1990 | 8 | Heathrow | 18.5
1990-08-18 | 1990 | 8 | Heathrow | 22.2
1990-08-19 | 1990 | 8 | Heathrow | 21.6
1990-08-20 | 1990 | 8 | Heathrow | 22
1990-08-21 | 1990 | 8 | Heathrow | 26.7
1990-08-22 | 1990 | 8 | Heathrow | 27.6
1990-08-23 | 1990 | 8 | Heathrow | 27.8
1990-08-24 | 1990 | 8 | Heathrow | 27.7
1990-08-25 | 1990 | 8 | Heathrow | 26.9
1990-08-26 | 1990 | 8 | Heathrow | 25.2
1990-08-27 | 1990 | 8 | Heathrow | 27.7
1990-08-28 | 1990 | 8 | Heathrow | 30.3
1990-08-29 | 1990 | 8 | Heathrow | 30.2
1990-08-30 | 1990 | 8 | Heathrow | 20.9
1990-08-31 | 1990 | 8 | Heathrow | 23.8
1990-09-01 | 1990 | 9 | Heathrow | 25.6
1990-09-02 | 1990 | 9 | Heathrow | 24.5
1990-09-03 | 1990 | 9 | Heathrow | 20.9
1990-09-04 | 1990 | 9 | Heathrow | 20.8
1990-09-05 | 1990 | 9 | Heathrow | 18.8
1990-09-06 | 1990 | 9 | Heathrow | 20.2
1990-09-07 | 1990 | 9 | Heathrow | 19.1
1990-09-08 | 1990 | 9 | Heathrow | 21.8
1990-09-09 | 1990 | 9 | Heathrow | 20.5
1990-09-10 | 1990 | 9 | Heathrow | 21.9
1990-09-11 | 1990 | 9 | Heathrow | 21.2
1990-09-12 | 1990 | 9 | Heathrow | 22.2
1990-09-13 | 1990 | 9 | Heathrow | 22.1
1990-09-14 | 1990 | 9 | Heathrow | 19.5
1990-09-15 | 1990 | 9 | Heathrow | 18.8
1990-09-16 | 1990 | 9 | Heathrow | 18.7
1990-09-17 | 1990 | 9 | Heathrow | 22.6
1990-09-18 | 1990 | 9 | Heathrow | 17.7
1990-09-19 | 1990 | 9 | Heathrow | 17.6
1990-09-20 | 1990 | 9 | Heathrow | 16.7
1990-09-21 | 1990 | 9 | Heathrow | 15.1
1990-09-22 | 1990 | 9 | Heathrow | 16.6
1990-09-23 | 1990 | 9 | Heathrow | 17.1
1990-09-24 | 1990 | 9 | Heathrow | 16.7
1990-09-25 | 1990 | 9 | Heathrow | 17.2
1990-09-26 | 1990 | 9 | Heathrow | 17.3
1990-09-27 | 1990 | 9 | Heathrow | 21.4
1990-09-28 | 1990 | 9 | Heathrow | 18.1
1990-09-29 | 1990 | 9 | Heathrow | 20.8
1990-09-30 | 1990 | 9 | Heathrow | 17.7
1991-05-01 | 1991 | 5 | Heathrow | 11.4
1991-05-02 | 1991 | 5 | Heathrow | 11.4
1991-05-03 | 1991 | 5 | Heathrow | 12.3
1991-05-04 | 1991 | 5 | Heathrow | 10.5
1991-05-05 | 1991 | 5 | Heathrow | 9.7
1991-05-06 | 1991 | 5 | Heathrow | 11.4
1991-05-07 | 1991 | 5 | Heathrow | 14.1
1991-05-08 | 1991 | 5 | Heathrow | 14.6
1991-05-09 | 1991 | 5 | Heathrow | 16.8
1991-05-10 | 1991 | 5 | Heathrow | 15.6
1991-05-11 | 1991 | 5 | Heathrow | 19.1
1991-05-12 | 1991 | 5 | Heathrow | 20.5
1991-05-13 | 1991 | 5 | Heathrow | 16.1
1991-05-14 | 1991 | 5 | Heathrow | 15.7
1991-05-15 | 1991 | 5 | Heathrow | 12.4
1991-05-16 | 1991 | 5 | Heathrow | 12.6
1991-05-17 | 1991 | 5 | Heathrow | 14.1
1991-05-18 | 1991 | 5 | Heathrow | 17.5
1991-05-19 | 1991 | 5 | Heathrow | 21.7
1991-05-20 | 1991 | 5 | Heathrow | 24.6
1991-05-21 | 1991 | 5 | Heathrow | 21.2
1991-05-22 | 1991 | 5 | Heathrow | 18.2
1991-05-23 | 1991 | 5 | Heathrow | 18.4
1991-05-24 | 1991 | 5 | Heathrow | 21.8
1991-05-25 | 1991 | 5 | Heathrow | 16.9
1991-05-26 | 1991 | 5 | Heathrow | 20.5
1991-05-27 | 1991 | 5 | Heathrow | 20.5
1991-05-28 | 1991 | 5 | Heathrow | 15.1
1991-05-29 | 1991 | 5 | Heathrow | 16.2
1991-05-30 | 1991 | 5 | Heathrow | 13.6
1991-05-31 | 1991 | 5 | Heathrow | 14.1
1991-06-01 | 1991 | 6 | Heathrow | 15.5
1991-06-02 | 1991 | 6 | Heathrow | 14.6
1991-06-03 | 1991 | 6 | Heathrow | 15.8
1991-06-04 | 1991 | 6 | Heathrow | 16.2
1991-06-05 | 1991 | 6 | Heathrow | 17.2
1991-06-06 | 1991 | 6 | Heathrow | 16.1
1991-06-07 | 1991 | 6 | Heathrow | 16.3
1991-06-08 | 1991 | 6 | Heathrow | 19
1991-06-09 | 1991 | 6 | Heathrow | 18.9
1991-06-10 | 1991 | 6 | Heathrow | 16.2
1991-06-11 | 1991 | 6 | Heathrow | 20
1991-06-12 | 1991 | 6 | Heathrow | 18.4
1991-06-13 | 1991 | 6 | Heathrow | 19.2
1991-06-14 | 1991 | 6 | Heathrow | 16.6
1991-06-15 | 1991 | 6 | Heathrow | 16.5
1991-06-16 | 1991 | 6 | Heathrow | 15.3
1991-06-17 | 1991 | 6 | Heathrow | 15.6
1991-06-18 | 1991 | 6 | Heathrow | 17.5
1991-06-19 | 1991 | 6 | Heathrow | 19.1
1991-06-20 | 1991 | 6 | Heathrow | 22.6
1991-06-21 | 1991 | 6 | Heathrow | 19.9
1991-06-22 | 1991 | 6 | Heathrow | 15.9
1991-06-23 | 1991 | 6 | Heathrow | 17
1991-06-24 | 1991 | 6 | Heathrow | 18.6
1991-06-25 | 1991 | 6 | Heathrow | 18.1
1991-06-26 | 1991 | 6 | Heathrow | 19.9
1991-06-27 | 1991 | 6 | Heathrow | 20.5
1991-06-28 | 1991 | 6 | Heathrow | 20.5
1991-06-29 | 1991 | 6 | Heathrow | 21.3
1991-06-30 | 1991 | 6 | Heathrow | 20.7
1991-07-01 | 1991 | 7 | Heathrow | 20
1991-07-02 | 1991 | 7 | Heathrow | 24.1
1991-07-03 | 1991 | 7 | Heathrow | 27.4
1991-07-04 | 1991 | 7 | Heathrow | 27.6
1991-07-05 | 1991 | 7 | Heathrow | 23.4
1991-07-06 | 1991 | 7 | Heathrow | 26.5
1991-07-07 | 1991 | 7 | Heathrow | 26.5
1991-07-08 | 1991 | 7 | Heathrow | 22.7
1991-07-09 | 1991 | 7 | Heathrow | 25.5
1991-07-10 | 1991 | 7 | Heathrow | 27.6
1991-07-11 | 1991 | 7 | Heathrow | 27.6
1991-07-12 | 1991 | 7 | Heathrow | 19.4
1991-07-13 | 1991 | 7 | Heathrow | 24.1
1991-07-14 | 1991 | 7 | Heathrow | 20.9
1991-07-15 | 1991 | 7 | Heathrow | 21.4
1991-07-16 | 1991 | 7 | Heathrow | 21.2
1991-07-17 | 1991 | 7 | Heathrow | 23.8
1991-07-18 | 1991 | 7 | Heathrow | 19.9
1991-07-19 | 1991 | 7 | Heathrow | 23.8
1991-07-20 | 1991 | 7 | Heathrow | 21.2
1991-07-21 | 1991 | 7 | Heathrow | 24
1991-07-22 | 1991 | 7 | Heathrow | 27.1
1991-07-23 | 1991 | 7 | Heathrow | 27.1
1991-07-24 | 1991 | 7 | Heathrow | 21.8
1991-07-25 | 1991 | 7 | Heathrow | 24.1
1991-07-26 | 1991 | 7 | Heathrow | 24.6
1991-07-27 | 1991 | 7 | Heathrow | 25.6
1991-07-28 | 1991 | 7 | Heathrow | 28.5
1991-07-29 | 1991 | 7 | Heathrow | 28.5
1991-07-30 | 1991 | 7 | Heathrow | 23.4
1991-07-31 | 1991 | 7 | Heathrow | 23.6
1991-08-01 | 1991 | 8 | Heathrow | 23.7
1991-08-02 | 1991 | 8 | Heathrow | 23.9
1991-08-03 | 1991 | 8 | Heathrow | 24.5
1991-08-04 | 1991 | 8 | Heathrow | 23.5
1991-08-05 | 1991 | 8 | Heathrow | 22.5
1991-08-06 | 1991 | 8 | Heathrow | 19.9
1991-08-07 | 1991 | 8 | Heathrow | 23.9
1991-08-08 | 1991 | 8 | Heathrow | 24.6
1991-08-09 | 1991 | 8 | Heathrow | 26.7
1991-08-10 | 1991 | 8 | Heathrow | 26.6
1991-08-11 | 1991 | 8 | Heathrow | 23.2
1991-08-12 | 1991 | 8 | Heathrow | 23.7
1991-08-13 | 1991 | 8 | Heathrow | 25.1
1991-08-14 | 1991 | 8 | Heathrow | 25.1
1991-08-15 | 1991 | 8 | Heathrow | 24.1
1991-08-16 | 1991 | 8 | Heathrow | 24
1991-08-17 | 1991 | 8 | Heathrow | 21.6
1991-08-18 | 1991 | 8 | Heathrow | 24.7
1991-08-19 | 1991 | 8 | Heathrow | 25.2
1991-08-20 | 1991 | 8 | Heathrow | 27.9
1991-08-21 | 1991 | 8 | Heathrow | 24.5
1991-08-22 | 1991 | 8 | Heathrow | 24.5
1991-08-23 | 1991 | 8 | Heathrow | 22.6
1991-08-24 | 1991 | 8 | Heathrow | 24.6
1991-08-25 | 1991 | 8 | Heathrow | 27
1991-08-26 | 1991 | 8 | Heathrow | 26.7
1991-08-27 | 1991 | 8 | Heathrow | 24
1991-08-28 | 1991 | 8 | Heathrow | 23.7
1991-08-29 | 1991 | 8 | Heathrow | 25.4
1991-08-30 | 1991 | 8 | Heathrow | 26.7
1991-08-31 | 1991 | 8 | Heathrow | 29.7
1991-09-01 | 1991 | 9 | Heathrow | 26.3
1991-09-02 | 1991 | 9 | Heathrow | 25.8
1991-09-03 | 1991 | 9 | Heathrow | 27.5
1991-09-04 | 1991 | 9 | Heathrow | 25
1991-09-05 | 1991 | 9 | Heathrow | 20.7
1991-09-06 | 1991 | 9 | Heathrow | 21.4
1991-09-07 | 1991 | 9 | Heathrow | 24.7
1991-09-08 | 1991 | 9 | Heathrow | 23.9
1991-09-09 | 1991 | 9 | Heathrow | 24.3
1991-09-10 | 1991 | 9 | Heathrow | 18.8
1991-09-11 | 1991 | 9 | Heathrow | 21.6
1991-09-12 | 1991 | 9 | Heathrow | 23.3
1991-09-13 | 1991 | 9 | Heathrow | 24.6
1991-09-14 | 1991 | 9 | Heathrow | 22.2
1991-09-15 | 1991 | 9 | Heathrow | 20.8
1991-09-16 | 1991 | 9 | Heathrow | 21.8
1991-09-17 | 1991 | 9 | Heathrow | 21.4
1991-09-18 | 1991 | 9 | Heathrow | 19.6
1991-09-19 | 1991 | 9 | Heathrow | 20.2
1991-09-20 | 1991 | 9 | Heathrow | 24.6
1991-09-21 | 1991 | 9 | Heathrow | 18.8
1991-09-22 | 1991 | 9 | Heathrow | 19.6
1991-09-23 | 1991 | 9 | Heathrow | 18.7
1991-09-24 | 1991 | 9 | Heathrow | 18.9
1991-09-25 | 1991 | 9 | Heathrow | 17.7
1991-09-26 | 1991 | 9 | Heathrow | 17.6
1991-09-27 | 1991 | 9 | Heathrow | 14.2
1991-09-28 | 1991 | 9 | Heathrow | 16.9
1991-09-29 | 1991 | 9 | Heathrow | 15.2
1991-09-30 | 1991 | 9 | Heathrow | 17.2
1992-05-01 | 1992 | 5 | Heathrow | 13.2
1992-05-02 | 1992 | 5 | Heathrow | 15.6
1992-05-03 | 1992 | 5 | Heathrow | 18.2
1992-05-04 | 1992 | 5 | Heathrow | 13.3
1992-05-05 | 1992 | 5 | Heathrow | 20.3
1992-05-06 | 1992 | 5 | Heathrow | 20
1992-05-07 | 1992 | 5 | Heathrow | 15.1
1992-05-08 | 1992 | 5 | Heathrow | 15.8
1992-05-09 | 1992 | 5 | Heathrow | 13.4
1992-05-10 | 1992 | 5 | Heathrow | 16
1992-05-11 | 1992 | 5 | Heathrow | 16.7
1992-05-12 | 1992 | 5 | Heathrow | 22.6
1992-05-13 | 1992 | 5 | Heathrow | 26.7
1992-05-14 | 1992 | 5 | Heathrow | 20.4
1992-05-15 | 1992 | 5 | Heathrow | 21.3
1992-05-16 | 1992 | 5 | Heathrow | 18.2
1992-05-17 | 1992 | 5 | Heathrow | 21.6
1992-05-18 | 1992 | 5 | Heathrow | 26.5
1992-05-19 | 1992 | 5 | Heathrow | 26.8
1992-05-20 | 1992 | 5 | Heathrow | 26.8
1992-05-21 | 1992 | 5 | Heathrow | 26.6
1992-05-22 | 1992 | 5 | Heathrow | 25.9
1992-05-23 | 1992 | 5 | Heathrow | 27.3
1992-05-24 | 1992 | 5 | Heathrow | 26.6
1992-05-25 | 1992 | 5 | Heathrow | 26.7
1992-05-26 | 1992 | 5 | Heathrow | 23.4
1992-05-27 | 1992 | 5 | Heathrow | 26.2
1992-05-28 | 1992 | 5 | Heathrow | 26.1
1992-05-29 | 1992 | 5 | Heathrow | 20.7
1992-05-30 | 1992 | 5 | Heathrow | 24
1992-05-31 | 1992 | 5 | Heathrow | 19.5
1992-06-01 | 1992 | 6 | Heathrow | 20.4
1992-06-02 | 1992 | 6 | Heathrow | 21.3
1992-06-03 | 1992 | 6 | Heathrow | 21.2
1992-06-04 | 1992 | 6 | Heathrow | 15.1
1992-06-05 | 1992 | 6 | Heathrow | 23.2
1992-06-06 | 1992 | 6 | Heathrow | 18
1992-06-07 | 1992 | 6 | Heathrow | 21.9
1992-06-08 | 1992 | 6 | Heathrow | 23.2
1992-06-09 | 1992 | 6 | Heathrow | 23.6
1992-06-10 | 1992 | 6 | Heathrow | 22.4
1992-06-11 | 1992 | 6 | Heathrow | 24.1
1992-06-12 | 1992 | 6 | Heathrow | 25.9
1992-06-13 | 1992 | 6 | Heathrow | 27.4
1992-06-14 | 1992 | 6 | Heathrow | 28.2
1992-06-15 | 1992 | 6 | Heathrow | 20.9
1992-06-16 | 1992 | 6 | Heathrow | 20.3
1992-06-17 | 1992 | 6 | Heathrow | 19.4
1992-06-18 | 1992 | 6 | Heathrow | 16.4
1992-06-19 | 1992 | 6 | Heathrow | 20.9
1992-06-20 | 1992 | 6 | Heathrow | 22.7
1992-06-21 | 1992 | 6 | Heathrow | 21.8
1992-06-22 | 1992 | 6 | Heathrow | 21.6
1992-06-23 | 1992 | 6 | Heathrow | 22
1992-06-24 | 1992 | 6 | Heathrow | 23.6
1992-06-25 | 1992 | 6 | Heathrow | 26.2
1992-06-26 | 1992 | 6 | Heathrow | 25.9
1992-06-27 | 1992 | 6 | Heathrow | 27.8
1992-06-28 | 1992 | 6 | Heathrow | 30.2
1992-06-29 | 1992 | 6 | Heathrow | 23.7
1992-06-30 | 1992 | 6 | Heathrow | 23.6
1992-07-01 | 1992 | 7 | Heathrow | 18.7
1992-07-02 | 1992 | 7 | Heathrow | 17.5
1992-07-03 | 1992 | 7 | Heathrow | 21.1
1992-07-04 | 1992 | 7 | Heathrow | 20
1992-07-05 | 1992 | 7 | Heathrow | 22.7
1992-07-06 | 1992 | 7 | Heathrow | 21.2
1992-07-07 | 1992 | 7 | Heathrow | 17.1
1992-07-08 | 1992 | 7 | Heathrow | 20.3
1992-07-09 | 1992 | 7 | Heathrow | 20
1992-07-10 | 1992 | 7 | Heathrow | 19.5
1992-07-11 | 1992 | 7 | Heathrow | 22.9
1992-07-12 | 1992 | 7 | Heathrow | 20.2
1992-07-13 | 1992 | 7 | Heathrow | 20
1992-07-14 | 1992 | 7 | Heathrow | 23.5
1992-07-15 | 1992 | 7 | Heathrow | 25.5
1992-07-16 | 1992 | 7 | Heathrow | 25.4
1992-07-17 | 1992 | 7 | Heathrow | 24.9
1992-07-18 | 1992 | 7 | Heathrow | 23.6
1992-07-19 | 1992 | 7 | Heathrow | 24.5
1992-07-20 | 1992 | 7 | Heathrow | 24.5
1992-07-21 | 1992 | 7 | Heathrow | 24.1
1992-07-22 | 1992 | 7 | Heathrow | 24.6
1992-07-23 | 1992 | 7 | Heathrow | 24.7
1992-07-24 | 1992 | 7 | Heathrow | 23.6
1992-07-25 | 1992 | 7 | Heathrow | 21.1
1992-07-26 | 1992 | 7 | Heathrow | 22
1992-07-27 | 1992 | 7 | Heathrow | 22.9
1992-07-28 | 1992 | 7 | Heathrow | 26.6
1992-07-29 | 1992 | 7 | Heathrow | 26.6
1992-07-30 | 1992 | 7 | Heathrow | 28.6
1992-07-31 | 1992 | 7 | Heathrow | 28.5
1992-08-01 | 1992 | 8 | Heathrow | 22.3
1992-08-02 | 1992 | 8 | Heathrow | 24
1992-08-03 | 1992 | 8 | Heathrow | 23.6
1992-08-04 | 1992 | 8 | Heathrow | 24.1
1992-08-05 | 1992 | 8 | Heathrow | 24.1
1992-08-06 | 1992 | 8 | Heathrow | 26.9
1992-08-07 | 1992 | 8 | Heathrow | 25.2
1992-08-08 | 1992 | 8 | Heathrow | 24.8
1992-08-09 | 1992 | 8 | Heathrow | 23.5
1992-08-10 | 1992 | 8 | Heathrow | 20.7
1992-08-11 | 1992 | 8 | Heathrow | 19.1
1992-08-12 | 1992 | 8 | Heathrow | 19.1
1992-08-13 | 1992 | 8 | Heathrow | 18.7
1992-08-14 | 1992 | 8 | Heathrow | 22.1
1992-08-15 | 1992 | 8 | Heathrow | 20.7
1992-08-16 | 1992 | 8 | Heathrow | 20.8
1992-08-17 | 1992 | 8 | Heathrow | 19.5
1992-08-18 | 1992 | 8 | Heathrow | 22.5
1992-08-19 | 1992 | 8 | Heathrow | 19.8
1992-08-20 | 1992 | 8 | Heathrow | 22.9
1992-08-21 | 1992 | 8 | Heathrow | 20.2
1992-08-22 | 1992 | 8 | Heathrow | 20.4
1992-08-23 | 1992 | 8 | Heathrow | 19.5
1992-08-24 | 1992 | 8 | Heathrow | 23.7
1992-08-25 | 1992 | 8 | Heathrow | 19.3
1992-08-26 | 1992 | 8 | Heathrow | 21.9
1992-08-27 | 1992 | 8 | Heathrow | 21.2
1992-08-28 | 1992 | 8 | Heathrow | 19.2
1992-08-29 | 1992 | 8 | Heathrow | 18.4
1992-08-30 | 1992 | 8 | Heathrow | 18
1992-08-31 | 1992 | 8 | Heathrow | 17.2
1992-09-01 | 1992 | 9 | Heathrow | 21.7
1992-09-02 | 1992 | 9 | Heathrow | 17.5
1992-09-03 | 1992 | 9 | Heathrow | 17.2
1992-09-04 | 1992 | 9 | Heathrow | 16.6
1992-09-05 | 1992 | 9 | Heathrow | 17.7
1992-09-06 | 1992 | 9 | Heathrow | 18
1992-09-07 | 1992 | 9 | Heathrow | 17.3
1992-09-08 | 1992 | 9 | Heathrow | 17.9
1992-09-09 | 1992 | 9 | Heathrow | 21.2
1992-09-10 | 1992 | 9 | Heathrow | 19
1992-09-11 | 1992 | 9 | Heathrow | 17.5
1992-09-12 | 1992 | 9 | Heathrow | 15.7
1992-09-13 | 1992 | 9 | Heathrow | 18.3
1992-09-14 | 1992 | 9 | Heathrow | 19.9
1992-09-15 | 1992 | 9 | Heathrow | 20.2
1992-09-16 | 1992 | 9 | Heathrow | 23.5
1992-09-17 | 1992 | 9 | Heathrow | 19.5
1992-09-18 | 1992 | 9 | Heathrow | 18.3
1992-09-19 | 1992 | 9 | Heathrow | 19.3
1992-09-20 | 1992 | 9 | Heathrow | 18.3
1992-09-21 | 1992 | 9 | Heathrow | 17.4
1992-09-22 | 1992 | 9 | Heathrow | 16
1992-09-23 | 1992 | 9 | Heathrow | 18.5
1992-09-24 | 1992 | 9 | Heathrow | 14.9
1992-09-25 | 1992 | 9 | Heathrow | 23.9
1992-09-26 | 1992 | 9 | Heathrow | 23.6
1992-09-27 | 1992 | 9 | Heathrow | 21.6
1992-09-28 | 1992 | 9 | Heathrow | 20.7
1992-09-29 | 1992 | 9 | Heathrow | 17
1992-09-30 | 1992 | 9 | Heathrow | 17
1993-05-01 | 1993 | 5 | Heathrow | 20.1
1993-05-02 | 1993 | 5 | Heathrow | 13.5
1993-05-03 | 1993 | 5 | Heathrow | 15.6
1993-05-04 | 1993 | 5 | Heathrow | 15.2
1993-05-05 | 1993 | 5 | Heathrow | 14.7
1993-05-06 | 1993 | 5 | Heathrow | 16.3
1993-05-07 | 1993 | 5 | Heathrow | 18
1993-05-08 | 1993 | 5 | Heathrow | 17.5
1993-05-09 | 1993 | 5 | Heathrow | 20.6
1993-05-10 | 1993 | 5 | Heathrow | 25.1
1993-05-11 | 1993 | 5 | Heathrow | 19
1993-05-12 | 1993 | 5 | Heathrow | 16.3
1993-05-13 | 1993 | 5 | Heathrow | 15.7
1993-05-14 | 1993 | 5 | Heathrow | 15
1993-05-15 | 1993 | 5 | Heathrow | 17.7
1993-05-16 | 1993 | 5 | Heathrow | 22.7
1993-05-17 | 1993 | 5 | Heathrow | 18.6
1993-05-18 | 1993 | 5 | Heathrow | 18.5
1993-05-19 | 1993 | 5 | Heathrow | 18.6
1993-05-20 | 1993 | 5 | Heathrow | 17.7
1993-05-21 | 1993 | 5 | Heathrow | 19.8
1993-05-22 | 1993 | 5 | Heathrow | 22.8
1993-05-23 | 1993 | 5 | Heathrow | 24.9
1993-05-24 | 1993 | 5 | Heathrow | 25
1993-05-25 | 1993 | 5 | Heathrow | 17.3
1993-05-26 | 1993 | 5 | Heathrow | 14.5
1993-05-27 | 1993 | 5 | Heathrow | 18.1
1993-05-28 | 1993 | 5 | Heathrow | 20.6
1993-05-29 | 1993 | 5 | Heathrow | 16.9
1993-05-30 | 1993 | 5 | Heathrow | 18.5
1993-05-31 | 1993 | 5 | Heathrow | 20.9
1993-06-01 | 1993 | 6 | Heathrow | 18.9
1993-06-02 | 1993 | 6 | Heathrow | 18.5
1993-06-03 | 1993 | 6 | Heathrow | 22.2
1993-06-04 | 1993 | 6 | Heathrow | 23.6
1993-06-05 | 1993 | 6 | Heathrow | 26
1993-06-06 | 1993 | 6 | Heathrow | 26.5
1993-06-07 | 1993 | 6 | Heathrow | 28.4
1993-06-08 | 1993 | 6 | Heathrow | 27.5
1993-06-09 | 1993 | 6 | Heathrow | 23.4
1993-06-10 | 1993 | 6 | Heathrow | 23.5
1993-06-11 | 1993 | 6 | Heathrow | 17.5
1993-06-12 | 1993 | 6 | Heathrow | 18
1993-06-13 | 1993 | 6 | Heathrow | 18.4
1993-06-14 | 1993 | 6 | Heathrow | 21
1993-06-15 | 1993 | 6 | Heathrow | 16.7
1993-06-16 | 1993 | 6 | Heathrow | 22.1
1993-06-17 | 1993 | 6 | Heathrow | 19
1993-06-18 | 1993 | 6 | Heathrow | 20.4
1993-06-19 | 1993 | 6 | Heathrow | 20.8
1993-06-20 | 1993 | 6 | Heathrow | 19.1
1993-06-21 | 1993 | 6 | Heathrow | 19.4
1993-06-22 | 1993 | 6 | Heathrow | 19.2
1993-06-23 | 1993 | 6 | Heathrow | 21.8
1993-06-24 | 1993 | 6 | Heathrow | 21.7
1993-06-25 | 1993 | 6 | Heathrow | 23.7
1993-06-26 | 1993 | 6 | Heathrow | 25
1993-06-27 | 1993 | 6 | Heathrow | 23.7
1993-06-28 | 1993 | 6 | Heathrow | 25
1993-06-29 | 1993 | 6 | Heathrow | 27.7
1993-06-30 | 1993 | 6 | Heathrow | 23.9
1993-07-01 | 1993 | 7 | Heathrow | 26.1
1993-07-02 | 1993 | 7 | Heathrow | 27.6
1993-07-03 | 1993 | 7 | Heathrow | 28.1
1993-07-04 | 1993 | 7 | Heathrow | 28.1
1993-07-05 | 1993 | 7 | Heathrow | 24.1
1993-07-06 | 1993 | 7 | Heathrow | 23
1993-07-07 | 1993 | 7 | Heathrow | 23
1993-07-08 | 1993 | 7 | Heathrow | 18.5
1993-07-09 | 1993 | 7 | Heathrow | 17.3
1993-07-10 | 1993 | 7 | Heathrow | 18
1993-07-11 | 1993 | 7 | Heathrow | 18.7
1993-07-12 | 1993 | 7 | Heathrow | 18.5
1993-07-13 | 1993 | 7 | Heathrow | 23.4
1993-07-14 | 1993 | 7 | Heathrow | 22.2
1993-07-15 | 1993 | 7 | Heathrow | 22.2
1993-07-16 | 1993 | 7 | Heathrow | 22.4
1993-07-17 | 1993 | 7 | Heathrow | 20.5
1993-07-18 | 1993 | 7 | Heathrow | 21.2
1993-07-19 | 1993 | 7 | Heathrow | 19.2
1993-07-20 | 1993 | 7 | Heathrow | 18.1
1993-07-21 | 1993 | 7 | Heathrow | 22.7
1993-07-22 | 1993 | 7 | Heathrow | 25.2
1993-07-23 | 1993 | 7 | Heathrow | 25.2
1993-07-24 | 1993 | 7 | Heathrow | 20.4
1993-07-25 | 1993 | 7 | Heathrow | 19.1
1993-07-26 | 1993 | 7 | Heathrow | 20.3
1993-07-27 | 1993 | 7 | Heathrow | 24.4
1993-07-28 | 1993 | 7 | Heathrow | 20.3
1993-07-29 | 1993 | 7 | Heathrow | 21.6
1993-07-30 | 1993 | 7 | Heathrow | 20.8
1993-07-31 | 1993 | 7 | Heathrow | 22.3
1993-08-01 | 1993 | 8 | Heathrow | 22.3
1993-08-02 | 1993 | 8 | Heathrow | 22.2
1993-08-03 | 1993 | 8 | Heathrow | 20.4
1993-08-04 | 1993 | 8 | Heathrow | 21.8
1993-08-05 | 1993 | 8 | Heathrow | 22.2
1993-08-06 | 1993 | 8 | Heathrow | 24.2
1993-08-07 | 1993 | 8 | Heathrow | 21.7
1993-08-08 | 1993 | 8 | Heathrow | 23.2
1993-08-09 | 1993 | 8 | Heathrow | 19.4
1993-08-10 | 1993 | 8 | Heathrow | 21.1
1993-08-11 | 1993 | 8 | Heathrow | 21
1993-08-12 | 1993 | 8 | Heathrow | 21.2
1993-08-13 | 1993 | 8 | Heathrow | 25.9
1993-08-14 | 1993 | 8 | Heathrow | 23.1
1993-08-15 | 1993 | 8 | Heathrow | 22.4
1993-08-16 | 1993 | 8 | Heathrow | 23.1
1993-08-17 | 1993 | 8 | Heathrow | 23.8
1993-08-18 | 1993 | 8 | Heathrow | 26.3
1993-08-19 | 1993 | 8 | Heathrow | 25.5
1993-08-20 | 1993 | 8 | Heathrow | 23.9
1993-08-21 | 1993 | 8 | Heathrow | 24
1993-08-22 | 1993 | 8 | Heathrow | 17.4
1993-08-23 | 1993 | 8 | Heathrow | 18.2
1993-08-24 | 1993 | 8 | Heathrow | 18.8
1993-08-25 | 1993 | 8 | Heathrow | 18.3
1993-08-26 | 1993 | 8 | Heathrow | 18.4
1993-08-27 | 1993 | 8 | Heathrow | 20.5
1993-08-28 | 1993 | 8 | Heathrow | 22.7
1993-08-29 | 1993 | 8 | Heathrow | 24.1
1993-08-30 | 1993 | 8 | Heathrow | 24.1
1993-08-31 | 1993 | 8 | Heathrow | 24.5
1993-09-01 | 1993 | 9 | Heathrow | 20.4
1993-09-02 | 1993 | 9 | Heathrow | 19.3
1993-09-03 | 1993 | 9 | Heathrow | 16.6
1993-09-04 | 1993 | 9 | Heathrow | 18
1993-09-05 | 1993 | 9 | Heathrow | 19.2
1993-09-06 | 1993 | 9 | Heathrow | 23.4
1993-09-07 | 1993 | 9 | Heathrow | 21.4
1993-09-08 | 1993 | 9 | Heathrow | 20.7
1993-09-09 | 1993 | 9 | Heathrow | 20.7
1993-09-10 | 1993 | 9 | Heathrow | 18.1
1993-09-11 | 1993 | 9 | Heathrow | 16.3
1993-09-12 | 1993 | 9 | Heathrow | 17.7
1993-09-13 | 1993 | 9 | Heathrow | 15.1
1993-09-14 | 1993 | 9 | Heathrow | 16.6
1993-09-15 | 1993 | 9 | Heathrow | 14.8
1993-09-16 | 1993 | 9 | Heathrow | 16.3
1993-09-17 | 1993 | 9 | Heathrow | 17.9
1993-09-18 | 1993 | 9 | Heathrow | 21
1993-09-19 | 1993 | 9 | Heathrow | 16.6
1993-09-20 | 1993 | 9 | Heathrow | 19.6
1993-09-21 | 1993 | 9 | Heathrow | 18.8
1993-09-22 | 1993 | 9 | Heathrow | 16.6
1993-09-23 | 1993 | 9 | Heathrow | 17.4
1993-09-24 | 1993 | 9 | Heathrow | 13.7
1993-09-25 | 1993 | 9 | Heathrow | 14.3
1993-09-26 | 1993 | 9 | Heathrow | 10
1993-09-27 | 1993 | 9 | Heathrow | 12.5
1993-09-28 | 1993 | 9 | Heathrow | 14.8
1993-09-29 | 1993 | 9 | Heathrow | 15
1993-09-30 | 1993 | 9 | Heathrow | 13.9
1994-05-01 | 1994 | 5 | Heathrow | 17.5
1994-05-02 | 1994 | 5 | Heathrow | 19.8
1994-05-03 | 1994 | 5 | Heathrow | 14.6
1994-05-04 | 1994 | 5 | Heathrow | 13.2
1994-05-05 | 1994 | 5 | Heathrow | 15.9
1994-05-06 | 1994 | 5 | Heathrow | 14
1994-05-07 | 1994 | 5 | Heathrow | 16.5
1994-05-08 | 1994 | 5 | Heathrow | 17.3
1994-05-09 | 1994 | 5 | Heathrow | 18.4
1994-05-10 | 1994 | 5 | Heathrow | 18.3
1994-05-11 | 1994 | 5 | Heathrow | 17.8
1994-05-12 | 1994 | 5 | Heathrow | 19.7
1994-05-13 | 1994 | 5 | Heathrow | 20.1
1994-05-14 | 1994 | 5 | Heathrow | 20.1
1994-05-15 | 1994 | 5 | Heathrow | 20.1
1994-05-16 | 1994 | 5 | Heathrow | 14.1
1994-05-17 | 1994 | 5 | Heathrow | 14.5
1994-05-18 | 1994 | 5 | Heathrow | 13.9
1994-05-19 | 1994 | 5 | Heathrow | 15.7
1994-05-20 | 1994 | 5 | Heathrow | 13.7
1994-05-21 | 1994 | 5 | Heathrow | 16.9
1994-05-22 | 1994 | 5 | Heathrow | 16.1
1994-05-23 | 1994 | 5 | Heathrow | 13.6
1994-05-24 | 1994 | 5 | Heathrow | 14.5
1994-05-25 | 1994 | 5 | Heathrow | 12.9
1994-05-26 | 1994 | 5 | Heathrow | 12.6
1994-05-27 | 1994 | 5 | Heathrow | 12.4
1994-05-28 | 1994 | 5 | Heathrow | 16.8
1994-05-29 | 1994 | 5 | Heathrow | 18
1994-05-30 | 1994 | 5 | Heathrow | 21.3
1994-05-31 | 1994 | 5 | Heathrow | 25.3
1994-06-01 | 1994 | 6 | Heathrow | 19.1
1994-06-02 | 1994 | 6 | Heathrow | 17.8
1994-06-03 | 1994 | 6 | Heathrow | 17.9
1994-06-04 | 1994 | 6 | Heathrow | 17.1
1994-06-05 | 1994 | 6 | Heathrow | 21.5
1994-06-06 | 1994 | 6 | Heathrow | 21.3
1994-06-07 | 1994 | 6 | Heathrow | 17
1994-06-08 | 1994 | 6 | Heathrow | 15.8
1994-06-09 | 1994 | 6 | Heathrow | 17
1994-06-10 | 1994 | 6 | Heathrow | 19.4
1994-06-11 | 1994 | 6 | Heathrow | 20.4
1994-06-12 | 1994 | 6 | Heathrow | 23.3
1994-06-13 | 1994 | 6 | Heathrow | 24.5
1994-06-14 | 1994 | 6 | Heathrow | 23.6
1994-06-15 | 1994 | 6 | Heathrow | 23.6
1994-06-16 | 1994 | 6 | Heathrow | 25.7
1994-06-17 | 1994 | 6 | Heathrow | 23
1994-06-18 | 1994 | 6 | Heathrow | 21.4
1994-06-19 | 1994 | 6 | Heathrow | 18.9
1994-06-20 | 1994 | 6 | Heathrow | 18.2
1994-06-21 | 1994 | 6 | Heathrow | 22
1994-06-22 | 1994 | 6 | Heathrow | 24.1
1994-06-23 | 1994 | 6 | Heathrow | 29.3
1994-06-24 | 1994 | 6 | Heathrow | 22.1
1994-06-25 | 1994 | 6 | Heathrow | 21.2
1994-06-26 | 1994 | 6 | Heathrow | 25.7
1994-06-27 | 1994 | 6 | Heathrow | 28.2
1994-06-28 | 1994 | 6 | Heathrow | 21.9
1994-06-29 | 1994 | 6 | Heathrow | 24.2
1994-06-30 | 1994 | 6 | Heathrow | 26.6
1994-07-01 | 1994 | 7 | Heathrow | 27.6
1994-07-02 | 1994 | 7 | Heathrow | 28
1994-07-03 | 1994 | 7 | Heathrow | 24.4
1994-07-04 | 1994 | 7 | Heathrow | 22.5
1994-07-05 | 1994 | 7 | Heathrow | 21.4
1994-07-06 | 1994 | 7 | Heathrow | 22.4
1994-07-07 | 1994 | 7 | Heathrow | 18.3
1994-07-08 | 1994 | 7 | Heathrow | 25
1994-07-09 | 1994 | 7 | Heathrow | 26.6
1994-07-10 | 1994 | 7 | Heathrow | 30.4
1994-07-11 | 1994 | 7 | Heathrow | 33.1
1994-07-12 | 1994 | 7 | Heathrow | 33.1
1994-07-13 | 1994 | 7 | Heathrow | 26.7
1994-07-14 | 1994 | 7 | Heathrow | 23
1994-07-15 | 1994 | 7 | Heathrow | 25.1
1994-07-16 | 1994 | 7 | Heathrow | 25.1
1994-07-17 | 1994 | 7 | Heathrow | 25.1
1994-07-18 | 1994 | 7 | Heathrow | 26.3
1994-07-19 | 1994 | 7 | Heathrow | 27
1994-07-20 | 1994 | 7 | Heathrow | 29.3
1994-07-21 | 1994 | 7 | Heathrow | 27.8
1994-07-22 | 1994 | 7 | Heathrow | 28.5
1994-07-23 | 1994 | 7 | Heathrow | 32
1994-07-24 | 1994 | 7 | Heathrow | 30.2
1994-07-25 | 1994 | 7 | Heathrow | 30.2
1994-07-26 | 1994 | 7 | Heathrow | 27.2
1994-07-27 | 1994 | 7 | Heathrow | 27.2
1994-07-28 | 1994 | 7 | Heathrow | 26.3
1994-07-29 | 1994 | 7 | Heathrow | 31.8
1994-07-30 | 1994 | 7 | Heathrow | 26.1
1994-07-31 | 1994 | 7 | Heathrow | 24.5
1994-08-01 | 1994 | 8 | Heathrow | 23.9
1994-08-02 | 1994 | 8 | Heathrow | 31
1994-08-03 | 1994 | 8 | Heathrow | 25.2
1994-08-04 | 1994 | 8 | Heathrow | 27.4
1994-08-05 | 1994 | 8 | Heathrow | 27.2
1994-08-06 | 1994 | 8 | Heathrow | 23.9
1994-08-07 | 1994 | 8 | Heathrow | 24.5
1994-08-08 | 1994 | 8 | Heathrow | 23.8
1994-08-09 | 1994 | 8 | Heathrow | 19
1994-08-10 | 1994 | 8 | Heathrow | 18.3
1994-08-11 | 1994 | 8 | Heathrow | 20.1
1994-08-12 | 1994 | 8 | Heathrow | 21.6
1994-08-13 | 1994 | 8 | Heathrow | 20.6
1994-08-14 | 1994 | 8 | Heathrow | 23.8
1994-08-15 | 1994 | 8 | Heathrow | 26.1
1994-08-16 | 1994 | 8 | Heathrow | 20.8
1994-08-17 | 1994 | 8 | Heathrow | 22.5
1994-08-18 | 1994 | 8 | Heathrow | 23
1994-08-19 | 1994 | 8 | Heathrow | 21.8
1994-08-20 | 1994 | 8 | Heathrow | 23.1
1994-08-21 | 1994 | 8 | Heathrow | 26.4
1994-08-22 | 1994 | 8 | Heathrow | 22.6
1994-08-23 | 1994 | 8 | Heathrow | 22.6
1994-08-24 | 1994 | 8 | Heathrow | 19.9
1994-08-25 | 1994 | 8 | Heathrow | 24.5
1994-08-26 | 1994 | 8 | Heathrow | 21.9
1994-08-27 | 1994 | 8 | Heathrow | 20.6
1994-08-28 | 1994 | 8 | Heathrow | 21.1
1994-08-29 | 1994 | 8 | Heathrow | 21.1
1994-08-30 | 1994 | 8 | Heathrow | 18.5
1994-08-31 | 1994 | 8 | Heathrow | 17.9
1994-09-01 | 1994 | 9 | Heathrow | 22.1
1994-09-02 | 1994 | 9 | Heathrow | 19.5
1994-09-03 | 1994 | 9 | Heathrow | 21.7
1994-09-04 | 1994 | 9 | Heathrow | 20.2
1994-09-05 | 1994 | 9 | Heathrow | 17.7
1994-09-06 | 1994 | 9 | Heathrow | 19.3
1994-09-07 | 1994 | 9 | Heathrow | 18.7
1994-09-08 | 1994 | 9 | Heathrow | 19.2
1994-09-09 | 1994 | 9 | Heathrow | 17.8
1994-09-10 | 1994 | 9 | Heathrow | 18.4
1994-09-11 | 1994 | 9 | Heathrow | 18.7
1994-09-12 | 1994 | 9 | Heathrow | 19.4
1994-09-13 | 1994 | 9 | Heathrow | 18
1994-09-14 | 1994 | 9 | Heathrow | 18.1
1994-09-15 | 1994 | 9 | Heathrow | 14.4
1994-09-16 | 1994 | 9 | Heathrow | 15.1
1994-09-17 | 1994 | 9 | Heathrow | 14
1994-09-18 | 1994 | 9 | Heathrow | 13.8
1994-09-19 | 1994 | 9 | Heathrow | 16.5
1994-09-20 | 1994 | 9 | Heathrow | 20
1994-09-21 | 1994 | 9 | Heathrow | 19.5
1994-09-22 | 1994 | 9 | Heathrow | 19.1
1994-09-23 | 1994 | 9 | Heathrow | 18.6
1994-09-24 | 1994 | 9 | Heathrow | 18
1994-09-25 | 1994 | 9 | Heathrow | 18
1994-09-26 | 1994 | 9 | Heathrow | 18.8
1994-09-27 | 1994 | 9 | Heathrow | 18.3
1994-09-28 | 1994 | 9 | Heathrow | 15.4
1994-09-29 | 1994 | 9 | Heathrow | 14.7
1994-09-30 | 1994 | 9 | Heathrow | 16.1
1995-05-01 | 1995 | 5 | Heathrow | 24
1995-05-02 | 1995 | 5 | Heathrow | 25.3
1995-05-03 | 1995 | 5 | Heathrow | 26.7
1995-05-04 | 1995 | 5 | Heathrow | 26.8
1995-05-05 | 1995 | 5 | Heathrow | 26.9
1995-05-06 | 1995 | 5 | Heathrow | 27.1
1995-05-07 | 1995 | 5 | Heathrow | 27.1
1995-05-08 | 1995 | 5 | Heathrow | 15.9
1995-05-09 | 1995 | 5 | Heathrow | 16.7
1995-05-10 | 1995 | 5 | Heathrow | 11
1995-05-11 | 1995 | 5 | Heathrow | 10.5
1995-05-12 | 1995 | 5 | Heathrow | 12.6
1995-05-13 | 1995 | 5 | Heathrow | 14.6
1995-05-14 | 1995 | 5 | Heathrow | 16.4
1995-05-15 | 1995 | 5 | Heathrow | 15
1995-05-16 | 1995 | 5 | Heathrow | 12
1995-05-17 | 1995 | 5 | Heathrow | 14.6
1995-05-18 | 1995 | 5 | Heathrow | 16.5
1995-05-19 | 1995 | 5 | Heathrow | 15.4
1995-05-20 | 1995 | 5 | Heathrow | 17.1
1995-05-21 | 1995 | 5 | Heathrow | 19.6
1995-05-22 | 1995 | 5 | Heathrow | 23
1995-05-23 | 1995 | 5 | Heathrow | 20.4
1995-05-24 | 1995 | 5 | Heathrow | 20.5
1995-05-25 | 1995 | 5 | Heathrow | 20.6
1995-05-26 | 1995 | 5 | Heathrow | 21.2
1995-05-27 | 1995 | 5 | Heathrow | 21.1
1995-05-28 | 1995 | 5 | Heathrow | 20.2
1995-05-29 | 1995 | 5 | Heathrow | 18.9
1995-05-30 | 1995 | 5 | Heathrow | 20.4
1995-05-31 | 1995 | 5 | Heathrow | 18.7
1995-06-01 | 1995 | 6 | Heathrow | 18.8
1995-06-02 | 1995 | 6 | Heathrow | 15.9
1995-06-03 | 1995 | 6 | Heathrow | 16.2
1995-06-04 | 1995 | 6 | Heathrow | 18.4
1995-06-05 | 1995 | 6 | Heathrow | 17.7
1995-06-06 | 1995 | 6 | Heathrow | 20.1
1995-06-07 | 1995 | 6 | Heathrow | 20.1
1995-06-08 | 1995 | 6 | Heathrow | 18.5
1995-06-09 | 1995 | 6 | Heathrow | 15.2
1995-06-10 | 1995 | 6 | Heathrow | 16
1995-06-11 | 1995 | 6 | Heathrow | 14.6
1995-06-12 | 1995 | 6 | Heathrow | 14.5
1995-06-13 | 1995 | 6 | Heathrow | 16.7
1995-06-14 | 1995 | 6 | Heathrow | 17.8
1995-06-15 | 1995 | 6 | Heathrow | 22.5
1995-06-16 | 1995 | 6 | Heathrow | 17.2
1995-06-17 | 1995 | 6 | Heathrow | 22.8
1995-06-18 | 1995 | 6 | Heathrow | 25.3
1995-06-19 | 1995 | 6 | Heathrow | 24.8
1995-06-20 | 1995 | 6 | Heathrow | 23.2
1995-06-21 | 1995 | 6 | Heathrow | 22.9
1995-06-22 | 1995 | 6 | Heathrow | 21.9
1995-06-23 | 1995 | 6 | Heathrow | 16
1995-06-24 | 1995 | 6 | Heathrow | 24.1
1995-06-25 | 1995 | 6 | Heathrow | 25.5
1995-06-26 | 1995 | 6 | Heathrow | 27.1
1995-06-27 | 1995 | 6 | Heathrow | 31
1995-06-28 | 1995 | 6 | Heathrow | 29.3
1995-06-29 | 1995 | 6 | Heathrow | 32.3
1995-06-30 | 1995 | 6 | Heathrow | 32.4
1995-07-01 | 1995 | 7 | Heathrow | 20.4
1995-07-02 | 1995 | 7 | Heathrow | 20.1
1995-07-03 | 1995 | 7 | Heathrow | 23.3
1995-07-04 | 1995 | 7 | Heathrow | 24.5
1995-07-05 | 1995 | 7 | Heathrow | 25.1
1995-07-06 | 1995 | 7 | Heathrow | 24
1995-07-07 | 1995 | 7 | Heathrow | 28.8
1995-07-08 | 1995 | 7 | Heathrow | 29.1
1995-07-09 | 1995 | 7 | Heathrow | 32
1995-07-10 | 1995 | 7 | Heathrow | 27.8
1995-07-11 | 1995 | 7 | Heathrow | 26.9
1995-07-12 | 1995 | 7 | Heathrow | 23.9
1995-07-13 | 1995 | 7 | Heathrow | 24.4
1995-07-14 | 1995 | 7 | Heathrow | 23.2
1995-07-15 | 1995 | 7 | Heathrow | 24
1995-07-16 | 1995 | 7 | Heathrow | 23
1995-07-17 | 1995 | 7 | Heathrow | 26.5
1995-07-18 | 1995 | 7 | Heathrow | 26.7
1995-07-19 | 1995 | 7 | Heathrow | 31.8
1995-07-20 | 1995 | 7 | Heathrow | 29.8
1995-07-21 | 1995 | 7 | Heathrow | 29.9
1995-07-22 | 1995 | 7 | Heathrow | 26
1995-07-23 | 1995 | 7 | Heathrow | 28.5
1995-07-24 | 1995 | 7 | Heathrow | 28.6
1995-07-25 | 1995 | 7 | Heathrow | 26.3
1995-07-26 | 1995 | 7 | Heathrow | 24.9
1995-07-27 | 1995 | 7 | Heathrow | 26.2
1995-07-28 | 1995 | 7 | Heathrow | 30.6
1995-07-29 | 1995 | 7 | Heathrow | 31.2
1995-07-30 | 1995 | 7 | Heathrow | 32.6
1995-07-31 | 1995 | 7 | Heathrow | 34.3
1995-08-01 | 1995 | 8 | Heathrow | 33
1995-08-02 | 1995 | 8 | Heathrow | 32.2
1995-08-03 | 1995 | 8 | Heathrow | 27.5
1995-08-04 | 1995 | 8 | Heathrow | 27.9
1995-08-05 | 1995 | 8 | Heathrow | 26.6
1995-08-06 | 1995 | 8 | Heathrow | 22.8
1995-08-07 | 1995 | 8 | Heathrow | 22.2
1995-08-08 | 1995 | 8 | Heathrow | 26.3
1995-08-09 | 1995 | 8 | Heathrow | 29.3
1995-08-10 | 1995 | 8 | Heathrow | 31.8
1995-08-11 | 1995 | 8 | Heathrow | 31.3
1995-08-12 | 1995 | 8 | Heathrow | 25.9
1995-08-13 | 1995 | 8 | Heathrow | 25.4
1995-08-14 | 1995 | 8 | Heathrow | 29.9
1995-08-15 | 1995 | 8 | Heathrow | 30.6
1995-08-16 | 1995 | 8 | Heathrow | 27.9
1995-08-17 | 1995 | 8 | Heathrow | 29.8
1995-08-18 | 1995 | 8 | Heathrow | 30.7
1995-08-19 | 1995 | 8 | Heathrow | 30.2
1995-08-20 | 1995 | 8 | Heathrow | 30.6
1995-08-21 | 1995 | 8 | Heathrow | 28.9
1995-08-22 | 1995 | 8 | Heathrow | 23.3
1995-08-23 | 1995 | 8 | Heathrow | 24.9
1995-08-24 | 1995 | 8 | Heathrow | 25.9
1995-08-25 | 1995 | 8 | Heathrow | 24.9
1995-08-26 | 1995 | 8 | Heathrow | 20.9
1995-08-27 | 1995 | 8 | Heathrow | 20.3
1995-08-28 | 1995 | 8 | Heathrow | 18.9
1995-08-29 | 1995 | 8 | Heathrow | 22.1
1995-08-30 | 1995 | 8 | Heathrow | 20.8
1995-08-31 | 1995 | 8 | Heathrow | 19.9
1995-09-01 | 1995 | 9 | Heathrow | 19.1
1995-09-02 | 1995 | 9 | Heathrow | 20.9
1995-09-03 | 1995 | 9 | Heathrow | 22
1995-09-04 | 1995 | 9 | Heathrow | 20.8
1995-09-05 | 1995 | 9 | Heathrow | 21
1995-09-06 | 1995 | 9 | Heathrow | 19.6
1995-09-07 | 1995 | 9 | Heathrow | 20.3
1995-09-08 | 1995 | 9 | Heathrow | 22.4
1995-09-09 | 1995 | 9 | Heathrow | 18.4
1995-09-10 | 1995 | 9 | Heathrow | 21.9
1995-09-11 | 1995 | 9 | Heathrow | 19.2
1995-09-12 | 1995 | 9 | Heathrow | 19.8
1995-09-13 | 1995 | 9 | Heathrow | 19.7
1995-09-14 | 1995 | 9 | Heathrow | 18.4
1995-09-15 | 1995 | 9 | Heathrow | 18.4
1995-09-16 | 1995 | 9 | Heathrow | 20
1995-09-17 | 1995 | 9 | Heathrow | 19.9
1995-09-18 | 1995 | 9 | Heathrow | 18.7
1995-09-19 | 1995 | 9 | Heathrow | 18.4
1995-09-20 | 1995 | 9 | Heathrow | 19.6
1995-09-21 | 1995 | 9 | Heathrow | 20.2
1995-09-22 | 1995 | 9 | Heathrow | 18.9
1995-09-23 | 1995 | 9 | Heathrow | 16.5
1995-09-24 | 1995 | 9 | Heathrow | 17.2
1995-09-25 | 1995 | 9 | Heathrow | 18.4
1995-09-26 | 1995 | 9 | Heathrow | 16.3
1995-09-27 | 1995 | 9 | Heathrow | 15.6
1995-09-28 | 1995 | 9 | Heathrow | 17.2
1995-09-29 | 1995 | 9 | Heathrow | 18.1
1995-09-30 | 1995 | 9 | Heathrow | 20.9
1996-05-01 | 1996 | 5 | Heathrow | 11.5
1996-05-02 | 1996 | 5 | Heathrow | 12.4
1996-05-03 | 1996 | 5 | Heathrow | 12
1996-05-04 | 1996 | 5 | Heathrow | 12.4
1996-05-05 | 1996 | 5 | Heathrow | 15.6
1996-05-06 | 1996 | 5 | Heathrow | 15.2
1996-05-07 | 1996 | 5 | Heathrow | 14.1
1996-05-08 | 1996 | 5 | Heathrow | 13.5
1996-05-09 | 1996 | 5 | Heathrow | 11.8
1996-05-10 | 1996 | 5 | Heathrow | 12.6
1996-05-11 | 1996 | 5 | Heathrow | 15
1996-05-12 | 1996 | 5 | Heathrow | 17.9
1996-05-13 | 1996 | 5 | Heathrow | 15.9
1996-05-14 | 1996 | 5 | Heathrow | 16.9
1996-05-15 | 1996 | 5 | Heathrow | 17
1996-05-16 | 1996 | 5 | Heathrow | 9.6
1996-05-17 | 1996 | 5 | Heathrow | 9.8
1996-05-18 | 1996 | 5 | Heathrow | 13.4
1996-05-19 | 1996 | 5 | Heathrow | 15.6
1996-05-20 | 1996 | 5 | Heathrow | 17
1996-05-21 | 1996 | 5 | Heathrow | 14.5
1996-05-22 | 1996 | 5 | Heathrow | 17.2
1996-05-23 | 1996 | 5 | Heathrow | 14.4
1996-05-24 | 1996 | 5 | Heathrow | 18.5
1996-05-25 | 1996 | 5 | Heathrow | 15.8
1996-05-26 | 1996 | 5 | Heathrow | 16.5
1996-05-27 | 1996 | 5 | Heathrow | 17.3
1996-05-28 | 1996 | 5 | Heathrow | 21.1
1996-05-29 | 1996 | 5 | Heathrow | 26.1
1996-05-30 | 1996 | 5 | Heathrow | 20.5
1996-05-31 | 1996 | 5 | Heathrow | 18.7
1996-06-01 | 1996 | 6 | Heathrow | 19.4
1996-06-02 | 1996 | 6 | Heathrow | 20.5
1996-06-03 | 1996 | 6 | Heathrow | 23.1
1996-06-04 | 1996 | 6 | Heathrow | 27.7
1996-06-05 | 1996 | 6 | Heathrow | 30.6
1996-06-06 | 1996 | 6 | Heathrow | 31.8
1996-06-07 | 1996 | 6 | Heathrow | 31.9
1996-06-08 | 1996 | 6 | Heathrow | 23
1996-06-09 | 1996 | 6 | Heathrow | 24.1
1996-06-10 | 1996 | 6 | Heathrow | 22.8
1996-06-11 | 1996 | 6 | Heathrow | 21.2
1996-06-12 | 1996 | 6 | Heathrow | 22.1
1996-06-13 | 1996 | 6 | Heathrow | 22.5
1996-06-14 | 1996 | 6 | Heathrow | 23.9
1996-06-15 | 1996 | 6 | Heathrow | 26.4
1996-06-16 | 1996 | 6 | Heathrow | 28.5
1996-06-17 | 1996 | 6 | Heathrow | 22.4
1996-06-18 | 1996 | 6 | Heathrow | 22.7
1996-06-19 | 1996 | 6 | Heathrow | 22.7
1996-06-20 | 1996 | 6 | Heathrow | 17.4
1996-06-21 | 1996 | 6 | Heathrow | 17
1996-06-22 | 1996 | 6 | Heathrow | 21.7
1996-06-23 | 1996 | 6 | Heathrow | 22.1
1996-06-24 | 1996 | 6 | Heathrow | 25.7
1996-06-25 | 1996 | 6 | Heathrow | 26
1996-06-26 | 1996 | 6 | Heathrow | 24.1
1996-06-27 | 1996 | 6 | Heathrow | 24.1
1996-06-28 | 1996 | 6 | Heathrow | 18.2
1996-06-29 | 1996 | 6 | Heathrow | 22.6
1996-06-30 | 1996 | 6 | Heathrow | 16.8
1996-07-01 | 1996 | 7 | Heathrow | 20.9
1996-07-02 | 1996 | 7 | Heathrow | 19
1996-07-03 | 1996 | 7 | Heathrow | 20.4
1996-07-04 | 1996 | 7 | Heathrow | 20.8
1996-07-05 | 1996 | 7 | Heathrow | 18.8
1996-07-06 | 1996 | 7 | Heathrow | 20.3
1996-07-07 | 1996 | 7 | Heathrow | 19.9
1996-07-08 | 1996 | 7 | Heathrow | 20.8
1996-07-09 | 1996 | 7 | Heathrow | 26.6
1996-07-10 | 1996 | 7 | Heathrow | 25.2
1996-07-11 | 1996 | 7 | Heathrow | 24.1
1996-07-12 | 1996 | 7 | Heathrow | 25.6
1996-07-13 | 1996 | 7 | Heathrow | 25.2
1996-07-14 | 1996 | 7 | Heathrow | 25.4
1996-07-15 | 1996 | 7 | Heathrow | 22.6
1996-07-16 | 1996 | 7 | Heathrow | 24.8
1996-07-17 | 1996 | 7 | Heathrow | 27.4
1996-07-18 | 1996 | 7 | Heathrow | 26.5
1996-07-19 | 1996 | 7 | Heathrow | 28.6
1996-07-20 | 1996 | 7 | Heathrow | 30.7
1996-07-21 | 1996 | 7 | Heathrow | 31.6
1996-07-22 | 1996 | 7 | Heathrow | 28
1996-07-23 | 1996 | 7 | Heathrow | 28.1
1996-07-24 | 1996 | 7 | Heathrow | 25.4
1996-07-25 | 1996 | 7 | Heathrow | 28.9
1996-07-26 | 1996 | 7 | Heathrow | 23.7
1996-07-27 | 1996 | 7 | Heathrow | 23.7
1996-07-28 | 1996 | 7 | Heathrow | 25.3
1996-07-29 | 1996 | 7 | Heathrow | 24.6
1996-07-30 | 1996 | 7 | Heathrow | 25.8
1996-07-31 | 1996 | 7 | Heathrow | 23.5
1996-08-01 | 1996 | 8 | Heathrow | 20.8
1996-08-02 | 1996 | 8 | Heathrow | 24
1996-08-03 | 1996 | 8 | Heathrow | 25.5
1996-08-04 | 1996 | 8 | Heathrow | 27.6
1996-08-05 | 1996 | 8 | Heathrow | 22.3
1996-08-06 | 1996 | 8 | Heathrow | 22.7
1996-08-07 | 1996 | 8 | Heathrow | 23.5
1996-08-08 | 1996 | 8 | Heathrow | 21.7
1996-08-09 | 1996 | 8 | Heathrow | 23.1
1996-08-10 | 1996 | 8 | Heathrow | 22.6
1996-08-11 | 1996 | 8 | Heathrow | 20.7
1996-08-12 | 1996 | 8 | Heathrow | 23.4
1996-08-13 | 1996 | 8 | Heathrow | 21.6
1996-08-14 | 1996 | 8 | Heathrow | 21.1
1996-08-15 | 1996 | 8 | Heathrow | 26.6
1996-08-16 | 1996 | 8 | Heathrow | 28
1996-08-17 | 1996 | 8 | Heathrow | 30.6
1996-08-18 | 1996 | 8 | Heathrow | 31.4
1996-08-19 | 1996 | 8 | Heathrow | 24.8
1996-08-20 | 1996 | 8 | Heathrow | 25
1996-08-21 | 1996 | 8 | Heathrow | 23
1996-08-22 | 1996 | 8 | Heathrow | 22
1996-08-23 | 1996 | 8 | Heathrow | 21.4
1996-08-24 | 1996 | 8 | Heathrow | 20.9
1996-08-25 | 1996 | 8 | Heathrow | 21.1
1996-08-26 | 1996 | 8 | Heathrow | 21.1
1996-08-27 | 1996 | 8 | Heathrow | 21.2
1996-08-28 | 1996 | 8 | Heathrow | 17.9
1996-08-29 | 1996 | 8 | Heathrow | 18
1996-08-30 | 1996 | 8 | Heathrow | 19.1
1996-08-31 | 1996 | 8 | Heathrow | 21.5
1996-09-01 | 1996 | 9 | Heathrow | 22.6
1996-09-02 | 1996 | 9 | Heathrow | 21.6
1996-09-03 | 1996 | 9 | Heathrow | 19.2
1996-09-04 | 1996 | 9 | Heathrow | 23.4
1996-09-05 | 1996 | 9 | Heathrow | 21.9
1996-09-06 | 1996 | 9 | Heathrow | 20.7
1996-09-07 | 1996 | 9 | Heathrow | 20.6
1996-09-08 | 1996 | 9 | Heathrow | 19.5
1996-09-09 | 1996 | 9 | Heathrow | 17.6
1996-09-10 | 1996 | 9 | Heathrow | 20
1996-09-11 | 1996 | 9 | Heathrow | 18.1
1996-09-12 | 1996 | 9 | Heathrow | 18.6
1996-09-13 | 1996 | 9 | Heathrow | 19.6
1996-09-14 | 1996 | 9 | Heathrow | 23
1996-09-15 | 1996 | 9 | Heathrow | 22.6
1996-09-16 | 1996 | 9 | Heathrow | 19.7
1996-09-17 | 1996 | 9 | Heathrow | 16.6
1996-09-18 | 1996 | 9 | Heathrow | 14.3
1996-09-19 | 1996 | 9 | Heathrow | 15
1996-09-20 | 1996 | 9 | Heathrow | 17.1
1996-09-21 | 1996 | 9 | Heathrow | 16
1996-09-22 | 1996 | 9 | Heathrow | 15.5
1996-09-23 | 1996 | 9 | Heathrow | 18.9
1996-09-24 | 1996 | 9 | Heathrow | 19.6
1996-09-25 | 1996 | 9 | Heathrow | 17.9
1996-09-26 | 1996 | 9 | Heathrow | 21.2
1996-09-27 | 1996 | 9 | Heathrow | 20.5
1996-09-28 | 1996 | 9 | Heathrow | 18.9
1996-09-29 | 1996 | 9 | Heathrow | 19
1996-09-30 | 1996 | 9 | Heathrow | 17.1
1997-05-01 | 1997 | 5 | Heathrow | 25.8
1997-05-02 | 1997 | 5 | Heathrow | 25.7
1997-05-03 | 1997 | 5 | Heathrow | 20.1
1997-05-04 | 1997 | 5 | Heathrow | 18.5
1997-05-05 | 1997 | 5 | Heathrow | 18.6
1997-05-06 | 1997 | 5 | Heathrow | 12.9
1997-05-07 | 1997 | 5 | Heathrow | 12.5
1997-05-08 | 1997 | 5 | Heathrow | 14
1997-05-09 | 1997 | 5 | Heathrow | 15.2
1997-05-10 | 1997 | 5 | Heathrow | 16.2
1997-05-11 | 1997 | 5 | Heathrow | 15
1997-05-12 | 1997 | 5 | Heathrow | 17.8
1997-05-13 | 1997 | 5 | Heathrow | 19.6
1997-05-14 | 1997 | 5 | Heathrow | 19.2
1997-05-15 | 1997 | 5 | Heathrow | 23
1997-05-16 | 1997 | 5 | Heathrow | 26.6
1997-05-17 | 1997 | 5 | Heathrow | 20.7
1997-05-18 | 1997 | 5 | Heathrow | 18.8
1997-05-19 | 1997 | 5 | Heathrow | 15.5
1997-05-20 | 1997 | 5 | Heathrow | 13.9
1997-05-21 | 1997 | 5 | Heathrow | 14.8
1997-05-22 | 1997 | 5 | Heathrow | 15.5
1997-05-23 | 1997 | 5 | Heathrow | 16.5
1997-05-24 | 1997 | 5 | Heathrow | 19.1
1997-05-25 | 1997 | 5 | Heathrow | 23.2
1997-05-26 | 1997 | 5 | Heathrow | 20
1997-05-27 | 1997 | 5 | Heathrow | 17.9
1997-05-28 | 1997 | 5 | Heathrow | 23.2
1997-05-29 | 1997 | 5 | Heathrow | 24.3
1997-05-30 | 1997 | 5 | Heathrow | 23.2
1997-05-31 | 1997 | 5 | Heathrow | 19.7
1997-06-01 | 1997 | 6 | Heathrow | 22.1
1997-06-02 | 1997 | 6 | Heathrow | 22.8
1997-06-03 | 1997 | 6 | Heathrow | 22.8
1997-06-04 | 1997 | 6 | Heathrow | 26.7
1997-06-05 | 1997 | 6 | Heathrow | 25.9
1997-06-06 | 1997 | 6 | Heathrow | 24
1997-06-07 | 1997 | 6 | Heathrow | 22.2
1997-06-08 | 1997 | 6 | Heathrow | 22.8
1997-06-09 | 1997 | 6 | Heathrow | 26.3
1997-06-10 | 1997 | 6 | Heathrow | 24.5
1997-06-11 | 1997 | 6 | Heathrow | 24.6
1997-06-12 | 1997 | 6 | Heathrow | 22.6
1997-06-13 | 1997 | 6 | Heathrow | 22.6
1997-06-14 | 1997 | 6 | Heathrow | 19
1997-06-15 | 1997 | 6 | Heathrow | 20.3
1997-06-16 | 1997 | 6 | Heathrow | 20.4
1997-06-17 | 1997 | 6 | Heathrow | 21.4
1997-06-18 | 1997 | 6 | Heathrow | 16.8
1997-06-19 | 1997 | 6 | Heathrow | 16
1997-06-20 | 1997 | 6 | Heathrow | 18.9
1997-06-21 | 1997 | 6 | Heathrow | 18.1
1997-06-22 | 1997 | 6 | Heathrow | 19.9
1997-06-23 | 1997 | 6 | Heathrow | 19
1997-06-24 | 1997 | 6 | Heathrow | 16
1997-06-25 | 1997 | 6 | Heathrow | 16.1
1997-06-26 | 1997 | 6 | Heathrow | 16.1
1997-06-27 | 1997 | 6 | Heathrow | 16.2
1997-06-28 | 1997 | 6 | Heathrow | 18.2
1997-06-29 | 1997 | 6 | Heathrow | 16.6
1997-06-30 | 1997 | 6 | Heathrow | 18.5
1997-07-01 | 1997 | 7 | Heathrow | 18.6
1997-07-02 | 1997 | 7 | Heathrow | 17.4
1997-07-03 | 1997 | 7 | Heathrow | 18.3
1997-07-04 | 1997 | 7 | Heathrow | 22.4
1997-07-05 | 1997 | 7 | Heathrow | 24.8
1997-07-06 | 1997 | 7 | Heathrow | 26.7
1997-07-07 | 1997 | 7 | Heathrow | 27.6
1997-07-08 | 1997 | 7 | Heathrow | 26.3
1997-07-09 | 1997 | 7 | Heathrow | 22.8
1997-07-10 | 1997 | 7 | Heathrow | 23.8
1997-07-11 | 1997 | 7 | Heathrow | 25
1997-07-12 | 1997 | 7 | Heathrow | 24.2
1997-07-13 | 1997 | 7 | Heathrow | 24.1
1997-07-14 | 1997 | 7 | Heathrow | 25.1
1997-07-15 | 1997 | 7 | Heathrow | 22.2
1997-07-16 | 1997 | 7 | Heathrow | 20.4
1997-07-17 | 1997 | 7 | Heathrow | 20.8
1997-07-18 | 1997 | 7 | Heathrow | 24.8
1997-07-19 | 1997 | 7 | Heathrow | 24.9
1997-07-20 | 1997 | 7 | Heathrow | 25.4
1997-07-21 | 1997 | 7 | Heathrow | 26.7
1997-07-22 | 1997 | 7 | Heathrow | 27.7
1997-07-23 | 1997 | 7 | Heathrow | 24.4
1997-07-24 | 1997 | 7 | Heathrow | 24
1997-07-25 | 1997 | 7 | Heathrow | 21.4
1997-07-26 | 1997 | 7 | Heathrow | 25.1
1997-07-27 | 1997 | 7 | Heathrow | 25.8
1997-07-28 | 1997 | 7 | Heathrow | 27.3
1997-07-29 | 1997 | 7 | Heathrow | 24.4
1997-07-30 | 1997 | 7 | Heathrow | 24.5
1997-07-31 | 1997 | 7 | Heathrow | 24.2
1997-08-01 | 1997 | 8 | Heathrow | 23.2
1997-08-02 | 1997 | 8 | Heathrow | 21.5
1997-08-03 | 1997 | 8 | Heathrow | 21.8
1997-08-04 | 1997 | 8 | Heathrow | 22.8
1997-08-05 | 1997 | 8 | Heathrow | 26.7
1997-08-06 | 1997 | 8 | Heathrow | 26.8
1997-08-07 | 1997 | 8 | Heathrow | 30.9
1997-08-08 | 1997 | 8 | Heathrow | 28.5
1997-08-09 | 1997 | 8 | Heathrow | 31.5
1997-08-10 | 1997 | 8 | Heathrow | 29.6
1997-08-11 | 1997 | 8 | Heathrow | 29.5
1997-08-12 | 1997 | 8 | Heathrow | 27
1997-08-13 | 1997 | 8 | Heathrow | 26.3
1997-08-14 | 1997 | 8 | Heathrow | 28.4
1997-08-15 | 1997 | 8 | Heathrow | 29.4
1997-08-16 | 1997 | 8 | Heathrow | 24.8
1997-08-17 | 1997 | 8 | Heathrow | 29.7
1997-08-18 | 1997 | 8 | Heathrow | 31.1
1997-08-19 | 1997 | 8 | Heathrow | 29.5
1997-08-20 | 1997 | 8 | Heathrow | 26.9
1997-08-21 | 1997 | 8 | Heathrow | 25.1
1997-08-22 | 1997 | 8 | Heathrow | 27.1
1997-08-23 | 1997 | 8 | Heathrow | 24.8
1997-08-24 | 1997 | 8 | Heathrow | 22.3
1997-08-25 | 1997 | 8 | Heathrow | 23.3
1997-08-26 | 1997 | 8 | Heathrow | 19.7
1997-08-27 | 1997 | 8 | Heathrow | 20.3
1997-08-28 | 1997 | 8 | Heathrow | 20.9
1997-08-29 | 1997 | 8 | Heathrow | 21.8
1997-08-30 | 1997 | 8 | Heathrow | 24.8
1997-08-31 | 1997 | 8 | Heathrow | 21.7
1997-09-01 | 1997 | 9 | Heathrow | 21.9
1997-09-02 | 1997 | 9 | Heathrow | 19.5
1997-09-03 | 1997 | 9 | Heathrow | 21.8
1997-09-04 | 1997 | 9 | Heathrow | 19.7
1997-09-05 | 1997 | 9 | Heathrow | 20.9
1997-09-06 | 1997 | 9 | Heathrow | 22.6
1997-09-07 | 1997 | 9 | Heathrow | 22.5
1997-09-08 | 1997 | 9 | Heathrow | 22
1997-09-09 | 1997 | 9 | Heathrow | 21.2
1997-09-10 | 1997 | 9 | Heathrow | 20.6
1997-09-11 | 1997 | 9 | Heathrow | 20.1
1997-09-12 | 1997 | 9 | Heathrow | 17.7
1997-09-13 | 1997 | 9 | Heathrow | 19
1997-09-14 | 1997 | 9 | Heathrow | 20.3
1997-09-15 | 1997 | 9 | Heathrow | 22
1997-09-16 | 1997 | 9 | Heathrow | 21.9
1997-09-17 | 1997 | 9 | Heathrow | 25.1
1997-09-18 | 1997 | 9 | Heathrow | 25.1
1997-09-19 | 1997 | 9 | Heathrow | 18.8
1997-09-20 | 1997 | 9 | Heathrow | 19.1
1997-09-21 | 1997 | 9 | Heathrow | 21.4
1997-09-22 | 1997 | 9 | Heathrow | 21.2
1997-09-23 | 1997 | 9 | Heathrow | 20.4
1997-09-24 | 1997 | 9 | Heathrow | 19.8
1997-09-25 | 1997 | 9 | Heathrow | 22.1
1997-09-26 | 1997 | 9 | Heathrow | 19.4
1997-09-27 | 1997 | 9 | Heathrow | 19.9
1997-09-28 | 1997 | 9 | Heathrow | 23.5
1997-09-29 | 1997 | 9 | Heathrow | 21.6
1997-09-30 | 1997 | 9 | Heathrow | 25.5
1998-05-01 | 1998 | 5 | Heathrow | 15.7
1998-05-02 | 1998 | 5 | Heathrow | 12.4
1998-05-03 | 1998 | 5 | Heathrow | 16.7
1998-05-04 | 1998 | 5 | Heathrow | 14.3
1998-05-05 | 1998 | 5 | Heathrow | 17.2
1998-05-06 | 1998 | 5 | Heathrow | 16.2
1998-05-07 | 1998 | 5 | Heathrow | 22.6
1998-05-08 | 1998 | 5 | Heathrow | 22.6
1998-05-09 | 1998 | 5 | Heathrow | 23
1998-05-10 | 1998 | 5 | Heathrow | 23
1998-05-11 | 1998 | 5 | Heathrow | 22.1
1998-05-12 | 1998 | 5 | Heathrow | 24.9
1998-05-13 | 1998 | 5 | Heathrow | 24.5
1998-05-14 | 1998 | 5 | Heathrow | 25.7
1998-05-15 | 1998 | 5 | Heathrow | 24.2
1998-05-16 | 1998 | 5 | Heathrow | 21.6
1998-05-17 | 1998 | 5 | Heathrow | 23.1
1998-05-18 | 1998 | 5 | Heathrow | 23.8
1998-05-19 | 1998 | 5 | Heathrow | 24.5
1998-05-20 | 1998 | 5 | Heathrow | 24.6
1998-05-21 | 1998 | 5 | Heathrow | 18
1998-05-22 | 1998 | 5 | Heathrow | 17.2
1998-05-23 | 1998 | 5 | Heathrow | 18.1
1998-05-24 | 1998 | 5 | Heathrow | 19.6
1998-05-25 | 1998 | 5 | Heathrow | 17
1998-05-26 | 1998 | 5 | Heathrow | 17.1
1998-05-27 | 1998 | 5 | Heathrow | 17.2
1998-05-28 | 1998 | 5 | Heathrow | 18.7
1998-05-29 | 1998 | 5 | Heathrow | 22
1998-05-30 | 1998 | 5 | Heathrow | 20.4
1998-05-31 | 1998 | 5 | Heathrow | 21.4
1998-06-01 | 1998 | 6 | Heathrow | 19.5
1998-06-02 | 1998 | 6 | Heathrow | 18.9
1998-06-03 | 1998 | 6 | Heathrow | 17.2
1998-06-04 | 1998 | 6 | Heathrow | 18.4
1998-06-05 | 1998 | 6 | Heathrow | 23.4
1998-06-06 | 1998 | 6 | Heathrow | 21.3
1998-06-07 | 1998 | 6 | Heathrow | 17.2
1998-06-08 | 1998 | 6 | Heathrow | 19.8
1998-06-09 | 1998 | 6 | Heathrow | 17.5
1998-06-10 | 1998 | 6 | Heathrow | 17.6
1998-06-11 | 1998 | 6 | Heathrow | 17.8
1998-06-12 | 1998 | 6 | Heathrow | 15.5
1998-06-13 | 1998 | 6 | Heathrow | 18.1
1998-06-14 | 1998 | 6 | Heathrow | 18.3
1998-06-15 | 1998 | 6 | Heathrow | 18.1
1998-06-16 | 1998 | 6 | Heathrow | 17.9
1998-06-17 | 1998 | 6 | Heathrow | 18.6
1998-06-18 | 1998 | 6 | Heathrow | 25.2
1998-06-19 | 1998 | 6 | Heathrow | 28.4
1998-06-20 | 1998 | 6 | Heathrow | 25.2
1998-06-21 | 1998 | 6 | Heathrow | 21.8
1998-06-22 | 1998 | 6 | Heathrow | 20.5
1998-06-23 | 1998 | 6 | Heathrow | 23.8
1998-06-24 | 1998 | 6 | Heathrow | 20.2
1998-06-25 | 1998 | 6 | Heathrow | 18.6
1998-06-26 | 1998 | 6 | Heathrow | 20.3
1998-06-27 | 1998 | 6 | Heathrow | 22.2
1998-06-28 | 1998 | 6 | Heathrow | 19
1998-06-29 | 1998 | 6 | Heathrow | 19.6
1998-06-30 | 1998 | 6 | Heathrow | 19.9
1998-07-01 | 1998 | 7 | Heathrow | 17
1998-07-02 | 1998 | 7 | Heathrow | 19.6
1998-07-03 | 1998 | 7 | Heathrow | 19.1
1998-07-04 | 1998 | 7 | Heathrow | 23.3
1998-07-05 | 1998 | 7 | Heathrow | 19.3
1998-07-06 | 1998 | 7 | Heathrow | 20.5
1998-07-07 | 1998 | 7 | Heathrow | 22.7
1998-07-08 | 1998 | 7 | Heathrow | 21.9
1998-07-09 | 1998 | 7 | Heathrow | 21
1998-07-10 | 1998 | 7 | Heathrow | 21.1
1998-07-11 | 1998 | 7 | Heathrow | 19.1
1998-07-12 | 1998 | 7 | Heathrow | 19.8
1998-07-13 | 1998 | 7 | Heathrow | 20.2
1998-07-14 | 1998 | 7 | Heathrow | 20
1998-07-15 | 1998 | 7 | Heathrow | 22.3
1998-07-16 | 1998 | 7 | Heathrow | 22.8
1998-07-17 | 1998 | 7 | Heathrow | 21.9
1998-07-18 | 1998 | 7 | Heathrow | 23.2
1998-07-19 | 1998 | 7 | Heathrow | 26.3
1998-07-20 | 1998 | 7 | Heathrow | 21.8
1998-07-21 | 1998 | 7 | Heathrow | 22.5
1998-07-22 | 1998 | 7 | Heathrow | 23.5
1998-07-23 | 1998 | 7 | Heathrow | 21.9
1998-07-24 | 1998 | 7 | Heathrow | 22.7
1998-07-25 | 1998 | 7 | Heathrow | 21
1998-07-26 | 1998 | 7 | Heathrow | 23.1
1998-07-27 | 1998 | 7 | Heathrow | 21.7
1998-07-28 | 1998 | 7 | Heathrow | 22.3
1998-07-29 | 1998 | 7 | Heathrow | 22.5
1998-07-30 | 1998 | 7 | Heathrow | 22.6
1998-07-31 | 1998 | 7 | Heathrow | 21.9
1998-08-01 | 1998 | 8 | Heathrow | 20.8
1998-08-02 | 1998 | 8 | Heathrow | 18.4
1998-08-03 | 1998 | 8 | Heathrow | 23.1
1998-08-04 | 1998 | 8 | Heathrow | 26.6
1998-08-05 | 1998 | 8 | Heathrow | 27.2
1998-08-06 | 1998 | 8 | Heathrow | 29.2
1998-08-07 | 1998 | 8 | Heathrow | 29.9
1998-08-08 | 1998 | 8 | Heathrow | 26
1998-08-09 | 1998 | 8 | Heathrow | 31.2
1998-08-10 | 1998 | 8 | Heathrow | 29.7
1998-08-11 | 1998 | 8 | Heathrow | 23.8
1998-08-12 | 1998 | 8 | Heathrow | 22
1998-08-13 | 1998 | 8 | Heathrow | 26.7
1998-08-14 | 1998 | 8 | Heathrow | 22.6
1998-08-15 | 1998 | 8 | Heathrow | 24.7
1998-08-16 | 1998 | 8 | Heathrow | 25.3
1998-08-17 | 1998 | 8 | Heathrow | 22.6
1998-08-18 | 1998 | 8 | Heathrow | 25
1998-08-19 | 1998 | 8 | Heathrow | 22.2
1998-08-20 | 1998 | 8 | Heathrow | 22.7
1998-08-21 | 1998 | 8 | Heathrow | 20.4
1998-08-22 | 1998 | 8 | Heathrow | 19.4
1998-08-23 | 1998 | 8 | Heathrow | 19
1998-08-24 | 1998 | 8 | Heathrow | 22.1
1998-08-25 | 1998 | 8 | Heathrow | 17.8
1998-08-26 | 1998 | 8 | Heathrow | 20.3
1998-08-27 | 1998 | 8 | Heathrow | 20.1
1998-08-28 | 1998 | 8 | Heathrow | 22.7
1998-08-29 | 1998 | 8 | Heathrow | 21.7
1998-08-30 | 1998 | 8 | Heathrow | 22.7
1998-08-31 | 1998 | 8 | Heathrow | 25.9
1998-09-01 | 1998 | 9 | Heathrow | 23.3
1998-09-02 | 1998 | 9 | Heathrow | 22.4
1998-09-03 | 1998 | 9 | Heathrow | 20.2
1998-09-04 | 1998 | 9 | Heathrow | 20
1998-09-05 | 1998 | 9 | Heathrow | 21.7
1998-09-06 | 1998 | 9 | Heathrow | 23.3
1998-09-07 | 1998 | 9 | Heathrow | 23.3
1998-09-08 | 1998 | 9 | Heathrow | 21.5
1998-09-09 | 1998 | 9 | Heathrow | 21
1998-09-10 | 1998 | 9 | Heathrow | 18.2
1998-09-11 | 1998 | 9 | Heathrow | 14.8
1998-09-12 | 1998 | 9 | Heathrow | 15.9
1998-09-13 | 1998 | 9 | Heathrow | 17.6
1998-09-14 | 1998 | 9 | Heathrow | 18.7
1998-09-15 | 1998 | 9 | Heathrow | 18.6
1998-09-16 | 1998 | 9 | Heathrow | 18.4
1998-09-17 | 1998 | 9 | Heathrow | 21.6
1998-09-18 | 1998 | 9 | Heathrow | 23.6
1998-09-19 | 1998 | 9 | Heathrow | 21.4
1998-09-20 | 1998 | 9 | Heathrow | 21.6
1998-09-21 | 1998 | 9 | Heathrow | 18.4
1998-09-22 | 1998 | 9 | Heathrow | 21.5
1998-09-23 | 1998 | 9 | Heathrow | 22
1998-09-24 | 1998 | 9 | Heathrow | 23
1998-09-25 | 1998 | 9 | Heathrow | 22.2
1998-09-26 | 1998 | 9 | Heathrow | 19.2
1998-09-27 | 1998 | 9 | Heathrow | 18.1
1998-09-28 | 1998 | 9 | Heathrow | 16.8
1998-09-29 | 1998 | 9 | Heathrow | 18.4
1998-09-30 | 1998 | 9 | Heathrow | 17.8
1999-05-01 | 1999 | 5 | Heathrow | 20.3
1999-05-02 | 1999 | 5 | Heathrow | 22.4
1999-05-03 | 1999 | 5 | Heathrow | 18.1
1999-05-04 | 1999 | 5 | Heathrow | 18.1
1999-05-05 | 1999 | 5 | Heathrow | 17.6
1999-05-06 | 1999 | 5 | Heathrow | 16.7
1999-05-07 | 1999 | 5 | Heathrow | 16.5
1999-05-08 | 1999 | 5 | Heathrow | 20.5
1999-05-09 | 1999 | 5 | Heathrow | 18.4
1999-05-10 | 1999 | 5 | Heathrow | 19
1999-05-11 | 1999 | 5 | Heathrow | 17.8
1999-05-12 | 1999 | 5 | Heathrow | 19.1
1999-05-13 | 1999 | 5 | Heathrow | 17.2
1999-05-14 | 1999 | 5 | Heathrow | 15
1999-05-15 | 1999 | 5 | Heathrow | 16.5
1999-05-16 | 1999 | 5 | Heathrow | 15.8
1999-05-17 | 1999 | 5 | Heathrow | 16.5
1999-05-18 | 1999 | 5 | Heathrow | 22.8
1999-05-19 | 1999 | 5 | Heathrow | 22
1999-05-20 | 1999 | 5 | Heathrow | 18.6
1999-05-21 | 1999 | 5 | Heathrow | 17.6
1999-05-22 | 1999 | 5 | Heathrow | 19.7
1999-05-23 | 1999 | 5 | Heathrow | 18.9
1999-05-24 | 1999 | 5 | Heathrow | 18.4
1999-05-25 | 1999 | 5 | Heathrow | 21.7
1999-05-26 | 1999 | 5 | Heathrow | 26.4
1999-05-27 | 1999 | 5 | Heathrow | 22.5
1999-05-28 | 1999 | 5 | Heathrow | 25
1999-05-29 | 1999 | 5 | Heathrow | 25.1
1999-05-30 | 1999 | 5 | Heathrow | 17.7
1999-05-31 | 1999 | 5 | Heathrow | 22.7
1999-06-01 | 1999 | 6 | Heathrow | 20.7
1999-06-02 | 1999 | 6 | Heathrow | 17.7
1999-06-03 | 1999 | 6 | Heathrow | 17.9
1999-06-04 | 1999 | 6 | Heathrow | 18
1999-06-05 | 1999 | 6 | Heathrow | 19.7
1999-06-06 | 1999 | 6 | Heathrow | 17.6
1999-06-07 | 1999 | 6 | Heathrow | 18.3
1999-06-08 | 1999 | 6 | Heathrow | 19.1
1999-06-09 | 1999 | 6 | Heathrow | 18
1999-06-10 | 1999 | 6 | Heathrow | 17.3
1999-06-11 | 1999 | 6 | Heathrow | 16.5
1999-06-12 | 1999 | 6 | Heathrow | 20.9
1999-06-13 | 1999 | 6 | Heathrow | 23
1999-06-14 | 1999 | 6 | Heathrow | 24.9
1999-06-15 | 1999 | 6 | Heathrow | 25.5
1999-06-16 | 1999 | 6 | Heathrow | 21.4
1999-06-17 | 1999 | 6 | Heathrow | 23.2
1999-06-18 | 1999 | 6 | Heathrow | 21
1999-06-19 | 1999 | 6 | Heathrow | 18.9
1999-06-20 | 1999 | 6 | Heathrow | 17
1999-06-21 | 1999 | 6 | Heathrow | 18.4
1999-06-22 | 1999 | 6 | Heathrow | 21.7
1999-06-23 | 1999 | 6 | Heathrow | 23
1999-06-24 | 1999 | 6 | Heathrow | 22.3
1999-06-25 | 1999 | 6 | Heathrow | 26.7
1999-06-26 | 1999 | 6 | Heathrow | 26.7
1999-06-27 | 1999 | 6 | Heathrow | 19.5
1999-06-28 | 1999 | 6 | Heathrow | 17.5
1999-06-29 | 1999 | 6 | Heathrow | 20.5
1999-06-30 | 1999 | 6 | Heathrow | 21.5
1999-07-01 | 1999 | 7 | Heathrow | 26
1999-07-02 | 1999 | 7 | Heathrow | 23.9
1999-07-03 | 1999 | 7 | Heathrow | 21
1999-07-04 | 1999 | 7 | Heathrow | 23.2
1999-07-05 | 1999 | 7 | Heathrow | 25.5
1999-07-06 | 1999 | 7 | Heathrow | 24.7
1999-07-07 | 1999 | 7 | Heathrow | 27.6
1999-07-08 | 1999 | 7 | Heathrow | 25.2
1999-07-09 | 1999 | 7 | Heathrow | 26.6
1999-07-10 | 1999 | 7 | Heathrow | 27.2
1999-07-11 | 1999 | 7 | Heathrow | 24.4
1999-07-12 | 1999 | 7 | Heathrow | 26.1
1999-07-13 | 1999 | 7 | Heathrow | 19.9
1999-07-14 | 1999 | 7 | Heathrow | 21.6
1999-07-15 | 1999 | 7 | Heathrow | 22.1
1999-07-16 | 1999 | 7 | Heathrow | 25.9
1999-07-17 | 1999 | 7 | Heathrow | 28
1999-07-18 | 1999 | 7 | Heathrow | 26
1999-07-19 | 1999 | 7 | Heathrow | 24.7
1999-07-20 | 1999 | 7 | Heathrow | 20.8
1999-07-21 | 1999 | 7 | Heathrow | 20.9
1999-07-22 | 1999 | 7 | Heathrow | 25.5
1999-07-23 | 1999 | 7 | Heathrow | 29.8
1999-07-24 | 1999 | 7 | Heathrow | 27.8
1999-07-25 | 1999 | 7 | Heathrow | 23
1999-07-26 | 1999 | 7 | Heathrow | 21.7
1999-07-27 | 1999 | 7 | Heathrow | 25.3
1999-07-28 | 1999 | 7 | Heathrow | 28.6
1999-07-29 | 1999 | 7 | Heathrow | 29.4
1999-07-30 | 1999 | 7 | Heathrow | 31.3
1999-07-31 | 1999 | 7 | Heathrow | 32.7
1999-08-01 | 1999 | 8 | Heathrow | 31.9
1999-08-02 | 1999 | 8 | Heathrow | 32
1999-08-03 | 1999 | 8 | Heathrow | 27.6
1999-08-04 | 1999 | 8 | Heathrow | 26.2
1999-08-05 | 1999 | 8 | Heathrow | 26.9
1999-08-06 | 1999 | 8 | Heathrow | 24.4
1999-08-07 | 1999 | 8 | Heathrow | 22.7
1999-08-08 | 1999 | 8 | Heathrow | 21.3
1999-08-09 | 1999 | 8 | Heathrow | 21.4
1999-08-10 | 1999 | 8 | Heathrow | 20.5
1999-08-11 | 1999 | 8 | Heathrow | 21.7
1999-08-12 | 1999 | 8 | Heathrow | 22.4
1999-08-13 | 1999 | 8 | Heathrow | 22.4
1999-08-14 | 1999 | 8 | Heathrow | 21.4
1999-08-15 | 1999 | 8 | Heathrow | 19.1
1999-08-16 | 1999 | 8 | Heathrow | 17
1999-08-17 | 1999 | 8 | Heathrow | 19.9
1999-08-18 | 1999 | 8 | Heathrow | 19.9
1999-08-19 | 1999 | 8 | Heathrow | 21.2
1999-08-20 | 1999 | 8 | Heathrow | 19.1
1999-08-21 | 1999 | 8 | Heathrow | 19.3
1999-08-22 | 1999 | 8 | Heathrow | 21.2
1999-08-23 | 1999 | 8 | Heathrow | 20.4
1999-08-24 | 1999 | 8 | Heathrow | 25
1999-08-25 | 1999 | 8 | Heathrow | 24
1999-08-26 | 1999 | 8 | Heathrow | 22.3
1999-08-27 | 1999 | 8 | Heathrow | 24.8
1999-08-28 | 1999 | 8 | Heathrow | 24
1999-08-29 | 1999 | 8 | Heathrow | 23
1999-08-30 | 1999 | 8 | Heathrow | 23
1999-08-31 | 1999 | 8 | Heathrow | 24.5
1999-09-01 | 1999 | 9 | Heathrow | 26.3
1999-09-02 | 1999 | 9 | Heathrow | 26.7
1999-09-03 | 1999 | 9 | Heathrow | 27
1999-09-04 | 1999 | 9 | Heathrow | 27.4
1999-09-05 | 1999 | 9 | Heathrow | 26.7
1999-09-06 | 1999 | 9 | Heathrow | 23.9
1999-09-07 | 1999 | 9 | Heathrow | 24.3
1999-09-08 | 1999 | 9 | Heathrow | 21.6
1999-09-09 | 1999 | 9 | Heathrow | 24.8
1999-09-10 | 1999 | 9 | Heathrow | 28.5
1999-09-11 | 1999 | 9 | Heathrow | 28.6
1999-09-12 | 1999 | 9 | Heathrow | 19.7
1999-09-13 | 1999 | 9 | Heathrow | 19.7
1999-09-14 | 1999 | 9 | Heathrow | 17.2
1999-09-15 | 1999 | 9 | Heathrow | 18.9
1999-09-16 | 1999 | 9 | Heathrow | 20.1
1999-09-17 | 1999 | 9 | Heathrow | 19
1999-09-18 | 1999 | 9 | Heathrow | 18.8
1999-09-19 | 1999 | 9 | Heathrow | 18.9
1999-09-20 | 1999 | 9 | Heathrow | 20.5
1999-09-21 | 1999 | 9 | Heathrow | 21
1999-09-22 | 1999 | 9 | Heathrow | 20
1999-09-23 | 1999 | 9 | Heathrow | 20
1999-09-24 | 1999 | 9 | Heathrow | 19.9
1999-09-25 | 1999 | 9 | Heathrow | 17.9
1999-09-26 | 1999 | 9 | Heathrow | 18.8
1999-09-27 | 1999 | 9 | Heathrow | 18
1999-09-28 | 1999 | 9 | Heathrow | 18.5
1999-09-29 | 1999 | 9 | Heathrow | 18.1
1999-09-30 | 1999 | 9 | Heathrow | 17
2000-05-01 | 2000 | 5 | Heathrow | 14.6
2000-05-02 | 2000 | 5 | Heathrow | 14.6
2000-05-03 | 2000 | 5 | Heathrow | 12.6
2000-05-04 | 2000 | 5 | Heathrow | 20.5
2000-05-05 | 2000 | 5 | Heathrow | 24.1
2000-05-06 | 2000 | 5 | Heathrow | 23.3
2000-05-07 | 2000 | 5 | Heathrow | 19.4
2000-05-08 | 2000 | 5 | Heathrow | 23.4
2000-05-09 | 2000 | 5 | Heathrow | 17.9
2000-05-10 | 2000 | 5 | Heathrow | 17.8
2000-05-11 | 2000 | 5 | Heathrow | 19.5
2000-05-12 | 2000 | 5 | Heathrow | 24.9
2000-05-13 | 2000 | 5 | Heathrow | 25.3
2000-05-14 | 2000 | 5 | Heathrow | 26.6
2000-05-15 | 2000 | 5 | Heathrow | 22.5
2000-05-16 | 2000 | 5 | Heathrow | 22.6
2000-05-17 | 2000 | 5 | Heathrow | 15.5
2000-05-18 | 2000 | 5 | Heathrow | 14.3
2000-05-19 | 2000 | 5 | Heathrow | 15.8
2000-05-20 | 2000 | 5 | Heathrow | 16
2000-05-21 | 2000 | 5 | Heathrow | 18.6
2000-05-22 | 2000 | 5 | Heathrow | 14.3
2000-05-23 | 2000 | 5 | Heathrow | 16.2
2000-05-24 | 2000 | 5 | Heathrow | 16.8
2000-05-25 | 2000 | 5 | Heathrow | 16.9
2000-05-26 | 2000 | 5 | Heathrow | 14.8
2000-05-27 | 2000 | 5 | Heathrow | 15.6
2000-05-28 | 2000 | 5 | Heathrow | 17.4
2000-05-29 | 2000 | 5 | Heathrow | 15.7
2000-05-30 | 2000 | 5 | Heathrow | 19
2000-05-31 | 2000 | 5 | Heathrow | 16.8
2000-06-01 | 2000 | 6 | Heathrow | 18.8
2000-06-02 | 2000 | 6 | Heathrow | 22.9
2000-06-03 | 2000 | 6 | Heathrow | 18.1
2000-06-04 | 2000 | 6 | Heathrow | 16.1
2000-06-05 | 2000 | 6 | Heathrow | 18.9
2000-06-06 | 2000 | 6 | Heathrow | 20.6
2000-06-07 | 2000 | 6 | Heathrow | 22.4
2000-06-08 | 2000 | 6 | Heathrow | 17.8
2000-06-09 | 2000 | 6 | Heathrow | 20.3
2000-06-10 | 2000 | 6 | Heathrow | 19.3
2000-06-11 | 2000 | 6 | Heathrow | 25.1
2000-06-12 | 2000 | 6 | Heathrow | 22.6
2000-06-13 | 2000 | 6 | Heathrow | 22.5
2000-06-14 | 2000 | 6 | Heathrow | 20.1
2000-06-15 | 2000 | 6 | Heathrow | 22.3
2000-06-16 | 2000 | 6 | Heathrow | 25.9
2000-06-17 | 2000 | 6 | Heathrow | 30.8
2000-06-18 | 2000 | 6 | Heathrow | 31.4
2000-06-19 | 2000 | 6 | Heathrow | 31.5
2000-06-20 | 2000 | 6 | Heathrow | 19.5
2000-06-21 | 2000 | 6 | Heathrow | 19
2000-06-22 | 2000 | 6 | Heathrow | 19.7
2000-06-23 | 2000 | 6 | Heathrow | 19.7
2000-06-24 | 2000 | 6 | Heathrow | 18
2000-06-25 | 2000 | 6 | Heathrow | 19.9
2000-06-26 | 2000 | 6 | Heathrow | 21.9
2000-06-27 | 2000 | 6 | Heathrow | 20.9
2000-06-28 | 2000 | 6 | Heathrow | 20.3
2000-06-29 | 2000 | 6 | Heathrow | 20.8
2000-06-30 | 2000 | 6 | Heathrow | 20.9
2000-07-01 | 2000 | 7 | Heathrow | 22.3
2000-07-02 | 2000 | 7 | Heathrow | 23.3
2000-07-03 | 2000 | 7 | Heathrow | 23.4
2000-07-04 | 2000 | 7 | Heathrow | 17.1
2000-07-05 | 2000 | 7 | Heathrow | 22.7
2000-07-06 | 2000 | 7 | Heathrow | 17.9
2000-07-07 | 2000 | 7 | Heathrow | 17.9
2000-07-08 | 2000 | 7 | Heathrow | 19.1
2000-07-09 | 2000 | 7 | Heathrow | 19.1
2000-07-10 | 2000 | 7 | Heathrow | 16.3
2000-07-11 | 2000 | 7 | Heathrow | 18.7
2000-07-12 | 2000 | 7 | Heathrow | 20.9
2000-07-13 | 2000 | 7 | Heathrow | 21
2000-07-14 | 2000 | 7 | Heathrow | 18.1
2000-07-15 | 2000 | 7 | Heathrow | 18.2
2000-07-16 | 2000 | 7 | Heathrow | 22.6
2000-07-17 | 2000 | 7 | Heathrow | 24.7
2000-07-18 | 2000 | 7 | Heathrow | 25.2
2000-07-19 | 2000 | 7 | Heathrow | 25.3
2000-07-20 | 2000 | 7 | Heathrow | 25.9
2000-07-21 | 2000 | 7 | Heathrow | 21.6
2000-07-22 | 2000 | 7 | Heathrow | 19
2000-07-23 | 2000 | 7 | Heathrow | 17.2
2000-07-24 | 2000 | 7 | Heathrow | 19
2000-07-25 | 2000 | 7 | Heathrow | 23.4
2000-07-26 | 2000 | 7 | Heathrow | 25
2000-07-27 | 2000 | 7 | Heathrow | 20.9
2000-07-28 | 2000 | 7 | Heathrow | 24.9
2000-07-29 | 2000 | 7 | Heathrow | 24.8
2000-07-30 | 2000 | 7 | Heathrow | 25.3
2000-07-31 | 2000 | 7 | Heathrow | 24.5
2000-08-01 | 2000 | 8 | Heathrow | 23.5
2000-08-02 | 2000 | 8 | Heathrow | 19.7
2000-08-03 | 2000 | 8 | Heathrow | 22.4
2000-08-04 | 2000 | 8 | Heathrow | 24.2
2000-08-05 | 2000 | 8 | Heathrow | 24.7
2000-08-06 | 2000 | 8 | Heathrow | 23
2000-08-07 | 2000 | 8 | Heathrow | 22.6
2000-08-08 | 2000 | 8 | Heathrow | 23.9
2000-08-09 | 2000 | 8 | Heathrow | 25.4
2000-08-10 | 2000 | 8 | Heathrow | 24.9
2000-08-11 | 2000 | 8 | Heathrow | 27.4
2000-08-12 | 2000 | 8 | Heathrow | 23.6
2000-08-13 | 2000 | 8 | Heathrow | 23.7
2000-08-14 | 2000 | 8 | Heathrow | 24.4
2000-08-15 | 2000 | 8 | Heathrow | 23.1
2000-08-16 | 2000 | 8 | Heathrow | 23.1
2000-08-17 | 2000 | 8 | Heathrow | 19.9
2000-08-18 | 2000 | 8 | Heathrow | 23.2
2000-08-19 | 2000 | 8 | Heathrow | 21.7
2000-08-20 | 2000 | 8 | Heathrow | 22.2
2000-08-21 | 2000 | 8 | Heathrow | 22.7
2000-08-22 | 2000 | 8 | Heathrow | 23.9
2000-08-23 | 2000 | 8 | Heathrow | 27
2000-08-24 | 2000 | 8 | Heathrow | 26.2
2000-08-25 | 2000 | 8 | Heathrow | 26.2
2000-08-26 | 2000 | 8 | Heathrow | 21.8
2000-08-27 | 2000 | 8 | Heathrow | 20.1
2000-08-28 | 2000 | 8 | Heathrow | 21.8
2000-08-29 | 2000 | 8 | Heathrow | 22.2
2000-08-30 | 2000 | 8 | Heathrow | 22.6
2000-08-31 | 2000 | 8 | Heathrow | 18.9
2000-09-01 | 2000 | 9 | Heathrow | 19.9
2000-09-02 | 2000 | 9 | Heathrow | 18.6
2000-09-03 | 2000 | 9 | Heathrow | 20.5
2000-09-04 | 2000 | 9 | Heathrow | 20.4
2000-09-05 | 2000 | 9 | Heathrow | 20.7
2000-09-06 | 2000 | 9 | Heathrow | 20.3
2000-09-07 | 2000 | 9 | Heathrow | 20.2
2000-09-08 | 2000 | 9 | Heathrow | 22.3
2000-09-09 | 2000 | 9 | Heathrow | 25.6
2000-09-10 | 2000 | 9 | Heathrow | 27.5
2000-09-11 | 2000 | 9 | Heathrow | 24
2000-09-12 | 2000 | 9 | Heathrow | 21
2000-09-13 | 2000 | 9 | Heathrow | 21.6
2000-09-14 | 2000 | 9 | Heathrow | 18.5
2000-09-15 | 2000 | 9 | Heathrow | 18.2
2000-09-16 | 2000 | 9 | Heathrow | 20.6
2000-09-17 | 2000 | 9 | Heathrow | 16.8
2000-09-18 | 2000 | 9 | Heathrow | 15.6
2000-09-19 | 2000 | 9 | Heathrow | 16.9
2000-09-20 | 2000 | 9 | Heathrow | 18.6
2000-09-21 | 2000 | 9 | Heathrow | 21.5
2000-09-22 | 2000 | 9 | Heathrow | 24.8
2000-09-23 | 2000 | 9 | Heathrow | 24.9
2000-09-24 | 2000 | 9 | Heathrow | 18.5
2000-09-25 | 2000 | 9 | Heathrow | 20.7
2000-09-26 | 2000 | 9 | Heathrow | 18.2
2000-09-27 | 2000 | 9 | Heathrow | 18.4
2000-09-28 | 2000 | 9 | Heathrow | 18.9
2000-09-29 | 2000 | 9 | Heathrow | 17.9
2000-09-30 | 2000 | 9 | Heathrow | 18.6
2001-05-01 | 2001 | 5 | Heathrow | 15
2001-05-02 | 2001 | 5 | Heathrow | 17.2
2001-05-03 | 2001 | 5 | Heathrow | 13.4
2001-05-04 | 2001 | 5 | Heathrow | 13.4
2001-05-05 | 2001 | 5 | Heathrow | 12.8
2001-05-06 | 2001 | 5 | Heathrow | 15.4
2001-05-07 | 2001 | 5 | Heathrow | 17.3
2001-05-08 | 2001 | 5 | Heathrow | 17.6
2001-05-09 | 2001 | 5 | Heathrow | 23
2001-05-10 | 2001 | 5 | Heathrow | 26.1
2001-05-11 | 2001 | 5 | Heathrow | 24.9
2001-05-12 | 2001 | 5 | Heathrow | 24.9
2001-05-13 | 2001 | 5 | Heathrow | 25
2001-05-14 | 2001 | 5 | Heathrow | 19
2001-05-15 | 2001 | 5 | Heathrow | 15.7
2001-05-16 | 2001 | 5 | Heathrow | 15.7
2001-05-17 | 2001 | 5 | Heathrow | 16.5
2001-05-18 | 2001 | 5 | Heathrow | 16.1
2001-05-19 | 2001 | 5 | Heathrow | 18.2
2001-05-20 | 2001 | 5 | Heathrow | 18.1
2001-05-21 | 2001 | 5 | Heathrow | 19.3
2001-05-22 | 2001 | 5 | Heathrow | 22.6
2001-05-23 | 2001 | 5 | Heathrow | 23.3
2001-05-24 | 2001 | 5 | Heathrow | 20.7
2001-05-25 | 2001 | 5 | Heathrow | 23.2
2001-05-26 | 2001 | 5 | Heathrow | 21.2
2001-05-27 | 2001 | 5 | Heathrow | 24.6
2001-05-28 | 2001 | 5 | Heathrow | 22.5
2001-05-29 | 2001 | 5 | Heathrow | 23.2
2001-05-30 | 2001 | 5 | Heathrow | 19.1
2001-05-31 | 2001 | 5 | Heathrow | 19.1
2001-06-01 | 2001 | 6 | Heathrow | 16.6
2001-06-02 | 2001 | 6 | Heathrow | 16.8
2001-06-03 | 2001 | 6 | Heathrow | 20.3
2001-06-04 | 2001 | 6 | Heathrow | 20.6
2001-06-05 | 2001 | 6 | Heathrow | 19.4
2001-06-06 | 2001 | 6 | Heathrow | 18
2001-06-07 | 2001 | 6 | Heathrow | 16.8
2001-06-08 | 2001 | 6 | Heathrow | 17.7
2001-06-09 | 2001 | 6 | Heathrow | 15.1
2001-06-10 | 2001 | 6 | Heathrow | 18
2001-06-11 | 2001 | 6 | Heathrow | 18.5
2001-06-12 | 2001 | 6 | Heathrow | 21.6
2001-06-13 | 2001 | 6 | Heathrow | 21.5
2001-06-14 | 2001 | 6 | Heathrow | 20.5
2001-06-15 | 2001 | 6 | Heathrow | 20.6
2001-06-16 | 2001 | 6 | Heathrow | 15.6
2001-06-17 | 2001 | 6 | Heathrow | 17.9
2001-06-18 | 2001 | 6 | Heathrow | 21.8
2001-06-19 | 2001 | 6 | Heathrow | 24.6
2001-06-20 | 2001 | 6 | Heathrow | 21.5
2001-06-21 | 2001 | 6 | Heathrow | 22.4
2001-06-22 | 2001 | 6 | Heathrow | 23.7
2001-06-23 | 2001 | 6 | Heathrow | 27.4
2001-06-24 | 2001 | 6 | Heathrow | 29.1
2001-06-25 | 2001 | 6 | Heathrow | 31.9
2001-06-26 | 2001 | 6 | Heathrow | 25.1
2001-06-27 | 2001 | 6 | Heathrow | 22.7
2001-06-28 | 2001 | 6 | Heathrow | 21.3
2001-06-29 | 2001 | 6 | Heathrow | 23.3
2001-06-30 | 2001 | 6 | Heathrow | 26.2
2001-07-01 | 2001 | 7 | Heathrow | 27.1
2001-07-02 | 2001 | 7 | Heathrow | 29.5
2001-07-03 | 2001 | 7 | Heathrow | 29.2
2001-07-04 | 2001 | 7 | Heathrow | 30.5
2001-07-05 | 2001 | 7 | Heathrow | 26.2
2001-07-06 | 2001 | 7 | Heathrow | 26.2
2001-07-07 | 2001 | 7 | Heathrow | 20.8
2001-07-08 | 2001 | 7 | Heathrow | 21
2001-07-09 | 2001 | 7 | Heathrow | 20.2
2001-07-10 | 2001 | 7 | Heathrow | 21.4
2001-07-11 | 2001 | 7 | Heathrow | 21
2001-07-12 | 2001 | 7 | Heathrow | 22.2
2001-07-13 | 2001 | 7 | Heathrow | 19.2
2001-07-14 | 2001 | 7 | Heathrow | 19.8
2001-07-15 | 2001 | 7 | Heathrow | 22.3
2001-07-16 | 2001 | 7 | Heathrow | 21.8
2001-07-17 | 2001 | 7 | Heathrow | 20.8
2001-07-18 | 2001 | 7 | Heathrow | 17.5
2001-07-19 | 2001 | 7 | Heathrow | 21.6
2001-07-20 | 2001 | 7 | Heathrow | 22.4
2001-07-21 | 2001 | 7 | Heathrow | 20.5
2001-07-22 | 2001 | 7 | Heathrow | 25.3
2001-07-23 | 2001 | 7 | Heathrow | 23.2
2001-07-24 | 2001 | 7 | Heathrow | 26.3
2001-07-25 | 2001 | 7 | Heathrow | 28.7
2001-07-26 | 2001 | 7 | Heathrow | 29.3
2001-07-27 | 2001 | 7 | Heathrow | 31.6
2001-07-28 | 2001 | 7 | Heathrow | 31.9
2001-07-29 | 2001 | 7 | Heathrow | 28.9
2001-07-30 | 2001 | 7 | Heathrow | 26.6
2001-07-31 | 2001 | 7 | Heathrow | 26.7
2001-08-01 | 2001 | 8 | Heathrow | 26.7
2001-08-02 | 2001 | 8 | Heathrow | 23.9
2001-08-03 | 2001 | 8 | Heathrow | 22.8
2001-08-04 | 2001 | 8 | Heathrow | 23.2
2001-08-05 | 2001 | 8 | Heathrow | 24.7
2001-08-06 | 2001 | 8 | Heathrow | 20.6
2001-08-07 | 2001 | 8 | Heathrow | 21.5
2001-08-08 | 2001 | 8 | Heathrow | 21.6
2001-08-09 | 2001 | 8 | Heathrow | 20.5
2001-08-10 | 2001 | 8 | Heathrow | 21.9
2001-08-11 | 2001 | 8 | Heathrow | 20.1
2001-08-12 | 2001 | 8 | Heathrow | 26.3
2001-08-13 | 2001 | 8 | Heathrow | 27.4
2001-08-14 | 2001 | 8 | Heathrow | 30.1
2001-08-15 | 2001 | 8 | Heathrow | 30.1
2001-08-16 | 2001 | 8 | Heathrow | 23.4
2001-08-17 | 2001 | 8 | Heathrow | 25.4
2001-08-18 | 2001 | 8 | Heathrow | 22.7
2001-08-19 | 2001 | 8 | Heathrow | 22.7
2001-08-20 | 2001 | 8 | Heathrow | 24.2
2001-08-21 | 2001 | 8 | Heathrow | 25.8
2001-08-22 | 2001 | 8 | Heathrow | 24.1
2001-08-23 | 2001 | 8 | Heathrow | 28.4
2001-08-24 | 2001 | 8 | Heathrow | 31.5
2001-08-25 | 2001 | 8 | Heathrow | 31.6
2001-08-26 | 2001 | 8 | Heathrow | 22
2001-08-27 | 2001 | 8 | Heathrow | 22.1
2001-08-28 | 2001 | 8 | Heathrow | 23.4
2001-08-29 | 2001 | 8 | Heathrow | 20
2001-08-30 | 2001 | 8 | Heathrow | 19
2001-08-31 | 2001 | 8 | Heathrow | 20.8
2001-09-01 | 2001 | 9 | Heathrow | 22.2
2001-09-02 | 2001 | 9 | Heathrow | 19.9
2001-09-03 | 2001 | 9 | Heathrow | 17.8
2001-09-04 | 2001 | 9 | Heathrow | 20.2
2001-09-05 | 2001 | 9 | Heathrow | 19.4
2001-09-06 | 2001 | 9 | Heathrow | 20.9
2001-09-07 | 2001 | 9 | Heathrow | 18.3
2001-09-08 | 2001 | 9 | Heathrow | 18.4
2001-09-09 | 2001 | 9 | Heathrow | 17.1
2001-09-10 | 2001 | 9 | Heathrow | 17.9
2001-09-11 | 2001 | 9 | Heathrow | 18.9
2001-09-12 | 2001 | 9 | Heathrow | 16.9
2001-09-13 | 2001 | 9 | Heathrow | 19
2001-09-14 | 2001 | 9 | Heathrow | 18.7
2001-09-15 | 2001 | 9 | Heathrow | 17.4
2001-09-16 | 2001 | 9 | Heathrow | 13.6
2001-09-17 | 2001 | 9 | Heathrow | 14.7
2001-09-18 | 2001 | 9 | Heathrow | 14.2
2001-09-19 | 2001 | 9 | Heathrow | 17.9
2001-09-20 | 2001 | 9 | Heathrow | 16.3
2001-09-21 | 2001 | 9 | Heathrow | 18
2001-09-22 | 2001 | 9 | Heathrow | 15.7
2001-09-23 | 2001 | 9 | Heathrow | 17.7
2001-09-24 | 2001 | 9 | Heathrow | 17.3
2001-09-25 | 2001 | 9 | Heathrow | 17.4
2001-09-26 | 2001 | 9 | Heathrow | 20.2
2001-09-27 | 2001 | 9 | Heathrow | 23.6
2001-09-28 | 2001 | 9 | Heathrow | 19.2
2001-09-29 | 2001 | 9 | Heathrow | 17.3
2001-09-30 | 2001 | 9 | Heathrow | 19.1
2002-05-01 | 2002 | 5 | Heathrow | 15.5
2002-05-02 | 2002 | 5 | Heathrow | 16.9
2002-05-03 | 2002 | 5 | Heathrow | 13.8
2002-05-04 | 2002 | 5 | Heathrow | 12.2
2002-05-05 | 2002 | 5 | Heathrow | 16.1
2002-05-06 | 2002 | 5 | Heathrow | 16.6
2002-05-07 | 2002 | 5 | Heathrow | 16.7
2002-05-08 | 2002 | 5 | Heathrow | 13.3
2002-05-09 | 2002 | 5 | Heathrow | 16.7
2002-05-10 | 2002 | 5 | Heathrow | 17.5
2002-05-11 | 2002 | 5 | Heathrow | 16.9
2002-05-12 | 2002 | 5 | Heathrow | 14.7
2002-05-13 | 2002 | 5 | Heathrow | 16.8
2002-05-14 | 2002 | 5 | Heathrow | 19.7
2002-05-15 | 2002 | 5 | Heathrow | 25.1
2002-05-16 | 2002 | 5 | Heathrow | 23.5
2002-05-17 | 2002 | 5 | Heathrow | 18.9
2002-05-18 | 2002 | 5 | Heathrow | 19.8
2002-05-19 | 2002 | 5 | Heathrow | 19
2002-05-20 | 2002 | 5 | Heathrow | 18.3
2002-05-21 | 2002 | 5 | Heathrow | 18.6
2002-05-22 | 2002 | 5 | Heathrow | 18.3
2002-05-23 | 2002 | 5 | Heathrow | 17.9
2002-05-24 | 2002 | 5 | Heathrow | 16.8
2002-05-25 | 2002 | 5 | Heathrow | 13.5
2002-05-26 | 2002 | 5 | Heathrow | 18
2002-05-27 | 2002 | 5 | Heathrow | 16.2
2002-05-28 | 2002 | 5 | Heathrow | 17.6
2002-05-29 | 2002 | 5 | Heathrow | 17.3
2002-05-30 | 2002 | 5 | Heathrow | 19.8
2002-05-31 | 2002 | 5 | Heathrow | 22.8
2002-06-01 | 2002 | 6 | Heathrow | 26.8
2002-06-02 | 2002 | 6 | Heathrow | 26.9
2002-06-03 | 2002 | 6 | Heathrow | 16.6
2002-06-04 | 2002 | 6 | Heathrow | 15.4
2002-06-05 | 2002 | 6 | Heathrow | 17.4
2002-06-06 | 2002 | 6 | Heathrow | 15.5
2002-06-07 | 2002 | 6 | Heathrow | 17.8
2002-06-08 | 2002 | 6 | Heathrow | 15.3
2002-06-09 | 2002 | 6 | Heathrow | 17.2
2002-06-10 | 2002 | 6 | Heathrow | 18.2
2002-06-11 | 2002 | 6 | Heathrow | 17.6
2002-06-12 | 2002 | 6 | Heathrow | 20.7
2002-06-13 | 2002 | 6 | Heathrow | 21.6
2002-06-14 | 2002 | 6 | Heathrow | 21.1
2002-06-15 | 2002 | 6 | Heathrow | 22.1
2002-06-16 | 2002 | 6 | Heathrow | 26.6
2002-06-17 | 2002 | 6 | Heathrow | 22.6
2002-06-18 | 2002 | 6 | Heathrow | 21.5
2002-06-19 | 2002 | 6 | Heathrow | 22.3
2002-06-20 | 2002 | 6 | Heathrow | 21.9
2002-06-21 | 2002 | 6 | Heathrow | 19.5
2002-06-22 | 2002 | 6 | Heathrow | 20.4
2002-06-23 | 2002 | 6 | Heathrow | 22.2
2002-06-24 | 2002 | 6 | Heathrow | 20
2002-06-25 | 2002 | 6 | Heathrow | 24
2002-06-26 | 2002 | 6 | Heathrow | 18.8
2002-06-27 | 2002 | 6 | Heathrow | 18.5
2002-06-28 | 2002 | 6 | Heathrow | 19.5
2002-06-29 | 2002 | 6 | Heathrow | 20.3
2002-06-30 | 2002 | 6 | Heathrow | 18.4
2002-07-01 | 2002 | 7 | Heathrow | 19
2002-07-02 | 2002 | 7 | Heathrow | 17.9
2002-07-03 | 2002 | 7 | Heathrow | 19.9
2002-07-04 | 2002 | 7 | Heathrow | 19.8
2002-07-05 | 2002 | 7 | Heathrow | 20.9
2002-07-06 | 2002 | 7 | Heathrow | 20.8
2002-07-07 | 2002 | 7 | Heathrow | 19
2002-07-08 | 2002 | 7 | Heathrow | 21.4
2002-07-09 | 2002 | 7 | Heathrow | 19.1
2002-07-10 | 2002 | 7 | Heathrow | 20.1
2002-07-11 | 2002 | 7 | Heathrow | 17.3
2002-07-12 | 2002 | 7 | Heathrow | 22.7
2002-07-13 | 2002 | 7 | Heathrow | 25
2002-07-14 | 2002 | 7 | Heathrow | 25.9
2002-07-15 | 2002 | 7 | Heathrow | 25.6
2002-07-16 | 2002 | 7 | Heathrow | 21.9
2002-07-17 | 2002 | 7 | Heathrow | 23.4
2002-07-18 | 2002 | 7 | Heathrow | 24.2
2002-07-19 | 2002 | 7 | Heathrow | 23.2
2002-07-20 | 2002 | 7 | Heathrow | 19.8
2002-07-21 | 2002 | 7 | Heathrow | 22.3
2002-07-22 | 2002 | 7 | Heathrow | 20.4
2002-07-23 | 2002 | 7 | Heathrow | 20.3
2002-07-24 | 2002 | 7 | Heathrow | 21.7
2002-07-25 | 2002 | 7 | Heathrow | 27.6
2002-07-26 | 2002 | 7 | Heathrow | 24.9
2002-07-27 | 2002 | 7 | Heathrow | 29.7
2002-07-28 | 2002 | 7 | Heathrow | 32.5
2002-07-29 | 2002 | 7 | Heathrow | 25.4
2002-07-30 | 2002 | 7 | Heathrow | 25.5
2002-07-31 | 2002 | 7 | Heathrow | 21.1
2002-08-01 | 2002 | 8 | Heathrow | 23.6
2002-08-02 | 2002 | 8 | Heathrow | 19.3
2002-08-03 | 2002 | 8 | Heathrow | 21.8
2002-08-04 | 2002 | 8 | Heathrow | 21.3
2002-08-05 | 2002 | 8 | Heathrow | 24
2002-08-06 | 2002 | 8 | Heathrow | 26.7
2002-08-07 | 2002 | 8 | Heathrow | 26.7
2002-08-08 | 2002 | 8 | Heathrow | 19.7
2002-08-09 | 2002 | 8 | Heathrow | 22.1
2002-08-10 | 2002 | 8 | Heathrow | 21.9
2002-08-11 | 2002 | 8 | Heathrow | 22.6
2002-08-12 | 2002 | 8 | Heathrow | 25.6
2002-08-13 | 2002 | 8 | Heathrow | 25.4
2002-08-14 | 2002 | 8 | Heathrow | 28.4
2002-08-15 | 2002 | 8 | Heathrow | 27.1
2002-08-16 | 2002 | 8 | Heathrow | 30
2002-08-17 | 2002 | 8 | Heathrow | 25.8
2002-08-18 | 2002 | 8 | Heathrow | 25.5
2002-08-19 | 2002 | 8 | Heathrow | 23.2
2002-08-20 | 2002 | 8 | Heathrow | 23.2
2002-08-21 | 2002 | 8 | Heathrow | 23.5
2002-08-22 | 2002 | 8 | Heathrow | 23.5
2002-08-23 | 2002 | 8 | Heathrow | 23.6
2002-08-24 | 2002 | 8 | Heathrow | 21.7
2002-08-25 | 2002 | 8 | Heathrow | 21.7
2002-08-26 | 2002 | 8 | Heathrow | 22.1
2002-08-27 | 2002 | 8 | Heathrow | 24
2002-08-28 | 2002 | 8 | Heathrow | 24.5
2002-08-29 | 2002 | 8 | Heathrow | 22.6
2002-08-30 | 2002 | 8 | Heathrow | 20.9
2002-08-31 | 2002 | 8 | Heathrow | 21.1
2002-09-01 | 2002 | 9 | Heathrow | 22.9
2002-09-02 | 2002 | 9 | Heathrow | 24
2002-09-03 | 2002 | 9 | Heathrow | 23.4
2002-09-04 | 2002 | 9 | Heathrow | 23.4
2002-09-05 | 2002 | 9 | Heathrow | 22.7
2002-09-06 | 2002 | 9 | Heathrow | 21
2002-09-07 | 2002 | 9 | Heathrow | 20.6
2002-09-08 | 2002 | 9 | Heathrow | 15.6
2002-09-09 | 2002 | 9 | Heathrow | 21.1
2002-09-10 | 2002 | 9 | Heathrow | 22.4
2002-09-11 | 2002 | 9 | Heathrow | 23.5
2002-09-12 | 2002 | 9 | Heathrow | 24.6
2002-09-13 | 2002 | 9 | Heathrow | 19.3
2002-09-14 | 2002 | 9 | Heathrow | 18.3
2002-09-15 | 2002 | 9 | Heathrow | 19.5
2002-09-16 | 2002 | 9 | Heathrow | 19.2
2002-09-17 | 2002 | 9 | Heathrow | 18.7
2002-09-18 | 2002 | 9 | Heathrow | 19.7
2002-09-19 | 2002 | 9 | Heathrow | 18.9
2002-09-20 | 2002 | 9 | Heathrow | 19.1
2002-09-21 | 2002 | 9 | Heathrow | 17.9
2002-09-22 | 2002 | 9 | Heathrow | 19.2
2002-09-23 | 2002 | 9 | Heathrow | 18.1
2002-09-24 | 2002 | 9 | Heathrow | 19
2002-09-25 | 2002 | 9 | Heathrow | 18.2
2002-09-26 | 2002 | 9 | Heathrow | 17.2
2002-09-27 | 2002 | 9 | Heathrow | 19.2
2002-09-28 | 2002 | 9 | Heathrow | 20.7
2002-09-29 | 2002 | 9 | Heathrow | 21.4
2002-09-30 | 2002 | 9 | Heathrow | 21.8
2003-05-01 | 2003 | 5 | Heathrow | 14.6
2003-05-02 | 2003 | 5 | Heathrow | 16.9
2003-05-03 | 2003 | 5 | Heathrow | 22
2003-05-04 | 2003 | 5 | Heathrow | 17.3
2003-05-05 | 2003 | 5 | Heathrow | 17.6
2003-05-06 | 2003 | 5 | Heathrow | 19.7
2003-05-07 | 2003 | 5 | Heathrow | 15.9
2003-05-08 | 2003 | 5 | Heathrow | 18.1
2003-05-09 | 2003 | 5 | Heathrow | 15.3
2003-05-10 | 2003 | 5 | Heathrow | 17.2
2003-05-11 | 2003 | 5 | Heathrow | 14.6
2003-05-12 | 2003 | 5 | Heathrow | 13
2003-05-13 | 2003 | 5 | Heathrow | 15.9
2003-05-14 | 2003 | 5 | Heathrow | 16.8
2003-05-15 | 2003 | 5 | Heathrow | 12.9
2003-05-16 | 2003 | 5 | Heathrow | 16
2003-05-17 | 2003 | 5 | Heathrow | 16.7
2003-05-18 | 2003 | 5 | Heathrow | 16.5
2003-05-19 | 2003 | 5 | Heathrow | 15
2003-05-20 | 2003 | 5 | Heathrow | 16.6
2003-05-21 | 2003 | 5 | Heathrow | 19
2003-05-22 | 2003 | 5 | Heathrow | 18
2003-05-23 | 2003 | 5 | Heathrow | 17.8
2003-05-24 | 2003 | 5 | Heathrow | 18.3
2003-05-25 | 2003 | 5 | Heathrow | 19.9
2003-05-26 | 2003 | 5 | Heathrow | 19.3
2003-05-27 | 2003 | 5 | Heathrow | 23.7
2003-05-28 | 2003 | 5 | Heathrow | 25.8
2003-05-29 | 2003 | 5 | Heathrow | 27.2
2003-05-30 | 2003 | 5 | Heathrow | 28.9
2003-05-31 | 2003 | 5 | Heathrow | 24
2003-06-01 | 2003 | 6 | Heathrow | 22.7
2003-06-02 | 2003 | 6 | Heathrow | 22.5
2003-06-03 | 2003 | 6 | Heathrow | 21.5
2003-06-04 | 2003 | 6 | Heathrow | 21.8
2003-06-05 | 2003 | 6 | Heathrow | 19.1
2003-06-06 | 2003 | 6 | Heathrow | 23.2
2003-06-07 | 2003 | 6 | Heathrow | 21.9
2003-06-08 | 2003 | 6 | Heathrow | 21
2003-06-09 | 2003 | 6 | Heathrow | 22.7
2003-06-10 | 2003 | 6 | Heathrow | 21.6
2003-06-11 | 2003 | 6 | Heathrow | 23.5
2003-06-12 | 2003 | 6 | Heathrow | 23.6
2003-06-13 | 2003 | 6 | Heathrow | 24.8
2003-06-14 | 2003 | 6 | Heathrow | 26.5
2003-06-15 | 2003 | 6 | Heathrow | 27.5
2003-06-16 | 2003 | 6 | Heathrow | 26.1
2003-06-17 | 2003 | 6 | Heathrow | 21.1
2003-06-18 | 2003 | 6 | Heathrow | 24.7
2003-06-19 | 2003 | 6 | Heathrow | 22.4
2003-06-20 | 2003 | 6 | Heathrow | 25.3
2003-06-21 | 2003 | 6 | Heathrow | 25.7
2003-06-22 | 2003 | 6 | Heathrow | 23.4
2003-06-23 | 2003 | 6 | Heathrow | 23.6
2003-06-24 | 2003 | 6 | Heathrow | 22.8
2003-06-25 | 2003 | 6 | Heathrow | 24.4
2003-06-26 | 2003 | 6 | Heathrow | 22.3
2003-06-27 | 2003 | 6 | Heathrow | 22.5
2003-06-28 | 2003 | 6 | Heathrow | 26.3
2003-06-29 | 2003 | 6 | Heathrow | 21.2
2003-06-30 | 2003 | 6 | Heathrow | 20.3
2003-07-01 | 2003 | 7 | Heathrow | 20.4
2003-07-02 | 2003 | 7 | Heathrow | 19.8
2003-07-03 | 2003 | 7 | Heathrow | 22.1
2003-07-04 | 2003 | 7 | Heathrow | 19.4
2003-07-05 | 2003 | 7 | Heathrow | 23.2
2003-07-06 | 2003 | 7 | Heathrow | 22
2003-07-07 | 2003 | 7 | Heathrow | 25
2003-07-08 | 2003 | 7 | Heathrow | 28.3
2003-07-09 | 2003 | 7 | Heathrow | 29.3
2003-07-10 | 2003 | 7 | Heathrow | 23.9
2003-07-11 | 2003 | 7 | Heathrow | 26.7
2003-07-12 | 2003 | 7 | Heathrow | 28.5
2003-07-13 | 2003 | 7 | Heathrow | 29.6
2003-07-14 | 2003 | 7 | Heathrow | 32.8
2003-07-15 | 2003 | 7 | Heathrow | 32.9
2003-07-16 | 2003 | 7 | Heathrow | 24.5
2003-07-17 | 2003 | 7 | Heathrow | 25.1
2003-07-18 | 2003 | 7 | Heathrow | 28.5
2003-07-19 | 2003 | 7 | Heathrow | 24.4
2003-07-20 | 2003 | 7 | Heathrow | 25.1
2003-07-21 | 2003 | 7 | Heathrow | 24.2
2003-07-22 | 2003 | 7 | Heathrow | 24.6
2003-07-23 | 2003 | 7 | Heathrow | 24.2
2003-07-24 | 2003 | 7 | Heathrow | 21.4
2003-07-25 | 2003 | 7 | Heathrow | 20.7
2003-07-26 | 2003 | 7 | Heathrow | 23.5
2003-07-27 | 2003 | 7 | Heathrow | 23.1
2003-07-28 | 2003 | 7 | Heathrow | 21.4
2003-07-29 | 2003 | 7 | Heathrow | 24.8
2003-07-30 | 2003 | 7 | Heathrow | 23.1
2003-07-31 | 2003 | 7 | Heathrow | 19.5
2003-08-01 | 2003 | 8 | Heathrow | 25.1
2003-08-02 | 2003 | 8 | Heathrow | 29.5
2003-08-03 | 2003 | 8 | Heathrow | 31.8
2003-08-04 | 2003 | 8 | Heathrow | 32.2
2003-08-05 | 2003 | 8 | Heathrow | 35.2
2003-08-06 | 2003 | 8 | Heathrow | 29.7
2003-08-07 | 2003 | 8 | Heathrow | 30.7
2003-08-08 | 2003 | 8 | Heathrow | 35
2003-08-09 | 2003 | 8 | Heathrow | 37.9
2003-08-10 | 2003 | 8 | Heathrow | 33.7
2003-08-11 | 2003 | 8 | Heathrow | 30.1
2003-08-12 | 2003 | 8 | Heathrow | 28.5
2003-08-13 | 2003 | 8 | Heathrow | 25.1
2003-08-14 | 2003 | 8 | Heathrow | 24.5
2003-08-15 | 2003 | 8 | Heathrow | 24
2003-08-16 | 2003 | 8 | Heathrow | 27
2003-08-17 | 2003 | 8 | Heathrow | 25.3
2003-08-18 | 2003 | 8 | Heathrow | 23.2
2003-08-19 | 2003 | 8 | Heathrow | 23.4
2003-08-20 | 2003 | 8 | Heathrow | 23.7
2003-08-21 | 2003 | 8 | Heathrow | 26.3
2003-08-22 | 2003 | 8 | Heathrow | 27.1
2003-08-23 | 2003 | 8 | Heathrow | 25.4
2003-08-24 | 2003 | 8 | Heathrow | 25.5
2003-08-25 | 2003 | 8 | Heathrow | 23.1
2003-08-26 | 2003 | 8 | Heathrow | 23.2
2003-08-27 | 2003 | 8 | Heathrow | 23.2
2003-08-28 | 2003 | 8 | Heathrow | 19.2
2003-08-29 | 2003 | 8 | Heathrow | 19.5
2003-08-30 | 2003 | 8 | Heathrow | 20.5
2003-08-31 | 2003 | 8 | Heathrow | 19.4
2003-09-01 | 2003 | 9 | Heathrow | 21
2003-09-02 | 2003 | 9 | Heathrow | 22.4
2003-09-03 | 2003 | 9 | Heathrow | 24.5
2003-09-04 | 2003 | 9 | Heathrow | 26.9
2003-09-05 | 2003 | 9 | Heathrow | 21.8
2003-09-06 | 2003 | 9 | Heathrow | 19.3
2003-09-07 | 2003 | 9 | Heathrow | 22.1
2003-09-08 | 2003 | 9 | Heathrow | 20.8
2003-09-09 | 2003 | 9 | Heathrow | 21.9
2003-09-10 | 2003 | 9 | Heathrow | 18.5
2003-09-11 | 2003 | 9 | Heathrow | 20.9
2003-09-12 | 2003 | 9 | Heathrow | 23.9
2003-09-13 | 2003 | 9 | Heathrow | 26
2003-09-14 | 2003 | 9 | Heathrow | 26.1
2003-09-15 | 2003 | 9 | Heathrow | 27
2003-09-16 | 2003 | 9 | Heathrow | 27.9
2003-09-17 | 2003 | 9 | Heathrow | 21.7
2003-09-18 | 2003 | 9 | Heathrow | 23.5
2003-09-19 | 2003 | 9 | Heathrow | 27
2003-09-20 | 2003 | 9 | Heathrow | 26.8
2003-09-21 | 2003 | 9 | Heathrow | 21.9
2003-09-22 | 2003 | 9 | Heathrow | 22
2003-09-23 | 2003 | 9 | Heathrow | 17.3
2003-09-24 | 2003 | 9 | Heathrow | 19.7
2003-09-25 | 2003 | 9 | Heathrow | 20.4
2003-09-26 | 2003 | 9 | Heathrow | 17.6
2003-09-27 | 2003 | 9 | Heathrow | 16.1
2003-09-28 | 2003 | 9 | Heathrow | 18.8
2003-09-29 | 2003 | 9 | Heathrow | 20.8
2003-09-30 | 2003 | 9 | Heathrow | 18.6
2004-05-01 | 2004 | 5 | Heathrow | 19
2004-05-02 | 2004 | 5 | Heathrow | 13.5
2004-05-03 | 2004 | 5 | Heathrow | 11.6
2004-05-04 | 2004 | 5 | Heathrow | 13.5
2004-05-05 | 2004 | 5 | Heathrow | 14.8
2004-05-06 | 2004 | 5 | Heathrow | 16.9
2004-05-07 | 2004 | 5 | Heathrow | 12.7
2004-05-08 | 2004 | 5 | Heathrow | 15.6
2004-05-09 | 2004 | 5 | Heathrow | 19.5
2004-05-10 | 2004 | 5 | Heathrow | 19.6
2004-05-11 | 2004 | 5 | Heathrow | 13.6
2004-05-12 | 2004 | 5 | Heathrow | 18
2004-05-13 | 2004 | 5 | Heathrow | 20.3
2004-05-14 | 2004 | 5 | Heathrow | 21.9
2004-05-15 | 2004 | 5 | Heathrow | 22.6
2004-05-16 | 2004 | 5 | Heathrow | 24.5
2004-05-17 | 2004 | 5 | Heathrow | 23.3
2004-05-18 | 2004 | 5 | Heathrow | 23.9
2004-05-19 | 2004 | 5 | Heathrow | 21.7
2004-05-20 | 2004 | 5 | Heathrow | 21.7
2004-05-21 | 2004 | 5 | Heathrow | 15.8
2004-05-22 | 2004 | 5 | Heathrow | 18.9
2004-05-23 | 2004 | 5 | Heathrow | 20.4
2004-05-24 | 2004 | 5 | Heathrow | 19.6
2004-05-25 | 2004 | 5 | Heathrow | 18.4
2004-05-26 | 2004 | 5 | Heathrow | 17.7
2004-05-27 | 2004 | 5 | Heathrow | 20.1
2004-05-28 | 2004 | 5 | Heathrow | 20.5
2004-05-29 | 2004 | 5 | Heathrow | 18.7
2004-05-30 | 2004 | 5 | Heathrow | 21.6
2004-05-31 | 2004 | 5 | Heathrow | 17
2004-06-01 | 2004 | 6 | Heathrow | 20.5
2004-06-02 | 2004 | 6 | Heathrow | 20.6
2004-06-03 | 2004 | 6 | Heathrow | 23.3
2004-06-04 | 2004 | 6 | Heathrow | 20.3
2004-06-05 | 2004 | 6 | Heathrow | 24.4
2004-06-06 | 2004 | 6 | Heathrow | 27.7
2004-06-07 | 2004 | 6 | Heathrow | 30.5
2004-06-08 | 2004 | 6 | Heathrow | 24
2004-06-09 | 2004 | 6 | Heathrow | 24.6
2004-06-10 | 2004 | 6 | Heathrow | 22.1
2004-06-11 | 2004 | 6 | Heathrow | 21.7
2004-06-12 | 2004 | 6 | Heathrow | 25.3
2004-06-13 | 2004 | 6 | Heathrow | 29
2004-06-14 | 2004 | 6 | Heathrow | 27
2004-06-15 | 2004 | 6 | Heathrow | 26.8
2004-06-16 | 2004 | 6 | Heathrow | 26.9
2004-06-17 | 2004 | 6 | Heathrow | 18.4
2004-06-18 | 2004 | 6 | Heathrow | 19.3
2004-06-19 | 2004 | 6 | Heathrow | 16.9
2004-06-20 | 2004 | 6 | Heathrow | 19.4
2004-06-21 | 2004 | 6 | Heathrow | 20.3
2004-06-22 | 2004 | 6 | Heathrow | 16.6
2004-06-23 | 2004 | 6 | Heathrow | 19.7
2004-06-24 | 2004 | 6 | Heathrow | 21.5
2004-06-25 | 2004 | 6 | Heathrow | 19.5
2004-06-26 | 2004 | 6 | Heathrow | 23.6
2004-06-27 | 2004 | 6 | Heathrow | 20.6
2004-06-28 | 2004 | 6 | Heathrow | 22.8
2004-06-29 | 2004 | 6 | Heathrow | 21.2
2004-06-30 | 2004 | 6 | Heathrow | 20.1
2004-07-01 | 2004 | 7 | Heathrow | 19.2
2004-07-02 | 2004 | 7 | Heathrow | 20
2004-07-03 | 2004 | 7 | Heathrow | 18.1
2004-07-04 | 2004 | 7 | Heathrow | 21.3
2004-07-05 | 2004 | 7 | Heathrow | 23.7
2004-07-06 | 2004 | 7 | Heathrow | 22.1
2004-07-07 | 2004 | 7 | Heathrow | 18.9
2004-07-08 | 2004 | 7 | Heathrow | 19.2
2004-07-09 | 2004 | 7 | Heathrow | 18.4
2004-07-10 | 2004 | 7 | Heathrow | 18.4
2004-07-11 | 2004 | 7 | Heathrow | 18.7
2004-07-12 | 2004 | 7 | Heathrow | 21.1
2004-07-13 | 2004 | 7 | Heathrow | 22.1
2004-07-14 | 2004 | 7 | Heathrow | 24
2004-07-15 | 2004 | 7 | Heathrow | 24
2004-07-16 | 2004 | 7 | Heathrow | 24.6
2004-07-17 | 2004 | 7 | Heathrow | 22.6
2004-07-18 | 2004 | 7 | Heathrow | 22.8
2004-07-19 | 2004 | 7 | Heathrow | 24.7
2004-07-20 | 2004 | 7 | Heathrow | 22.7
2004-07-21 | 2004 | 7 | Heathrow | 26.7
2004-07-22 | 2004 | 7 | Heathrow | 25.5
2004-07-23 | 2004 | 7 | Heathrow | 24.5
2004-07-24 | 2004 | 7 | Heathrow | 23.7
2004-07-25 | 2004 | 7 | Heathrow | 22.9
2004-07-26 | 2004 | 7 | Heathrow | 24.3
2004-07-27 | 2004 | 7 | Heathrow | 27.3
2004-07-28 | 2004 | 7 | Heathrow | 29.9
2004-07-29 | 2004 | 7 | Heathrow | 25.5
2004-07-30 | 2004 | 7 | Heathrow | 28
2004-07-31 | 2004 | 7 | Heathrow | 26.7
2004-08-01 | 2004 | 8 | Heathrow | 28.1
2004-08-02 | 2004 | 8 | Heathrow | 27.9
2004-08-03 | 2004 | 8 | Heathrow | 28.1
2004-08-04 | 2004 | 8 | Heathrow | 27.3
2004-08-05 | 2004 | 8 | Heathrow | 27.6
2004-08-06 | 2004 | 8 | Heathrow | 29.2
2004-08-07 | 2004 | 8 | Heathrow | 30.5
2004-08-08 | 2004 | 8 | Heathrow | 30.6
2004-08-09 | 2004 | 8 | Heathrow | 25.4
2004-08-10 | 2004 | 8 | Heathrow | 24.9
2004-08-11 | 2004 | 8 | Heathrow | 24.2
2004-08-12 | 2004 | 8 | Heathrow | 22.9
2004-08-13 | 2004 | 8 | Heathrow | 24.2
2004-08-14 | 2004 | 8 | Heathrow | 24.2
2004-08-15 | 2004 | 8 | Heathrow | 21.7
2004-08-16 | 2004 | 8 | Heathrow | 23.5
2004-08-17 | 2004 | 8 | Heathrow | 23.8
2004-08-18 | 2004 | 8 | Heathrow | 22.6
2004-08-19 | 2004 | 8 | Heathrow | 21.5
2004-08-20 | 2004 | 8 | Heathrow | 20.5
2004-08-21 | 2004 | 8 | Heathrow | 22
2004-08-22 | 2004 | 8 | Heathrow | 21.3
2004-08-23 | 2004 | 8 | Heathrow | 22.6
2004-08-24 | 2004 | 8 | Heathrow | 21.1
2004-08-25 | 2004 | 8 | Heathrow | 21.6
2004-08-26 | 2004 | 8 | Heathrow | 21.1
2004-08-27 | 2004 | 8 | Heathrow | 20
2004-08-28 | 2004 | 8 | Heathrow | 19
2004-08-29 | 2004 | 8 | Heathrow | 20.2
2004-08-30 | 2004 | 8 | Heathrow | 20.3
2004-08-31 | 2004 | 8 | Heathrow | 21.6
2004-09-01 | 2004 | 9 | Heathrow | 24.4
2004-09-02 | 2004 | 9 | Heathrow | 26.1
2004-09-03 | 2004 | 9 | Heathrow | 26.2
2004-09-04 | 2004 | 9 | Heathrow | 27.7
2004-09-05 | 2004 | 9 | Heathrow | 25.7
2004-09-06 | 2004 | 9 | Heathrow | 24.7
2004-09-07 | 2004 | 9 | Heathrow | 23.7
2004-09-08 | 2004 | 9 | Heathrow | 25.1
2004-09-09 | 2004 | 9 | Heathrow | 21.3
2004-09-10 | 2004 | 9 | Heathrow | 22.2
2004-09-11 | 2004 | 9 | Heathrow | 19.4
2004-09-12 | 2004 | 9 | Heathrow | 19.3
2004-09-13 | 2004 | 9 | Heathrow | 19.2
2004-09-14 | 2004 | 9 | Heathrow | 18.5
2004-09-15 | 2004 | 9 | Heathrow | 19.5
2004-09-16 | 2004 | 9 | Heathrow | 20.1
2004-09-17 | 2004 | 9 | Heathrow | 20.8
2004-09-18 | 2004 | 9 | Heathrow | 20.9
2004-09-19 | 2004 | 9 | Heathrow | 19.5
2004-09-20 | 2004 | 9 | Heathrow | 16.7
2004-09-21 | 2004 | 9 | Heathrow | 18.6
2004-09-22 | 2004 | 9 | Heathrow | 20.7
2004-09-23 | 2004 | 9 | Heathrow | 20.7
2004-09-24 | 2004 | 9 | Heathrow | 15.3
2004-09-25 | 2004 | 9 | Heathrow | 20.7
2004-09-26 | 2004 | 9 | Heathrow | 20.7
2004-09-27 | 2004 | 9 | Heathrow | 19.1
2004-09-28 | 2004 | 9 | Heathrow | 19.1
2004-09-29 | 2004 | 9 | Heathrow | 19.5
2004-09-30 | 2004 | 9 | Heathrow | 16.7
2005-05-01 | 2005 | 5 | Heathrow | 23.4
2005-05-02 | 2005 | 5 | Heathrow | 21.3
2005-05-03 | 2005 | 5 | Heathrow | 18.1
2005-05-04 | 2005 | 5 | Heathrow | 11.8
2005-05-05 | 2005 | 5 | Heathrow | 18.5
2005-05-06 | 2005 | 5 | Heathrow | 17.2
2005-05-07 | 2005 | 5 | Heathrow | 14.9
2005-05-08 | 2005 | 5 | Heathrow | 15.2
2005-05-09 | 2005 | 5 | Heathrow | 13.1
2005-05-10 | 2005 | 5 | Heathrow | 12.9
2005-05-11 | 2005 | 5 | Heathrow | 13.1
2005-05-12 | 2005 | 5 | Heathrow | 15.3
2005-05-13 | 2005 | 5 | Heathrow | 16.9
2005-05-14 | 2005 | 5 | Heathrow | 15.2
2005-05-15 | 2005 | 5 | Heathrow | 18.4
2005-05-16 | 2005 | 5 | Heathrow | 16.7
2005-05-17 | 2005 | 5 | Heathrow | 12.9
2005-05-18 | 2005 | 5 | Heathrow | 15.6
2005-05-19 | 2005 | 5 | Heathrow | 14.6
2005-05-20 | 2005 | 5 | Heathrow | 19.1
2005-05-21 | 2005 | 5 | Heathrow | 16.8
2005-05-22 | 2005 | 5 | Heathrow | 16.5
2005-05-23 | 2005 | 5 | Heathrow | 17.8
2005-05-24 | 2005 | 5 | Heathrow | 18.7
2005-05-25 | 2005 | 5 | Heathrow | 22.2
2005-05-26 | 2005 | 5 | Heathrow | 24.4
2005-05-27 | 2005 | 5 | Heathrow | 30.7
2005-05-28 | 2005 | 5 | Heathrow | 20.9
2005-05-29 | 2005 | 5 | Heathrow | 17.2
2005-05-30 | 2005 | 5 | Heathrow | 18.6
2005-05-31 | 2005 | 5 | Heathrow | 20.3
2005-06-01 | 2005 | 6 | Heathrow | 16.7
2005-06-02 | 2005 | 6 | Heathrow | 19.5
2005-06-03 | 2005 | 6 | Heathrow | 22.3
2005-06-04 | 2005 | 6 | Heathrow | 20.1
2005-06-05 | 2005 | 6 | Heathrow | 18.7
2005-06-06 | 2005 | 6 | Heathrow | 16.9
2005-06-07 | 2005 | 6 | Heathrow | 18.2
2005-06-08 | 2005 | 6 | Heathrow | 21.4
2005-06-09 | 2005 | 6 | Heathrow | 22.9
2005-06-10 | 2005 | 6 | Heathrow | 19.7
2005-06-11 | 2005 | 6 | Heathrow | 17.7
2005-06-12 | 2005 | 6 | Heathrow | 19.7
2005-06-13 | 2005 | 6 | Heathrow | 19.9
2005-06-14 | 2005 | 6 | Heathrow | 20.7
2005-06-15 | 2005 | 6 | Heathrow | 21.5
2005-06-16 | 2005 | 6 | Heathrow | 20.5
2005-06-17 | 2005 | 6 | Heathrow | 26.4
2005-06-18 | 2005 | 6 | Heathrow | 29.9
2005-06-19 | 2005 | 6 | Heathrow | 32.6
2005-06-20 | 2005 | 6 | Heathrow | 27.7
2005-06-21 | 2005 | 6 | Heathrow | 26.1
2005-06-22 | 2005 | 6 | Heathrow | 28.7
2005-06-23 | 2005 | 6 | Heathrow | 31.1
2005-06-24 | 2005 | 6 | Heathrow | 25.3
2005-06-25 | 2005 | 6 | Heathrow | 18.8
2005-06-26 | 2005 | 6 | Heathrow | 21.1
2005-06-27 | 2005 | 6 | Heathrow | 26.2
2005-06-28 | 2005 | 6 | Heathrow | 27.3
2005-06-29 | 2005 | 6 | Heathrow | 25.9
2005-06-30 | 2005 | 6 | Heathrow | 19.6
2005-07-01 | 2005 | 7 | Heathrow | 22.3
2005-07-02 | 2005 | 7 | Heathrow | 22.2
2005-07-03 | 2005 | 7 | Heathrow | 20.1
2005-07-04 | 2005 | 7 | Heathrow | 18.3
2005-07-05 | 2005 | 7 | Heathrow | 17.6
2005-07-06 | 2005 | 7 | Heathrow | 19.9
2005-07-07 | 2005 | 7 | Heathrow | 20.2
2005-07-08 | 2005 | 7 | Heathrow | 20.3
2005-07-09 | 2005 | 7 | Heathrow | 22.8
2005-07-10 | 2005 | 7 | Heathrow | 29.3
2005-07-11 | 2005 | 7 | Heathrow | 27.7
2005-07-12 | 2005 | 7 | Heathrow | 27.3
2005-07-13 | 2005 | 7 | Heathrow | 30
2005-07-14 | 2005 | 7 | Heathrow | 30.9
2005-07-15 | 2005 | 7 | Heathrow | 28.2
2005-07-16 | 2005 | 7 | Heathrow | 24.3
2005-07-17 | 2005 | 7 | Heathrow | 29
2005-07-18 | 2005 | 7 | Heathrow | 26.4
2005-07-19 | 2005 | 7 | Heathrow | 23.8
2005-07-20 | 2005 | 7 | Heathrow | 25.1
2005-07-21 | 2005 | 7 | Heathrow | 23.2
2005-07-22 | 2005 | 7 | Heathrow | 22
2005-07-23 | 2005 | 7 | Heathrow | 22.4
2005-07-24 | 2005 | 7 | Heathrow | 21.8
2005-07-25 | 2005 | 7 | Heathrow | 18.1
2005-07-26 | 2005 | 7 | Heathrow | 20.2
2005-07-27 | 2005 | 7 | Heathrow | 17.5
2005-07-28 | 2005 | 7 | Heathrow | 25.3
2005-07-29 | 2005 | 7 | Heathrow | 23.4
2005-07-30 | 2005 | 7 | Heathrow | 21.5
2005-07-31 | 2005 | 7 | Heathrow | 19.6
2005-08-01 | 2005 | 8 | Heathrow | 21.8
2005-08-02 | 2005 | 8 | Heathrow | 24.9
2005-08-03 | 2005 | 8 | Heathrow | 23.8
2005-08-04 | 2005 | 8 | Heathrow | 22.9
2005-08-05 | 2005 | 8 | Heathrow | 22.4
2005-08-06 | 2005 | 8 | Heathrow | 20.6
2005-08-07 | 2005 | 8 | Heathrow | 21.6
2005-08-08 | 2005 | 8 | Heathrow | 23.2
2005-08-09 | 2005 | 8 | Heathrow | 25.7
2005-08-10 | 2005 | 8 | Heathrow | 25.1
2005-08-11 | 2005 | 8 | Heathrow | 26.4
2005-08-12 | 2005 | 8 | Heathrow | 22.5
2005-08-13 | 2005 | 8 | Heathrow | 22.2
2005-08-14 | 2005 | 8 | Heathrow | 20.2
2005-08-15 | 2005 | 8 | Heathrow | 23.8
2005-08-16 | 2005 | 8 | Heathrow | 25.6
2005-08-17 | 2005 | 8 | Heathrow | 26.8
2005-08-18 | 2005 | 8 | Heathrow | 29
2005-08-19 | 2005 | 8 | Heathrow | 18.5
2005-08-20 | 2005 | 8 | Heathrow | 20.5
2005-08-21 | 2005 | 8 | Heathrow | 24.8
2005-08-22 | 2005 | 8 | Heathrow | 19.1
2005-08-23 | 2005 | 8 | Heathrow | 22.2
2005-08-24 | 2005 | 8 | Heathrow | 16.9
2005-08-25 | 2005 | 8 | Heathrow | 19.1
2005-08-26 | 2005 | 8 | Heathrow | 19.6
2005-08-27 | 2005 | 8 | Heathrow | 21.3
2005-08-28 | 2005 | 8 | Heathrow | 24.4
2005-08-29 | 2005 | 8 | Heathrow | 26.1
2005-08-30 | 2005 | 8 | Heathrow | 27.6
2005-08-31 | 2005 | 8 | Heathrow | 31.8
2005-09-01 | 2005 | 9 | Heathrow | 24.5
2005-09-02 | 2005 | 9 | Heathrow | 24
2005-09-03 | 2005 | 9 | Heathrow | 26.3
2005-09-04 | 2005 | 9 | Heathrow | 29.4
2005-09-05 | 2005 | 9 | Heathrow | 22
2005-09-06 | 2005 | 9 | Heathrow | 21.8
2005-09-07 | 2005 | 9 | Heathrow | 26.1
2005-09-08 | 2005 | 9 | Heathrow | 25
2005-09-09 | 2005 | 9 | Heathrow | 26.8
2005-09-10 | 2005 | 9 | Heathrow | 23.4
2005-09-11 | 2005 | 9 | Heathrow | 17.1
2005-09-12 | 2005 | 9 | Heathrow | 22.2
2005-09-13 | 2005 | 9 | Heathrow | 22.9
2005-09-14 | 2005 | 9 | Heathrow | 24.9
2005-09-15 | 2005 | 9 | Heathrow | 22
2005-09-16 | 2005 | 9 | Heathrow | 16.2
2005-09-17 | 2005 | 9 | Heathrow | 16.9
2005-09-18 | 2005 | 9 | Heathrow | 16.5
2005-09-19 | 2005 | 9 | Heathrow | 19.2
2005-09-20 | 2005 | 9 | Heathrow | 21.8
2005-09-21 | 2005 | 9 | Heathrow | 21.1
2005-09-22 | 2005 | 9 | Heathrow | 21.3
2005-09-23 | 2005 | 9 | Heathrow | 19.2
2005-09-24 | 2005 | 9 | Heathrow | 18.1
2005-09-25 | 2005 | 9 | Heathrow | 21.7
2005-09-26 | 2005 | 9 | Heathrow | 18.3
2005-09-27 | 2005 | 9 | Heathrow | 20.4
2005-09-28 | 2005 | 9 | Heathrow | 16.3
2005-09-29 | 2005 | 9 | Heathrow | 16.9
2005-09-30 | 2005 | 9 | Heathrow | 20.1
2006-05-01 | 2006 | 5 | Heathrow | 15.1
2006-05-02 | 2006 | 5 | Heathrow | 16.5
2006-05-03 | 2006 | 5 | Heathrow | 19.3
2006-05-04 | 2006 | 5 | Heathrow | 27.5
2006-05-05 | 2006 | 5 | Heathrow | 21.5
2006-05-06 | 2006 | 5 | Heathrow | 17
2006-05-07 | 2006 | 5 | Heathrow | 18.5
2006-05-08 | 2006 | 5 | Heathrow | 15.2
2006-05-09 | 2006 | 5 | Heathrow | 19.2
2006-05-10 | 2006 | 5 | Heathrow | 22.5
2006-05-11 | 2006 | 5 | Heathrow | 23.8
2006-05-12 | 2006 | 5 | Heathrow | 24.2
2006-05-13 | 2006 | 5 | Heathrow | 18.2
2006-05-14 | 2006 | 5 | Heathrow | 16.3
2006-05-15 | 2006 | 5 | Heathrow | 18.2
2006-05-16 | 2006 | 5 | Heathrow | 17.3
2006-05-17 | 2006 | 5 | Heathrow | 17.2
2006-05-18 | 2006 | 5 | Heathrow | 18.4
2006-05-19 | 2006 | 5 | Heathrow | 17.6
2006-05-20 | 2006 | 5 | Heathrow | 15.8
2006-05-21 | 2006 | 5 | Heathrow | 14.9
2006-05-22 | 2006 | 5 | Heathrow | 15.4
2006-05-23 | 2006 | 5 | Heathrow | 14.8
2006-05-24 | 2006 | 5 | Heathrow | 14.8
2006-05-25 | 2006 | 5 | Heathrow | 18.3
2006-05-26 | 2006 | 5 | Heathrow | 19.7
2006-05-27 | 2006 | 5 | Heathrow | 16.4
2006-05-28 | 2006 | 5 | Heathrow | 17.6
2006-05-29 | 2006 | 5 | Heathrow | 15.3
2006-05-30 | 2006 | 5 | Heathrow | 14.3
2006-05-31 | 2006 | 5 | Heathrow | 16
2006-06-01 | 2006 | 6 | Heathrow | 16.2
2006-06-02 | 2006 | 6 | Heathrow | 20.6
2006-06-03 | 2006 | 6 | Heathrow | 24.2
2006-06-04 | 2006 | 6 | Heathrow | 23.6
2006-06-05 | 2006 | 6 | Heathrow | 20.1
2006-06-06 | 2006 | 6 | Heathrow | 21.6
2006-06-07 | 2006 | 6 | Heathrow | 25.8
2006-06-08 | 2006 | 6 | Heathrow | 26.3
2006-06-09 | 2006 | 6 | Heathrow | 26.8
2006-06-10 | 2006 | 6 | Heathrow | 29.4
2006-06-11 | 2006 | 6 | Heathrow | 28.3
2006-06-12 | 2006 | 6 | Heathrow | 31.4
2006-06-13 | 2006 | 6 | Heathrow | 25.2
2006-06-14 | 2006 | 6 | Heathrow | 19
2006-06-15 | 2006 | 6 | Heathrow | 21.2
2006-06-16 | 2006 | 6 | Heathrow | 24.5
2006-06-17 | 2006 | 6 | Heathrow | 28
2006-06-18 | 2006 | 6 | Heathrow | 26.1
2006-06-19 | 2006 | 6 | Heathrow | 21.6
2006-06-20 | 2006 | 6 | Heathrow | 23.5
2006-06-21 | 2006 | 6 | Heathrow | 20.7
2006-06-22 | 2006 | 6 | Heathrow | 21
2006-06-23 | 2006 | 6 | Heathrow | 22.2
2006-06-24 | 2006 | 6 | Heathrow | 25.1
2006-06-25 | 2006 | 6 | Heathrow | 24.5
2006-06-26 | 2006 | 6 | Heathrow | 15.7
2006-06-27 | 2006 | 6 | Heathrow | 19.4
2006-06-28 | 2006 | 6 | Heathrow | 23.4
2006-06-29 | 2006 | 6 | Heathrow | 26.6
2006-06-30 | 2006 | 6 | Heathrow | 29.1
2006-07-01 | 2006 | 7 | Heathrow | 29.7
2006-07-02 | 2006 | 7 | Heathrow | 32.3
2006-07-03 | 2006 | 7 | Heathrow | 31.4
2006-07-04 | 2006 | 7 | Heathrow | 31.3
2006-07-05 | 2006 | 7 | Heathrow | 21.9
2006-07-06 | 2006 | 7 | Heathrow | 25.4
2006-07-07 | 2006 | 7 | Heathrow | 22.8
2006-07-08 | 2006 | 7 | Heathrow | 23.5
2006-07-09 | 2006 | 7 | Heathrow | 23.9
2006-07-10 | 2006 | 7 | Heathrow | 23.4
2006-07-11 | 2006 | 7 | Heathrow | 25.2
2006-07-12 | 2006 | 7 | Heathrow | 27.6
2006-07-13 | 2006 | 7 | Heathrow | 23.6
2006-07-14 | 2006 | 7 | Heathrow | 24
2006-07-15 | 2006 | 7 | Heathrow | 26.3
2006-07-16 | 2006 | 7 | Heathrow | 30.5
2006-07-17 | 2006 | 7 | Heathrow | 32.7
2006-07-18 | 2006 | 7 | Heathrow | 33.2
2006-07-19 | 2006 | 7 | Heathrow | 35.5
2006-07-20 | 2006 | 7 | Heathrow | 31.7
2006-07-21 | 2006 | 7 | Heathrow | 31.7
2006-07-22 | 2006 | 7 | Heathrow | 29.5
2006-07-23 | 2006 | 7 | Heathrow | 26.5
2006-07-24 | 2006 | 7 | Heathrow | 30
2006-07-25 | 2006 | 7 | Heathrow | 33
2006-07-26 | 2006 | 7 | Heathrow | 32.7
2006-07-27 | 2006 | 7 | Heathrow | 30.3
2006-07-28 | 2006 | 7 | Heathrow | 29.1
2006-07-29 | 2006 | 7 | Heathrow | 26.7
2006-07-30 | 2006 | 7 | Heathrow | 25.8
2006-07-31 | 2006 | 7 | Heathrow | 24.2
2006-08-01 | 2006 | 8 | Heathrow | 22.9
2006-08-02 | 2006 | 8 | Heathrow | 23.2
2006-08-03 | 2006 | 8 | Heathrow | 21.1
2006-08-04 | 2006 | 8 | Heathrow | 23
2006-08-05 | 2006 | 8 | Heathrow | 27.1
2006-08-06 | 2006 | 8 | Heathrow | 28.2
2006-08-07 | 2006 | 8 | Heathrow | 23.5
2006-08-08 | 2006 | 8 | Heathrow | 26.1
2006-08-09 | 2006 | 8 | Heathrow | 23.4
2006-08-10 | 2006 | 8 | Heathrow | 21
2006-08-11 | 2006 | 8 | Heathrow | 21.7
2006-08-12 | 2006 | 8 | Heathrow | 19
2006-08-13 | 2006 | 8 | Heathrow | 18.7
2006-08-14 | 2006 | 8 | Heathrow | 19.3
2006-08-15 | 2006 | 8 | Heathrow | 21.9
2006-08-16 | 2006 | 8 | Heathrow | 22.5
2006-08-17 | 2006 | 8 | Heathrow | 24.2
2006-08-18 | 2006 | 8 | Heathrow | 20.9
2006-08-19 | 2006 | 8 | Heathrow | 22.3
2006-08-20 | 2006 | 8 | Heathrow | 20.5
2006-08-21 | 2006 | 8 | Heathrow | 22.6
2006-08-22 | 2006 | 8 | Heathrow | 22.4
2006-08-23 | 2006 | 8 | Heathrow | 20.9
2006-08-24 | 2006 | 8 | Heathrow | 21.4
2006-08-25 | 2006 | 8 | Heathrow | 22.7
2006-08-26 | 2006 | 8 | Heathrow | 21.2
2006-08-27 | 2006 | 8 | Heathrow | 21.6
2006-08-28 | 2006 | 8 | Heathrow | 20
2006-08-29 | 2006 | 8 | Heathrow | 19.4
2006-08-30 | 2006 | 8 | Heathrow | 21
2006-08-31 | 2006 | 8 | Heathrow | 23.6
2006-09-01 | 2006 | 9 | Heathrow | 23.3
2006-09-02 | 2006 | 9 | Heathrow | 20.7
2006-09-03 | 2006 | 9 | Heathrow | 26.6
2006-09-04 | 2006 | 9 | Heathrow | 24.7
2006-09-05 | 2006 | 9 | Heathrow | 25.7
2006-09-06 | 2006 | 9 | Heathrow | 26.5
2006-09-07 | 2006 | 9 | Heathrow | 21.3
2006-09-08 | 2006 | 9 | Heathrow | 21.2
2006-09-09 | 2006 | 9 | Heathrow | 22.7
2006-09-10 | 2006 | 9 | Heathrow | 27.1
2006-09-11 | 2006 | 9 | Heathrow | 30.2
2006-09-12 | 2006 | 9 | Heathrow | 20.9
2006-09-13 | 2006 | 9 | Heathrow | 24
2006-09-14 | 2006 | 9 | Heathrow | 20.6
2006-09-15 | 2006 | 9 | Heathrow | 22.4
2006-09-16 | 2006 | 9 | Heathrow | 21.3
2006-09-17 | 2006 | 9 | Heathrow | 24.1
2006-09-18 | 2006 | 9 | Heathrow | 21.2
2006-09-19 | 2006 | 9 | Heathrow | 20.3
2006-09-20 | 2006 | 9 | Heathrow | 22.9
2006-09-21 | 2006 | 9 | Heathrow | 27.8
2006-09-22 | 2006 | 9 | Heathrow | 18.5
2006-09-23 | 2006 | 9 | Heathrow | 23.5
2006-09-24 | 2006 | 9 | Heathrow | 22.6
2006-09-25 | 2006 | 9 | Heathrow | 19.7
2006-09-26 | 2006 | 9 | Heathrow | 21.3
2006-09-27 | 2006 | 9 | Heathrow | 19.9
2006-09-28 | 2006 | 9 | Heathrow | 20.1
2006-09-29 | 2006 | 9 | Heathrow | 19.9
2006-09-30 | 2006 | 9 | Heathrow | 19.4
2007-05-01 | 2007 | 5 | Heathrow | 21.5
2007-05-02 | 2007 | 5 | Heathrow | 22.1
2007-05-03 | 2007 | 5 | Heathrow | 15.4
2007-05-04 | 2007 | 5 | Heathrow | 17.5
2007-05-05 | 2007 | 5 | Heathrow | 14.9
2007-05-06 | 2007 | 5 | Heathrow | 20.4
2007-05-07 | 2007 | 5 | Heathrow | 19.2
2007-05-08 | 2007 | 5 | Heathrow | 20
2007-05-09 | 2007 | 5 | Heathrow | 15
2007-05-10 | 2007 | 5 | Heathrow | 16.8
2007-05-11 | 2007 | 5 | Heathrow | 16.7
2007-05-12 | 2007 | 5 | Heathrow | 17.3
2007-05-13 | 2007 | 5 | Heathrow | 15.3
2007-05-14 | 2007 | 5 | Heathrow | 11.9
2007-05-15 | 2007 | 5 | Heathrow | 16.9
2007-05-16 | 2007 | 5 | Heathrow | 16.2
2007-05-17 | 2007 | 5 | Heathrow | 19.2
2007-05-18 | 2007 | 5 | Heathrow | 21.4
2007-05-19 | 2007 | 5 | Heathrow | 18
2007-05-20 | 2007 | 5 | Heathrow | 19.7
2007-05-21 | 2007 | 5 | Heathrow | 16.5
2007-05-22 | 2007 | 5 | Heathrow | 22.1
2007-05-23 | 2007 | 5 | Heathrow | 24.5
2007-05-24 | 2007 | 5 | Heathrow | 25.7
2007-05-25 | 2007 | 5 | Heathrow | 23.3
2007-05-26 | 2007 | 5 | Heathrow | 13.4
2007-05-27 | 2007 | 5 | Heathrow | 12.5
2007-05-28 | 2007 | 5 | Heathrow | 10.1
2007-05-29 | 2007 | 5 | Heathrow | 15.6
2007-05-30 | 2007 | 5 | Heathrow | 17.1
2007-05-31 | 2007 | 5 | Heathrow | 19.6
2007-06-01 | 2007 | 6 | Heathrow | 22.1
2007-06-02 | 2007 | 6 | Heathrow | 24.7
2007-06-03 | 2007 | 6 | Heathrow | 25
2007-06-04 | 2007 | 6 | Heathrow | 20
2007-06-05 | 2007 | 6 | Heathrow | 21.8
2007-06-06 | 2007 | 6 | Heathrow | 17.8
2007-06-07 | 2007 | 6 | Heathrow | 18.3
2007-06-08 | 2007 | 6 | Heathrow | 21.4
2007-06-09 | 2007 | 6 | Heathrow | 24.9
2007-06-10 | 2007 | 6 | Heathrow | 24.9
2007-06-11 | 2007 | 6 | Heathrow | 21.6
2007-06-12 | 2007 | 6 | Heathrow | 23.7
2007-06-13 | 2007 | 6 | Heathrow | 24.3
2007-06-14 | 2007 | 6 | Heathrow | 22.6
2007-06-15 | 2007 | 6 | Heathrow | 20.9
2007-06-16 | 2007 | 6 | Heathrow | 19.5
2007-06-17 | 2007 | 6 | Heathrow | 21.3
2007-06-18 | 2007 | 6 | Heathrow | 20.6
2007-06-19 | 2007 | 6 | Heathrow | 25.4
2007-06-20 | 2007 | 6 | Heathrow | 22.2
2007-06-21 | 2007 | 6 | Heathrow | 21.1
2007-06-22 | 2007 | 6 | Heathrow | 20
2007-06-23 | 2007 | 6 | Heathrow | 20.4
2007-06-24 | 2007 | 6 | Heathrow | 16.6
2007-06-25 | 2007 | 6 | Heathrow | 16.2
2007-06-26 | 2007 | 6 | Heathrow | 17
2007-06-27 | 2007 | 6 | Heathrow | 19.6
2007-06-28 | 2007 | 6 | Heathrow | 20.1
2007-06-29 | 2007 | 6 | Heathrow | 22.2
2007-06-30 | 2007 | 6 | Heathrow | 18.3
2007-07-01 | 2007 | 7 | Heathrow | 20.7
2007-07-02 | 2007 | 7 | Heathrow | 20.6
2007-07-03 | 2007 | 7 | Heathrow | 20
2007-07-04 | 2007 | 7 | Heathrow | 19.3
2007-07-05 | 2007 | 7 | Heathrow | 19.8
2007-07-06 | 2007 | 7 | Heathrow | 20.8
2007-07-07 | 2007 | 7 | Heathrow | 22.4
2007-07-08 | 2007 | 7 | Heathrow | 22.1
2007-07-09 | 2007 | 7 | Heathrow | 21.2
2007-07-10 | 2007 | 7 | Heathrow | 19.7
2007-07-11 | 2007 | 7 | Heathrow | 21.2
2007-07-12 | 2007 | 7 | Heathrow | 24
2007-07-13 | 2007 | 7 | Heathrow | 23.5
2007-07-14 | 2007 | 7 | Heathrow | 23.1
2007-07-15 | 2007 | 7 | Heathrow | 23.8
2007-07-16 | 2007 | 7 | Heathrow | 22.5
2007-07-17 | 2007 | 7 | Heathrow | 21.7
2007-07-18 | 2007 | 7 | Heathrow | 23.9
2007-07-19 | 2007 | 7 | Heathrow | 23.7
2007-07-20 | 2007 | 7 | Heathrow | 20.1
2007-07-21 | 2007 | 7 | Heathrow | 20.1
2007-07-22 | 2007 | 7 | Heathrow | 20.6
2007-07-23 | 2007 | 7 | Heathrow | 19.4
2007-07-24 | 2007 | 7 | Heathrow | 22.4
2007-07-25 | 2007 | 7 | Heathrow | 19.9
2007-07-26 | 2007 | 7 | Heathrow | 18.6
2007-07-27 | 2007 | 7 | Heathrow | 22.2
2007-07-28 | 2007 | 7 | Heathrow | 22.7
2007-07-29 | 2007 | 7 | Heathrow | 20.4
2007-07-30 | 2007 | 7 | Heathrow | 20.6
2007-07-31 | 2007 | 7 | Heathrow | 21.8
2007-08-01 | 2007 | 8 | Heathrow | 24.2
2007-08-02 | 2007 | 8 | Heathrow | 19.9
2007-08-03 | 2007 | 8 | Heathrow | 24.9
2007-08-04 | 2007 | 8 | Heathrow | 26.2
2007-08-05 | 2007 | 8 | Heathrow | 29
2007-08-06 | 2007 | 8 | Heathrow | 23.6
2007-08-07 | 2007 | 8 | Heathrow | 22.7
2007-08-08 | 2007 | 8 | Heathrow | 21.7
2007-08-09 | 2007 | 8 | Heathrow | 21.7
2007-08-10 | 2007 | 8 | Heathrow | 24.4
2007-08-11 | 2007 | 8 | Heathrow | 25.8
2007-08-12 | 2007 | 8 | Heathrow | 22.7
2007-08-13 | 2007 | 8 | Heathrow | 22.1
2007-08-14 | 2007 | 8 | Heathrow | 19.5
2007-08-15 | 2007 | 8 | Heathrow | 22.1
2007-08-16 | 2007 | 8 | Heathrow | 19.6
2007-08-17 | 2007 | 8 | Heathrow | 20.1
2007-08-18 | 2007 | 8 | Heathrow | 19.3
2007-08-19 | 2007 | 8 | Heathrow | 17.8
2007-08-20 | 2007 | 8 | Heathrow | 16.4
2007-08-21 | 2007 | 8 | Heathrow | 17
2007-08-22 | 2007 | 8 | Heathrow | 17.1
2007-08-23 | 2007 | 8 | Heathrow | 18.3
2007-08-24 | 2007 | 8 | Heathrow | 19.4
2007-08-25 | 2007 | 8 | Heathrow | 26.5
2007-08-26 | 2007 | 8 | Heathrow | 23.3
2007-08-27 | 2007 | 8 | Heathrow | 20.3
2007-08-28 | 2007 | 8 | Heathrow | 20.8
2007-08-29 | 2007 | 8 | Heathrow | 21.3
2007-08-30 | 2007 | 8 | Heathrow | 19.5
2007-08-31 | 2007 | 8 | Heathrow | 20.3
2007-09-01 | 2007 | 9 | Heathrow | 20.9
2007-09-02 | 2007 | 9 | Heathrow | 21.6
2007-09-03 | 2007 | 9 | Heathrow | 19.5
2007-09-04 | 2007 | 9 | Heathrow | 19.3
2007-09-05 | 2007 | 9 | Heathrow | 23.7
2007-09-06 | 2007 | 9 | Heathrow | 24.7
2007-09-07 | 2007 | 9 | Heathrow | 24
2007-09-08 | 2007 | 9 | Heathrow | 19.8
2007-09-09 | 2007 | 9 | Heathrow | 21.3
2007-09-10 | 2007 | 9 | Heathrow | 21.3
2007-09-11 | 2007 | 9 | Heathrow | 20.4
2007-09-12 | 2007 | 9 | Heathrow | 22
2007-09-13 | 2007 | 9 | Heathrow | 22.8
2007-09-14 | 2007 | 9 | Heathrow | 22.9
2007-09-15 | 2007 | 9 | Heathrow | 21
2007-09-16 | 2007 | 9 | Heathrow | 21.6
2007-09-17 | 2007 | 9 | Heathrow | 16.6
2007-09-18 | 2007 | 9 | Heathrow | 15.7
2007-09-19 | 2007 | 9 | Heathrow | 19.1
2007-09-20 | 2007 | 9 | Heathrow | 20.7
2007-09-21 | 2007 | 9 | Heathrow | 20.2
2007-09-22 | 2007 | 9 | Heathrow | 21.8
2007-09-23 | 2007 | 9 | Heathrow | 21.3
2007-09-24 | 2007 | 9 | Heathrow | 18.1
2007-09-25 | 2007 | 9 | Heathrow | 18.3
2007-09-26 | 2007 | 9 | Heathrow | 13
2007-09-27 | 2007 | 9 | Heathrow | 14.2
2007-09-28 | 2007 | 9 | Heathrow | 14.6
2007-09-29 | 2007 | 9 | Heathrow | 18
2007-09-30 | 2007 | 9 | Heathrow | 18.3
2008-05-01 | 2008 | 5 | Heathrow | 15.2
2008-05-02 | 2008 | 5 | Heathrow | 15.8
2008-05-03 | 2008 | 5 | Heathrow | 20.3
2008-05-04 | 2008 | 5 | Heathrow | 22
2008-05-05 | 2008 | 5 | Heathrow | 21.8
2008-05-06 | 2008 | 5 | Heathrow | 22.2
2008-05-07 | 2008 | 5 | Heathrow | 24.7
2008-05-08 | 2008 | 5 | Heathrow | 25
2008-05-09 | 2008 | 5 | Heathrow | 25.1
2008-05-10 | 2008 | 5 | Heathrow | 26.2
2008-05-11 | 2008 | 5 | Heathrow | 26.7
2008-05-12 | 2008 | 5 | Heathrow | 25.2
2008-05-13 | 2008 | 5 | Heathrow | 21.9
2008-05-14 | 2008 | 5 | Heathrow | 20.1
2008-05-15 | 2008 | 5 | Heathrow | 14.7
2008-05-16 | 2008 | 5 | Heathrow | 13
2008-05-17 | 2008 | 5 | Heathrow | 13.1
2008-05-18 | 2008 | 5 | Heathrow | 15.8
2008-05-19 | 2008 | 5 | Heathrow | 14.3
2008-05-20 | 2008 | 5 | Heathrow | 16.5
2008-05-21 | 2008 | 5 | Heathrow | 18.7
2008-05-22 | 2008 | 5 | Heathrow | 22.1
2008-05-23 | 2008 | 5 | Heathrow | 19.8
2008-05-24 | 2008 | 5 | Heathrow | 21.5
2008-05-25 | 2008 | 5 | Heathrow | 18.9
2008-05-26 | 2008 | 5 | Heathrow | 13
2008-05-27 | 2008 | 5 | Heathrow | 18.9
2008-05-28 | 2008 | 5 | Heathrow | 17.1
2008-05-29 | 2008 | 5 | Heathrow | 22
2008-05-30 | 2008 | 5 | Heathrow | 18.8
2008-05-31 | 2008 | 5 | Heathrow | 21.9
2008-06-01 | 2008 | 6 | Heathrow | 18.4
2008-06-02 | 2008 | 6 | Heathrow | 19.2
2008-06-03 | 2008 | 6 | Heathrow | 16.2
2008-06-04 | 2008 | 6 | Heathrow | 20.5
2008-06-05 | 2008 | 6 | Heathrow | 20.8
2008-06-06 | 2008 | 6 | Heathrow | 19.6
2008-06-07 | 2008 | 6 | Heathrow | 19.9
2008-06-08 | 2008 | 6 | Heathrow | 25.5
2008-06-09 | 2008 | 6 | Heathrow | 26.4
2008-06-10 | 2008 | 6 | Heathrow | 23.3
2008-06-11 | 2008 | 6 | Heathrow | 20.6
2008-06-12 | 2008 | 6 | Heathrow | 15.5
2008-06-13 | 2008 | 6 | Heathrow | 17.8
2008-06-14 | 2008 | 6 | Heathrow | 19.7
2008-06-15 | 2008 | 6 | Heathrow | 18.1
2008-06-16 | 2008 | 6 | Heathrow | 20.1
2008-06-17 | 2008 | 6 | Heathrow | 20.8
2008-06-18 | 2008 | 6 | Heathrow | 18.8
2008-06-19 | 2008 | 6 | Heathrow | 21.6
2008-06-20 | 2008 | 6 | Heathrow | 19.4
2008-06-21 | 2008 | 6 | Heathrow | 19.3
2008-06-22 | 2008 | 6 | Heathrow | 21.8
2008-06-23 | 2008 | 6 | Heathrow | 21.5
2008-06-24 | 2008 | 6 | Heathrow | 23
2008-06-25 | 2008 | 6 | Heathrow | 22.9
2008-06-26 | 2008 | 6 | Heathrow | 22.1
2008-06-27 | 2008 | 6 | Heathrow | 21.2
2008-06-28 | 2008 | 6 | Heathrow | 23.2
2008-06-29 | 2008 | 6 | Heathrow | 22.3
2008-06-30 | 2008 | 6 | Heathrow | 23
2008-07-01 | 2008 | 7 | Heathrow | 27.3
2008-07-02 | 2008 | 7 | Heathrow | 19.5
2008-07-03 | 2008 | 7 | Heathrow | 21.3
2008-07-04 | 2008 | 7 | Heathrow | 22.4
2008-07-05 | 2008 | 7 | Heathrow | 22.4
2008-07-06 | 2008 | 7 | Heathrow | 19.7
2008-07-07 | 2008 | 7 | Heathrow | 20.7
2008-07-08 | 2008 | 7 | Heathrow | 19.9
2008-07-09 | 2008 | 7 | Heathrow | 18
2008-07-10 | 2008 | 7 | Heathrow | 20.5
2008-07-11 | 2008 | 7 | Heathrow | 21.2
2008-07-12 | 2008 | 7 | Heathrow | 18.2
2008-07-13 | 2008 | 7 | Heathrow | 20.9
2008-07-14 | 2008 | 7 | Heathrow | 23.3
2008-07-15 | 2008 | 7 | Heathrow | 25.9
2008-07-16 | 2008 | 7 | Heathrow | 20.5
2008-07-17 | 2008 | 7 | Heathrow | 19
2008-07-18 | 2008 | 7 | Heathrow | 19.8
2008-07-19 | 2008 | 7 | Heathrow | 21.4
2008-07-20 | 2008 | 7 | Heathrow | 18.6
2008-07-21 | 2008 | 7 | Heathrow | 21.3
2008-07-22 | 2008 | 7 | Heathrow | 23.3
2008-07-23 | 2008 | 7 | Heathrow | 26.4
2008-07-24 | 2008 | 7 | Heathrow | 28.2
2008-07-25 | 2008 | 7 | Heathrow | 25.5
2008-07-26 | 2008 | 7 | Heathrow | 26.9
2008-07-27 | 2008 | 7 | Heathrow | 29.2
2008-07-28 | 2008 | 7 | Heathrow | 29.5
2008-07-29 | 2008 | 7 | Heathrow | 23.1
2008-07-30 | 2008 | 7 | Heathrow | 26.2
2008-07-31 | 2008 | 7 | Heathrow | 25.4
2008-08-01 | 2008 | 8 | Heathrow | 22.9
2008-08-02 | 2008 | 8 | Heathrow | 23.5
2008-08-03 | 2008 | 8 | Heathrow | 21.4
2008-08-04 | 2008 | 8 | Heathrow | 21.6
2008-08-05 | 2008 | 8 | Heathrow | 19.9
2008-08-06 | 2008 | 8 | Heathrow | 25.3
2008-08-07 | 2008 | 8 | Heathrow | 24.1
2008-08-08 | 2008 | 8 | Heathrow | 18.4
2008-08-09 | 2008 | 8 | Heathrow | 18.5
2008-08-10 | 2008 | 8 | Heathrow | 22.1
2008-08-11 | 2008 | 8 | Heathrow | 19.9
2008-08-12 | 2008 | 8 | Heathrow | 20.7
2008-08-13 | 2008 | 8 | Heathrow | 18.2
2008-08-14 | 2008 | 8 | Heathrow | 20.5
2008-08-15 | 2008 | 8 | Heathrow | 21.5
2008-08-16 | 2008 | 8 | Heathrow | 22.3
2008-08-17 | 2008 | 8 | Heathrow | 21.7
2008-08-18 | 2008 | 8 | Heathrow | 20.7
2008-08-19 | 2008 | 8 | Heathrow | 21.7
2008-08-20 | 2008 | 8 | Heathrow | 22.1
2008-08-21 | 2008 | 8 | Heathrow | 22.3
2008-08-22 | 2008 | 8 | Heathrow | 20.7
2008-08-23 | 2008 | 8 | Heathrow | 21.3
2008-08-24 | 2008 | 8 | Heathrow | 22
2008-08-25 | 2008 | 8 | Heathrow | 20.6
2008-08-26 | 2008 | 8 | Heathrow | 19.7
2008-08-27 | 2008 | 8 | Heathrow | 19.8
2008-08-28 | 2008 | 8 | Heathrow | 20.9
2008-08-29 | 2008 | 8 | Heathrow | 22.6
2008-08-30 | 2008 | 8 | Heathrow | 26.7
2008-08-31 | 2008 | 8 | Heathrow | 22.4
2008-09-01 | 2008 | 9 | Heathrow | 20.6
2008-09-02 | 2008 | 9 | Heathrow | 18.7
2008-09-03 | 2008 | 9 | Heathrow | 20
2008-09-04 | 2008 | 9 | Heathrow | 18.4
2008-09-05 | 2008 | 9 | Heathrow | 17.9
2008-09-06 | 2008 | 9 | Heathrow | 17.3
2008-09-07 | 2008 | 9 | Heathrow | 16.6
2008-09-08 | 2008 | 9 | Heathrow | 17.7
2008-09-09 | 2008 | 9 | Heathrow | 18.8
2008-09-10 | 2008 | 9 | Heathrow | 20.2
2008-09-11 | 2008 | 9 | Heathrow | 19.5
2008-09-12 | 2008 | 9 | Heathrow | 18.7
2008-09-13 | 2008 | 9 | Heathrow | 19.3
2008-09-14 | 2008 | 9 | Heathrow | 19.4
2008-09-15 | 2008 | 9 | Heathrow | 18.5
2008-09-16 | 2008 | 9 | Heathrow | 16.3
2008-09-17 | 2008 | 9 | Heathrow | 16.9
2008-09-18 | 2008 | 9 | Heathrow | 18.5
2008-09-19 | 2008 | 9 | Heathrow | 20.5
2008-09-20 | 2008 | 9 | Heathrow | 20.2
2008-09-21 | 2008 | 9 | Heathrow | 19.5
2008-09-22 | 2008 | 9 | Heathrow | 19.6
2008-09-23 | 2008 | 9 | Heathrow | 17.1
2008-09-24 | 2008 | 9 | Heathrow | 16.2
2008-09-25 | 2008 | 9 | Heathrow | 18.3
2008-09-26 | 2008 | 9 | Heathrow | 19.3
2008-09-27 | 2008 | 9 | Heathrow | 19.9
2008-09-28 | 2008 | 9 | Heathrow | 19.2
2008-09-29 | 2008 | 9 | Heathrow | 17
2008-09-30 | 2008 | 9 | Heathrow | 15.3
2009-05-01 | 2009 | 5 | Heathrow | 20.3
2009-05-02 | 2009 | 5 | Heathrow | 18.6
2009-05-03 | 2009 | 5 | Heathrow | 15.8
2009-05-04 | 2009 | 5 | Heathrow | 14.6
2009-05-05 | 2009 | 5 | Heathrow | 20.2
2009-05-06 | 2009 | 5 | Heathrow | 21.2
2009-05-07 | 2009 | 5 | Heathrow | 16
2009-05-08 | 2009 | 5 | Heathrow | 16.4
2009-05-09 | 2009 | 5 | Heathrow | 17.2
2009-05-10 | 2009 | 5 | Heathrow | 19.7
2009-05-11 | 2009 | 5 | Heathrow | 17.1
2009-05-12 | 2009 | 5 | Heathrow | 17.5
2009-05-13 | 2009 | 5 | Heathrow | 16.1
2009-05-14 | 2009 | 5 | Heathrow | 18.4
2009-05-15 | 2009 | 5 | Heathrow | 16
2009-05-16 | 2009 | 5 | Heathrow | 17.1
2009-05-17 | 2009 | 5 | Heathrow | 14.5
2009-05-18 | 2009 | 5 | Heathrow | 17
2009-05-19 | 2009 | 5 | Heathrow | 17.6
2009-05-20 | 2009 | 5 | Heathrow | 19
2009-05-21 | 2009 | 5 | Heathrow | 19.8
2009-05-22 | 2009 | 5 | Heathrow | 20
2009-05-23 | 2009 | 5 | Heathrow | 20.8
2009-05-24 | 2009 | 5 | Heathrow | 25.2
2009-05-25 | 2009 | 5 | Heathrow | 23.7
2009-05-26 | 2009 | 5 | Heathrow | 17.8
2009-05-27 | 2009 | 5 | Heathrow | 18.3
2009-05-28 | 2009 | 5 | Heathrow | 22.5
2009-05-29 | 2009 | 5 | Heathrow | 24.9
2009-05-30 | 2009 | 5 | Heathrow | 23.4
2009-05-31 | 2009 | 5 | Heathrow | 25.6
2009-06-01 | 2009 | 6 | Heathrow | 25.7
2009-06-02 | 2009 | 6 | Heathrow | 25.5
2009-06-03 | 2009 | 6 | Heathrow | 20.1
2009-06-04 | 2009 | 6 | Heathrow | 18.9
2009-06-05 | 2009 | 6 | Heathrow | 14.3
2009-06-06 | 2009 | 6 | Heathrow | 14.5
2009-06-07 | 2009 | 6 | Heathrow | 18
2009-06-08 | 2009 | 6 | Heathrow | 18.7
2009-06-09 | 2009 | 6 | Heathrow | 16
2009-06-10 | 2009 | 6 | Heathrow | 16.9
2009-06-11 | 2009 | 6 | Heathrow | 21.2
2009-06-12 | 2009 | 6 | Heathrow | 20.2
2009-06-13 | 2009 | 6 | Heathrow | 24.7
2009-06-14 | 2009 | 6 | Heathrow | 24
2009-06-15 | 2009 | 6 | Heathrow | 24.6
2009-06-16 | 2009 | 6 | Heathrow | 23.8
2009-06-17 | 2009 | 6 | Heathrow | 23.7
2009-06-18 | 2009 | 6 | Heathrow | 19.8
2009-06-19 | 2009 | 6 | Heathrow | 19.8
2009-06-20 | 2009 | 6 | Heathrow | 19.7
2009-06-21 | 2009 | 6 | Heathrow | 21.2
2009-06-22 | 2009 | 6 | Heathrow | 22.7
2009-06-23 | 2009 | 6 | Heathrow | 24.7
2009-06-24 | 2009 | 6 | Heathrow | 25.2
2009-06-25 | 2009 | 6 | Heathrow | 28
2009-06-26 | 2009 | 6 | Heathrow | 24
2009-06-27 | 2009 | 6 | Heathrow | 27.3
2009-06-28 | 2009 | 6 | Heathrow | 27.6
2009-06-29 | 2009 | 6 | Heathrow | 30.8
2009-06-30 | 2009 | 6 | Heathrow | 30.9
2009-07-01 | 2009 | 7 | Heathrow | 30.6
2009-07-02 | 2009 | 7 | Heathrow | 26
2009-07-03 | 2009 | 7 | Heathrow | 26
2009-07-04 | 2009 | 7 | Heathrow | 25.3
2009-07-05 | 2009 | 7 | Heathrow | 22.8
2009-07-06 | 2009 | 7 | Heathrow | 20.5
2009-07-07 | 2009 | 7 | Heathrow | 19.9
2009-07-08 | 2009 | 7 | Heathrow | 19.6
2009-07-09 | 2009 | 7 | Heathrow | 21.8
2009-07-10 | 2009 | 7 | Heathrow | 21.6
2009-07-11 | 2009 | 7 | Heathrow | 24.6
2009-07-12 | 2009 | 7 | Heathrow | 22.6
2009-07-13 | 2009 | 7 | Heathrow | 24
2009-07-14 | 2009 | 7 | Heathrow | 24
2009-07-15 | 2009 | 7 | Heathrow | 24.8
2009-07-16 | 2009 | 7 | Heathrow | 24.9
2009-07-17 | 2009 | 7 | Heathrow | 21.8
2009-07-18 | 2009 | 7 | Heathrow | 21.3
2009-07-19 | 2009 | 7 | Heathrow | 22.4
2009-07-20 | 2009 | 7 | Heathrow | 22.5
2009-07-21 | 2009 | 7 | Heathrow | 23.2
2009-07-22 | 2009 | 7 | Heathrow | 22.8
2009-07-23 | 2009 | 7 | Heathrow | 20.4
2009-07-24 | 2009 | 7 | Heathrow | 24.6
2009-07-25 | 2009 | 7 | Heathrow | 22.2
2009-07-26 | 2009 | 7 | Heathrow | 22.4
2009-07-27 | 2009 | 7 | Heathrow | 22.1
2009-07-28 | 2009 | 7 | Heathrow | 21
2009-07-29 | 2009 | 7 | Heathrow | 20.7
2009-07-30 | 2009 | 7 | Heathrow | 22.5
2009-07-31 | 2009 | 7 | Heathrow | 20.6
2009-08-01 | 2009 | 8 | Heathrow | 22.2
2009-08-02 | 2009 | 8 | Heathrow | 23.3
2009-08-03 | 2009 | 8 | Heathrow | 23.3
2009-08-04 | 2009 | 8 | Heathrow | 27.9
2009-08-05 | 2009 | 8 | Heathrow | 24.9
2009-08-06 | 2009 | 8 | Heathrow | 22.8
2009-08-07 | 2009 | 8 | Heathrow | 24.9
2009-08-08 | 2009 | 8 | Heathrow | 25.9
2009-08-09 | 2009 | 8 | Heathrow | 22.2
2009-08-10 | 2009 | 8 | Heathrow | 25
2009-08-11 | 2009 | 8 | Heathrow | 23.5
2009-08-12 | 2009 | 8 | Heathrow | 23.5
2009-08-13 | 2009 | 8 | Heathrow | 24.1
2009-08-14 | 2009 | 8 | Heathrow | 23.5
2009-08-15 | 2009 | 8 | Heathrow | 25.4
2009-08-16 | 2009 | 8 | Heathrow | 23.8
2009-08-17 | 2009 | 8 | Heathrow | 24.9
2009-08-18 | 2009 | 8 | Heathrow | 28.9
2009-08-19 | 2009 | 8 | Heathrow | 23.9
2009-08-20 | 2009 | 8 | Heathrow | 21.5
2009-08-21 | 2009 | 8 | Heathrow | 22.6
2009-08-22 | 2009 | 8 | Heathrow | 27.7
2009-08-23 | 2009 | 8 | Heathrow | 25.2
2009-08-24 | 2009 | 8 | Heathrow | 22.5
2009-08-25 | 2009 | 8 | Heathrow | 23.3
2009-08-26 | 2009 | 8 | Heathrow | 23.6
2009-08-27 | 2009 | 8 | Heathrow | 21.7
2009-08-28 | 2009 | 8 | Heathrow | 20.7
2009-08-29 | 2009 | 8 | Heathrow | 20.4
2009-08-30 | 2009 | 8 | Heathrow | 26.2
2009-08-31 | 2009 | 8 | Heathrow | 22.3
2009-09-01 | 2009 | 9 | Heathrow | 20.2
2009-09-02 | 2009 | 9 | Heathrow | 19.7
2009-09-03 | 2009 | 9 | Heathrow | 19.1
2009-09-04 | 2009 | 9 | Heathrow | 20.2
2009-09-05 | 2009 | 9 | Heathrow | 20.3
2009-09-06 | 2009 | 9 | Heathrow | 21.7
2009-09-07 | 2009 | 9 | Heathrow | 28.1
2009-09-08 | 2009 | 9 | Heathrow | 28.1
2009-09-09 | 2009 | 9 | Heathrow | 20.3
2009-09-10 | 2009 | 9 | Heathrow | 21.1
2009-09-11 | 2009 | 9 | Heathrow | 22.2
2009-09-12 | 2009 | 9 | Heathrow | 17.8
2009-09-13 | 2009 | 9 | Heathrow | 20
2009-09-14 | 2009 | 9 | Heathrow | 16.7
2009-09-15 | 2009 | 9 | Heathrow | 20.6
2009-09-16 | 2009 | 9 | Heathrow | 17.4
2009-09-17 | 2009 | 9 | Heathrow | 20.6
2009-09-18 | 2009 | 9 | Heathrow | 23.5
2009-09-19 | 2009 | 9 | Heathrow | 20.3
2009-09-20 | 2009 | 9 | Heathrow | 21.2
2009-09-21 | 2009 | 9 | Heathrow | 21.7
2009-09-22 | 2009 | 9 | Heathrow | 18.7
2009-09-23 | 2009 | 9 | Heathrow | 20.2
2009-09-24 | 2009 | 9 | Heathrow | 20.1
2009-09-25 | 2009 | 9 | Heathrow | 20.2
2009-09-26 | 2009 | 9 | Heathrow | 21.9
2009-09-27 | 2009 | 9 | Heathrow | 19.4
2009-09-28 | 2009 | 9 | Heathrow | 21.5
2009-09-29 | 2009 | 9 | Heathrow | 19
2009-09-30 | 2009 | 9 | Heathrow | 18
2010-05-01 | 2010 | 5 | Heathrow | 17.5
2010-05-02 | 2010 | 5 | Heathrow | 11.5
2010-05-03 | 2010 | 5 | Heathrow | 12.1
2010-05-04 | 2010 | 5 | Heathrow | 15.5
2010-05-05 | 2010 | 5 | Heathrow | 15.3
2010-05-06 | 2010 | 5 | Heathrow | 13.5
2010-05-07 | 2010 | 5 | Heathrow | 13.6
2010-05-08 | 2010 | 5 | Heathrow | 12.3
2010-05-09 | 2010 | 5 | Heathrow | 13.9
2010-05-10 | 2010 | 5 | Heathrow | 10.5
2010-05-11 | 2010 | 5 | Heathrow | 12.1
2010-05-12 | 2010 | 5 | Heathrow | 14.5
2010-05-13 | 2010 | 5 | Heathrow | 15
2010-05-14 | 2010 | 5 | Heathrow | 17.9
2010-05-15 | 2010 | 5 | Heathrow | 16.4
2010-05-16 | 2010 | 5 | Heathrow | 18.3
2010-05-17 | 2010 | 5 | Heathrow | 19.3
2010-05-18 | 2010 | 5 | Heathrow | 21.7
2010-05-19 | 2010 | 5 | Heathrow | 22.7
2010-05-20 | 2010 | 5 | Heathrow | 25.2
2010-05-21 | 2010 | 5 | Heathrow | 25
2010-05-22 | 2010 | 5 | Heathrow | 28.1
2010-05-23 | 2010 | 5 | Heathrow | 28.8
2010-05-24 | 2010 | 5 | Heathrow | 28.9
2010-05-25 | 2010 | 5 | Heathrow | 17.4
2010-05-26 | 2010 | 5 | Heathrow | 18.7
2010-05-27 | 2010 | 5 | Heathrow | 19.7
2010-05-28 | 2010 | 5 | Heathrow | 16.5
2010-05-29 | 2010 | 5 | Heathrow | 20.3
2010-05-30 | 2010 | 5 | Heathrow | 16.5
2010-05-31 | 2010 | 5 | Heathrow | 15.4
2010-06-01 | 2010 | 6 | Heathrow | 22.6
2010-06-02 | 2010 | 6 | Heathrow | 23.4
2010-06-03 | 2010 | 6 | Heathrow | 27.9
2010-06-04 | 2010 | 6 | Heathrow | 28
2010-06-05 | 2010 | 6 | Heathrow | 24.3
2010-06-06 | 2010 | 6 | Heathrow | 21
2010-06-07 | 2010 | 6 | Heathrow | 20.4
2010-06-08 | 2010 | 6 | Heathrow | 22.4
2010-06-09 | 2010 | 6 | Heathrow | 19.9
2010-06-10 | 2010 | 6 | Heathrow | 20.5
2010-06-11 | 2010 | 6 | Heathrow | 20.2
2010-06-12 | 2010 | 6 | Heathrow | 22.2
2010-06-13 | 2010 | 6 | Heathrow | 20.9
2010-06-14 | 2010 | 6 | Heathrow | 18.9
2010-06-15 | 2010 | 6 | Heathrow | 20.8
2010-06-16 | 2010 | 6 | Heathrow | 23.3
2010-06-17 | 2010 | 6 | Heathrow | 20.8
2010-06-18 | 2010 | 6 | Heathrow | 20.9
2010-06-19 | 2010 | 6 | Heathrow | 20.3
2010-06-20 | 2010 | 6 | Heathrow | 24.7
2010-06-21 | 2010 | 6 | Heathrow | 27.3
2010-06-22 | 2010 | 6 | Heathrow | 27.3
2010-06-23 | 2010 | 6 | Heathrow | 26.3
2010-06-24 | 2010 | 6 | Heathrow | 27.8
2010-06-25 | 2010 | 6 | Heathrow | 27.6
2010-06-26 | 2010 | 6 | Heathrow | 30.6
2010-06-27 | 2010 | 6 | Heathrow | 28.7
2010-06-28 | 2010 | 6 | Heathrow | 28.6
2010-06-29 | 2010 | 6 | Heathrow | 26.4
2010-06-30 | 2010 | 6 | Heathrow | 27.2
2010-07-01 | 2010 | 7 | Heathrow | 25.8
2010-07-02 | 2010 | 7 | Heathrow | 26.1
2010-07-03 | 2010 | 7 | Heathrow | 24.5
2010-07-04 | 2010 | 7 | Heathrow | 24.2
2010-07-05 | 2010 | 7 | Heathrow | 23.8
2010-07-06 | 2010 | 7 | Heathrow | 24
2010-07-07 | 2010 | 7 | Heathrow | 27.1
2010-07-08 | 2010 | 7 | Heathrow | 31.2
2010-07-09 | 2010 | 7 | Heathrow | 29.1
2010-07-10 | 2010 | 7 | Heathrow | 27.5
2010-07-11 | 2010 | 7 | Heathrow | 23.9
2010-07-12 | 2010 | 7 | Heathrow | 21.7
2010-07-13 | 2010 | 7 | Heathrow | 21.8
2010-07-14 | 2010 | 7 | Heathrow | 21.5
2010-07-15 | 2010 | 7 | Heathrow | 22.8
2010-07-16 | 2010 | 7 | Heathrow | 22
2010-07-17 | 2010 | 7 | Heathrow | 24.5
2010-07-18 | 2010 | 7 | Heathrow | 29.5
2010-07-19 | 2010 | 7 | Heathrow | 28.7
2010-07-20 | 2010 | 7 | Heathrow | 25.1
2010-07-21 | 2010 | 7 | Heathrow | 22.7
2010-07-22 | 2010 | 7 | Heathrow | 20.6
2010-07-23 | 2010 | 7 | Heathrow | 25.5
2010-07-24 | 2010 | 7 | Heathrow | 26
2010-07-25 | 2010 | 7 | Heathrow | 23.5
2010-07-26 | 2010 | 7 | Heathrow | 26.3
2010-07-27 | 2010 | 7 | Heathrow | 25.2
2010-07-28 | 2010 | 7 | Heathrow | 23.3
2010-07-29 | 2010 | 7 | Heathrow | 23.1
2010-07-30 | 2010 | 7 | Heathrow | 25.1
2010-07-31 | 2010 | 7 | Heathrow | 23.9
2010-08-01 | 2010 | 8 | Heathrow | 23.4
2010-08-02 | 2010 | 8 | Heathrow | 23.6
2010-08-03 | 2010 | 8 | Heathrow | 20.1
2010-08-04 | 2010 | 8 | Heathrow | 22.6
2010-08-05 | 2010 | 8 | Heathrow | 21.4
2010-08-06 | 2010 | 8 | Heathrow | 21.8
2010-08-07 | 2010 | 8 | Heathrow | 24.5
2010-08-08 | 2010 | 8 | Heathrow | 25.1
2010-08-09 | 2010 | 8 | Heathrow | 25.1
2010-08-10 | 2010 | 8 | Heathrow | 23
2010-08-11 | 2010 | 8 | Heathrow | 20.4
2010-08-12 | 2010 | 8 | Heathrow | 18
2010-08-13 | 2010 | 8 | Heathrow | 18.4
2010-08-14 | 2010 | 8 | Heathrow | 22.7
2010-08-15 | 2010 | 8 | Heathrow | 25.4
2010-08-16 | 2010 | 8 | Heathrow | 21
2010-08-17 | 2010 | 8 | Heathrow | 21.6
2010-08-18 | 2010 | 8 | Heathrow | 21.9
2010-08-19 | 2010 | 8 | Heathrow | 22.1
2010-08-20 | 2010 | 8 | Heathrow | 24.3
2010-08-21 | 2010 | 8 | Heathrow | 23.1
2010-08-22 | 2010 | 8 | Heathrow | 21.7
2010-08-23 | 2010 | 8 | Heathrow | 20.9
2010-08-24 | 2010 | 8 | Heathrow | 19.3
2010-08-25 | 2010 | 8 | Heathrow | 21.3
2010-08-26 | 2010 | 8 | Heathrow | 18.5
2010-08-27 | 2010 | 8 | Heathrow | 20.6
2010-08-28 | 2010 | 8 | Heathrow | 19.6
2010-08-29 | 2010 | 8 | Heathrow | 19.5
2010-08-30 | 2010 | 8 | Heathrow | 20.5
2010-08-31 | 2010 | 8 | Heathrow | 21.3
2010-09-01 | 2010 | 9 | Heathrow | 21.9
2010-09-02 | 2010 | 9 | Heathrow | 22.5
2010-09-03 | 2010 | 9 | Heathrow | 22
2010-09-04 | 2010 | 9 | Heathrow | 21.8
2010-09-05 | 2010 | 9 | Heathrow | 21.8
2010-09-06 | 2010 | 9 | Heathrow | 19.6
2010-09-07 | 2010 | 9 | Heathrow | 20.6
2010-09-08 | 2010 | 9 | Heathrow | 22.5
2010-09-09 | 2010 | 9 | Heathrow | 22.4
2010-09-10 | 2010 | 9 | Heathrow | 22.5
2010-09-11 | 2010 | 9 | Heathrow | 20.8
2010-09-12 | 2010 | 9 | Heathrow | 18.5
2010-09-13 | 2010 | 9 | Heathrow | 20.1
2010-09-14 | 2010 | 9 | Heathrow | 18
2010-09-15 | 2010 | 9 | Heathrow | 18.1
2010-09-16 | 2010 | 9 | Heathrow | 16.4
2010-09-17 | 2010 | 9 | Heathrow | 18
2010-09-18 | 2010 | 9 | Heathrow | 18.3
2010-09-19 | 2010 | 9 | Heathrow | 22.8
2010-09-20 | 2010 | 9 | Heathrow | 21.9
2010-09-21 | 2010 | 9 | Heathrow | 23.9
2010-09-22 | 2010 | 9 | Heathrow | 18.3
2010-09-23 | 2010 | 9 | Heathrow | 18.4
2010-09-24 | 2010 | 9 | Heathrow | 13.9
2010-09-25 | 2010 | 9 | Heathrow | 13.8
2010-09-26 | 2010 | 9 | Heathrow | 15.9
2010-09-27 | 2010 | 9 | Heathrow | 16.9
2010-09-28 | 2010 | 9 | Heathrow | 17.3
2010-09-29 | 2010 | 9 | Heathrow | 16.4
2010-09-30 | 2010 | 9 | Heathrow | 16.6
2011-05-01 | 2011 | 5 | Heathrow | 17
2011-05-02 | 2011 | 5 | Heathrow | 15.3
2011-05-03 | 2011 | 5 | Heathrow | 18.5
2011-05-04 | 2011 | 5 | Heathrow | 21.5
2011-05-05 | 2011 | 5 | Heathrow | 25
2011-05-06 | 2011 | 5 | Heathrow | 23.3
2011-05-07 | 2011 | 5 | Heathrow | 19.9
2011-05-08 | 2011 | 5 | Heathrow | 20.5
2011-05-09 | 2011 | 5 | Heathrow | 21.6
2011-05-10 | 2011 | 5 | Heathrow | 18.1
2011-05-11 | 2011 | 5 | Heathrow | 19.3
2011-05-12 | 2011 | 5 | Heathrow | 18.6
2011-05-13 | 2011 | 5 | Heathrow | 17.4
2011-05-14 | 2011 | 5 | Heathrow | 16
2011-05-15 | 2011 | 5 | Heathrow | 20.1
2011-05-16 | 2011 | 5 | Heathrow | 18.7
2011-05-17 | 2011 | 5 | Heathrow | 20.3
2011-05-18 | 2011 | 5 | Heathrow | 20.5
2011-05-19 | 2011 | 5 | Heathrow | 19.3
2011-05-20 | 2011 | 5 | Heathrow | 21.5
2011-05-21 | 2011 | 5 | Heathrow | 20
2011-05-22 | 2011 | 5 | Heathrow | 19.8
2011-05-23 | 2011 | 5 | Heathrow | 19.4
2011-05-24 | 2011 | 5 | Heathrow | 20.5
2011-05-25 | 2011 | 5 | Heathrow | 17
2011-05-26 | 2011 | 5 | Heathrow | 16.4
2011-05-27 | 2011 | 5 | Heathrow | 17.6
2011-05-28 | 2011 | 5 | Heathrow | 20
2011-05-29 | 2011 | 5 | Heathrow | 20.6
2011-05-30 | 2011 | 5 | Heathrow | 18.7
2011-05-31 | 2011 | 5 | Heathrow | 21.6
2011-06-01 | 2011 | 6 | Heathrow | 23.8
2011-06-02 | 2011 | 6 | Heathrow | 25.8
2011-06-03 | 2011 | 6 | Heathrow | 27
2011-06-04 | 2011 | 6 | Heathrow | 27.1
2011-06-05 | 2011 | 6 | Heathrow | 19.6
2011-06-06 | 2011 | 6 | Heathrow | 19.5
2011-06-07 | 2011 | 6 | Heathrow | 18.2
2011-06-08 | 2011 | 6 | Heathrow | 17.9
2011-06-09 | 2011 | 6 | Heathrow | 15.9
2011-06-10 | 2011 | 6 | Heathrow | 18.9
2011-06-11 | 2011 | 6 | Heathrow | 17
2011-06-12 | 2011 | 6 | Heathrow | 21.7
2011-06-13 | 2011 | 6 | Heathrow | 23
2011-06-14 | 2011 | 6 | Heathrow | 20.2
2011-06-15 | 2011 | 6 | Heathrow | 17.7
2011-06-16 | 2011 | 6 | Heathrow | 15.4
2011-06-17 | 2011 | 6 | Heathrow | 18.6
2011-06-18 | 2011 | 6 | Heathrow | 19
2011-06-19 | 2011 | 6 | Heathrow | 21.3
2011-06-20 | 2011 | 6 | Heathrow | 21.5
2011-06-21 | 2011 | 6 | Heathrow | 18.9
2011-06-22 | 2011 | 6 | Heathrow | 19.2
2011-06-23 | 2011 | 6 | Heathrow | 19.6
2011-06-24 | 2011 | 6 | Heathrow | 23.9
2011-06-25 | 2011 | 6 | Heathrow | 28.4
2011-06-26 | 2011 | 6 | Heathrow | 31.2
2011-06-27 | 2011 | 6 | Heathrow | 31.2
2011-06-28 | 2011 | 6 | Heathrow | 20.5
2011-06-29 | 2011 | 6 | Heathrow | 20.3
2011-06-30 | 2011 | 6 | Heathrow | 20.7
2011-07-01 | 2011 | 7 | Heathrow | 22.8
2011-07-02 | 2011 | 7 | Heathrow | 24.1
2011-07-03 | 2011 | 7 | Heathrow | 25.5
2011-07-04 | 2011 | 7 | Heathrow | 25.9
2011-07-05 | 2011 | 7 | Heathrow | 20.8
2011-07-06 | 2011 | 7 | Heathrow | 20.4
2011-07-07 | 2011 | 7 | Heathrow | 19.8
2011-07-08 | 2011 | 7 | Heathrow | 22.1
2011-07-09 | 2011 | 7 | Heathrow | 22.9
2011-07-10 | 2011 | 7 | Heathrow | 24.6
2011-07-11 | 2011 | 7 | Heathrow | 19.7
2011-07-12 | 2011 | 7 | Heathrow | 18.4
2011-07-13 | 2011 | 7 | Heathrow | 23.7
2011-07-14 | 2011 | 7 | Heathrow | 25.3
2011-07-15 | 2011 | 7 | Heathrow | 19.9
2011-07-16 | 2011 | 7 | Heathrow | 19.3
2011-07-17 | 2011 | 7 | Heathrow | 19.6
2011-07-18 | 2011 | 7 | Heathrow | 19.4
2011-07-19 | 2011 | 7 | Heathrow | 18.1
2011-07-20 | 2011 | 7 | Heathrow | 19
2011-07-21 | 2011 | 7 | Heathrow | 20.2
2011-07-22 | 2011 | 7 | Heathrow | 18.9
2011-07-23 | 2011 | 7 | Heathrow | 23.9
2011-07-24 | 2011 | 7 | Heathrow | 24
2011-07-25 | 2011 | 7 | Heathrow | 20.5
2011-07-26 | 2011 | 7 | Heathrow | 20.8
2011-07-27 | 2011 | 7 | Heathrow | 24.5
2011-07-28 | 2011 | 7 | Heathrow | 21.1
2011-07-29 | 2011 | 7 | Heathrow | 22.6
2011-07-30 | 2011 | 7 | Heathrow | 24.5
2011-07-31 | 2011 | 7 | Heathrow | 29
2011-08-01 | 2011 | 8 | Heathrow | 28.3
2011-08-02 | 2011 | 8 | Heathrow | 30.1
2011-08-03 | 2011 | 8 | Heathrow | 30.1
2011-08-04 | 2011 | 8 | Heathrow | 25.5
2011-08-05 | 2011 | 8 | Heathrow | 20.6
2011-08-06 | 2011 | 8 | Heathrow | 20.3
2011-08-07 | 2011 | 8 | Heathrow | 21.9
2011-08-08 | 2011 | 8 | Heathrow | 21.6
2011-08-09 | 2011 | 8 | Heathrow | 23.9
2011-08-10 | 2011 | 8 | Heathrow | 22.6
2011-08-11 | 2011 | 8 | Heathrow | 23.4
2011-08-12 | 2011 | 8 | Heathrow | 22.2
2011-08-13 | 2011 | 8 | Heathrow | 23.2
2011-08-14 | 2011 | 8 | Heathrow | 22.9
2011-08-15 | 2011 | 8 | Heathrow | 21.7
2011-08-16 | 2011 | 8 | Heathrow | 21.1
2011-08-17 | 2011 | 8 | Heathrow | 21.1
2011-08-18 | 2011 | 8 | Heathrow | 21.7
2011-08-19 | 2011 | 8 | Heathrow | 21.6
2011-08-20 | 2011 | 8 | Heathrow | 24.1
2011-08-21 | 2011 | 8 | Heathrow | 23.5
2011-08-22 | 2011 | 8 | Heathrow | 23.6
2011-08-23 | 2011 | 8 | Heathrow | 22
2011-08-24 | 2011 | 8 | Heathrow | 20.6
2011-08-25 | 2011 | 8 | Heathrow | 17.5
2011-08-26 | 2011 | 8 | Heathrow | 19
2011-08-27 | 2011 | 8 | Heathrow | 19.5
2011-08-28 | 2011 | 8 | Heathrow | 18.1
2011-08-29 | 2011 | 8 | Heathrow | 17.3
2011-08-30 | 2011 | 8 | Heathrow | 18.5
2011-08-31 | 2011 | 8 | Heathrow | 21.2
2011-09-01 | 2011 | 9 | Heathrow | 27
2011-09-02 | 2011 | 9 | Heathrow | 24.1
2011-09-03 | 2011 | 9 | Heathrow | 19.4
2011-09-04 | 2011 | 9 | Heathrow | 19.7
2011-09-05 | 2011 | 9 | Heathrow | 18.7
2011-09-06 | 2011 | 9 | Heathrow | 17.1
2011-09-07 | 2011 | 9 | Heathrow | 20.8
2011-09-08 | 2011 | 9 | Heathrow | 21.5
2011-09-09 | 2011 | 9 | Heathrow | 22.7
2011-09-10 | 2011 | 9 | Heathrow | 21
2011-09-11 | 2011 | 9 | Heathrow | 21.7
2011-09-12 | 2011 | 9 | Heathrow | 19.5
2011-09-13 | 2011 | 9 | Heathrow | 20
2011-09-14 | 2011 | 9 | Heathrow | 20.1
2011-09-15 | 2011 | 9 | Heathrow | 22.7
2011-09-16 | 2011 | 9 | Heathrow | 19.6
2011-09-17 | 2011 | 9 | Heathrow | 17
2011-09-18 | 2011 | 9 | Heathrow | 19.4
2011-09-19 | 2011 | 9 | Heathrow | 20.2
2011-09-20 | 2011 | 9 | Heathrow | 18.5
2011-09-21 | 2011 | 9 | Heathrow | 19.2
2011-09-22 | 2011 | 9 | Heathrow | 19
2011-09-23 | 2011 | 9 | Heathrow | 20.9
2011-09-24 | 2011 | 9 | Heathrow | 21.8
2011-09-25 | 2011 | 9 | Heathrow | 22.7
2011-09-26 | 2011 | 9 | Heathrow | 21.8
2011-09-27 | 2011 | 9 | Heathrow | 25.9
2011-09-28 | 2011 | 9 | Heathrow | 28.1
2011-09-29 | 2011 | 9 | Heathrow | 28.5
2011-09-30 | 2011 | 9 | Heathrow | 28.8
2012-05-01 | 2012 | 5 | Heathrow | 14.7
2012-05-02 | 2012 | 5 | Heathrow | 14.7
2012-05-03 | 2012 | 5 | Heathrow | 10
2012-05-04 | 2012 | 5 | Heathrow | 10.3
2012-05-05 | 2012 | 5 | Heathrow | 10.4
2012-05-06 | 2012 | 5 | Heathrow | 15.1
2012-05-07 | 2012 | 5 | Heathrow | 18.1
2012-05-08 | 2012 | 5 | Heathrow | 16.8
2012-05-09 | 2012 | 5 | Heathrow | 17.1
2012-05-10 | 2012 | 5 | Heathrow | 16.5
2012-05-11 | 2012 | 5 | Heathrow | 15.7
2012-05-12 | 2012 | 5 | Heathrow | 17.3
2012-05-13 | 2012 | 5 | Heathrow | 12.5
2012-05-14 | 2012 | 5 | Heathrow | 12.4
2012-05-15 | 2012 | 5 | Heathrow | 14.9
2012-05-16 | 2012 | 5 | Heathrow | 15.5
2012-05-17 | 2012 | 5 | Heathrow | 16.2
2012-05-18 | 2012 | 5 | Heathrow | 17.4
2012-05-19 | 2012 | 5 | Heathrow | 17.5
2012-05-20 | 2012 | 5 | Heathrow | 17.5
2012-05-21 | 2012 | 5 | Heathrow | 25.7
2012-05-22 | 2012 | 5 | Heathrow | 27.2
2012-05-23 | 2012 | 5 | Heathrow | 27
2012-05-24 | 2012 | 5 | Heathrow | 25.9
2012-05-25 | 2012 | 5 | Heathrow | 25.9
2012-05-26 | 2012 | 5 | Heathrow | 27.6
2012-05-27 | 2012 | 5 | Heathrow | 26.3
2012-05-28 | 2012 | 5 | Heathrow | 23.8
2012-05-29 | 2012 | 5 | Heathrow | 25.4
2012-05-30 | 2012 | 5 | Heathrow | 20.8
2012-05-31 | 2012 | 5 | Heathrow | 21.4
2012-06-01 | 2012 | 6 | Heathrow | 19.5
2012-06-02 | 2012 | 6 | Heathrow | 19.6
2012-06-03 | 2012 | 6 | Heathrow | 14.9
2012-06-04 | 2012 | 6 | Heathrow | 16.2
2012-06-05 | 2012 | 6 | Heathrow | 18.8
2012-06-06 | 2012 | 6 | Heathrow | 17.8
2012-06-07 | 2012 | 6 | Heathrow | 16.3
2012-06-08 | 2012 | 6 | Heathrow | 19.5
2012-06-09 | 2012 | 6 | Heathrow | 17.3
2012-06-10 | 2012 | 6 | Heathrow | 13
2012-06-11 | 2012 | 6 | Heathrow | 15.4
2012-06-12 | 2012 | 6 | Heathrow | 18.3
2012-06-13 | 2012 | 6 | Heathrow | 18.6
2012-06-14 | 2012 | 6 | Heathrow | 19.3
2012-06-15 | 2012 | 6 | Heathrow | 19.3
2012-06-16 | 2012 | 6 | Heathrow | 20.4
2012-06-17 | 2012 | 6 | Heathrow | 19.5
2012-06-18 | 2012 | 6 | Heathrow | 20.5
2012-06-19 | 2012 | 6 | Heathrow | 22.7
2012-06-20 | 2012 | 6 | Heathrow | 20.4
2012-06-21 | 2012 | 6 | Heathrow | 18.7
2012-06-22 | 2012 | 6 | Heathrow | 20.2
2012-06-23 | 2012 | 6 | Heathrow | 20.9
2012-06-24 | 2012 | 6 | Heathrow | 22.5
2012-06-25 | 2012 | 6 | Heathrow | 22.3
2012-06-26 | 2012 | 6 | Heathrow | 23.4
2012-06-27 | 2012 | 6 | Heathrow | 27.6
2012-06-28 | 2012 | 6 | Heathrow | 27.6
2012-06-29 | 2012 | 6 | Heathrow | 21.6
2012-06-30 | 2012 | 6 | Heathrow | 19.3
2012-07-01 | 2012 | 7 | Heathrow | 17.9
2012-07-02 | 2012 | 7 | Heathrow | 19.3
2012-07-03 | 2012 | 7 | Heathrow | 22.2
2012-07-04 | 2012 | 7 | Heathrow | 22.5
2012-07-05 | 2012 | 7 | Heathrow | 19
2012-07-06 | 2012 | 7 | Heathrow | 19.4
2012-07-07 | 2012 | 7 | Heathrow | 22
2012-07-08 | 2012 | 7 | Heathrow | 18.8
2012-07-09 | 2012 | 7 | Heathrow | 18.7
2012-07-10 | 2012 | 7 | Heathrow | 20.2
2012-07-11 | 2012 | 7 | Heathrow | 19.3
2012-07-12 | 2012 | 7 | Heathrow | 20.1
2012-07-13 | 2012 | 7 | Heathrow | 16.9
2012-07-14 | 2012 | 7 | Heathrow | 18.8
2012-07-15 | 2012 | 7 | Heathrow | 18.7
2012-07-16 | 2012 | 7 | Heathrow | 23.8
2012-07-17 | 2012 | 7 | Heathrow | 19.2
2012-07-18 | 2012 | 7 | Heathrow | 20.3
2012-07-19 | 2012 | 7 | Heathrow | 19
2012-07-20 | 2012 | 7 | Heathrow | 20.7
2012-07-21 | 2012 | 7 | Heathrow | 23.3
2012-07-22 | 2012 | 7 | Heathrow | 27.4
2012-07-23 | 2012 | 7 | Heathrow | 28.9
2012-07-24 | 2012 | 7 | Heathrow | 30.2
2012-07-25 | 2012 | 7 | Heathrow | 27.4
2012-07-26 | 2012 | 7 | Heathrow | 24.8
2012-07-27 | 2012 | 7 | Heathrow | 21.6
2012-07-28 | 2012 | 7 | Heathrow | 18.9
2012-07-29 | 2012 | 7 | Heathrow | 20.7
2012-07-30 | 2012 | 7 | Heathrow | 20.8
2012-07-31 | 2012 | 7 | Heathrow | 23.6
2012-08-01 | 2012 | 8 | Heathrow | 22.8
2012-08-02 | 2012 | 8 | Heathrow | 23
2012-08-03 | 2012 | 8 | Heathrow | 21.3
2012-08-04 | 2012 | 8 | Heathrow | 21.5
2012-08-05 | 2012 | 8 | Heathrow | 22.3
2012-08-06 | 2012 | 8 | Heathrow | 20.3
2012-08-07 | 2012 | 8 | Heathrow | 23.7
2012-08-08 | 2012 | 8 | Heathrow | 26.3
2012-08-09 | 2012 | 8 | Heathrow | 26.9
2012-08-10 | 2012 | 8 | Heathrow | 24.1
2012-08-11 | 2012 | 8 | Heathrow | 26.9
2012-08-12 | 2012 | 8 | Heathrow | 23.8
2012-08-13 | 2012 | 8 | Heathrow | 25.1
2012-08-14 | 2012 | 8 | Heathrow | 23
2012-08-15 | 2012 | 8 | Heathrow | 22.9
2012-08-16 | 2012 | 8 | Heathrow | 28.5
2012-08-17 | 2012 | 8 | Heathrow | 30.3
2012-08-18 | 2012 | 8 | Heathrow | 30.5
2012-08-19 | 2012 | 8 | Heathrow | 25.5
2012-08-20 | 2012 | 8 | Heathrow | 22.2
2012-08-21 | 2012 | 8 | Heathrow | 23.4
2012-08-22 | 2012 | 8 | Heathrow | 22.4
2012-08-23 | 2012 | 8 | Heathrow | 20.8
2012-08-24 | 2012 | 8 | Heathrow | 22.5
2012-08-25 | 2012 | 8 | Heathrow | 21.5
2012-08-26 | 2012 | 8 | Heathrow | 22.6
2012-08-27 | 2012 | 8 | Heathrow | 24.2
2012-08-28 | 2012 | 8 | Heathrow | 21
2012-08-29 | 2012 | 8 | Heathrow | 18.1
2012-08-30 | 2012 | 8 | Heathrow | 18.8
2012-08-31 | 2012 | 8 | Heathrow | 22.8
2012-09-01 | 2012 | 9 | Heathrow | 18.8
2012-09-02 | 2012 | 9 | Heathrow | 24.7
2012-09-03 | 2012 | 9 | Heathrow | 25.1
2012-09-04 | 2012 | 9 | Heathrow | 20.7
2012-09-05 | 2012 | 9 | Heathrow | 21.7
2012-09-06 | 2012 | 9 | Heathrow | 26.4
2012-09-07 | 2012 | 9 | Heathrow | 27.3
2012-09-08 | 2012 | 9 | Heathrow | 28.3
2012-09-09 | 2012 | 9 | Heathrow | 21.5
2012-09-10 | 2012 | 9 | Heathrow | 19
2012-09-11 | 2012 | 9 | Heathrow | 19
2012-09-12 | 2012 | 9 | Heathrow | 19.2
2012-09-13 | 2012 | 9 | Heathrow | 21
2012-09-14 | 2012 | 9 | Heathrow | 22.9
2012-09-15 | 2012 | 9 | Heathrow | 18.9
2012-09-16 | 2012 | 9 | Heathrow | 19.5
2012-09-17 | 2012 | 9 | Heathrow | 18.1
2012-09-18 | 2012 | 9 | Heathrow | 17.8
2012-09-19 | 2012 | 9 | Heathrow | 17.8
2012-09-20 | 2012 | 9 | Heathrow | 16.8
2012-09-21 | 2012 | 9 | Heathrow | 16.8
2012-09-22 | 2012 | 9 | Heathrow | 15
2012-09-23 | 2012 | 9 | Heathrow | 16
2012-09-24 | 2012 | 9 | Heathrow | 17.1
2012-09-25 | 2012 | 9 | Heathrow | 16
2012-09-26 | 2012 | 9 | Heathrow | 17.5
2012-09-27 | 2012 | 9 | Heathrow | 18.1
2012-09-28 | 2012 | 9 | Heathrow | 16.7
2012-09-29 | 2012 | 9 | Heathrow | 18.1
2012-09-30 | 2012 | 9 | Heathrow | 17.3
2013-05-01 | 2013 | 5 | Heathrow | 17.6
2013-05-02 | 2013 | 5 | Heathrow | 19.4
2013-05-03 | 2013 | 5 | Heathrow | 17.2
2013-05-04 | 2013 | 5 | Heathrow | 18.7
2013-05-05 | 2013 | 5 | Heathrow | 22
2013-05-06 | 2013 | 5 | Heathrow | 22.6
2013-05-07 | 2013 | 5 | Heathrow | 17.9
2013-05-08 | 2013 | 5 | Heathrow | 18
2013-05-09 | 2013 | 5 | Heathrow | 18.3
2013-05-10 | 2013 | 5 | Heathrow | 14.1
2013-05-11 | 2013 | 5 | Heathrow | 15.4
2013-05-12 | 2013 | 5 | Heathrow | 15.8
2013-05-13 | 2013 | 5 | Heathrow | 15.9
2013-05-14 | 2013 | 5 | Heathrow | 14.4
2013-05-15 | 2013 | 5 | Heathrow | 16.9
2013-05-16 | 2013 | 5 | Heathrow | 12.6
2013-05-17 | 2013 | 5 | Heathrow | 16
2013-05-18 | 2013 | 5 | Heathrow | 18.8
2013-05-19 | 2013 | 5 | Heathrow | 17.3
2013-05-20 | 2013 | 5 | Heathrow | 15.3
2013-05-21 | 2013 | 5 | Heathrow | 15
2013-05-22 | 2013 | 5 | Heathrow | 15.1
2013-05-23 | 2013 | 5 | Heathrow | 9.9
2013-05-24 | 2013 | 5 | Heathrow | 16.2
2013-05-25 | 2013 | 5 | Heathrow | 19.8
2013-05-26 | 2013 | 5 | Heathrow | 18.2
2013-05-27 | 2013 | 5 | Heathrow | 18.2
2013-05-28 | 2013 | 5 | Heathrow | 13.2
2013-05-29 | 2013 | 5 | Heathrow | 15.2
2013-05-30 | 2013 | 5 | Heathrow | 21.9
2013-05-31 | 2013 | 5 | Heathrow | 18.8
2013-06-01 | 2013 | 6 | Heathrow | 18.7
2013-06-02 | 2013 | 6 | Heathrow | 19.3
2013-06-03 | 2013 | 6 | Heathrow | 21.2
2013-06-04 | 2013 | 6 | Heathrow | 21.5
2013-06-05 | 2013 | 6 | Heathrow | 22.9
2013-06-06 | 2013 | 6 | Heathrow | 20.6
2013-06-07 | 2013 | 6 | Heathrow | 18.6
2013-06-08 | 2013 | 6 | Heathrow | 15.3
2013-06-09 | 2013 | 6 | Heathrow | 16.1
2013-06-10 | 2013 | 6 | Heathrow | 18.1
2013-06-11 | 2013 | 6 | Heathrow | 17.8
2013-06-12 | 2013 | 6 | Heathrow | 19.3
2013-06-13 | 2013 | 6 | Heathrow | 19.7
2013-06-14 | 2013 | 6 | Heathrow | 18.3
2013-06-15 | 2013 | 6 | Heathrow | 18.2
2013-06-16 | 2013 | 6 | Heathrow | 21.3
2013-06-17 | 2013 | 6 | Heathrow | 21
2013-06-18 | 2013 | 6 | Heathrow | 26.1
2013-06-19 | 2013 | 6 | Heathrow | 21.3
2013-06-20 | 2013 | 6 | Heathrow | 23.7
2013-06-21 | 2013 | 6 | Heathrow | 19.4
2013-06-22 | 2013 | 6 | Heathrow | 18.6
2013-06-23 | 2013 | 6 | Heathrow | 17.7
2013-06-24 | 2013 | 6 | Heathrow | 21.1
2013-06-25 | 2013 | 6 | Heathrow | 22.5
2013-06-26 | 2013 | 6 | Heathrow | 20.7
2013-06-27 | 2013 | 6 | Heathrow | 21.5
2013-06-28 | 2013 | 6 | Heathrow | 22.2
2013-06-29 | 2013 | 6 | Heathrow | 27.2
2013-06-30 | 2013 | 6 | Heathrow | 21.3
2013-07-01 | 2013 | 7 | Heathrow | 17.9
2013-07-02 | 2013 | 7 | Heathrow | 21.5
2013-07-03 | 2013 | 7 | Heathrow | 24.9
2013-07-04 | 2013 | 7 | Heathrow | 26.3
2013-07-05 | 2013 | 7 | Heathrow | 28.1
2013-07-06 | 2013 | 7 | Heathrow | 29.5
2013-07-07 | 2013 | 7 | Heathrow | 27.7
2013-07-08 | 2013 | 7 | Heathrow | 27.2
2013-07-09 | 2013 | 7 | Heathrow | 24.6
2013-07-10 | 2013 | 7 | Heathrow | 23.4
2013-07-11 | 2013 | 7 | Heathrow | 25.9
2013-07-12 | 2013 | 7 | Heathrow | 31.4
2013-07-13 | 2013 | 7 | Heathrow | 29.8
2013-07-14 | 2013 | 7 | Heathrow | 30.9
2013-07-15 | 2013 | 7 | Heathrow | 31
2013-07-16 | 2013 | 7 | Heathrow | 31.9
2013-07-17 | 2013 | 7 | Heathrow | 29.5
2013-07-18 | 2013 | 7 | Heathrow | 29.3
2013-07-19 | 2013 | 7 | Heathrow | 24.6
2013-07-20 | 2013 | 7 | Heathrow | 27.5
2013-07-21 | 2013 | 7 | Heathrow | 33.5
2013-07-22 | 2013 | 7 | Heathrow | 29.6
2013-07-23 | 2013 | 7 | Heathrow | 27.7
2013-07-24 | 2013 | 7 | Heathrow | 26.9
2013-07-25 | 2013 | 7 | Heathrow | 26.8
2013-07-26 | 2013 | 7 | Heathrow | 28.9
2013-07-27 | 2013 | 7 | Heathrow | 24.9
2013-07-28 | 2013 | 7 | Heathrow | 24.7
2013-07-29 | 2013 | 7 | Heathrow | 22.3
2013-07-30 | 2013 | 7 | Heathrow | 26.9
2013-07-31 | 2013 | 7 | Heathrow | 34.1
2013-08-01 | 2013 | 8 | Heathrow | 26.4
2013-08-02 | 2013 | 8 | Heathrow | 24.7
2013-08-03 | 2013 | 8 | Heathrow | 24.5
2013-08-04 | 2013 | 8 | Heathrow | 23.8
2013-08-05 | 2013 | 8 | Heathrow | 22.7
2013-08-06 | 2013 | 8 | Heathrow | 23.1
2013-08-07 | 2013 | 8 | Heathrow | 25.5
2013-08-08 | 2013 | 8 | Heathrow | 24.9
2013-08-09 | 2013 | 8 | Heathrow | 23
2013-08-10 | 2013 | 8 | Heathrow | 24
2013-08-11 | 2013 | 8 | Heathrow | 22.8
2013-08-12 | 2013 | 8 | Heathrow | 21.5
2013-08-13 | 2013 | 8 | Heathrow | 23.4
2013-08-14 | 2013 | 8 | Heathrow | 24.2
2013-08-15 | 2013 | 8 | Heathrow | 23.6
2013-08-16 | 2013 | 8 | Heathrow | 20.9
2013-08-17 | 2013 | 8 | Heathrow | 23.9
2013-08-18 | 2013 | 8 | Heathrow | 23.5
2013-08-19 | 2013 | 8 | Heathrow | 24.9
2013-08-20 | 2013 | 8 | Heathrow | 27.5
2013-08-21 | 2013 | 8 | Heathrow | 23.9
2013-08-22 | 2013 | 8 | Heathrow | 27.7
2013-08-23 | 2013 | 8 | Heathrow | 27.7
2013-08-24 | 2013 | 8 | Heathrow | 24.7
2013-08-25 | 2013 | 8 | Heathrow | 25.9
2013-08-26 | 2013 | 8 | Heathrow | 23.6
2013-08-27 | 2013 | 8 | Heathrow | 24.7
2013-08-28 | 2013 | 8 | Heathrow | 24.7
2013-08-29 | 2013 | 8 | Heathrow | 25.4
2013-08-30 | 2013 | 8 | Heathrow | 21.4
2013-08-31 | 2013 | 8 | Heathrow | 22.3
2013-09-01 | 2013 | 9 | Heathrow | 26.2
2013-09-02 | 2013 | 9 | Heathrow | 26
2013-09-03 | 2013 | 9 | Heathrow | 28.5
2013-09-04 | 2013 | 9 | Heathrow | 29.5
2013-09-05 | 2013 | 9 | Heathrow | 29.6
2013-09-06 | 2013 | 9 | Heathrow | 19.5
2013-09-07 | 2013 | 9 | Heathrow | 18.5
2013-09-08 | 2013 | 9 | Heathrow | 14.1
2013-09-09 | 2013 | 9 | Heathrow | 17.2
2013-09-10 | 2013 | 9 | Heathrow | 17.4
2013-09-11 | 2013 | 9 | Heathrow | 20.5
2013-09-12 | 2013 | 9 | Heathrow | 19.6
2013-09-13 | 2013 | 9 | Heathrow | 19.6
2013-09-14 | 2013 | 9 | Heathrow | 16.2
2013-09-15 | 2013 | 9 | Heathrow | 15.2
2013-09-16 | 2013 | 9 | Heathrow | 14.8
2013-09-17 | 2013 | 9 | Heathrow | 16.3
2013-09-18 | 2013 | 9 | Heathrow | 17.5
2013-09-19 | 2013 | 9 | Heathrow | 19.2
2013-09-20 | 2013 | 9 | Heathrow | 18.9
2013-09-21 | 2013 | 9 | Heathrow | 19.8
2013-09-22 | 2013 | 9 | Heathrow | 18.6
2013-09-23 | 2013 | 9 | Heathrow | 22.2
2013-09-24 | 2013 | 9 | Heathrow | 21.9
2013-09-25 | 2013 | 9 | Heathrow | 20.2
2013-09-26 | 2013 | 9 | Heathrow | 18.7
2013-09-27 | 2013 | 9 | Heathrow | 20.2
2013-09-28 | 2013 | 9 | Heathrow | 19.1
2013-09-29 | 2013 | 9 | Heathrow | 19.1
2013-09-30 | 2013 | 9 | Heathrow | 17.5
2014-05-01 | 2014 | 5 | Heathrow | 12.5
2014-05-02 | 2014 | 5 | Heathrow | 14.5
2014-05-03 | 2014 | 5 | Heathrow | 16.6
2014-05-04 | 2014 | 5 | Heathrow | 18.5
2014-05-05 | 2014 | 5 | Heathrow | 18.8
2014-05-06 | 2014 | 5 | Heathrow | 17.8
2014-05-07 | 2014 | 5 | Heathrow | 15.8
2014-05-08 | 2014 | 5 | Heathrow | 17.8
2014-05-09 | 2014 | 5 | Heathrow | 18.1
2014-05-10 | 2014 | 5 | Heathrow | 14.9
2014-05-11 | 2014 | 5 | Heathrow | 17.9
2014-05-12 | 2014 | 5 | Heathrow | 16.4
2014-05-13 | 2014 | 5 | Heathrow | 19.5
2014-05-14 | 2014 | 5 | Heathrow | 21.5
2014-05-15 | 2014 | 5 | Heathrow | 22.8
2014-05-16 | 2014 | 5 | Heathrow | 23.8
2014-05-17 | 2014 | 5 | Heathrow | 23.5
2014-05-18 | 2014 | 5 | Heathrow | 26.3
2014-05-19 | 2014 | 5 | Heathrow | 20.1
2014-05-20 | 2014 | 5 | Heathrow | 19.3
2014-05-21 | 2014 | 5 | Heathrow | 17.8
2014-05-22 | 2014 | 5 | Heathrow | 17
2014-05-23 | 2014 | 5 | Heathrow | 16.2
2014-05-24 | 2014 | 5 | Heathrow | 18.2
2014-05-25 | 2014 | 5 | Heathrow | 18.2
2014-05-26 | 2014 | 5 | Heathrow | 13.4
2014-05-27 | 2014 | 5 | Heathrow | 16.1
2014-05-28 | 2014 | 5 | Heathrow | 19.6
2014-05-29 | 2014 | 5 | Heathrow | 16.4
2014-05-30 | 2014 | 5 | Heathrow | 19.2
2014-05-31 | 2014 | 5 | Heathrow | 22.2
2014-06-01 | 2014 | 6 | Heathrow | 21.2
2014-06-02 | 2014 | 6 | Heathrow | 19.9
2014-06-03 | 2014 | 6 | Heathrow | 20
2014-06-04 | 2014 | 6 | Heathrow | 19.7
2014-06-05 | 2014 | 6 | Heathrow | 23.6
2014-06-06 | 2014 | 6 | Heathrow | 22.3
2014-06-07 | 2014 | 6 | Heathrow | 24.5
2014-06-08 | 2014 | 6 | Heathrow | 26
2014-06-09 | 2014 | 6 | Heathrow | 22.5
2014-06-10 | 2014 | 6 | Heathrow | 22.4
2014-06-11 | 2014 | 6 | Heathrow | 25
2014-06-12 | 2014 | 6 | Heathrow | 26.1
2014-06-13 | 2014 | 6 | Heathrow | 22.2
2014-06-14 | 2014 | 6 | Heathrow | 18.5
2014-06-15 | 2014 | 6 | Heathrow | 17.8
2014-06-16 | 2014 | 6 | Heathrow | 21.4
2014-06-17 | 2014 | 6 | Heathrow | 22.5
2014-06-18 | 2014 | 6 | Heathrow | 21.5
2014-06-19 | 2014 | 6 | Heathrow | 23.4
2014-06-20 | 2014 | 6 | Heathrow | 24.1
2014-06-21 | 2014 | 6 | Heathrow | 23.9
2014-06-22 | 2014 | 6 | Heathrow | 25.8
2014-06-23 | 2014 | 6 | Heathrow | 24.9
2014-06-24 | 2014 | 6 | Heathrow | 21.3
2014-06-25 | 2014 | 6 | Heathrow | 21.8
2014-06-26 | 2014 | 6 | Heathrow | 23.3
2014-06-27 | 2014 | 6 | Heathrow | 18.8
2014-06-28 | 2014 | 6 | Heathrow | 19.5
2014-06-29 | 2014 | 6 | Heathrow | 21.2
2014-06-30 | 2014 | 6 | Heathrow | 23.3
2014-07-01 | 2014 | 7 | Heathrow | 24.7
2014-07-02 | 2014 | 7 | Heathrow | 27.1
2014-07-03 | 2014 | 7 | Heathrow | 27
2014-07-04 | 2014 | 7 | Heathrow | 21.9
2014-07-05 | 2014 | 7 | Heathrow | 21.9
2014-07-06 | 2014 | 7 | Heathrow | 21.5
2014-07-07 | 2014 | 7 | Heathrow | 20.4
2014-07-08 | 2014 | 7 | Heathrow | 23.4
2014-07-09 | 2014 | 7 | Heathrow | 21.9
2014-07-10 | 2014 | 7 | Heathrow | 21.1
2014-07-11 | 2014 | 7 | Heathrow | 27.7
2014-07-12 | 2014 | 7 | Heathrow | 24.2
2014-07-13 | 2014 | 7 | Heathrow | 25.2
2014-07-14 | 2014 | 7 | Heathrow | 26.5
2014-07-15 | 2014 | 7 | Heathrow | 27.4
2014-07-16 | 2014 | 7 | Heathrow | 29.1
2014-07-17 | 2014 | 7 | Heathrow | 30.3
2014-07-18 | 2014 | 7 | Heathrow | 28.3
2014-07-19 | 2014 | 7 | Heathrow | 26.9
2014-07-20 | 2014 | 7 | Heathrow | 26.9
2014-07-21 | 2014 | 7 | Heathrow | 27.5
2014-07-22 | 2014 | 7 | Heathrow | 29.8
2014-07-23 | 2014 | 7 | Heathrow | 29.6
2014-07-24 | 2014 | 7 | Heathrow | 27.3
2014-07-25 | 2014 | 7 | Heathrow | 29.1
2014-07-26 | 2014 | 7 | Heathrow | 26.2
2014-07-27 | 2014 | 7 | Heathrow | 23.5
2014-07-28 | 2014 | 7 | Heathrow | 27.2
2014-07-29 | 2014 | 7 | Heathrow | 26.4
2014-07-30 | 2014 | 7 | Heathrow | 25.5
2014-07-31 | 2014 | 7 | Heathrow | 25.4
2014-08-01 | 2014 | 8 | Heathrow | 24.6
2014-08-02 | 2014 | 8 | Heathrow | 24.2
2014-08-03 | 2014 | 8 | Heathrow | 24.3
2014-08-04 | 2014 | 8 | Heathrow | 25.1
2014-08-05 | 2014 | 8 | Heathrow | 26.4
2014-08-06 | 2014 | 8 | Heathrow | 26.1
2014-08-07 | 2014 | 8 | Heathrow | 23.7
2014-08-08 | 2014 | 8 | Heathrow | 23.7
2014-08-09 | 2014 | 8 | Heathrow | 22.6
2014-08-10 | 2014 | 8 | Heathrow | 21.9
2014-08-11 | 2014 | 8 | Heathrow | 20.7
2014-08-12 | 2014 | 8 | Heathrow | 22.7
2014-08-13 | 2014 | 8 | Heathrow | 21.6
2014-08-14 | 2014 | 8 | Heathrow | 20.7
2014-08-15 | 2014 | 8 | Heathrow | 21.8
2014-08-16 | 2014 | 8 | Heathrow | 21.5
2014-08-17 | 2014 | 8 | Heathrow | 20.2
2014-08-18 | 2014 | 8 | Heathrow | 18.9
2014-08-19 | 2014 | 8 | Heathrow | 19
2014-08-20 | 2014 | 8 | Heathrow | 18.1
2014-08-21 | 2014 | 8 | Heathrow | 20.7
2014-08-22 | 2014 | 8 | Heathrow | 19.5
2014-08-23 | 2014 | 8 | Heathrow | 19
2014-08-24 | 2014 | 8 | Heathrow | 17.4
2014-08-25 | 2014 | 8 | Heathrow | 17.1
2014-08-26 | 2014 | 8 | Heathrow | 20
2014-08-27 | 2014 | 8 | Heathrow | 22.8
2014-08-28 | 2014 | 8 | Heathrow | 21.5
2014-08-29 | 2014 | 8 | Heathrow | 20.2
2014-08-30 | 2014 | 8 | Heathrow | 21.7
2014-08-31 | 2014 | 8 | Heathrow | 19.2
2014-09-01 | 2014 | 9 | Heathrow | 22.9
2014-09-02 | 2014 | 9 | Heathrow | 23.6
2014-09-03 | 2014 | 9 | Heathrow | 21.3
2014-09-04 | 2014 | 9 | Heathrow | 20.7
2014-09-05 | 2014 | 9 | Heathrow | 21.8
2014-09-06 | 2014 | 9 | Heathrow | 21.6
2014-09-07 | 2014 | 9 | Heathrow | 22.5
2014-09-08 | 2014 | 9 | Heathrow | 22.4
2014-09-09 | 2014 | 9 | Heathrow | 21.2
2014-09-10 | 2014 | 9 | Heathrow | 18.5
2014-09-11 | 2014 | 9 | Heathrow | 23.5
2014-09-12 | 2014 | 9 | Heathrow | 21.3
2014-09-13 | 2014 | 9 | Heathrow | 21.4
2014-09-14 | 2014 | 9 | Heathrow | 22.1
2014-09-15 | 2014 | 9 | Heathrow | 23.8
2014-09-16 | 2014 | 9 | Heathrow | 20.7
2014-09-17 | 2014 | 9 | Heathrow | 25.8
2014-09-18 | 2014 | 9 | Heathrow | 24.5
2014-09-19 | 2014 | 9 | Heathrow | 24.6
2014-09-20 | 2014 | 9 | Heathrow | 18.6
2014-09-21 | 2014 | 9 | Heathrow | 19.3
2014-09-22 | 2014 | 9 | Heathrow | 19.1
2014-09-23 | 2014 | 9 | Heathrow | 19
2014-09-24 | 2014 | 9 | Heathrow | 19.8
2014-09-25 | 2014 | 9 | Heathrow | 22.2
2014-09-26 | 2014 | 9 | Heathrow | 21.3
2014-09-27 | 2014 | 9 | Heathrow | 24.7
2014-09-28 | 2014 | 9 | Heathrow | 24.7
2014-09-29 | 2014 | 9 | Heathrow | 22.7
2014-09-30 | 2014 | 9 | Heathrow | 21.6
2015-05-01 | 2015 | 5 | Heathrow | 15.7
2015-05-02 | 2015 | 5 | Heathrow | 20.3
2015-05-03 | 2015 | 5 | Heathrow | 18.9
2015-05-04 | 2015 | 5 | Heathrow | 16.4
2015-05-05 | 2015 | 5 | Heathrow | 14.8
2015-05-06 | 2015 | 5 | Heathrow | 17.6
2015-05-07 | 2015 | 5 | Heathrow | 16.7
2015-05-08 | 2015 | 5 | Heathrow | 19.3
2015-05-09 | 2015 | 5 | Heathrow | 19.4
2015-05-10 | 2015 | 5 | Heathrow | 21.6
2015-05-11 | 2015 | 5 | Heathrow | 18.2
2015-05-12 | 2015 | 5 | Heathrow | 20.1
2015-05-13 | 2015 | 5 | Heathrow | 20.1
2015-05-14 | 2015 | 5 | Heathrow | 15.6
2015-05-15 | 2015 | 5 | Heathrow | 18.8
2015-05-16 | 2015 | 5 | Heathrow | 17.7
2015-05-17 | 2015 | 5 | Heathrow | 15.8
2015-05-18 | 2015 | 5 | Heathrow | 14.7
2015-05-19 | 2015 | 5 | Heathrow | 16
2015-05-20 | 2015 | 5 | Heathrow | 20.4
2015-05-21 | 2015 | 5 | Heathrow | 19.6
2015-05-22 | 2015 | 5 | Heathrow | 17.7
2015-05-23 | 2015 | 5 | Heathrow | 20
2015-05-24 | 2015 | 5 | Heathrow | 16.7
2015-05-25 | 2015 | 5 | Heathrow | 19.7
2015-05-26 | 2015 | 5 | Heathrow | 20.3
2015-05-27 | 2015 | 5 | Heathrow | 18.1
2015-05-28 | 2015 | 5 | Heathrow | 18.1
2015-05-29 | 2015 | 5 | Heathrow | 18.6
2015-05-30 | 2015 | 5 | Heathrow | 16.3
2015-05-31 | 2015 | 5 | Heathrow | 16.5
2015-06-01 | 2015 | 6 | Heathrow | 20.1
2015-06-02 | 2015 | 6 | Heathrow | 20.4
2015-06-03 | 2015 | 6 | Heathrow | 23.6
2015-06-04 | 2015 | 6 | Heathrow | 24.4
2015-06-05 | 2015 | 6 | Heathrow | 20.5
2015-06-06 | 2015 | 6 | Heathrow | 20.4
2015-06-07 | 2015 | 6 | Heathrow | 18.9
2015-06-08 | 2015 | 6 | Heathrow | 15.7
2015-06-09 | 2015 | 6 | Heathrow | 19.2
2015-06-10 | 2015 | 6 | Heathrow | 24.7
2015-06-11 | 2015 | 6 | Heathrow | 25.4
2015-06-12 | 2015 | 6 | Heathrow | 20
2015-06-13 | 2015 | 6 | Heathrow | 18.1
2015-06-14 | 2015 | 6 | Heathrow | 20.7
2015-06-15 | 2015 | 6 | Heathrow | 24.5
2015-06-16 | 2015 | 6 | Heathrow | 26.1
2015-06-17 | 2015 | 6 | Heathrow | 22.1
2015-06-18 | 2015 | 6 | Heathrow | 22.1
2015-06-19 | 2015 | 6 | Heathrow | 20.4
2015-06-20 | 2015 | 6 | Heathrow | 21.2
2015-06-21 | 2015 | 6 | Heathrow | 18.4
2015-06-22 | 2015 | 6 | Heathrow | 21.3
2015-06-23 | 2015 | 6 | Heathrow | 24.4
2015-06-24 | 2015 | 6 | Heathrow | 25.2
2015-06-25 | 2015 | 6 | Heathrow | 27.7
2015-06-26 | 2015 | 6 | Heathrow | 25.1
2015-06-27 | 2015 | 6 | Heathrow | 21.4
2015-06-28 | 2015 | 6 | Heathrow | 25.9
2015-06-29 | 2015 | 6 | Heathrow | 32.5
2015-06-30 | 2015 | 6 | Heathrow | 36.7
2015-07-01 | 2015 | 7 | Heathrow | 36.7
2015-07-02 | 2015 | 7 | Heathrow | 27.2
2015-07-03 | 2015 | 7 | Heathrow | 27.2
2015-07-04 | 2015 | 7 | Heathrow | 24.7
2015-07-05 | 2015 | 7 | Heathrow | 23.7
2015-07-06 | 2015 | 7 | Heathrow | 24.3
2015-07-07 | 2015 | 7 | Heathrow | 21.5
2015-07-08 | 2015 | 7 | Heathrow | 23.1
2015-07-09 | 2015 | 7 | Heathrow | 26.7
2015-07-10 | 2015 | 7 | Heathrow | 26
2015-07-11 | 2015 | 7 | Heathrow | 22.6
2015-07-12 | 2015 | 7 | Heathrow | 20.8
2015-07-13 | 2015 | 7 | Heathrow | 22.9
2015-07-14 | 2015 | 7 | Heathrow | 22.5
2015-07-15 | 2015 | 7 | Heathrow | 25.3
2015-07-16 | 2015 | 7 | Heathrow | 25.1
2015-07-17 | 2015 | 7 | Heathrow | 23.6
2015-07-18 | 2015 | 7 | Heathrow | 24.9
2015-07-19 | 2015 | 7 | Heathrow | 24.7
2015-07-20 | 2015 | 7 | Heathrow | 26.5
2015-07-21 | 2015 | 7 | Heathrow | 23
2015-07-22 | 2015 | 7 | Heathrow | 22.4
2015-07-23 | 2015 | 7 | Heathrow | 22.5
2015-07-24 | 2015 | 7 | Heathrow | 21.7
2015-07-25 | 2015 | 7 | Heathrow | 19.1
2015-07-26 | 2015 | 7 | Heathrow | 20.9
2015-07-27 | 2015 | 7 | Heathrow | 20.8
2015-07-28 | 2015 | 7 | Heathrow | 20.3
2015-07-29 | 2015 | 7 | Heathrow | 20.3
2015-07-30 | 2015 | 7 | Heathrow | 22.7
2015-07-31 | 2015 | 7 | Heathrow | 21.5
2015-08-01 | 2015 | 8 | Heathrow | 26.2
2015-08-02 | 2015 | 8 | Heathrow | 25.1
2015-08-03 | 2015 | 8 | Heathrow | 22.4
2015-08-04 | 2015 | 8 | Heathrow | 22
2015-08-05 | 2015 | 8 | Heathrow | 23.9
2015-08-06 | 2015 | 8 | Heathrow | 24.8
2015-08-07 | 2015 | 8 | Heathrow | 26.6
2015-08-08 | 2015 | 8 | Heathrow | 26.6
2015-08-09 | 2015 | 8 | Heathrow | 22.7
2015-08-10 | 2015 | 8 | Heathrow | 21.3
2015-08-11 | 2015 | 8 | Heathrow | 23.4
2015-08-12 | 2015 | 8 | Heathrow | 20.3
2015-08-13 | 2015 | 8 | Heathrow | 21.3
2015-08-14 | 2015 | 8 | Heathrow | 20.7
2015-08-15 | 2015 | 8 | Heathrow | 20.8
2015-08-16 | 2015 | 8 | Heathrow | 22.1
2015-08-17 | 2015 | 8 | Heathrow | 19.5
2015-08-18 | 2015 | 8 | Heathrow | 20.9
2015-08-19 | 2015 | 8 | Heathrow | 21.1
2015-08-20 | 2015 | 8 | Heathrow | 26.5
2015-08-21 | 2015 | 8 | Heathrow | 30.7
2015-08-22 | 2015 | 8 | Heathrow | 30.7
2015-08-23 | 2015 | 8 | Heathrow | 22.1
2015-08-24 | 2015 | 8 | Heathrow | 19
2015-08-25 | 2015 | 8 | Heathrow | 19.9
2015-08-26 | 2015 | 8 | Heathrow | 19.6
2015-08-27 | 2015 | 8 | Heathrow | 21.1
2015-08-28 | 2015 | 8 | Heathrow | 22.3
2015-08-29 | 2015 | 8 | Heathrow | 20.8
2015-08-30 | 2015 | 8 | Heathrow | 20.9
2015-08-31 | 2015 | 8 | Heathrow | 19.2
2015-09-01 | 2015 | 9 | Heathrow | 19
2015-09-02 | 2015 | 9 | Heathrow | 16.4
2015-09-03 | 2015 | 9 | Heathrow | 16.6
2015-09-04 | 2015 | 9 | Heathrow | 16.3
2015-09-05 | 2015 | 9 | Heathrow | 19.9
2015-09-06 | 2015 | 9 | Heathrow | 19.3
2015-09-07 | 2015 | 9 | Heathrow | 16.5
2015-09-08 | 2015 | 9 | Heathrow | 19.7
2015-09-09 | 2015 | 9 | Heathrow | 21.2
2015-09-10 | 2015 | 9 | Heathrow | 22.3
2015-09-11 | 2015 | 9 | Heathrow | 21.5
2015-09-12 | 2015 | 9 | Heathrow | 20
2015-09-13 | 2015 | 9 | Heathrow | 19.8
2015-09-14 | 2015 | 9 | Heathrow | 19.9
2015-09-15 | 2015 | 9 | Heathrow | 16
2015-09-16 | 2015 | 9 | Heathrow | 18.5
2015-09-17 | 2015 | 9 | Heathrow | 19.5
2015-09-18 | 2015 | 9 | Heathrow | 19.6
2015-09-19 | 2015 | 9 | Heathrow | 20.2
2015-09-20 | 2015 | 9 | Heathrow | 14.8
2015-09-21 | 2015 | 9 | Heathrow | 15.3
2015-09-22 | 2015 | 9 | Heathrow | 17.4
2015-09-23 | 2015 | 9 | Heathrow | 18.7
2015-09-24 | 2015 | 9 | Heathrow | 17.9
2015-09-25 | 2015 | 9 | Heathrow | 18
2015-09-26 | 2015 | 9 | Heathrow | 19.3
2015-09-27 | 2015 | 9 | Heathrow | 18.4
2015-09-28 | 2015 | 9 | Heathrow | 19.1
2015-09-29 | 2015 | 9 | Heathrow | 18.7
2015-09-30 | 2015 | 9 | Heathrow | 18.8
2016-05-01 | 2016 | 5 | Heathrow | 18.4
2016-05-02 | 2016 | 5 | Heathrow | 15.7
2016-05-03 | 2016 | 5 | Heathrow | 17.4
2016-05-04 | 2016 | 5 | Heathrow | 20.7
2016-05-05 | 2016 | 5 | Heathrow | 23.5
2016-05-06 | 2016 | 5 | Heathrow | 23.9
2016-05-07 | 2016 | 5 | Heathrow | 26.8
2016-05-08 | 2016 | 5 | Heathrow | 24.9
2016-05-09 | 2016 | 5 | Heathrow | 25
2016-05-10 | 2016 | 5 | Heathrow | 18.9
2016-05-11 | 2016 | 5 | Heathrow | 24.3
2016-05-12 | 2016 | 5 | Heathrow | 24.4
2016-05-13 | 2016 | 5 | Heathrow | 14.6
2016-05-14 | 2016 | 5 | Heathrow | 17.4
2016-05-15 | 2016 | 5 | Heathrow | 18.1
2016-05-16 | 2016 | 5 | Heathrow | 17.8
2016-05-17 | 2016 | 5 | Heathrow | 14.2
2016-05-18 | 2016 | 5 | Heathrow | 19
2016-05-19 | 2016 | 5 | Heathrow | 19.2
2016-05-20 | 2016 | 5 | Heathrow | 18.3
2016-05-21 | 2016 | 5 | Heathrow | 18.8
2016-05-22 | 2016 | 5 | Heathrow | 19.7
2016-05-23 | 2016 | 5 | Heathrow | 17.2
2016-05-24 | 2016 | 5 | Heathrow | 14.7
2016-05-25 | 2016 | 5 | Heathrow | 21.2
2016-05-26 | 2016 | 5 | Heathrow | 22.2
2016-05-27 | 2016 | 5 | Heathrow | 21
2016-05-28 | 2016 | 5 | Heathrow | 19.2
2016-05-29 | 2016 | 5 | Heathrow | 18
2016-05-30 | 2016 | 5 | Heathrow | 18.1
2016-05-31 | 2016 | 5 | Heathrow | 13.8
2016-06-01 | 2016 | 6 | Heathrow | 13.7
2016-06-02 | 2016 | 6 | Heathrow | 14.5
2016-06-03 | 2016 | 6 | Heathrow | 19.2
2016-06-04 | 2016 | 6 | Heathrow | 24.2
2016-06-05 | 2016 | 6 | Heathrow | 25
2016-06-06 | 2016 | 6 | Heathrow | 24.4
2016-06-07 | 2016 | 6 | Heathrow | 25.9
2016-06-08 | 2016 | 6 | Heathrow | 23.2
2016-06-09 | 2016 | 6 | Heathrow | 24
2016-06-10 | 2016 | 6 | Heathrow | 22.5
2016-06-11 | 2016 | 6 | Heathrow | 21.5
2016-06-12 | 2016 | 6 | Heathrow | 19.2
2016-06-13 | 2016 | 6 | Heathrow | 19.1
2016-06-14 | 2016 | 6 | Heathrow | 20.5
2016-06-15 | 2016 | 6 | Heathrow | 18
2016-06-16 | 2016 | 6 | Heathrow | 20.3
2016-06-17 | 2016 | 6 | Heathrow | 17.7
2016-06-18 | 2016 | 6 | Heathrow | 20.2
2016-06-19 | 2016 | 6 | Heathrow | 22.7
2016-06-20 | 2016 | 6 | Heathrow | 21.7
2016-06-21 | 2016 | 6 | Heathrow | 22.5
2016-06-22 | 2016 | 6 | Heathrow | 21.1
2016-06-23 | 2016 | 6 | Heathrow | 22.6
2016-06-24 | 2016 | 6 | Heathrow | 20.3
2016-06-25 | 2016 | 6 | Heathrow | 21.2
2016-06-26 | 2016 | 6 | Heathrow | 21.7
2016-06-27 | 2016 | 6 | Heathrow | 21.4
2016-06-28 | 2016 | 6 | Heathrow | 17.2
2016-06-29 | 2016 | 6 | Heathrow | 20.5
2016-06-30 | 2016 | 6 | Heathrow | 19.9
2016-07-01 | 2016 | 7 | Heathrow | 20.6
2016-07-02 | 2016 | 7 | Heathrow | 21.6
2016-07-03 | 2016 | 7 | Heathrow | 21.3
2016-07-04 | 2016 | 7 | Heathrow | 21.6
2016-07-05 | 2016 | 7 | Heathrow | 22.6
2016-07-06 | 2016 | 7 | Heathrow | 23.6
2016-07-07 | 2016 | 7 | Heathrow | 23.1
2016-07-08 | 2016 | 7 | Heathrow | 23.2
2016-07-09 | 2016 | 7 | Heathrow | 23.5
2016-07-10 | 2016 | 7 | Heathrow | 22
2016-07-11 | 2016 | 7 | Heathrow | 19.2
2016-07-12 | 2016 | 7 | Heathrow | 20
2016-07-13 | 2016 | 7 | Heathrow | 22
2016-07-14 | 2016 | 7 | Heathrow | 21.1
2016-07-15 | 2016 | 7 | Heathrow | 27
2016-07-16 | 2016 | 7 | Heathrow | 27.6
2016-07-17 | 2016 | 7 | Heathrow | 29.4
2016-07-18 | 2016 | 7 | Heathrow | 33.2
2016-07-19 | 2016 | 7 | Heathrow | 31.4
2016-07-20 | 2016 | 7 | Heathrow | 31.5
2016-07-21 | 2016 | 7 | Heathrow | 23.9
2016-07-22 | 2016 | 7 | Heathrow | 28.6
2016-07-23 | 2016 | 7 | Heathrow | 25.8
2016-07-24 | 2016 | 7 | Heathrow | 24.7
2016-07-25 | 2016 | 7 | Heathrow | 23.1
2016-07-26 | 2016 | 7 | Heathrow | 25.6
2016-07-27 | 2016 | 7 | Heathrow | 23.1
2016-07-28 | 2016 | 7 | Heathrow | 23.5
2016-07-29 | 2016 | 7 | Heathrow | 22.4
2016-07-30 | 2016 | 7 | Heathrow | 22.4
2016-07-31 | 2016 | 7 | Heathrow | 19.2
2016-08-01 | 2016 | 8 | Heathrow | 21.9
2016-08-02 | 2016 | 8 | Heathrow | 24.7
2016-08-03 | 2016 | 8 | Heathrow | 23.5
2016-08-04 | 2016 | 8 | Heathrow | 24.1
2016-08-05 | 2016 | 8 | Heathrow | 26.4
2016-08-06 | 2016 | 8 | Heathrow | 27.3
2016-08-07 | 2016 | 8 | Heathrow | 22.3
2016-08-08 | 2016 | 8 | Heathrow | 20.8
2016-08-09 | 2016 | 8 | Heathrow | 20.4
2016-08-10 | 2016 | 8 | Heathrow | 24.5
2016-08-11 | 2016 | 8 | Heathrow | 27.7
2016-08-12 | 2016 | 8 | Heathrow | 25.8
2016-08-13 | 2016 | 8 | Heathrow | 22.9
2016-08-14 | 2016 | 8 | Heathrow | 24.7
2016-08-15 | 2016 | 8 | Heathrow | 25
2016-08-16 | 2016 | 8 | Heathrow | 26.7
2016-08-17 | 2016 | 8 | Heathrow | 25.5
2016-08-18 | 2016 | 8 | Heathrow | 25.6
2016-08-19 | 2016 | 8 | Heathrow | 21.9
2016-08-20 | 2016 | 8 | Heathrow | 23.5
2016-08-21 | 2016 | 8 | Heathrow | 26
2016-08-22 | 2016 | 8 | Heathrow | 31
2016-08-23 | 2016 | 8 | Heathrow | 33.1
2016-08-24 | 2016 | 8 | Heathrow | 27.6
2016-08-25 | 2016 | 8 | Heathrow | 27
2016-08-26 | 2016 | 8 | Heathrow | 26.5
2016-08-27 | 2016 | 8 | Heathrow | 21.5
2016-08-28 | 2016 | 8 | Heathrow | 24.3
2016-08-29 | 2016 | 8 | Heathrow | 27
2016-08-30 | 2016 | 8 | Heathrow | 24.8
2016-08-31 | 2016 | 8 | Heathrow | 24.8
2016-09-01 | 2016 | 9 | Heathrow | 20.2
2016-09-02 | 2016 | 9 | Heathrow | 21.5
2016-09-03 | 2016 | 9 | Heathrow | 20.9
2016-09-04 | 2016 | 9 | Heathrow | 22.9
2016-09-05 | 2016 | 9 | Heathrow | 23.9
2016-09-06 | 2016 | 9 | Heathrow | 28.4
2016-09-07 | 2016 | 9 | Heathrow | 23.9
2016-09-08 | 2016 | 9 | Heathrow | 24.3
2016-09-09 | 2016 | 9 | Heathrow | 24.4
2016-09-10 | 2016 | 9 | Heathrow | 22
2016-09-11 | 2016 | 9 | Heathrow | 25.8
2016-09-12 | 2016 | 9 | Heathrow | 32.8
2016-09-13 | 2016 | 9 | Heathrow | 27.8
2016-09-14 | 2016 | 9 | Heathrow | 29.4
2016-09-15 | 2016 | 9 | Heathrow | 29.5
2016-09-16 | 2016 | 9 | Heathrow | 17.9
2016-09-17 | 2016 | 9 | Heathrow | 20.6
2016-09-18 | 2016 | 9 | Heathrow | 19.6
2016-09-19 | 2016 | 9 | Heathrow | 19
2016-09-20 | 2016 | 9 | Heathrow | 22.1
2016-09-21 | 2016 | 9 | Heathrow | 20.8
2016-09-22 | 2016 | 9 | Heathrow | 20.7
2016-09-23 | 2016 | 9 | Heathrow | 23.2
2016-09-24 | 2016 | 9 | Heathrow | 21
2016-09-25 | 2016 | 9 | Heathrow | 18.7
2016-09-26 | 2016 | 9 | Heathrow | 19.6
2016-09-27 | 2016 | 9 | Heathrow | 23.2
2016-09-28 | 2016 | 9 | Heathrow | 20.3
2016-09-29 | 2016 | 9 | Heathrow | 19.7
2016-09-30 | 2016 | 9 | Heathrow | 16.1
2017-05-01 | 2017 | 5 | Heathrow | 18.4
2017-05-02 | 2017 | 5 | Heathrow | 18.5
2017-05-03 | 2017 | 5 | Heathrow | 14.9
2017-05-04 | 2017 | 5 | Heathrow | 16.9
2017-05-05 | 2017 | 5 | Heathrow | 15.5
2017-05-06 | 2017 | 5 | Heathrow | 18.7
2017-05-07 | 2017 | 5 | Heathrow | 18.7
2017-05-08 | 2017 | 5 | Heathrow | 14.9
2017-05-09 | 2017 | 5 | Heathrow | 19.2
2017-05-10 | 2017 | 5 | Heathrow | 22.5
2017-05-11 | 2017 | 5 | Heathrow | 20
2017-05-12 | 2017 | 5 | Heathrow | 19.6
2017-05-13 | 2017 | 5 | Heathrow | 20.9
2017-05-14 | 2017 | 5 | Heathrow | 20.9
2017-05-15 | 2017 | 5 | Heathrow | 25
2017-05-16 | 2017 | 5 | Heathrow | 25.1
2017-05-17 | 2017 | 5 | Heathrow | 16.5
2017-05-18 | 2017 | 5 | Heathrow | 16.2
2017-05-19 | 2017 | 5 | Heathrow | 16.7
2017-05-20 | 2017 | 5 | Heathrow | 20.7
2017-05-21 | 2017 | 5 | Heathrow | 24.9
2017-05-22 | 2017 | 5 | Heathrow | 21.3
2017-05-23 | 2017 | 5 | Heathrow | 26.3
2017-05-24 | 2017 | 5 | Heathrow | 27
2017-05-25 | 2017 | 5 | Heathrow | 27.8
2017-05-26 | 2017 | 5 | Heathrow | 24
2017-05-27 | 2017 | 5 | Heathrow | 23.9
2017-05-28 | 2017 | 5 | Heathrow | 20.7
2017-05-29 | 2017 | 5 | Heathrow | 20.8
2017-05-30 | 2017 | 5 | Heathrow | 23
2017-05-31 | 2017 | 5 | Heathrow | 25.5
2017-06-01 | 2017 | 6 | Heathrow | 24.8
2017-06-02 | 2017 | 6 | Heathrow | 21.5
2017-06-03 | 2017 | 6 | Heathrow | 20.3
2017-06-04 | 2017 | 6 | Heathrow | 18.7
2017-06-05 | 2017 | 6 | Heathrow | 17.7
2017-06-06 | 2017 | 6 | Heathrow | 20.9
2017-06-07 | 2017 | 6 | Heathrow | 18
2017-06-08 | 2017 | 6 | Heathrow | 21.2
2017-06-09 | 2017 | 6 | Heathrow | 23.8
2017-06-10 | 2017 | 6 | Heathrow | 23.9
2017-06-11 | 2017 | 6 | Heathrow | 20.9
2017-06-12 | 2017 | 6 | Heathrow | 24.8
2017-06-13 | 2017 | 6 | Heathrow | 27.1
2017-06-14 | 2017 | 6 | Heathrow | 25.1
2017-06-15 | 2017 | 6 | Heathrow | 24.3
2017-06-16 | 2017 | 6 | Heathrow | 30.1
2017-06-17 | 2017 | 6 | Heathrow | 31.7
2017-06-18 | 2017 | 6 | Heathrow | 32
2017-06-19 | 2017 | 6 | Heathrow | 31.4
2017-06-20 | 2017 | 6 | Heathrow | 34.5
2017-06-22 | 2017 | 6 | Heathrow | 24.9
2017-06-23 | 2017 | 6 | Heathrow | 24.1
2017-06-24 | 2017 | 6 | Heathrow | 24.2
2017-06-25 | 2017 | 6 | Heathrow | 24.5
2017-06-26 | 2017 | 6 | Heathrow | 21.2
2017-06-27 | 2017 | 6 | Heathrow | 21.2
2017-06-28 | 2017 | 6 | Heathrow | 18.7
2017-06-29 | 2017 | 6 | Heathrow | 22
2017-06-30 | 2017 | 6 | Heathrow | 23.3
2017-07-01 | 2017 | 7 | Heathrow | 23.6
2017-07-02 | 2017 | 7 | Heathrow | 25.1
2017-07-03 | 2017 | 7 | Heathrow | 24.6
2017-07-04 | 2017 | 7 | Heathrow | 29.5
2017-07-05 | 2017 | 7 | Heathrow | 32.2
2017-07-06 | 2017 | 7 | Heathrow | 30.1
2017-07-07 | 2017 | 7 | Heathrow | 26.7
2017-07-08 | 2017 | 7 | Heathrow | 28.4
2017-07-09 | 2017 | 7 | Heathrow | 26.4
2017-07-10 | 2017 | 7 | Heathrow | 26.5
2017-07-11 | 2017 | 7 | Heathrow | 22.4
2017-07-12 | 2017 | 7 | Heathrow | 23.2
2017-07-13 | 2017 | 7 | Heathrow | 21.8
2017-07-14 | 2017 | 7 | Heathrow | 22.5
2017-07-15 | 2017 | 7 | Heathrow | 25.4
2017-07-16 | 2017 | 7 | Heathrow | 26.9
2017-07-17 | 2017 | 7 | Heathrow | 26.9
2017-07-18 | 2017 | 7 | Heathrow | 22.7
2017-07-19 | 2017 | 7 | Heathrow | 21.6
2017-07-20 | 2017 | 7 | Heathrow | 22.8
2017-07-21 | 2017 | 7 | Heathrow | 19.2
2017-07-22 | 2017 | 7 | Heathrow | 20.6
2017-07-23 | 2017 | 7 | Heathrow | 19.4
2017-07-24 | 2017 | 7 | Heathrow | 22.9
2017-07-25 | 2017 | 7 | Heathrow | 22.1
2017-07-26 | 2017 | 7 | Heathrow | 22.2
2017-07-27 | 2017 | 7 | Heathrow | 22.2
2017-07-28 | 2017 | 7 | Heathrow | 20.4
2017-07-29 | 2017 | 7 | Heathrow | 21.5
2017-07-30 | 2017 | 7 | Heathrow | 22.7
2017-07-31 | 2017 | 7 | Heathrow | 22.4
2017-08-01 | 2017 | 8 | Heathrow | 19.3
2017-08-02 | 2017 | 8 | Heathrow | 21.8
2017-08-03 | 2017 | 8 | Heathrow | 22.9
2017-08-04 | 2017 | 8 | Heathrow | 20.8
2017-08-05 | 2017 | 8 | Heathrow | 22.8
2017-08-06 | 2017 | 8 | Heathrow | 21.1
2017-08-07 | 2017 | 8 | Heathrow | 21.1
2017-08-08 | 2017 | 8 | Heathrow | 16.1
2017-08-09 | 2017 | 8 | Heathrow | 21
2017-08-10 | 2017 | 8 | Heathrow | 22.6
2017-08-11 | 2017 | 8 | Heathrow | 22.5
2017-08-12 | 2017 | 8 | Heathrow | 22.7
2017-08-13 | 2017 | 8 | Heathrow | 23.5
2017-08-14 | 2017 | 8 | Heathrow | 24.2
2017-08-15 | 2017 | 8 | Heathrow | 23.6
2017-08-16 | 2017 | 8 | Heathrow | 24.8
2017-08-17 | 2017 | 8 | Heathrow | 20.3
2017-08-18 | 2017 | 8 | Heathrow | 20.8
2017-08-19 | 2017 | 8 | Heathrow | 21.5
2017-08-20 | 2017 | 8 | Heathrow | 19.7
2017-08-21 | 2017 | 8 | Heathrow | 23.1
2017-08-22 | 2017 | 8 | Heathrow | 22.4
2017-08-23 | 2017 | 8 | Heathrow | 21.5
2017-08-24 | 2017 | 8 | Heathrow | 24
2017-08-25 | 2017 | 8 | Heathrow | 24.7
2017-08-26 | 2017 | 8 | Heathrow | 26.3
2017-08-27 | 2017 | 8 | Heathrow | 27.7
2017-08-28 | 2017 | 8 | Heathrow | 26.1
2017-08-29 | 2017 | 8 | Heathrow | 26.1
2017-08-30 | 2017 | 8 | Heathrow | 20.3
2017-08-31 | 2017 | 8 | Heathrow | 21.9
2017-09-01 | 2017 | 9 | Heathrow | 22
2017-09-02 | 2017 | 9 | Heathrow | 18.1
2017-09-03 | 2017 | 9 | Heathrow | 22.6
2017-09-04 | 2017 | 9 | Heathrow | 21.3
2017-09-05 | 2017 | 9 | Heathrow | 19.4
2017-09-06 | 2017 | 9 | Heathrow | 19.9
2017-09-07 | 2017 | 9 | Heathrow | 19.6
2017-09-08 | 2017 | 9 | Heathrow | 18.6
2017-09-09 | 2017 | 9 | Heathrow | 17.4
2017-09-10 | 2017 | 9 | Heathrow | 19.8
2017-09-11 | 2017 | 9 | Heathrow | 19.6
2017-09-12 | 2017 | 9 | Heathrow | 19
2017-09-13 | 2017 | 9 | Heathrow | 18.1
2017-09-14 | 2017 | 9 | Heathrow | 16.8
2017-09-15 | 2017 | 9 | Heathrow | 15.9
2017-09-16 | 2017 | 9 | Heathrow | 17.3
2017-09-17 | 2017 | 9 | Heathrow | 17.4
2017-09-18 | 2017 | 9 | Heathrow | 16.3
2017-09-19 | 2017 | 9 | Heathrow | 18.3
2017-09-20 | 2017 | 9 | Heathrow | 18
2017-09-21 | 2017 | 9 | Heathrow | 19
2017-09-22 | 2017 | 9 | Heathrow | 19.5
2017-09-23 | 2017 | 9 | Heathrow | 22.8
2017-09-24 | 2017 | 9 | Heathrow | 18.2
2017-09-25 | 2017 | 9 | Heathrow | 21.1
2017-09-26 | 2017 | 9 | Heathrow | 20.9
2017-09-27 | 2017 | 9 | Heathrow | 20.5
2017-09-28 | 2017 | 9 | Heathrow | 18.9
2017-09-29 | 2017 | 9 | Heathrow | 17.6
2017-09-30 | 2017 | 9 | Heathrow | 18.4
2018-05-01 | 2018 | 5 | Heathrow | 15
2018-05-02 | 2018 | 5 | Heathrow | 18.1
2018-05-03 | 2018 | 5 | Heathrow | 20
2018-05-04 | 2018 | 5 | Heathrow | 22.8
2018-05-05 | 2018 | 5 | Heathrow | 26.3
2018-05-06 | 2018 | 5 | Heathrow | 28.1
2018-05-07 | 2018 | 5 | Heathrow | 26.5
2018-05-08 | 2018 | 5 | Heathrow | 20.8
2018-05-09 | 2018 | 5 | Heathrow | 18
2018-05-10 | 2018 | 5 | Heathrow | 18
2018-05-11 | 2018 | 5 | Heathrow | 15
2018-05-12 | 2018 | 5 | Heathrow | 18.6
2018-05-13 | 2018 | 5 | Heathrow | 21
2018-05-14 | 2018 | 5 | Heathrow | 23.2
2018-05-15 | 2018 | 5 | Heathrow | 23.2
2018-05-16 | 2018 | 5 | Heathrow | 18
2018-05-17 | 2018 | 5 | Heathrow | 18.7
2018-05-18 | 2018 | 5 | Heathrow | 22.2
2018-05-19 | 2018 | 5 | Heathrow | 22
2018-05-20 | 2018 | 5 | Heathrow | 22.7
2018-05-21 | 2018 | 5 | Heathrow | 23.5
2018-05-22 | 2018 | 5 | Heathrow | 19.1
2018-05-23 | 2018 | 5 | Heathrow | 19.3
2018-05-24 | 2018 | 5 | Heathrow | 18.8
2018-05-25 | 2018 | 5 | Heathrow | 26.6
2018-05-26 | 2018 | 5 | Heathrow | 27.4
2018-05-27 | 2018 | 5 | Heathrow | 24.8
2018-05-28 | 2018 | 5 | Heathrow | 24.9
2018-05-29 | 2018 | 5 | Heathrow | 19.4
2018-05-30 | 2018 | 5 | Heathrow | 23.5
2018-05-31 | 2018 | 5 | Heathrow | 24
2018-06-01 | 2018 | 6 | Heathrow | 24.4
2018-06-02 | 2018 | 6 | Heathrow | 27
2018-06-03 | 2018 | 6 | Heathrow | 27.1
2018-06-04 | 2018 | 6 | Heathrow | 18.8
2018-06-05 | 2018 | 6 | Heathrow | 23
2018-06-06 | 2018 | 6 | Heathrow | 21.4
2018-06-07 | 2018 | 6 | Heathrow | 23
2018-06-08 | 2018 | 6 | Heathrow | 21.9
2018-06-09 | 2018 | 6 | Heathrow | 24
2018-06-10 | 2018 | 6 | Heathrow | 25.4
2018-06-11 | 2018 | 6 | Heathrow | 25.5
2018-06-12 | 2018 | 6 | Heathrow | 23.3
2018-06-13 | 2018 | 6 | Heathrow | 23.9
2018-06-14 | 2018 | 6 | Heathrow | 23.4
2018-06-15 | 2018 | 6 | Heathrow | 20.5
2018-06-16 | 2018 | 6 | Heathrow | 20.1
2018-06-17 | 2018 | 6 | Heathrow | 26.6
2018-06-18 | 2018 | 6 | Heathrow | 24.8
2018-06-19 | 2018 | 6 | Heathrow | 26.1
2018-06-20 | 2018 | 6 | Heathrow | 20.6
2018-06-21 | 2018 | 6 | Heathrow | 22.9
2018-06-22 | 2018 | 6 | Heathrow | 24.1
2018-06-23 | 2018 | 6 | Heathrow | 26.5
2018-06-24 | 2018 | 6 | Heathrow | 29.8
2018-06-25 | 2018 | 6 | Heathrow | 29.1
2018-06-26 | 2018 | 6 | Heathrow | 27.9
2018-06-27 | 2018 | 6 | Heathrow | 28.3
2018-06-28 | 2018 | 6 | Heathrow | 28.8
2018-06-29 | 2018 | 6 | Heathrow | 28.8
2018-06-30 | 2018 | 6 | Heathrow | 31.8
2018-07-01 | 2018 | 7 | Heathrow | 30.1
2018-07-02 | 2018 | 7 | Heathrow | 27.6
2018-07-03 | 2018 | 7 | Heathrow | 27
2018-07-04 | 2018 | 7 | Heathrow | 30.1
2018-07-05 | 2018 | 7 | Heathrow | 30.9
2018-07-06 | 2018 | 7 | Heathrow | 31.5
2018-07-07 | 2018 | 7 | Heathrow | 31
2018-07-08 | 2018 | 7 | Heathrow | 30.5
2018-07-09 | 2018 | 7 | Heathrow | 30.6
2018-07-10 | 2018 | 7 | Heathrow | 24.4
2018-07-11 | 2018 | 7 | Heathrow | 25.1
2018-07-12 | 2018 | 7 | Heathrow | 27.5
2018-07-13 | 2018 | 7 | Heathrow | 28.9
2018-07-14 | 2018 | 7 | Heathrow | 30.3
2018-07-15 | 2018 | 7 | Heathrow | 30
2018-07-16 | 2018 | 7 | Heathrow | 25
2018-07-17 | 2018 | 7 | Heathrow | 26.5
2018-07-18 | 2018 | 7 | Heathrow | 29
2018-07-19 | 2018 | 7 | Heathrow | 25.2
2018-07-20 | 2018 | 7 | Heathrow | 28.5
2018-07-21 | 2018 | 7 | Heathrow | 28.9
2018-07-22 | 2018 | 7 | Heathrow | 32.2
2018-07-23 | 2018 | 7 | Heathrow | 30.2
2018-07-24 | 2018 | 7 | Heathrow | 30.9
2018-07-25 | 2018 | 7 | Heathrow | 35
2018-07-26 | 2018 | 7 | Heathrow | 32
2018-07-28 | 2018 | 7 | Heathrow | 20.8
2018-07-29 | 2018 | 7 | Heathrow | 24.2
2018-07-30 | 2018 | 7 | Heathrow | 25.5
2018-07-31 | 2018 | 7 | Heathrow | 26.5
2018-08-01 | 2018 | 8 | Heathrow | 30.4
2018-08-02 | 2018 | 8 | Heathrow | 32.6
2018-08-03 | 2018 | 8 | Heathrow | 29
2018-08-04 | 2018 | 8 | Heathrow | 29.8
2018-08-05 | 2018 | 8 | Heathrow | 32.4
2018-08-06 | 2018 | 8 | Heathrow | 31.2
2018-08-07 | 2018 | 8 | Heathrow | 25.3
2018-08-09 | 2018 | 8 | Heathrow | 21
2018-08-10 | 2018 | 8 | Heathrow | 22.5
2018-08-11 | 2018 | 8 | Heathrow | 22.4
2018-08-12 | 2018 | 8 | Heathrow | 25.2
2018-08-13 | 2018 | 8 | Heathrow | 26.6
2018-08-14 | 2018 | 8 | Heathrow | 25.7
2018-08-15 | 2018 | 8 | Heathrow | 21.4
2018-08-16 | 2018 | 8 | Heathrow | 23.7
2018-08-17 | 2018 | 8 | Heathrow | 22.5
2018-08-18 | 2018 | 8 | Heathrow | 28.3
2018-08-19 | 2018 | 8 | Heathrow | 26.2
2018-08-20 | 2018 | 8 | Heathrow | 27.3
2018-08-21 | 2018 | 8 | Heathrow | 24.1
2018-08-22 | 2018 | 8 | Heathrow | 22.9
2018-08-23 | 2018 | 8 | Heathrow | 21
2018-08-24 | 2018 | 8 | Heathrow | 20
2018-08-25 | 2018 | 8 | Heathrow | 18.4
2018-08-26 | 2018 | 8 | Heathrow | 19.7
2018-08-27 | 2018 | 8 | Heathrow | 21.1
2018-08-28 | 2018 | 8 | Heathrow | 20.1
2018-08-29 | 2018 | 8 | Heathrow | 21
2018-08-30 | 2018 | 8 | Heathrow | 22.5
2018-08-31 | 2018 | 8 | Heathrow | 24.5
2018-09-01 | 2018 | 9 | Heathrow | 24.8
2018-09-02 | 2018 | 9 | Heathrow | 24.5
2018-09-03 | 2018 | 9 | Heathrow | 20.7
2018-09-04 | 2018 | 9 | Heathrow | 22.6
2018-09-05 | 2018 | 9 | Heathrow | 22.6
2018-09-06 | 2018 | 9 | Heathrow | 20.4
2018-09-07 | 2018 | 9 | Heathrow | 21
2018-09-08 | 2018 | 9 | Heathrow | 24.7
2018-09-09 | 2018 | 9 | Heathrow | 22.7
2018-09-10 | 2018 | 9 | Heathrow | 25.2
2018-09-11 | 2018 | 9 | Heathrow | 25.2
2018-09-12 | 2018 | 9 | Heathrow | 20.9
2018-09-13 | 2018 | 9 | Heathrow | 18.6
2018-09-14 | 2018 | 9 | Heathrow | 22.1
2018-09-15 | 2018 | 9 | Heathrow | 24.2
2018-09-16 | 2018 | 9 | Heathrow | 25.3
2018-09-17 | 2018 | 9 | Heathrow | 23.5
2018-09-18 | 2018 | 9 | Heathrow | 23.7
2018-09-19 | 2018 | 9 | Heathrow | 21.9
2018-09-20 | 2018 | 9 | Heathrow | 22
2018-09-21 | 2018 | 9 | Heathrow | 17.7
2018-09-22 | 2018 | 9 | Heathrow | 14.9
2018-09-23 | 2018 | 9 | Heathrow | 16.2
2018-09-24 | 2018 | 9 | Heathrow | 18.2
2018-09-25 | 2018 | 9 | Heathrow | 22.8
2018-09-26 | 2018 | 9 | Heathrow | 23.4
2018-09-27 | 2018 | 9 | Heathrow | 17.5
2018-09-28 | 2018 | 9 | Heathrow | 18.3
2018-09-29 | 2018 | 9 | Heathrow | 15.4
2018-09-30 | 2018 | 9 | Heathrow | 16.7
2019-05-01 | 2019 | 5 | Heathrow | 16.7
2019-05-02 | 2019 | 5 | Heathrow | 15.5
2019-05-03 | 2019 | 5 | Heathrow | 11.6
2019-05-04 | 2019 | 5 | Heathrow | 12.7
2019-05-05 | 2019 | 5 | Heathrow | 13.1
2019-05-06 | 2019 | 5 | Heathrow | 17.5
2019-05-07 | 2019 | 5 | Heathrow | 15.7
2019-05-08 | 2019 | 5 | Heathrow | 15.8
2019-05-09 | 2019 | 5 | Heathrow | 16.4
2019-05-10 | 2019 | 5 | Heathrow | 16.8
2019-05-11 | 2019 | 5 | Heathrow | 18.1
2019-05-12 | 2019 | 5 | Heathrow | 17.8
2019-05-13 | 2019 | 5 | Heathrow | 18.8
2019-05-14 | 2019 | 5 | Heathrow | 20.7
2019-05-15 | 2019 | 5 | Heathrow | 19
2019-05-16 | 2019 | 5 | Heathrow | 14.8
2019-05-17 | 2019 | 5 | Heathrow | 17.2
2019-05-18 | 2019 | 5 | Heathrow | 18.6
2019-05-19 | 2019 | 5 | Heathrow | 20.4
2019-05-20 | 2019 | 5 | Heathrow | 20.9
2019-05-21 | 2019 | 5 | Heathrow | 22.5
2019-05-22 | 2019 | 5 | Heathrow | 24.7
2019-05-23 | 2019 | 5 | Heathrow | 22.6
2019-05-24 | 2019 | 5 | Heathrow | 24.2
2019-05-25 | 2019 | 5 | Heathrow | 21.2
2019-05-26 | 2019 | 5 | Heathrow | 20
2019-05-27 | 2019 | 5 | Heathrow | 18.4
2019-05-28 | 2019 | 5 | Heathrow | 19.2
2019-05-29 | 2019 | 5 | Heathrow | 24.8
2019-05-30 | 2019 | 5 | Heathrow | 20.7
2019-05-31 | 2019 | 5 | Heathrow | 27.6
2019-06-01 | 2019 | 6 | Heathrow | 27.3
2019-06-02 | 2019 | 6 | Heathrow | 22
2019-06-03 | 2019 | 6 | Heathrow | 17.5
2019-06-04 | 2019 | 6 | Heathrow | 19.8
2019-06-05 | 2019 | 6 | Heathrow | 21
2019-06-06 | 2019 | 6 | Heathrow | 19.3
2019-06-07 | 2019 | 6 | Heathrow | 20.3
2019-06-08 | 2019 | 6 | Heathrow | 21
2019-06-09 | 2019 | 6 | Heathrow | 14.8
2019-06-10 | 2019 | 6 | Heathrow | 18.4
2019-06-11 | 2019 | 6 | Heathrow | 16.1
2019-06-12 | 2019 | 6 | Heathrow | 16.1
2019-06-13 | 2019 | 6 | Heathrow | 20.1
2019-06-14 | 2019 | 6 | Heathrow | 20
2019-06-15 | 2019 | 6 | Heathrow | 21.4
2019-06-16 | 2019 | 6 | Heathrow | 22.7
2019-06-17 | 2019 | 6 | Heathrow | 19.7
2019-06-18 | 2019 | 6 | Heathrow | 19.5
2019-06-19 | 2019 | 6 | Heathrow | 20.5
2019-06-20 | 2019 | 6 | Heathrow | 22.4
2019-06-21 | 2019 | 6 | Heathrow | 23.8
2019-06-22 | 2019 | 6 | Heathrow | 24.9
2019-06-23 | 2019 | 6 | Heathrow | 24.5
2019-06-24 | 2019 | 6 | Heathrow | 23.9
2019-06-25 | 2019 | 6 | Heathrow | 22.2
2019-06-26 | 2019 | 6 | Heathrow | 24.6
2019-06-27 | 2019 | 6 | Heathrow | 24.7
2019-06-28 | 2019 | 6 | Heathrow | 34
2019-06-29 | 2019 | 6 | Heathrow | 25.1
2019-06-30 | 2019 | 6 | Heathrow | 22.5
2019-07-01 | 2019 | 7 | Heathrow | 23.2
2019-07-02 | 2019 | 7 | Heathrow | 24.4
2019-07-03 | 2019 | 7 | Heathrow | 26.7
2019-07-04 | 2019 | 7 | Heathrow | 27.6
2019-07-05 | 2019 | 7 | Heathrow | 23.6
2019-07-06 | 2019 | 7 | Heathrow | 21.5
2019-07-07 | 2019 | 7 | Heathrow | 23.9
2019-07-08 | 2019 | 7 | Heathrow | 25.8
2019-07-09 | 2019 | 7 | Heathrow | 26.7
2019-07-10 | 2019 | 7 | Heathrow | 27.3
2019-07-11 | 2019 | 7 | Heathrow | 25.5
2019-07-12 | 2019 | 7 | Heathrow | 23.7
2019-07-13 | 2019 | 7 | Heathrow | 21.9
2019-07-14 | 2019 | 7 | Heathrow | 22.9
2019-07-15 | 2019 | 7 | Heathrow | 27.3
2019-07-16 | 2019 | 7 | Heathrow | 26.4
2019-07-17 | 2019 | 7 | Heathrow | 24.8
2019-07-18 | 2019 | 7 | Heathrow | 24.9
2019-07-19 | 2019 | 7 | Heathrow | 25.6
2019-07-20 | 2019 | 7 | Heathrow | 24.6
2019-07-21 | 2019 | 7 | Heathrow | 27.9
2019-07-22 | 2019 | 7 | Heathrow | 33.6
2019-07-23 | 2019 | 7 | Heathrow | 32.8
2019-07-24 | 2019 | 7 | Heathrow | 37.9
2019-07-25 | 2019 | 7 | Heathrow | 38
2019-07-26 | 2019 | 7 | Heathrow | 25.7
2019-07-27 | 2019 | 7 | Heathrow | 24.3
2019-07-28 | 2019 | 7 | Heathrow | 26.2
2019-07-29 | 2019 | 7 | Heathrow | 19.9
2019-07-30 | 2019 | 7 | Heathrow | 24.9
2019-07-31 | 2019 | 7 | Heathrow | 26
2019-08-01 | 2019 | 8 | Heathrow | 25.8
2019-08-02 | 2019 | 8 | Heathrow | 24.7
2019-08-03 | 2019 | 8 | Heathrow | 27.4
2019-08-04 | 2019 | 8 | Heathrow | 26.5
2019-08-05 | 2019 | 8 | Heathrow | 25
2019-08-06 | 2019 | 8 | Heathrow | 24.9
2019-08-07 | 2019 | 8 | Heathrow | 24.5
2019-08-08 | 2019 | 8 | Heathrow | 25
2019-08-09 | 2019 | 8 | Heathrow | 23.6
2019-08-10 | 2019 | 8 | Heathrow | 23.2
2019-08-11 | 2019 | 8 | Heathrow | 19.5
2019-08-12 | 2019 | 8 | Heathrow | 23.4
2019-08-13 | 2019 | 8 | Heathrow | 19.4
2019-08-14 | 2019 | 8 | Heathrow | 23.5
2019-08-15 | 2019 | 8 | Heathrow | 19.2
2019-08-16 | 2019 | 8 | Heathrow | 24.1
2019-08-17 | 2019 | 8 | Heathrow | 22.5
2019-08-18 | 2019 | 8 | Heathrow | 22.4
2019-08-19 | 2019 | 8 | Heathrow | 22.8
2019-08-20 | 2019 | 8 | Heathrow | 23.6
2019-08-21 | 2019 | 8 | Heathrow | 25.1
2019-08-22 | 2019 | 8 | Heathrow | 27.7
2019-08-23 | 2019 | 8 | Heathrow | 30.7
2019-08-24 | 2019 | 8 | Heathrow | 33.3
2019-08-25 | 2019 | 8 | Heathrow | 33.2
2019-08-26 | 2019 | 8 | Heathrow | 33.4
2019-08-27 | 2019 | 8 | Heathrow | 26.6
2019-08-28 | 2019 | 8 | Heathrow | 24.7
2019-08-29 | 2019 | 8 | Heathrow | 24.8
2019-08-30 | 2019 | 8 | Heathrow | 24.9
2019-08-31 | 2019 | 8 | Heathrow | 21.6
2019-09-01 | 2019 | 9 | Heathrow | 23.6
2019-09-02 | 2019 | 9 | Heathrow | 22.8
2019-09-03 | 2019 | 9 | Heathrow | 21.1
2019-09-04 | 2019 | 9 | Heathrow | 18.7
2019-09-05 | 2019 | 9 | Heathrow | 18.8
2019-09-06 | 2019 | 9 | Heathrow | 17.8
2019-09-07 | 2019 | 9 | Heathrow | 18.6
2019-09-08 | 2019 | 9 | Heathrow | 16.1
2019-09-09 | 2019 | 9 | Heathrow | 21.9
2019-09-10 | 2019 | 9 | Heathrow | 21.8
2019-09-11 | 2019 | 9 | Heathrow | 25.7
2019-09-12 | 2019 | 9 | Heathrow | 22.6
2019-09-13 | 2019 | 9 | Heathrow | 24
2019-09-14 | 2019 | 9 | Heathrow | 26.6
2019-09-15 | 2019 | 9 | Heathrow | 20.6
2019-09-16 | 2019 | 9 | Heathrow | 20
2019-09-17 | 2019 | 9 | Heathrow | 20
2019-09-18 | 2019 | 9 | Heathrow | 22.2
2019-09-19 | 2019 | 9 | Heathrow | 22.4
2019-09-20 | 2019 | 9 | Heathrow | 26.4
2019-09-21 | 2019 | 9 | Heathrow | 23.9
2019-09-22 | 2019 | 9 | Heathrow | 24
2019-09-23 | 2019 | 9 | Heathrow | 20.5
2019-09-24 | 2019 | 9 | Heathrow | 22.2
2019-09-25 | 2019 | 9 | Heathrow | 20.9
2019-09-26 | 2019 | 9 | Heathrow | 19
2019-09-27 | 2019 | 9 | Heathrow | 19.7
2019-09-28 | 2019 | 9 | Heathrow | 19.8
2019-09-29 | 2019 | 9 | Heathrow | 17.8
2019-09-30 | 2019 | 9 | Heathrow | 21.1
2020-05-01 | 2020 | 5 | Heathrow | 17.6
2020-05-02 | 2020 | 5 | Heathrow | 15.2
2020-05-03 | 2020 | 5 | Heathrow | 17.8
2020-05-04 | 2020 | 5 | Heathrow | 15.4
2020-05-05 | 2020 | 5 | Heathrow | 18.7
2020-05-06 | 2020 | 5 | Heathrow | 23.1
2020-05-07 | 2020 | 5 | Heathrow | 24.2
2020-05-08 | 2020 | 5 | Heathrow | 24.9
2020-05-09 | 2020 | 5 | Heathrow | 17.9
2020-05-10 | 2020 | 5 | Heathrow | 18.1
2020-05-11 | 2020 | 5 | Heathrow | 16.2
2020-05-12 | 2020 | 5 | Heathrow | 13.3
2020-05-13 | 2020 | 5 | Heathrow | 14.7
2020-05-14 | 2020 | 5 | Heathrow | 19.6
2020-05-15 | 2020 | 5 | Heathrow | 19
2020-05-16 | 2020 | 5 | Heathrow | 21.1
2020-05-17 | 2020 | 5 | Heathrow | 23.9
2020-05-18 | 2020 | 5 | Heathrow | 26
2020-05-19 | 2020 | 5 | Heathrow | 27.8
2020-05-20 | 2020 | 5 | Heathrow | 27.4
2020-05-21 | 2020 | 5 | Heathrow | 23.2
2020-05-22 | 2020 | 5 | Heathrow | 19.9
2020-05-23 | 2020 | 5 | Heathrow | 22.5
2020-05-24 | 2020 | 5 | Heathrow | 26.1
2020-05-25 | 2020 | 5 | Heathrow | 26.5
2020-05-26 | 2020 | 5 | Heathrow | 26.3
2020-05-27 | 2020 | 5 | Heathrow | 22.6
2020-05-28 | 2020 | 5 | Heathrow | 24.3
2020-05-29 | 2020 | 5 | Heathrow | 25.7
2020-05-30 | 2020 | 5 | Heathrow | 25.3
2020-05-31 | 2020 | 5 | Heathrow | 26.8
2020-06-01 | 2020 | 6 | Heathrow | 25.4
2020-06-02 | 2020 | 6 | Heathrow | 19.2
2020-06-03 | 2020 | 6 | Heathrow | 16.6
2020-06-04 | 2020 | 6 | Heathrow | 16.4
2020-06-05 | 2020 | 6 | Heathrow | 14.5
2020-06-06 | 2020 | 6 | Heathrow | 18.7
2020-06-07 | 2020 | 6 | Heathrow | 16.6
2020-06-08 | 2020 | 6 | Heathrow | 20.1
2020-06-09 | 2020 | 6 | Heathrow | 16.4
2020-06-10 | 2020 | 6 | Heathrow | 21.4
2020-06-11 | 2020 | 6 | Heathrow | 21.4
2020-06-12 | 2020 | 6 | Heathrow | 25.1
2020-06-13 | 2020 | 6 | Heathrow | 22.9
2020-06-14 | 2020 | 6 | Heathrow | 25.3
2020-06-15 | 2020 | 6 | Heathrow | 24.9
2020-06-16 | 2020 | 6 | Heathrow | 22.6
2020-06-17 | 2020 | 6 | Heathrow | 19.1
2020-06-18 | 2020 | 6 | Heathrow | 20.8
2020-06-19 | 2020 | 6 | Heathrow | 23
2020-06-20 | 2020 | 6 | Heathrow | 23.9
2020-06-21 | 2020 | 6 | Heathrow | 23.9
2020-06-22 | 2020 | 6 | Heathrow | 28.6
2020-06-23 | 2020 | 6 | Heathrow | 32.6
2020-06-24 | 2020 | 6 | Heathrow | 33.4
2020-06-25 | 2020 | 6 | Heathrow | 31
2020-06-26 | 2020 | 6 | Heathrow | 31.1
2020-06-27 | 2020 | 6 | Heathrow | 22
2020-06-28 | 2020 | 6 | Heathrow | 21.7
2020-06-29 | 2020 | 6 | Heathrow | 20.1
2020-06-30 | 2020 | 6 | Heathrow | 22.6
2020-07-01 | 2020 | 7 | Heathrow | 22.5
2020-07-02 | 2020 | 7 | Heathrow | 22.5
2020-07-03 | 2020 | 7 | Heathrow | 21.4
2020-07-04 | 2020 | 7 | Heathrow | 23
2020-07-05 | 2020 | 7 | Heathrow | 20.5
2020-07-06 | 2020 | 7 | Heathrow | 22.6
2020-07-07 | 2020 | 7 | Heathrow | 20.4
2020-07-08 | 2020 | 7 | Heathrow | 20.6
2020-07-09 | 2020 | 7 | Heathrow | 19.7
2020-07-10 | 2020 | 7 | Heathrow | 21.5
2020-07-11 | 2020 | 7 | Heathrow | 25.2
2020-07-12 | 2020 | 7 | Heathrow | 26.2
2020-07-13 | 2020 | 7 | Heathrow | 23.1
2020-07-14 | 2020 | 7 | Heathrow | 19.4
2020-07-15 | 2020 | 7 | Heathrow | 24.1
2020-07-16 | 2020 | 7 | Heathrow | 28.5
2020-07-17 | 2020 | 7 | Heathrow | 26.3
2020-07-18 | 2020 | 7 | Heathrow | 21.4
2020-07-19 | 2020 | 7 | Heathrow | 22.6
2020-07-20 | 2020 | 7 | Heathrow | 22.7
2020-07-21 | 2020 | 7 | Heathrow | 26.3
2020-07-22 | 2020 | 7 | Heathrow | 26.6
2020-07-23 | 2020 | 7 | Heathrow | 25.6
2020-07-24 | 2020 | 7 | Heathrow | 23
2020-07-25 | 2020 | 7 | Heathrow | 23.7
2020-07-26 | 2020 | 7 | Heathrow | 21.6
2020-07-27 | 2020 | 7 | Heathrow | 21.6
2020-07-28 | 2020 | 7 | Heathrow | 24.5
2020-07-29 | 2020 | 7 | Heathrow | 29.8
2020-07-30 | 2020 | 7 | Heathrow | 37.8
2020-07-31 | 2020 | 7 | Heathrow | 27.7
2020-08-01 | 2020 | 8 | Heathrow | 25.4
2020-08-02 | 2020 | 8 | Heathrow | 23.5
2020-08-03 | 2020 | 8 | Heathrow | 24.9
2020-08-04 | 2020 | 8 | Heathrow | 26.8
2020-08-05 | 2020 | 8 | Heathrow | 29.7
2020-08-06 | 2020 | 8 | Heathrow | 36.4
2020-08-07 | 2020 | 8 | Heathrow | 33.4
2020-08-08 | 2020 | 8 | Heathrow | 33.8
2020-08-09 | 2020 | 8 | Heathrow | 35.5
2020-08-10 | 2020 | 8 | Heathrow | 35.7
2020-08-11 | 2020 | 8 | Heathrow | 35.4
2020-08-12 | 2020 | 8 | Heathrow | 35.5
2020-08-13 | 2020 | 8 | Heathrow | 28.5
2020-08-14 | 2020 | 8 | Heathrow | 21.1
2020-08-15 | 2020 | 8 | Heathrow | 24.8
2020-08-16 | 2020 | 8 | Heathrow | 25.1
2020-08-17 | 2020 | 8 | Heathrow | 25
2020-08-18 | 2020 | 8 | Heathrow | 20.6
2020-08-19 | 2020 | 8 | Heathrow | 25.8
2020-08-20 | 2020 | 8 | Heathrow | 23.9
2020-08-21 | 2020 | 8 | Heathrow | 24.4
2020-08-22 | 2020 | 8 | Heathrow | 23.6
2020-08-23 | 2020 | 8 | Heathrow | 23.7
2020-08-24 | 2020 | 8 | Heathrow | 22.4
2020-08-25 | 2020 | 8 | Heathrow | 23.6
2020-08-26 | 2020 | 8 | Heathrow | 23.6
2020-08-27 | 2020 | 8 | Heathrow | 20.3
2020-08-28 | 2020 | 8 | Heathrow | 20.4
2020-08-29 | 2020 | 8 | Heathrow | 17.9
2020-08-30 | 2020 | 8 | Heathrow | 18.4
2020-08-31 | 2020 | 8 | Heathrow | 20.9
2020-09-01 | 2020 | 9 | Heathrow | 20.4
2020-09-02 | 2020 | 9 | Heathrow | 22.4
2020-09-03 | 2020 | 9 | Heathrow | 20.8
2020-09-04 | 2020 | 9 | Heathrow | 20.1
2020-09-05 | 2020 | 9 | Heathrow | 20.5
2020-09-06 | 2020 | 9 | Heathrow | 21.9
2020-09-07 | 2020 | 9 | Heathrow | 25.7
2020-09-08 | 2020 | 9 | Heathrow | 22.3
2020-09-09 | 2020 | 9 | Heathrow | 20.3
2020-09-10 | 2020 | 9 | Heathrow | 20.3
2020-09-11 | 2020 | 9 | Heathrow | 22.7
2020-09-12 | 2020 | 9 | Heathrow | 25.5
2020-09-13 | 2020 | 9 | Heathrow | 29.5
2020-09-14 | 2020 | 9 | Heathrow | 29.4
2020-09-15 | 2020 | 9 | Heathrow | 26.5
2020-09-16 | 2020 | 9 | Heathrow | 22.5
2020-09-17 | 2020 | 9 | Heathrow | 21.9
2020-09-18 | 2020 | 9 | Heathrow | 25.2
2020-09-19 | 2020 | 9 | Heathrow | 25.2
2020-09-20 | 2020 | 9 | Heathrow | 24.8
2020-09-21 | 2020 | 9 | Heathrow | 25.7
2020-09-22 | 2020 | 9 | Heathrow | 25.7
2020-09-23 | 2020 | 9 | Heathrow | 18.6
2020-09-24 | 2020 | 9 | Heathrow | 15
2020-09-25 | 2020 | 9 | Heathrow | 13.6
2020-09-26 | 2020 | 9 | Heathrow | 14.5
2020-09-27 | 2020 | 9 | Heathrow | 18.2
2020-09-28 | 2020 | 9 | Heathrow | 19.6
2020-09-29 | 2020 | 9 | Heathrow | 18
2020-09-30 | 2020 | 9 | Heathrow | 16.3
2021-05-01 | 2021 | 5 | Heathrow | 15.3
2021-05-02 | 2021 | 5 | Heathrow | 14
2021-05-03 | 2021 | 5 | Heathrow | 15.1
2021-05-04 | 2021 | 5 | Heathrow | 14.4
2021-05-05 | 2021 | 5 | Heathrow | 12.8
2021-05-06 | 2021 | 5 | Heathrow | 15.7
2021-05-07 | 2021 | 5 | Heathrow | 17.5
2021-05-08 | 2021 | 5 | Heathrow | 20.4
2021-05-09 | 2021 | 5 | Heathrow | 17.1
2021-05-10 | 2021 | 5 | Heathrow | 17.8
2021-05-11 | 2021 | 5 | Heathrow | 17.5
2021-05-12 | 2021 | 5 | Heathrow | 14.5
2021-05-13 | 2021 | 5 | Heathrow | 13.4
2021-05-14 | 2021 | 5 | Heathrow | 15
2021-05-15 | 2021 | 5 | Heathrow | 15
2021-05-16 | 2021 | 5 | Heathrow | 16.5
2021-05-17 | 2021 | 5 | Heathrow | 17.1
2021-05-18 | 2021 | 5 | Heathrow | 18.3
2021-05-19 | 2021 | 5 | Heathrow | 14.1
2021-05-20 | 2021 | 5 | Heathrow | 13.3
2021-05-21 | 2021 | 5 | Heathrow | 14.9
2021-05-22 | 2021 | 5 | Heathrow | 13.6
2021-05-23 | 2021 | 5 | Heathrow | 14.1
2021-05-24 | 2021 | 5 | Heathrow | 15.9
2021-05-25 | 2021 | 5 | Heathrow | 17.7
2021-05-26 | 2021 | 5 | Heathrow | 21.2
2021-05-27 | 2021 | 5 | Heathrow | 19.7
2021-05-28 | 2021 | 5 | Heathrow | 21.6
2021-05-29 | 2021 | 5 | Heathrow | 21.5
2021-05-30 | 2021 | 5 | Heathrow | 24.1
2021-05-31 | 2021 | 5 | Heathrow | 25.7
2021-06-01 | 2021 | 6 | Heathrow | 27.9
2021-06-02 | 2021 | 6 | Heathrow | 23.8
2021-06-04 | 2021 | 6 | Heathrow | 23.5
2021-06-05 | 2021 | 6 | Heathrow | 23.2
2021-06-06 | 2021 | 6 | Heathrow | 23.3
2021-06-07 | 2021 | 6 | Heathrow | 24.7
2021-06-08 | 2021 | 6 | Heathrow | 26.3
2021-06-09 | 2021 | 6 | Heathrow | 24.7
2021-06-10 | 2021 | 6 | Heathrow | 25.6
2021-06-11 | 2021 | 6 | Heathrow | 24.6
2021-06-12 | 2021 | 6 | Heathrow | 28
2021-06-13 | 2021 | 6 | Heathrow | 28.8
2021-06-14 | 2021 | 6 | Heathrow | 26.6
2021-06-15 | 2021 | 6 | Heathrow | 29.2
2021-06-18 | 2021 | 6 | Heathrow | 16.4
2021-06-19 | 2021 | 6 | Heathrow | 18.4
2021-06-21 | 2021 | 6 | Heathrow | 18
2021-06-22 | 2021 | 6 | Heathrow | 22.3
2021-06-23 | 2021 | 6 | Heathrow | 20.3
2021-06-24 | 2021 | 6 | Heathrow | 23
2021-06-25 | 2021 | 6 | Heathrow | 23.6
2021-06-26 | 2021 | 6 | Heathrow | 20.5
2021-06-27 | 2021 | 6 | Heathrow | 20.2
2021-06-28 | 2021 | 6 | Heathrow | 19.5
2021-06-29 | 2021 | 6 | Heathrow | 18.7
2021-06-30 | 2021 | 6 | Heathrow | 22.4
2021-07-01 | 2021 | 7 | Heathrow | 24.5
2021-07-02 | 2021 | 7 | Heathrow | 22.4
2021-07-03 | 2021 | 7 | Heathrow | 21.7
2021-07-04 | 2021 | 7 | Heathrow | 21.7
2021-07-05 | 2021 | 7 | Heathrow | 20.8
2021-07-06 | 2021 | 7 | Heathrow | 21.3
2021-07-07 | 2021 | 7 | Heathrow | 21.7
2021-07-08 | 2021 | 7 | Heathrow | 24.7
2021-07-10 | 2021 | 7 | Heathrow | 21.5
2021-07-11 | 2021 | 7 | Heathrow | 22
2021-07-12 | 2021 | 7 | Heathrow | 22.5
2021-07-13 | 2021 | 7 | Heathrow | 25.2
2021-07-14 | 2021 | 7 | Heathrow | 22.1
2021-07-15 | 2021 | 7 | Heathrow | 26.8
2021-07-16 | 2021 | 7 | Heathrow | 28.4
2021-07-17 | 2021 | 7 | Heathrow | 31.6
2021-07-18 | 2021 | 7 | Heathrow | 31.4
2021-07-19 | 2021 | 7 | Heathrow | 32.2
2021-07-20 | 2021 | 7 | Heathrow | 30.4
2021-07-21 | 2021 | 7 | Heathrow | 29.8
2021-07-22 | 2021 | 7 | Heathrow | 25.5
2021-07-23 | 2021 | 7 | Heathrow | 23.4
2021-07-24 | 2021 | 7 | Heathrow | 21.5
2021-07-25 | 2021 | 7 | Heathrow | 26.1
2021-07-26 | 2021 | 7 | Heathrow | 22.1
2021-07-27 | 2021 | 7 | Heathrow | 22.1
2021-07-28 | 2021 | 7 | Heathrow | 23.3
2021-07-29 | 2021 | 7 | Heathrow | 19.4
2021-07-30 | 2021 | 7 | Heathrow | 21.7
2021-07-31 | 2021 | 7 | Heathrow | 21.9
2021-08-01 | 2021 | 8 | Heathrow | 20.8
2021-08-02 | 2021 | 8 | Heathrow | 23.8
2021-08-03 | 2021 | 8 | Heathrow | 23.9
2021-08-04 | 2021 | 8 | Heathrow | 22
2021-08-05 | 2021 | 8 | Heathrow | 23.8
2021-08-06 | 2021 | 8 | Heathrow | 21.3
2021-08-07 | 2021 | 8 | Heathrow | 20.7
2021-08-08 | 2021 | 8 | Heathrow | 23
2021-08-09 | 2021 | 8 | Heathrow | 24.1
2021-08-10 | 2021 | 8 | Heathrow | 24.5
2021-08-11 | 2021 | 8 | Heathrow | 22.5
2021-08-12 | 2021 | 8 | Heathrow | 22.9
2021-08-13 | 2021 | 8 | Heathrow | 25.3
2021-08-14 | 2021 | 8 | Heathrow | 24.3
2021-08-16 | 2021 | 8 | Heathrow | 18.6
2021-08-17 | 2021 | 8 | Heathrow | 24.1
2021-08-18 | 2021 | 8 | Heathrow | 21.7
2021-08-19 | 2021 | 8 | Heathrow | 21.6
2021-08-20 | 2021 | 8 | Heathrow | 21.1
2021-08-21 | 2021 | 8 | Heathrow | 23.1
2021-08-22 | 2021 | 8 | Heathrow | 22
2021-08-23 | 2021 | 8 | Heathrow | 24
2021-08-24 | 2021 | 8 | Heathrow | 22.3
2021-08-25 | 2021 | 8 | Heathrow | 18.7
2021-08-26 | 2021 | 8 | Heathrow | 19.7
2021-08-27 | 2021 | 8 | Heathrow | 20.9
2021-08-28 | 2021 | 8 | Heathrow | 19.9
2021-08-29 | 2021 | 8 | Heathrow | 17.1
2021-08-30 | 2021 | 8 | Heathrow | 18.9
2021-08-31 | 2021 | 8 | Heathrow | 18.7
2021-09-01 | 2021 | 9 | Heathrow | 20.2
2021-09-02 | 2021 | 9 | Heathrow | 22.4
2021-09-03 | 2021 | 9 | Heathrow | 20.1
2021-09-04 | 2021 | 9 | Heathrow | 26.4
2021-09-05 | 2021 | 9 | Heathrow | 28.3
2021-09-06 | 2021 | 9 | Heathrow | 30.2
2021-09-07 | 2021 | 9 | Heathrow | 30.3
2021-09-08 | 2021 | 9 | Heathrow | 23.9
2021-09-09 | 2021 | 9 | Heathrow | 22.6
2021-09-10 | 2021 | 9 | Heathrow | 24
2021-09-11 | 2021 | 9 | Heathrow | 20.8
2021-09-12 | 2021 | 9 | Heathrow | 21.8
2021-09-13 | 2021 | 9 | Heathrow | 21
2021-09-14 | 2021 | 9 | Heathrow | 22.3
2021-09-15 | 2021 | 9 | Heathrow | 23.7
2021-09-16 | 2021 | 9 | Heathrow | 22.1
2021-09-17 | 2021 | 9 | Heathrow | 25.2
2021-09-19 | 2021 | 9 | Heathrow | 20.5
2021-09-20 | 2021 | 9 | Heathrow | 22.2
2021-09-21 | 2021 | 9 | Heathrow | 23
2021-09-22 | 2021 | 9 | Heathrow | 24.3
2021-09-23 | 2021 | 9 | Heathrow | 24.6
2021-09-25 | 2021 | 9 | Heathrow | 23.4
2021-09-26 | 2021 | 9 | Heathrow | 19.1
2021-09-27 | 2021 | 9 | Heathrow | 18.9
2021-09-28 | 2021 | 9 | Heathrow | 16.7
2021-09-29 | 2021 | 9 | Heathrow | 16.5
2021-09-30 | 2021 | 9 | Heathrow | 18.6
2022-05-01 | 2022 | 5 | Heathrow | 17.1
2022-05-02 | 2022 | 5 | Heathrow | 16.1
2022-05-03 | 2022 | 5 | Heathrow | 20
2022-05-04 | 2022 | 5 | Heathrow | 19.9
2022-05-05 | 2022 | 5 | Heathrow | 23.3
2022-05-06 | 2022 | 5 | Heathrow | 20.3
2022-05-07 | 2022 | 5 | Heathrow | 20.6
2022-05-08 | 2022 | 5 | Heathrow | 23.4
2022-05-09 | 2022 | 5 | Heathrow | 20.9
2022-05-11 | 2022 | 5 | Heathrow | 18.9
2022-05-12 | 2022 | 5 | Heathrow | 21.4
2022-05-13 | 2022 | 5 | Heathrow | 23.4
2022-05-14 | 2022 | 5 | Heathrow | 18.9
2022-05-15 | 2022 | 5 | Heathrow | 23.1
2022-05-16 | 2022 | 5 | Heathrow | 27.5
2022-05-17 | 2022 | 5 | Heathrow | 23.1
2022-05-18 | 2022 | 5 | Heathrow | 22.4
2022-05-19 | 2022 | 5 | Heathrow | 19
2022-05-20 | 2022 | 5 | Heathrow | 22
2022-05-21 | 2022 | 5 | Heathrow | 23.8
2022-05-22 | 2022 | 5 | Heathrow | 20.7
2022-05-23 | 2022 | 5 | Heathrow | 19.8
2022-05-24 | 2022 | 5 | Heathrow | 19.1
2022-05-25 | 2022 | 5 | Heathrow | 21.8
2022-05-26 | 2022 | 5 | Heathrow | 20.8
2022-05-27 | 2022 | 5 | Heathrow | 19.1
2022-05-28 | 2022 | 5 | Heathrow | 17
2022-05-29 | 2022 | 5 | Heathrow | 16.1
2022-05-30 | 2022 | 5 | Heathrow | 16.4
2022-05-31 | 2022 | 5 | Heathrow | 18.7
2022-06-01 | 2022 | 6 | Heathrow | 22.3
2022-06-02 | 2022 | 6 | Heathrow | 23.3
2022-06-03 | 2022 | 6 | Heathrow | 21.6
2022-06-05 | 2022 | 6 | Heathrow | 19
2022-06-06 | 2022 | 6 | Heathrow | 22.4
2022-06-07 | 2022 | 6 | Heathrow | 23.5
2022-06-08 | 2022 | 6 | Heathrow | 21
2022-06-09 | 2022 | 6 | Heathrow | 24.5
2022-06-10 | 2022 | 6 | Heathrow | 23.8
2022-06-11 | 2022 | 6 | Heathrow | 22.9
2022-06-12 | 2022 | 6 | Heathrow | 21.7
2022-06-13 | 2022 | 6 | Heathrow | 24.9
2022-06-14 | 2022 | 6 | Heathrow | 27.9
2022-06-15 | 2022 | 6 | Heathrow | 29.4
2022-06-16 | 2022 | 6 | Heathrow | 32.7
2022-06-17 | 2022 | 6 | Heathrow | 24.8
2022-06-19 | 2022 | 6 | Heathrow | 22.5
2022-06-20 | 2022 | 6 | Heathrow | 26.2
2022-06-21 | 2022 | 6 | Heathrow | 27.9
2022-06-22 | 2022 | 6 | Heathrow | 26.7
2022-06-23 | 2022 | 6 | Heathrow | 22.5
2022-06-24 | 2022 | 6 | Heathrow | 22.3
2022-06-25 | 2022 | 6 | Heathrow | 22.8
2022-06-26 | 2022 | 6 | Heathrow | 21
2022-06-27 | 2022 | 6 | Heathrow | 23.2
2022-06-28 | 2022 | 6 | Heathrow | 22
2022-06-29 | 2022 | 6 | Heathrow | 20.7
2022-06-30 | 2022 | 6 | Heathrow | 22.1
2022-07-01 | 2022 | 7 | Heathrow | 23.8
2022-07-02 | 2022 | 7 | Heathrow | 24.2
2022-07-03 | 2022 | 7 | Heathrow | 23.3
2022-07-04 | 2022 | 7 | Heathrow | 22.3
2022-07-05 | 2022 | 7 | Heathrow | 25.3
2022-07-06 | 2022 | 7 | Heathrow | 25.2
2022-07-07 | 2022 | 7 | Heathrow | 28.7
2022-07-08 | 2022 | 7 | Heathrow | 27.5
2022-07-09 | 2022 | 7 | Heathrow | 29.7
2022-07-10 | 2022 | 7 | Heathrow | 31.8
2022-07-11 | 2022 | 7 | Heathrow | 31.3
2022-07-12 | 2022 | 7 | Heathrow | 28.7
2022-07-13 | 2022 | 7 | Heathrow | 25.3
2022-07-14 | 2022 | 7 | Heathrow | 27.2
2022-07-15 | 2022 | 7 | Heathrow | 29.1
2022-07-16 | 2022 | 7 | Heathrow | 30.8
2022-07-17 | 2022 | 7 | Heathrow | 37.1
2022-07-18 | 2022 | 7 | Heathrow | 40.2
2022-07-20 | 2022 | 7 | Heathrow | 24.2
2022-07-21 | 2022 | 7 | Heathrow | 23
2022-07-22 | 2022 | 7 | Heathrow | 27.9
2022-07-23 | 2022 | 7 | Heathrow | 29
2022-07-24 | 2022 | 7 | Heathrow | 24.9
2022-07-25 | 2022 | 7 | Heathrow | 22.8
2022-07-26 | 2022 | 7 | Heathrow | 22.1
2022-07-27 | 2022 | 7 | Heathrow | 25.2
2022-07-28 | 2022 | 7 | Heathrow | 28.4
2022-07-29 | 2022 | 7 | Heathrow | 27
2022-07-30 | 2022 | 7 | Heathrow | 27.6
2022-07-31 | 2022 | 7 | Heathrow | 27.8
2022-08-01 | 2022 | 8 | Heathrow | 26.9
2022-08-02 | 2022 | 8 | Heathrow | 27.2
2022-08-03 | 2022 | 8 | Heathrow | 25.5
2022-08-04 | 2022 | 8 | Heathrow | 23.3
2022-08-05 | 2022 | 8 | Heathrow | 24.8
2022-08-06 | 2022 | 8 | Heathrow | 27.6
2022-08-07 | 2022 | 8 | Heathrow | 29.7
2022-08-08 | 2022 | 8 | Heathrow | 29.1
2022-08-09 | 2022 | 8 | Heathrow | 30.9
2022-08-10 | 2022 | 8 | Heathrow | 33.3
2022-08-11 | 2022 | 8 | Heathrow | 33.9
2022-08-12 | 2022 | 8 | Heathrow | 34.2
2022-08-13 | 2022 | 8 | Heathrow | 33.1
2022-08-14 | 2022 | 8 | Heathrow | 29.5
2022-08-16 | 2022 | 8 | Heathrow | 24.4
2022-08-17 | 2022 | 8 | Heathrow | 27.8
2022-08-18 | 2022 | 8 | Heathrow | 25.2
2022-08-19 | 2022 | 8 | Heathrow | 26
2022-08-20 | 2022 | 8 | Heathrow | 25.4
2022-08-21 | 2022 | 8 | Heathrow | 23.4
2022-08-22 | 2022 | 8 | Heathrow | 26.5
2022-08-23 | 2022 | 8 | Heathrow | 29.1
2022-08-25 | 2022 | 8 | Heathrow | 25.2
2022-08-26 | 2022 | 8 | Heathrow | 25.3
2022-08-27 | 2022 | 8 | Heathrow | 24.4
2022-08-28 | 2022 | 8 | Heathrow | 23.3
2022-08-29 | 2022 | 8 | Heathrow | 24.4
2022-08-30 | 2022 | 8 | Heathrow | 24.7
2022-08-31 | 2022 | 8 | Heathrow | 23.7
2022-09-01 | 2022 | 9 | Heathrow | 24.2
2022-09-02 | 2022 | 9 | Heathrow | 23.7
2022-09-03 | 2022 | 9 | Heathrow | 24.6
2022-09-04 | 2022 | 9 | Heathrow | 22.8
2022-09-05 | 2022 | 9 | Heathrow | 22.2
2022-09-06 | 2022 | 9 | Heathrow | 21.3
2022-09-07 | 2022 | 9 | Heathrow | 20.1
2022-09-08 | 2022 | 9 | Heathrow | 22.1
2022-09-09 | 2022 | 9 | Heathrow | 22.5
2022-09-10 | 2022 | 9 | Heathrow | 23.4
2022-09-11 | 2022 | 9 | Heathrow | 26.2
2022-09-13 | 2022 | 9 | Heathrow | 22
2022-09-14 | 2022 | 9 | Heathrow | 19.1
2022-09-15 | 2022 | 9 | Heathrow | 17.7
2022-09-16 | 2022 | 9 | Heathrow | 17.6
2022-09-17 | 2022 | 9 | Heathrow | 18
2022-09-18 | 2022 | 9 | Heathrow | 18.6
2022-09-19 | 2022 | 9 | Heathrow | 19.8
2022-09-20 | 2022 | 9 | Heathrow | 21.2
2022-09-21 | 2022 | 9 | Heathrow | 20.7
2022-09-22 | 2022 | 9 | Heathrow | 18.9
2022-09-23 | 2022 | 9 | Heathrow | 18.9
2022-09-24 | 2022 | 9 | Heathrow | 16.7
2022-09-25 | 2022 | 9 | Heathrow | 15.7
2022-09-26 | 2022 | 9 | Heathrow | 15
2022-09-27 | 2022 | 9 | Heathrow | 15.6
2022-09-28 | 2022 | 9 | Heathrow | 16.9
2022-09-29 | 2022 | 9 | Heathrow | 16.7
2022-09-30 | 2022 | 9 | Heathrow | 19.4
2023-05-01 | 2023 | 5 | Heathrow | 15.1
2023-05-02 | 2023 | 5 | Heathrow | 15.6
2023-05-03 | 2023 | 5 | Heathrow | 19
2023-05-04 | 2023 | 5 | Heathrow | 19.5
2023-05-06 | 2023 | 5 | Heathrow | 20.6
2023-05-08 | 2023 | 5 | Heathrow | 18.2
2023-05-09 | 2023 | 5 | Heathrow | 18
2023-05-10 | 2023 | 5 | Heathrow | 18.8
2023-05-11 | 2023 | 5 | Heathrow | 13.8
2023-05-12 | 2023 | 5 | Heathrow | 14
2023-05-13 | 2023 | 5 | Heathrow | 21.4
2023-05-14 | 2023 | 5 | Heathrow | 17
2023-05-15 | 2023 | 5 | Heathrow | 17.5
2023-05-16 | 2023 | 5 | Heathrow | 19
2023-05-17 | 2023 | 5 | Heathrow | 20.4
2023-05-18 | 2023 | 5 | Heathrow | 17.9
2023-05-19 | 2023 | 5 | Heathrow | 20.1
2023-05-20 | 2023 | 5 | Heathrow | 19.7
2023-05-21 | 2023 | 5 | Heathrow | 19.7
2023-05-22 | 2023 | 5 | Heathrow | 18.9
2023-05-23 | 2023 | 5 | Heathrow | 21.9
2023-05-24 | 2023 | 5 | Heathrow | 19.4
2023-05-25 | 2023 | 5 | Heathrow | 20.4
2023-05-26 | 2023 | 5 | Heathrow | 22.1
2023-05-27 | 2023 | 5 | Heathrow | 22.7
2023-05-28 | 2023 | 5 | Heathrow | 18.4
2023-05-29 | 2023 | 5 | Heathrow | 18.6
2023-05-30 | 2023 | 5 | Heathrow | 19.6
2023-05-31 | 2023 | 5 | Heathrow | 19.8
2023-06-01 | 2023 | 6 | Heathrow | 19.4
2023-06-02 | 2023 | 6 | Heathrow | 22.8
2023-06-03 | 2023 | 6 | Heathrow | 22.9
2023-06-04 | 2023 | 6 | Heathrow | 18.8
2023-06-05 | 2023 | 6 | Heathrow | 18
2023-06-06 | 2023 | 6 | Heathrow | 22.7
2023-06-07 | 2023 | 6 | Heathrow | 23.4
2023-06-08 | 2023 | 6 | Heathrow | 27
2023-06-09 | 2023 | 6 | Heathrow | 31
2023-06-10 | 2023 | 6 | Heathrow | 31.2
2023-06-11 | 2023 | 6 | Heathrow | 28.7
2023-06-12 | 2023 | 6 | Heathrow | 28.8
2023-06-13 | 2023 | 6 | Heathrow | 28.7
2023-06-14 | 2023 | 6 | Heathrow | 27.5
2023-06-15 | 2023 | 6 | Heathrow | 28.1
2023-06-16 | 2023 | 6 | Heathrow | 26.2
2023-06-17 | 2023 | 6 | Heathrow | 27.1
2023-06-18 | 2023 | 6 | Heathrow | 25
2023-06-19 | 2023 | 6 | Heathrow | 22.9
2023-06-20 | 2023 | 6 | Heathrow | 25.8
2023-06-21 | 2023 | 6 | Heathrow | 29
2023-06-22 | 2023 | 6 | Heathrow | 27.6
2023-06-23 | 2023 | 6 | Heathrow | 29.2
2023-06-24 | 2023 | 6 | Heathrow | 31.3
2023-06-26 | 2023 | 6 | Heathrow | 23.2
2023-06-27 | 2023 | 6 | Heathrow | 26.6
2023-06-28 | 2023 | 6 | Heathrow | 23
2023-06-29 | 2023 | 6 | Heathrow | 19.4
2023-06-30 | 2023 | 6 | Heathrow | 23.2
2023-07-01 | 2023 | 7 | Heathrow | 22.2
2023-07-02 | 2023 | 7 | Heathrow | 21.6
2023-07-03 | 2023 | 7 | Heathrow | 18.7
2023-07-04 | 2023 | 7 | Heathrow | 21.6
2023-07-05 | 2023 | 7 | Heathrow | 22.8
2023-07-06 | 2023 | 7 | Heathrow | 29.7
2023-07-07 | 2023 | 7 | Heathrow | 26.8
2023-07-08 | 2023 | 7 | Heathrow | 24.6
2023-07-09 | 2023 | 7 | Heathrow | 25.2
2023-07-10 | 2023 | 7 | Heathrow | 23.6
2023-07-11 | 2023 | 7 | Heathrow | 23.2
2023-07-12 | 2023 | 7 | Heathrow | 23.4
2023-07-13 | 2023 | 7 | Heathrow | 20.1
2023-07-14 | 2023 | 7 | Heathrow | 22.4
2023-07-15 | 2023 | 7 | Heathrow | 22.9
2023-07-16 | 2023 | 7 | Heathrow | 24.1
2023-07-17 | 2023 | 7 | Heathrow | 24.3
2023-07-18 | 2023 | 7 | Heathrow | 23.7
2023-07-19 | 2023 | 7 | Heathrow | 23.6
2023-07-20 | 2023 | 7 | Heathrow | 22
2023-07-21 | 2023 | 7 | Heathrow | 20
2023-07-22 | 2023 | 7 | Heathrow | 24.3
2023-07-24 | 2023 | 7 | Heathrow | 21.9
2023-07-25 | 2023 | 7 | Heathrow | 23.7
2023-07-26 | 2023 | 7 | Heathrow | 22.9
2023-07-27 | 2023 | 7 | Heathrow | 23.9
2023-07-28 | 2023 | 7 | Heathrow | 25
2023-07-29 | 2023 | 7 | Heathrow | 21.1
2023-07-30 | 2023 | 7 | Heathrow | 20.3
2023-07-31 | 2023 | 7 | Heathrow | 24.5
2023-08-01 | 2023 | 8 | Heathrow | 21.2
2023-08-02 | 2023 | 8 | Heathrow | 22.2
2023-08-03 | 2023 | 8 | Heathrow | 20.4
2023-08-04 | 2023 | 8 | Heathrow | 19
2023-08-05 | 2023 | 8 | Heathrow | 20.2
2023-08-06 | 2023 | 8 | Heathrow | 22.7
2023-08-07 | 2023 | 8 | Heathrow | 18.9
2023-08-08 | 2023 | 8 | Heathrow | 25
2023-08-09 | 2023 | 8 | Heathrow | 26.3
2023-08-10 | 2023 | 8 | Heathrow | 25.3
2023-08-11 | 2023 | 8 | Heathrow | 22.5
2023-08-12 | 2023 | 8 | Heathrow | 23.6
2023-08-13 | 2023 | 8 | Heathrow | 22.4
2023-08-14 | 2023 | 8 | Heathrow | 25
2023-08-15 | 2023 | 8 | Heathrow | 26.3
2023-08-16 | 2023 | 8 | Heathrow | 24.6
2023-08-17 | 2023 | 8 | Heathrow | 24.2
2023-08-18 | 2023 | 8 | Heathrow | 24.7
2023-08-19 | 2023 | 8 | Heathrow | 25.9
2023-08-20 | 2023 | 8 | Heathrow | 25.1
2023-08-21 | 2023 | 8 | Heathrow | 26.4
2023-08-22 | 2023 | 8 | Heathrow | 27.6
2023-08-23 | 2023 | 8 | Heathrow | 24.6
2023-08-24 | 2023 | 8 | Heathrow | 22.1
2023-08-25 | 2023 | 8 | Heathrow | 21.1
2023-08-26 | 2023 | 8 | Heathrow | 21.4
2023-08-27 | 2023 | 8 | Heathrow | 21
2023-08-28 | 2023 | 8 | Heathrow | 21.5
2023-08-29 | 2023 | 8 | Heathrow | 21.1
2023-08-30 | 2023 | 8 | Heathrow | 17.3
2023-08-31 | 2023 | 8 | Heathrow | 22.9
2023-09-01 | 2023 | 9 | Heathrow | 24.4
2023-09-02 | 2023 | 9 | Heathrow | 26.8
2023-09-03 | 2023 | 9 | Heathrow | 30
2023-09-04 | 2023 | 9 | Heathrow | 30.5
2023-09-05 | 2023 | 9 | Heathrow | 31.6
2023-09-06 | 2023 | 9 | Heathrow | 32.3
2023-09-07 | 2023 | 9 | Heathrow | 30.5
2023-09-08 | 2023 | 9 | Heathrow | 33
2023-09-09 | 2023 | 9 | Heathrow | 30.3
2023-09-10 | 2023 | 9 | Heathrow | 26.5
2023-09-11 | 2023 | 9 | Heathrow | 24.2
2023-09-12 | 2023 | 9 | Heathrow | 21.6
2023-09-13 | 2023 | 9 | Heathrow | 24.4
2023-09-14 | 2023 | 9 | Heathrow | 25.8
2023-09-15 | 2023 | 9 | Heathrow | 27
2023-09-16 | 2023 | 9 | Heathrow | 22.6
2023-09-17 | 2023 | 9 | Heathrow | 21
2023-09-18 | 2023 | 9 | Heathrow | 20.2
2023-09-19 | 2023 | 9 | Heathrow | 20.9
2023-09-20 | 2023 | 9 | Heathrow | 18.9
2023-09-21 | 2023 | 9 | Heathrow | 18.7
2023-09-22 | 2023 | 9 | Heathrow | 19.1
2023-09-23 | 2023 | 9 | Heathrow | 21.7
2023-09-24 | 2023 | 9 | Heathrow | 22.8
2023-09-25 | 2023 | 9 | Heathrow | 23.4
2023-09-26 | 2023 | 9 | Heathrow | 21.8
2023-09-27 | 2023 | 9 | Heathrow | 19.6
2023-09-28 | 2023 | 9 | Heathrow | 20.4
2023-09-29 | 2023 | 9 | Heathrow | 20.1
2023-09-30 | 2023 | 9 | Heathrow | 22.2
2024-05-01 | 2024 | 5 | Heathrow | 16.3
2024-05-03 | 2024 | 5 | Heathrow | 17.9
2024-05-04 | 2024 | 5 | Heathrow | 18.9
2024-05-05 | 2024 | 5 | Heathrow | 16.4
2024-05-06 | 2024 | 5 | Heathrow | 20.2
2024-05-07 | 2024 | 5 | Heathrow | 21.9
2024-05-08 | 2024 | 5 | Heathrow | 24.3
2024-05-09 | 2024 | 5 | Heathrow | 24.3
2024-05-10 | 2024 | 5 | Heathrow | 22.9
2024-05-11 | 2024 | 5 | Heathrow | 27
2024-05-13 | 2024 | 5 | Heathrow | 17.5
2024-05-14 | 2024 | 5 | Heathrow | 21.1
2024-05-15 | 2024 | 5 | Heathrow | 17.8
2024-05-16 | 2024 | 5 | Heathrow | 22.8
2024-05-17 | 2024 | 5 | Heathrow | 20.5
2024-05-18 | 2024 | 5 | Heathrow | 23.5
2024-05-19 | 2024 | 5 | Heathrow | 21.7
2024-05-21 | 2024 | 5 | Heathrow | 15.5
2024-05-22 | 2024 | 5 | Heathrow | 19.1
2024-05-23 | 2024 | 5 | Heathrow | 19.9
2024-05-24 | 2024 | 5 | Heathrow | 21.4
2024-05-25 | 2024 | 5 | Heathrow | 20.3
2024-05-26 | 2024 | 5 | Heathrow | 18.7
2024-05-27 | 2024 | 5 | Heathrow | 18.5
2024-05-28 | 2024 | 5 | Heathrow | 21.2
2024-05-29 | 2024 | 5 | Heathrow | 18.4
2024-05-31 | 2024 | 5 | Heathrow | 17
2024-06-01 | 2024 | 6 | Heathrow | 24.1
2024-06-02 | 2024 | 6 | Heathrow | 21.3
2024-06-03 | 2024 | 6 | Heathrow | 20.6
2024-06-04 | 2024 | 6 | Heathrow | 18.3
2024-06-05 | 2024 | 6 | Heathrow | 19.8
2024-06-06 | 2024 | 6 | Heathrow | 21
2024-06-07 | 2024 | 6 | Heathrow | 20.1
2024-06-08 | 2024 | 6 | Heathrow | 17.2
2024-06-09 | 2024 | 6 | Heathrow | 16.7
2024-06-10 | 2024 | 6 | Heathrow | 17.5
2024-06-11 | 2024 | 6 | Heathrow | 17.1
2024-06-12 | 2024 | 6 | Heathrow | 17.5
2024-06-13 | 2024 | 6 | Heathrow | 20.3
2024-06-14 | 2024 | 6 | Heathrow | 19.4
2024-06-15 | 2024 | 6 | Heathrow | 22.1
2024-06-16 | 2024 | 6 | Heathrow | 23.5
2024-06-17 | 2024 | 6 | Heathrow | 22.9
2024-06-18 | 2024 | 6 | Heathrow | 22.1
2024-06-19 | 2024 | 6 | Heathrow | 24.3
2024-06-20 | 2024 | 6 | Heathrow | 26.1
2024-06-21 | 2024 | 6 | Heathrow | 23.9
2024-06-22 | 2024 | 6 | Heathrow | 25.3
2024-06-23 | 2024 | 6 | Heathrow | 28
2024-06-24 | 2024 | 6 | Heathrow | 29.7
2024-06-25 | 2024 | 6 | Heathrow | 30.3
2024-06-26 | 2024 | 6 | Heathrow | 25.5
2024-06-27 | 2024 | 6 | Heathrow | 22.3
2024-06-28 | 2024 | 6 | Heathrow | 25.2
2024-06-29 | 2024 | 6 | Heathrow | 21
2024-06-30 | 2024 | 6 | Heathrow | 21.1
2024-07-01 | 2024 | 7 | Heathrow | 20
2024-07-02 | 2024 | 7 | Heathrow | 20.4
2024-07-03 | 2024 | 7 | Heathrow | 22.3
2024-07-04 | 2024 | 7 | Heathrow | 21.8
2024-07-05 | 2024 | 7 | Heathrow | 17.8
2024-07-06 | 2024 | 7 | Heathrow | 18.8
2024-07-07 | 2024 | 7 | Heathrow | 19.7
2024-07-08 | 2024 | 7 | Heathrow | 19.4
2024-07-09 | 2024 | 7 | Heathrow | 22.6
2024-07-10 | 2024 | 7 | Heathrow | 24.1
2024-07-11 | 2024 | 7 | Heathrow | 20.2
2024-07-12 | 2024 | 7 | Heathrow | 20.6
2024-07-13 | 2024 | 7 | Heathrow | 22.6
2024-07-14 | 2024 | 7 | Heathrow | 21.3
2024-07-15 | 2024 | 7 | Heathrow | 22.4
2024-07-16 | 2024 | 7 | Heathrow | 24.3
2024-07-17 | 2024 | 7 | Heathrow | 28.1
2024-07-18 | 2024 | 7 | Heathrow | 31.2
2024-07-19 | 2024 | 7 | Heathrow | 23.8
2024-07-20 | 2024 | 7 | Heathrow | 23.9
2024-07-21 | 2024 | 7 | Heathrow | 25
2024-07-22 | 2024 | 7 | Heathrow | 24.3
2024-07-23 | 2024 | 7 | Heathrow | 26
2024-07-25 | 2024 | 7 | Heathrow | 24.2
2024-07-26 | 2024 | 7 | Heathrow | 24.7
2024-07-27 | 2024 | 7 | Heathrow | 26.6
2024-07-28 | 2024 | 7 | Heathrow | 29.3
2024-07-29 | 2024 | 7 | Heathrow | 32
2024-07-30 | 2024 | 7 | Heathrow | 30.2
2024-07-31 | 2024 | 7 | Heathrow | 28.7
2024-08-01 | 2024 | 8 | Heathrow | 28.2
2024-08-02 | 2024 | 8 | Heathrow | 26
2024-08-03 | 2024 | 8 | Heathrow | 23.9
2024-08-04 | 2024 | 8 | Heathrow | 26.2
2024-08-05 | 2024 | 8 | Heathrow | 22.6
2024-08-06 | 2024 | 8 | Heathrow | 22.3
2024-08-07 | 2024 | 8 | Heathrow | 21.4
2024-08-08 | 2024 | 8 | Heathrow | 25.3
2024-08-09 | 2024 | 8 | Heathrow | 25
2024-08-10 | 2024 | 8 | Heathrow | 29.7
2024-08-11 | 2024 | 8 | Heathrow | 33
2024-08-12 | 2024 | 8 | Heathrow | 27.2
2024-08-13 | 2024 | 8 | Heathrow | 23.6
2024-08-14 | 2024 | 8 | Heathrow | 24
2024-08-15 | 2024 | 8 | Heathrow | 25
2024-08-16 | 2024 | 8 | Heathrow | 23.5
2024-08-17 | 2024 | 8 | Heathrow | 24.6
2024-08-18 | 2024 | 8 | Heathrow | 21.1
2024-08-19 | 2024 | 8 | Heathrow | 24.7
2024-08-20 | 2024 | 8 | Heathrow | 21.9
2024-08-21 | 2024 | 8 | Heathrow | 19.9
2024-08-22 | 2024 | 8 | Heathrow | 23.7
2024-08-24 | 2024 | 8 | Heathrow | 21.8
2024-08-25 | 2024 | 8 | Heathrow | 23.4
2024-08-26 | 2024 | 8 | Heathrow | 25.2
2024-08-27 | 2024 | 8 | Heathrow | 29.4
2024-08-28 | 2024 | 8 | Heathrow | 23.6
2024-08-29 | 2024 | 8 | Heathrow | 23.9
2024-08-30 | 2024 | 8 | Heathrow | 21.8
2024-08-31 | 2024 | 8 | Heathrow | 29.5
2024-09-01 | 2024 | 9 | Heathrow | 22.9
2024-09-02 | 2024 | 9 | Heathrow | 23.9
2024-09-03 | 2024 | 9 | Heathrow | 21
2024-09-04 | 2024 | 9 | Heathrow | 19.4
2024-09-05 | 2024 | 9 | Heathrow | 19.4
2024-09-06 | 2024 | 9 | Heathrow | 20.8
2024-09-07 | 2024 | 9 | Heathrow | 21
2024-09-08 | 2024 | 9 | Heathrow | 18.1
2024-09-09 | 2024 | 9 | Heathrow | 19.8
2024-09-10 | 2024 | 9 | Heathrow | 16.8
2024-09-11 | 2024 | 9 | Heathrow | 16.5
2024-09-12 | 2024 | 9 | Heathrow | 17.5
2024-09-13 | 2024 | 9 | Heathrow | 20
2024-09-14 | 2024 | 9 | Heathrow | 20.1
2024-09-15 | 2024 | 9 | Heathrow | 20.7
2024-09-16 | 2024 | 9 | Heathrow | 21.8
2024-09-17 | 2024 | 9 | Heathrow | 24
2024-09-18 | 2024 | 9 | Heathrow | 25.9
2024-09-19 | 2024 | 9 | Heathrow | 24
2024-09-20 | 2024 | 9 | Heathrow | 24.5
2024-09-21 | 2024 | 9 | Heathrow | 21.4
2024-09-23 | 2024 | 9 | Heathrow | 17.6
2024-09-24 | 2024 | 9 | Heathrow | 18.1
2024-09-25 | 2024 | 9 | Heathrow | 18.4
2024-09-27 | 2024 | 9 | Heathrow | 15.9
2024-09-28 | 2024 | 9 | Heathrow | 15.8
2024-09-29 | 2024 | 9 | Heathrow | 16.8
2024-09-30 | 2024 | 9 | Heathrow | 14.9
2025-05-01 | 2025 | 5 | Heathrow | 24.7
2025-05-02 | 2025 | 5 | Heathrow | 20.4
2025-05-04 | 2025 | 5 | Heathrow | 14.9
2025-05-05 | 2025 | 5 | Heathrow | 16.1
2025-05-06 | 2025 | 5 | Heathrow | 17.1
2025-05-07 | 2025 | 5 | Heathrow | 17
2025-05-08 | 2025 | 5 | Heathrow | 19.6
2025-05-09 | 2025 | 5 | Heathrow | 23.5
2025-05-10 | 2025 | 5 | Heathrow | 25.7
2025-05-11 | 2025 | 5 | Heathrow | 23.9
2025-05-12 | 2025 | 5 | Heathrow | 25.4
2025-05-13 | 2025 | 5 | Heathrow | 23.9
2025-05-15 | 2025 | 5 | Heathrow | 19.3
2025-05-16 | 2025 | 5 | Heathrow | 19.7
2025-05-17 | 2025 | 5 | Heathrow | 17.9
2025-05-18 | 2025 | 5 | Heathrow | 21.7
2025-05-19 | 2025 | 5 | Heathrow | 23
2025-05-20 | 2025 | 5 | Heathrow | 20.2
2025-05-21 | 2025 | 5 | Heathrow | 16.7
2025-05-22 | 2025 | 5 | Heathrow | 21.9
2025-05-23 | 2025 | 5 | Heathrow | 21.9
2025-05-24 | 2025 | 5 | Heathrow | 21.9
2025-05-25 | 2025 | 5 | Heathrow | 20.8
2025-05-26 | 2025 | 5 | Heathrow | 18.4
2025-05-27 | 2025 | 5 | Heathrow | 21.7
2025-05-28 | 2025 | 5 | Heathrow | 25.5
2025-05-29 | 2025 | 5 | Heathrow | 25.7
2025-05-30 | 2025 | 5 | Heathrow | 26.8
2025-05-31 | 2025 | 5 | Heathrow | 23.3
2025-06-01 | 2025 | 6 | Heathrow | 22.6
2025-06-02 | 2025 | 6 | Heathrow | 19.2
2025-06-03 | 2025 | 6 | Heathrow | 20.1
2025-06-04 | 2025 | 6 | Heathrow | 16.6
2025-06-05 | 2025 | 6 | Heathrow | 21.7
2025-06-06 | 2025 | 6 | Heathrow | 18.1
2025-06-07 | 2025 | 6 | Heathrow | 19.6
2025-06-08 | 2025 | 6 | Heathrow | 21.9
2025-06-09 | 2025 | 6 | Heathrow | 23.1
2025-06-10 | 2025 | 6 | Heathrow | 24.3
2025-06-11 | 2025 | 6 | Heathrow | 25.4
2025-06-12 | 2025 | 6 | Heathrow | 28.9
2025-06-13 | 2025 | 6 | Heathrow | 25.4
2025-06-14 | 2025 | 6 | Heathrow | 25.2
2025-06-15 | 2025 | 6 | Heathrow | 26.5
2025-06-16 | 2025 | 6 | Heathrow | 27.9
2025-06-17 | 2025 | 6 | Heathrow | 29.2
2025-06-18 | 2025 | 6 | Heathrow | 32.2
2025-06-19 | 2025 | 6 | Heathrow | 30.9
2025-06-20 | 2025 | 6 | Heathrow | 32.1
2025-06-21 | 2025 | 6 | Heathrow | 26.7
2025-06-22 | 2025 | 6 | Heathrow | 23.8
2025-06-23 | 2025 | 6 | Heathrow | 27.8
2025-06-24 | 2025 | 6 | Heathrow | 27.6
2025-06-25 | 2025 | 6 | Heathrow | 26.6
2025-06-26 | 2025 | 6 | Heathrow | 28.2
2025-06-27 | 2025 | 6 | Heathrow | 31.3
2025-06-28 | 2025 | 6 | Heathrow | 30.2
2025-06-29 | 2025 | 6 | Heathrow | 33.1
2025-06-30 | 2025 | 6 | Heathrow | 33.9
2025-07-02 | 2025 | 7 | Heathrow | 25.9
2025-07-03 | 2025 | 7 | Heathrow | 28.6
2025-07-04 | 2025 | 7 | Heathrow | 23.4
2025-07-05 | 2025 | 7 | Heathrow | 22.8
2025-07-06 | 2025 | 7 | Heathrow | 22.4
2025-07-07 | 2025 | 7 | Heathrow | 25.2
2025-07-08 | 2025 | 7 | Heathrow | 27.3
2025-07-09 | 2025 | 7 | Heathrow | 31.7
2025-07-10 | 2025 | 7 | Heathrow | 32.4
2025-07-11 | 2025 | 7 | Heathrow | 30.8
2025-07-12 | 2025 | 7 | Heathrow | 28.5
2025-07-13 | 2025 | 7 | Heathrow | 26.7
2025-07-14 | 2025 | 7 | Heathrow | 23.7
2025-07-15 | 2025 | 7 | Heathrow | 26
2025-07-16 | 2025 | 7 | Heathrow | 27.1
2025-07-17 | 2025 | 7 | Heathrow | 30.8
2025-07-19 | 2025 | 7 | Heathrow | 23.1
2025-07-20 | 2025 | 7 | Heathrow | 25.7
2025-07-21 | 2025 | 7 | Heathrow | 23.3
2025-07-22 | 2025 | 7 | Heathrow | 22.5
2025-07-23 | 2025 | 7 | Heathrow | 22.6
2025-07-24 | 2025 | 7 | Heathrow | 26.9
2025-07-25 | 2025 | 7 | Heathrow | 23.8
2025-07-26 | 2025 | 7 | Heathrow | 21.9
2025-07-27 | 2025 | 7 | Heathrow | 25.2
2025-07-28 | 2025 | 7 | Heathrow | 19.8
2025-07-29 | 2025 | 7 | Heathrow | 25.1
2025-07-30 | 2025 | 7 | Heathrow | 23.2
2025-07-31 | 2025 | 7 | Heathrow | 22
2025-08-01 | 2025 | 8 | Heathrow | 23.2
2025-08-02 | 2025 | 8 | Heathrow | 25.5
2025-08-03 | 2025 | 8 | Heathrow | 22.8
2025-08-04 | 2025 | 8 | Heathrow | 23.3
2025-08-05 | 2025 | 8 | Heathrow | 24.5
2025-08-06 | 2025 | 8 | Heathrow | 24.9
2025-08-07 | 2025 | 8 | Heathrow | 26.5
2025-08-08 | 2025 | 8 | Heathrow | 26.6
2025-08-09 | 2025 | 8 | Heathrow | 27.5
2025-08-10 | 2025 | 8 | Heathrow | 31.9
2025-08-11 | 2025 | 8 | Heathrow | 33.3
2025-08-12 | 2025 | 8 | Heathrow | 26.8
2025-08-13 | 2025 | 8 | Heathrow | 28.9
2025-08-14 | 2025 | 8 | Heathrow | 30.2
2025-08-16 | 2025 | 8 | Heathrow | 27.2
2025-08-17 | 2025 | 8 | Heathrow | 22
2025-08-18 | 2025 | 8 | Heathrow | 25.8
2025-08-19 | 2025 | 8 | Heathrow | 21.5
2025-08-20 | 2025 | 8 | Heathrow | 21.1
2025-08-21 | 2025 | 8 | Heathrow | 23.3
2025-08-22 | 2025 | 8 | Heathrow | 23.2
2025-08-23 | 2025 | 8 | Heathrow | 25.9
2025-08-24 | 2025 | 8 | Heathrow | 28.1
2025-08-25 | 2025 | 8 | Heathrow | 27.1
2025-08-26 | 2025 | 8 | Heathrow | 22.7
2025-08-27 | 2025 | 8 | Heathrow | 22.4
2025-08-28 | 2025 | 8 | Heathrow | 21.2
2025-08-29 | 2025 | 8 | Heathrow | 21.7
2025-08-30 | 2025 | 8 | Heathrow | 23.2
2025-08-31 | 2025 | 8 | Heathrow | 21.8
2025-09-01 | 2025 | 9 | Heathrow | 19.4
2025-09-02 | 2025 | 9 | Heathrow | 22.4
2025-09-03 | 2025 | 9 | Heathrow | 20.5
2025-09-04 | 2025 | 9 | Heathrow | 23.2
2025-09-05 | 2025 | 9 | Heathrow | 24.6
2025-09-06 | 2025 | 9 | Heathrow | 27.3
2025-09-07 | 2025 | 9 | Heathrow | 22.4
2025-09-08 | 2025 | 9 | Heathrow | 22.3
2025-09-09 | 2025 | 9 | Heathrow | 19.2
2025-09-10 | 2025 | 9 | Heathrow | 19.6
2025-09-11 | 2025 | 9 | Heathrow | 20
2025-09-12 | 2025 | 9 | Heathrow | 19.6
2025-09-13 | 2025 | 9 | Heathrow | 18.1
2025-09-14 | 2025 | 9 | Heathrow | 19.9
2025-09-15 | 2025 | 9 | Heathrow | 20.3
2025-09-16 | 2025 | 9 | Heathrow | 19.7
2025-09-17 | 2025 | 9 | Heathrow | 22.1
2025-09-18 | 2025 | 9 | Heathrow | 27.4
2025-09-19 | 2025 | 9 | Heathrow | 21
2025-09-21 | 2025 | 9 | Heathrow | 16.9
2025-09-22 | 2025 | 9 | Heathrow | 17.8
2025-09-23 | 2025 | 9 | Heathrow | 18.6
2025-09-24 | 2025 | 9 | Heathrow | 19.5
2025-09-25 | 2025 | 9 | Heathrow | 15.2
2025-09-26 | 2025 | 9 | Heathrow | 18.3
2025-09-27 | 2025 | 9 | Heathrow | 16.2
2025-09-28 | 2025 | 9 | Heathrow | 19
2025-09-29 | 2025 | 9 | Heathrow | 20.7
2025-09-30 | 2025 | 9 | Heathrow | 19.4
2026-05-01 | 2026 | 5 | Heathrow | 23.1
2026-05-02 | 2026 | 5 | Heathrow | 19.6
2026-05-03 | 2026 | 5 | Heathrow | 16.2
2026-05-04 | 2026 | 5 | Heathrow | 16.7
2026-05-05 | 2026 | 5 | Heathrow | 14.6
2026-05-06 | 2026 | 5 | Heathrow | 17.6
2026-05-07 | 2026 | 5 | Heathrow | 19.3
2026-05-08 | 2026 | 5 | Heathrow | 22.1
2026-05-10 | 2026 | 5 | Heathrow | 13.4
2026-05-11 | 2026 | 5 | Heathrow | 17
2026-05-12 | 2026 | 5 | Heathrow | 13
2026-05-13 | 2026 | 5 | Heathrow | 14.7
2026-05-14 | 2026 | 5 | Heathrow | 15
2026-05-15 | 2026 | 5 | Heathrow | 16.1
2026-05-16 | 2026 | 5 | Heathrow | 18.6
2026-05-17 | 2026 | 5 | Heathrow | 16.5
2026-05-18 | 2026 | 5 | Heathrow | 19.1
2026-05-19 | 2026 | 5 | Heathrow | 21.8
2026-05-20 | 2026 | 5 | Heathrow | 24.6
2026-05-21 | 2026 | 5 | Heathrow | 28.4
2026-05-22 | 2026 | 5 | Heathrow | 29.7
2026-05-23 | 2026 | 5 | Heathrow | 32.1
2026-05-24 | 2026 | 5 | Heathrow | 34.4
2026-05-25 | 2026 | 5 | Heathrow | 35
2026-05-26 | 2026 | 5 | Heathrow | 28.6
2026-05-27 | 2026 | 5 | Heathrow | 32
2026-05-28 | 2026 | 5 | Heathrow | 26.1
2026-05-29 | 2026 | 5 | Heathrow | 30.1
2026-05-30 | 2026 | 5 | Heathrow | 24
2026-05-31 | 2026 | 5 | Heathrow | 24.2
2026-06-01 | 2026 | 6 | Heathrow | 20.9
2026-06-02 | 2026 | 6 | Heathrow | 20.8
2026-06-03 | 2026 | 6 | Heathrow | 20.5
2026-06-04 | 2026 | 6 | Heathrow | 18.9
2026-06-05 | 2026 | 6 | Heathrow | 17.3
2026-06-06 | 2026 | 6 | Heathrow | 19
2026-06-07 | 2026 | 6 | Heathrow | 17.5
2026-06-08 | 2026 | 6 | Heathrow | 20.6
2026-06-09 | 2026 | 6 | Heathrow | 19.3
2026-06-10 | 2026 | 6 | Heathrow | 17.3
2026-06-11 | 2026 | 6 | Heathrow | 22.9
2026-06-12 | 2026 | 6 | Heathrow | 22.4
2026-06-13 | 2026 | 6 | Heathrow | 21.3
2026-06-14 | 2026 | 6 | Heathrow | 23.3
2026-06-15 | 2026 | 6 | Heathrow | 27.1
2026-06-16 | 2026 | 6 | Heathrow | 26.6
2026-06-17 | 2026 | 6 | Heathrow | 25.7
2026-06-18 | 2026 | 6 | Heathrow | 30.3
2026-06-19 | 2026 | 6 | Heathrow | 26.4
2026-06-20 | 2026 | 6 | Heathrow | 31.8
2026-06-21 | 2026 | 6 | Heathrow | 30
2026-06-22 | 2026 | 6 | Heathrow | 34.3
2026-06-23 | 2026 | 6 | Heathrow | 35.3
2026-06-24 | 2026 | 6 | Heathrow | 33.1
2026-06-25 | 2026 | 6 | Heathrow | 36.4
2026-06-26 | 2026 | 6 | Heathrow | 31.7
2026-06-27 | 2026 | 6 | Heathrow | 27.2
2026-06-28 | 2026 | 6 | Heathrow | 24.7
2026-06-29 | 2026 | 6 | Heathrow | 25.6
2026-06-30 | 2026 | 6 | Heathrow | 27.6
2026-07-01 | 2026 | 7 | Heathrow | 26.4
2026-07-02 | 2026 | 7 | Heathrow | 27.5
2026-07-03 | 2026 | 7 | Heathrow | 29.1
2026-07-04 | 2026 | 7 | Heathrow | 30.3
2026-07-05 | 2026 | 7 | Heathrow | 33.3
2026-07-06 | 2026 | 7 | Heathrow | 32
2026-07-07 | 2026 | 7 | Heathrow | 33.7
2026-07-08 | 2026 | 7 | Heathrow | 34.9
2026-07-09 | 2026 | 7 | Heathrow | 31.1
2026-07-10 | 2026 | 7 | Heathrow | 31
2026-07-11 | 2026 | 7 | Heathrow | 31.5
2026-07-12 | 2026 | 7 | Heathrow | 28.6
2026-07-13 | 2026 | 7 | Heathrow | 30.4
2026-07-14 | 2026 | 7 | Heathrow | 29.6
2026-07-15 | 2026 | 7 | Heathrow | 30.3
2026-07-16 | 2026 | 7 | Heathrow | 29.6
2026-07-17 | 2026 | 7 | Heathrow | 23.5
2026-07-18 | 2026 | 7 | Heathrow | 23.8
2026-07-19 | 2026 | 7 | Heathrow | 26.6
2026-07-20 | 2026 | 7 | Heathrow | 24.7
2026-07-21 | 2026 | 7 | Heathrow | 27.9
2026-07-22 | 2026 | 7 | Heathrow | 28
2026-07-23 | 2026 | 7 | Heathrow | 29.2
2026-07-24 | 2026 | 7 | Heathrow | 29.8
2026-07-25 | 2026 | 7 | Heathrow | 27.1
2026-07-26 | 2026 | 7 | Heathrow | 28
2026-07-27 | 2026 | 7 | Heathrow | 30.7
2026-07-28 | 2026 | 7 | Heathrow | 35
2026-07-29 | 2026 | 7 | Heathrow | 29.3
2026-07-30 | 2026 | 7 | Heathrow | 26.8
2026-07-31 | 2026 | 7 | Heathrow | 26.7
2026-08-01 | 2026 | 8 | Heathrow | 28.8
2026-08-02 | 2026 | 8 | Heathrow | 33.2
2026-08-03 | 2026 | 8 | Heathrow | 31.5
2026-08-04 | 2026 | 8 | Heathrow | 26.1
2026-08-05 | 2026 | 8 | Heathrow | 23.2
2026-08-06 | 2026 | 8 | Heathrow | 26.7
2026-08-07 | 2026 | 8 | Heathrow | 28.8
2026-08-08 | 2026 | 8 | Heathrow | 32.3
2026-08-09 | 2026 | 8 | Heathrow | 27.4
2026-08-10 | 2026 | 8 | Heathrow | 27.1
2026-08-11 | 2026 | 8 | Heathrow | 34
2026-08-12 | 2026 | 8 | Heathrow | 37.7
2026-08-13 | 2026 | 8 | Heathrow | 34.7
2026-08-14 | 2026 | 8 | Heathrow | 28
2026-08-15 | 2026 | 8 | Heathrow | 27.5
2026-08-16 | 2026 | 8 | Heathrow | 29
2026-08-17 | 2026 | 8 | Heathrow | 26.1
2026-08-18 | 2026 | 8 | Heathrow | 26.3
2026-08-19 | 2026 | 8 | Heathrow | 24.6
2026-08-20 | 2026 | 8 | Heathrow | 21.8
2026-08-21 | 2026 | 8 | Heathrow | 23.2
2026-08-22 | 2026 | 8 | Heathrow | 25.7
2026-08-23 | 2026 | 8 | Heathrow | 24
2026-08-24 | 2026 | 8 | Heathrow | 26.6
2026-08-25 | 2026 | 8 | Heathrow | 27.5
2026-08-26 | 2026 | 8 | Heathrow | 26.2
2026-08-27 | 2026 | 8 | Heathrow | 26.1
2026-08-28 | 2026 | 8 | Heathrow | 21.4
2026-08-29 | 2026 | 8 | Heathrow | 24.6
2026-08-30 | 2026 | 8 | Heathrow | 25
2026-08-31 | 2026 | 8 | Heathrow | 25
2026-09-01 | 2026 | 9 | Heathrow | 21.6
2026-09-02 | 2026 | 9 | Heathrow | 27.8
2026-09-04 | 2026 | 9 | Heathrow | 23.9
2026-09-05 | 2026 | 9 | Heathrow | 28.2
2026-09-06 | 2026 | 9 | Heathrow | 25.3
2026-09-08 | 2026 | 9 | Heathrow | 19
2026-09-09 | 2026 | 9 | Heathrow | 21.4
2026-09-10 | 2026 | 9 | Heathrow | 22.4
2026-09-11 | 2026 | 9 | Heathrow | 24.3
2026-09-12 | 2026 | 9 | Heathrow | 24.2
2026-09-13 | 2026 | 9 | Heathrow | 26.6
2026-09-14 | 2026 | 9 | Heathrow | 24.3
2026-09-15 | 2026 | 9 | Heathrow | 21.9
2026-09-16 | 2026 | 9 | Heathrow | 22.6
2026-09-17 | 2026 | 9 | Heathrow | 21.5
2026-09-18 | 2026 | 9 | Heathrow | 23.7
2026-09-19 | 2026 | 9 | Heathrow | 21.5
2026-09-20 | 2026 | 9 | Heathrow | 24.7
2026-09-21 | 2026 | 9 | Heathrow | 26.9
2026-09-22 | 2026 | 9 | Heathrow | 24.7
2026-09-23 | 2026 | 9 | Heathrow | 22.4
2026-09-24 | 2026 | 9 | Heathrow | 25.1
2026-09-25 | 2026 | 9 | Heathrow | 22.6
2026-09-26 | 2026 | 9 | Heathrow | 22.5
2026-09-27 | 2026 | 9 | Heathrow | 20.6
2026-09-28 | 2026 | 9 | Heathrow | 27.7
2026-09-29 | 2026 | 9 | Heathrow | 24.9
2026-09-30 | 2026 | 9 | Heathrow | 25.1
1979-05-02 | 1979 | 5 | Wisley | 9.9
1979-05-03 | 1979 | 5 | Wisley | 9.5
1979-05-04 | 1979 | 5 | Wisley | 10.8
1979-05-05 | 1979 | 5 | Wisley | 11.9
1979-05-06 | 1979 | 5 | Wisley | 13.4
1979-05-07 | 1979 | 5 | Wisley | 17.1
1979-05-08 | 1979 | 5 | Wisley | 15.9
1979-05-09 | 1979 | 5 | Wisley | 13.6
1979-05-10 | 1979 | 5 | Wisley | 17.1
1979-05-11 | 1979 | 5 | Wisley | 21.4
1979-05-12 | 1979 | 5 | Wisley | 22.5
1979-05-13 | 1979 | 5 | Wisley | 26.1
1979-05-14 | 1979 | 5 | Wisley | 25.9
1979-05-15 | 1979 | 5 | Wisley | 22
1979-05-17 | 1979 | 5 | Wisley | 15.8
1979-05-18 | 1979 | 5 | Wisley | 17.8
1979-05-19 | 1979 | 5 | Wisley | 17.5
1979-05-20 | 1979 | 5 | Wisley | 15.1
1979-05-21 | 1979 | 5 | Wisley | 15.2
1979-05-22 | 1979 | 5 | Wisley | 14.9
1979-05-23 | 1979 | 5 | Wisley | 14.9
1979-05-24 | 1979 | 5 | Wisley | 13.9
1979-05-25 | 1979 | 5 | Wisley | 15.4
1979-05-26 | 1979 | 5 | Wisley | 16.5
1979-05-27 | 1979 | 5 | Wisley | 15.9
1979-05-28 | 1979 | 5 | Wisley | 17.4
1979-05-29 | 1979 | 5 | Wisley | 21.9
1979-05-30 | 1979 | 5 | Wisley | 17
1979-05-31 | 1979 | 5 | Wisley | 19.4
1979-06-01 | 1979 | 6 | Wisley | 21.4
1979-06-02 | 1979 | 6 | Wisley | 19.4
1979-06-03 | 1979 | 6 | Wisley | 19
1979-06-04 | 1979 | 6 | Wisley | 20.4
1979-06-05 | 1979 | 6 | Wisley | 16.5
1979-06-06 | 1979 | 6 | Wisley | 15
1979-06-07 | 1979 | 6 | Wisley | 16.5
1979-06-08 | 1979 | 6 | Wisley | 18.5
1979-06-09 | 1979 | 6 | Wisley | 17.4
1979-06-10 | 1979 | 6 | Wisley | 16.4
1979-06-11 | 1979 | 6 | Wisley | 15.9
1979-06-12 | 1979 | 6 | Wisley | 18
1979-06-13 | 1979 | 6 | Wisley | 16.4
1979-06-14 | 1979 | 6 | Wisley | 16.2
1979-06-15 | 1979 | 6 | Wisley | 19.5
1979-06-16 | 1979 | 6 | Wisley | 20.5
1979-06-17 | 1979 | 6 | Wisley | 23
1979-06-18 | 1979 | 6 | Wisley | 25.4
1979-06-19 | 1979 | 6 | Wisley | 25.4
1979-06-20 | 1979 | 6 | Wisley | 19.3
1979-06-21 | 1979 | 6 | Wisley | 20.5
1979-06-22 | 1979 | 6 | Wisley | 19.2
1979-06-23 | 1979 | 6 | Wisley | 17.4
1979-06-24 | 1979 | 6 | Wisley | 17.9
1979-06-25 | 1979 | 6 | Wisley | 19.8
1979-06-26 | 1979 | 6 | Wisley | 21
1979-06-27 | 1979 | 6 | Wisley | 20.1
1979-06-28 | 1979 | 6 | Wisley | 18.2
1979-06-29 | 1979 | 6 | Wisley | 16.6
1979-06-30 | 1979 | 6 | Wisley | 17.4
1979-07-01 | 1979 | 7 | Wisley | 19.2
1979-07-02 | 1979 | 7 | Wisley | 22.2
1979-07-03 | 1979 | 7 | Wisley | 23.4
1979-07-04 | 1979 | 7 | Wisley | 25.4
1979-07-05 | 1979 | 7 | Wisley | 25
1979-07-06 | 1979 | 7 | Wisley | 25
1979-07-07 | 1979 | 7 | Wisley | 22.4
1979-07-08 | 1979 | 7 | Wisley | 21.4
1979-07-09 | 1979 | 7 | Wisley | 22.4
1979-07-10 | 1979 | 7 | Wisley | 21.4
1979-07-11 | 1979 | 7 | Wisley | 25
1979-07-12 | 1979 | 7 | Wisley | 26.4
1979-07-13 | 1979 | 7 | Wisley | 22.4
1979-07-14 | 1979 | 7 | Wisley | 21.5
1979-07-15 | 1979 | 7 | Wisley | 23
1979-07-16 | 1979 | 7 | Wisley | 26.1
1979-07-17 | 1979 | 7 | Wisley | 22
1979-07-19 | 1979 | 7 | Wisley | 20.6
1979-07-20 | 1979 | 7 | Wisley | 19.7
1979-07-21 | 1979 | 7 | Wisley | 18
1979-07-22 | 1979 | 7 | Wisley | 18
1979-07-23 | 1979 | 7 | Wisley | 22
1979-07-24 | 1979 | 7 | Wisley | 24.5
1979-07-25 | 1979 | 7 | Wisley | 26.6
1979-07-26 | 1979 | 7 | Wisley | 30
1979-07-27 | 1979 | 7 | Wisley | 25.5
1979-07-30 | 1979 | 7 | Wisley | 20
1979-07-31 | 1979 | 7 | Wisley | 22
1979-08-01 | 1979 | 8 | Wisley | 19.9
1979-08-02 | 1979 | 8 | Wisley | 19.9
1979-08-03 | 1979 | 8 | Wisley | 20.7
1979-08-04 | 1979 | 8 | Wisley | 22.4
1979-08-05 | 1979 | 8 | Wisley | 22.9
1979-08-06 | 1979 | 8 | Wisley | 23
1979-08-07 | 1979 | 8 | Wisley | 19.6
1979-08-08 | 1979 | 8 | Wisley | 19.1
1979-08-09 | 1979 | 8 | Wisley | 20.1
1979-08-10 | 1979 | 8 | Wisley | 22.9
1979-08-11 | 1979 | 8 | Wisley | 24.4
1979-08-12 | 1979 | 8 | Wisley | 19.6
1979-08-14 | 1979 | 8 | Wisley | 20
1979-08-15 | 1979 | 8 | Wisley | 19.6
1979-08-16 | 1979 | 8 | Wisley | 17
1979-08-17 | 1979 | 8 | Wisley | 17.5
1979-08-18 | 1979 | 8 | Wisley | 19.4
1979-08-19 | 1979 | 8 | Wisley | 22.1
1979-08-20 | 1979 | 8 | Wisley | 19
1979-08-21 | 1979 | 8 | Wisley | 18.5
1979-08-22 | 1979 | 8 | Wisley | 16.2
1979-08-23 | 1979 | 8 | Wisley | 16.8
1979-08-24 | 1979 | 8 | Wisley | 15.9
1979-08-25 | 1979 | 8 | Wisley | 18.4
1979-08-26 | 1979 | 8 | Wisley | 17.4
1979-08-27 | 1979 | 8 | Wisley | 21.2
1979-08-28 | 1979 | 8 | Wisley | 22
1979-08-29 | 1979 | 8 | Wisley | 25.1
1979-08-30 | 1979 | 8 | Wisley | 21.8
1979-08-31 | 1979 | 8 | Wisley | 22.9
1979-09-01 | 1979 | 9 | Wisley | 20.4
1979-09-02 | 1979 | 9 | Wisley | 19.4
1979-09-03 | 1979 | 9 | Wisley | 21.6
1979-09-04 | 1979 | 9 | Wisley | 22.5
1979-09-05 | 1979 | 9 | Wisley | 25.2
1979-09-06 | 1979 | 9 | Wisley | 21.9
1979-09-07 | 1979 | 9 | Wisley | 24
1979-09-08 | 1979 | 9 | Wisley | 21.6
1979-09-09 | 1979 | 9 | Wisley | 20.5
1979-09-10 | 1979 | 9 | Wisley | 22
1979-09-11 | 1979 | 9 | Wisley | 16.4
1979-09-12 | 1979 | 9 | Wisley | 18.6
1979-09-13 | 1979 | 9 | Wisley | 17.9
1979-09-14 | 1979 | 9 | Wisley | 18
1979-09-15 | 1979 | 9 | Wisley | 19.6
1979-09-16 | 1979 | 9 | Wisley | 20.5
1979-09-17 | 1979 | 9 | Wisley | 18.2
1979-09-18 | 1979 | 9 | Wisley | 17.4
1979-09-19 | 1979 | 9 | Wisley | 17
1979-09-20 | 1979 | 9 | Wisley | 16.4
1979-09-21 | 1979 | 9 | Wisley | 14.8
1979-09-22 | 1979 | 9 | Wisley | 14.5
1979-09-23 | 1979 | 9 | Wisley | 16.8
1979-09-24 | 1979 | 9 | Wisley | 17.9
1979-09-25 | 1979 | 9 | Wisley | 19.3
1979-09-26 | 1979 | 9 | Wisley | 17.5
1979-09-27 | 1979 | 9 | Wisley | 17.6
1979-09-28 | 1979 | 9 | Wisley | 17.2
1979-09-29 | 1979 | 9 | Wisley | 16.4
1979-09-30 | 1979 | 9 | Wisley | 19.6
1980-05-01 | 1980 | 5 | Wisley | 11.4
1980-05-03 | 1980 | 5 | Wisley | 16.8
1980-05-04 | 1980 | 5 | Wisley | 12.1
1980-05-05 | 1980 | 5 | Wisley | 13.9
1980-05-06 | 1980 | 5 | Wisley | 11.4
1980-05-07 | 1980 | 5 | Wisley | 12.4
1980-05-08 | 1980 | 5 | Wisley | 13.9
1980-05-09 | 1980 | 5 | Wisley | 19.4
1980-05-10 | 1980 | 5 | Wisley | 22.2
1980-05-11 | 1980 | 5 | Wisley | 25.4
1980-05-12 | 1980 | 5 | Wisley | 24.4
1980-05-13 | 1980 | 5 | Wisley | 21
1980-05-14 | 1980 | 5 | Wisley | 18
1980-05-15 | 1980 | 5 | Wisley | 21.9
1980-05-16 | 1980 | 5 | Wisley | 21.9
1980-05-17 | 1980 | 5 | Wisley | 22.5
1980-05-18 | 1980 | 5 | Wisley | 24.5
1980-05-20 | 1980 | 5 | Wisley | 20.9
1980-05-21 | 1980 | 5 | Wisley | 16.4
1980-05-23 | 1980 | 5 | Wisley | 14.2
1980-05-24 | 1980 | 5 | Wisley | 15.3
1980-05-25 | 1980 | 5 | Wisley | 17.4
1980-05-26 | 1980 | 5 | Wisley | 19.2
1980-05-27 | 1980 | 5 | Wisley | 17.9
1980-05-28 | 1980 | 5 | Wisley | 15.2
1980-05-29 | 1980 | 5 | Wisley | 16.3
1980-05-30 | 1980 | 5 | Wisley | 12.6
1980-05-31 | 1980 | 5 | Wisley | 18.3
1980-06-01 | 1980 | 6 | Wisley | 19.2
1980-06-02 | 1980 | 6 | Wisley | 25.4
1980-06-03 | 1980 | 6 | Wisley | 27.8
1980-06-04 | 1980 | 6 | Wisley | 25.5
1980-06-06 | 1980 | 6 | Wisley | 19.2
1980-06-07 | 1980 | 6 | Wisley | 19
1980-06-08 | 1980 | 6 | Wisley | 20.1
1980-06-09 | 1980 | 6 | Wisley | 15.9
1980-06-10 | 1980 | 6 | Wisley | 17.4
1980-06-11 | 1980 | 6 | Wisley | 22.6
1980-06-12 | 1980 | 6 | Wisley | 23.1
1980-06-13 | 1980 | 6 | Wisley | 18.2
1980-06-14 | 1980 | 6 | Wisley | 19
1980-06-15 | 1980 | 6 | Wisley | 17.1
1980-06-16 | 1980 | 6 | Wisley | 17
1980-06-17 | 1980 | 6 | Wisley | 19.5
1980-06-18 | 1980 | 6 | Wisley | 16.9
1980-06-19 | 1980 | 6 | Wisley | 16.6
1980-06-20 | 1980 | 6 | Wisley | 16.9
1980-06-21 | 1980 | 6 | Wisley | 15.6
1980-06-22 | 1980 | 6 | Wisley | 15.9
1980-06-23 | 1980 | 6 | Wisley | 17
1980-06-24 | 1980 | 6 | Wisley | 18.8
1980-06-25 | 1980 | 6 | Wisley | 19.6
1980-06-26 | 1980 | 6 | Wisley | 17.6
1980-06-27 | 1980 | 6 | Wisley | 19
1980-06-28 | 1980 | 6 | Wisley | 19
1980-06-29 | 1980 | 6 | Wisley | 19.5
1980-06-30 | 1980 | 6 | Wisley | 16.5
1980-07-01 | 1980 | 7 | Wisley | 21
1980-07-02 | 1980 | 7 | Wisley | 21.1
1980-07-03 | 1980 | 7 | Wisley | 17.6
1980-07-04 | 1980 | 7 | Wisley | 18.9
1980-07-05 | 1980 | 7 | Wisley | 18
1980-07-06 | 1980 | 7 | Wisley | 17.2
1980-07-09 | 1980 | 7 | Wisley | 16.4
1980-07-10 | 1980 | 7 | Wisley | 19
1980-07-11 | 1980 | 7 | Wisley | 16.5
1980-07-12 | 1980 | 7 | Wisley | 17.2
1980-07-13 | 1980 | 7 | Wisley | 17.4
1980-07-14 | 1980 | 7 | Wisley | 17.2
1980-07-15 | 1980 | 7 | Wisley | 19.5
1980-07-16 | 1980 | 7 | Wisley | 16.6
1980-07-17 | 1980 | 7 | Wisley | 17.3
1980-07-18 | 1980 | 7 | Wisley | 19.6
1980-07-19 | 1980 | 7 | Wisley | 17.5
1980-07-20 | 1980 | 7 | Wisley | 19.4
1980-07-21 | 1980 | 7 | Wisley | 21
1980-07-22 | 1980 | 7 | Wisley | 24
1980-07-23 | 1980 | 7 | Wisley | 24.1
1980-07-24 | 1980 | 7 | Wisley | 27
1980-07-25 | 1980 | 7 | Wisley | 20.9
1980-07-27 | 1980 | 7 | Wisley | 25.4
1980-07-28 | 1980 | 7 | Wisley | 24.9
1980-07-30 | 1980 | 7 | Wisley | 21
1980-07-31 | 1980 | 7 | Wisley | 22.5
1980-08-01 | 1980 | 8 | Wisley | 25
1980-08-02 | 1980 | 8 | Wisley | 21.8
1980-08-03 | 1980 | 8 | Wisley | 19.9
1980-08-04 | 1980 | 8 | Wisley | 19.5
1980-08-05 | 1980 | 8 | Wisley | 21.6
1980-08-06 | 1980 | 8 | Wisley | 24.1
1980-08-07 | 1980 | 8 | Wisley | 19
1980-08-08 | 1980 | 8 | Wisley | 21.9
1980-08-09 | 1980 | 8 | Wisley | 23.6
1980-08-10 | 1980 | 8 | Wisley | 18.9
1980-08-11 | 1980 | 8 | Wisley | 19.9
1980-08-12 | 1980 | 8 | Wisley | 25.1
1980-08-13 | 1980 | 8 | Wisley | 23.1
1980-08-14 | 1980 | 8 | Wisley | 23.3
1980-08-15 | 1980 | 8 | Wisley | 23.4
1980-08-16 | 1980 | 8 | Wisley | 22.4
1980-08-17 | 1980 | 8 | Wisley | 21.9
1980-08-18 | 1980 | 8 | Wisley | 19.2
1980-08-19 | 1980 | 8 | Wisley | 24.9
1980-08-20 | 1980 | 8 | Wisley | 20.6
1980-08-22 | 1980 | 8 | Wisley | 18.4
1980-08-23 | 1980 | 8 | Wisley | 20.1
1980-08-24 | 1980 | 8 | Wisley | 20.4
1980-08-25 | 1980 | 8 | Wisley | 22.8
1980-08-26 | 1980 | 8 | Wisley | 24.5
1980-08-27 | 1980 | 8 | Wisley | 22.5
1980-08-29 | 1980 | 8 | Wisley | 20.3
1980-08-30 | 1980 | 8 | Wisley | 20.4
1980-08-31 | 1980 | 8 | Wisley | 21.5
1980-09-01 | 1980 | 9 | Wisley | 21.7
1980-09-02 | 1980 | 9 | Wisley | 23.9
1980-09-03 | 1980 | 9 | Wisley | 20.9
1980-09-04 | 1980 | 9 | Wisley | 19.7
1980-09-05 | 1980 | 9 | Wisley | 20.9
1980-09-06 | 1980 | 9 | Wisley | 22.2
1980-09-07 | 1980 | 9 | Wisley | 20.6
1980-09-08 | 1980 | 9 | Wisley | 17.2
1980-09-09 | 1980 | 9 | Wisley | 19.2
1980-09-10 | 1980 | 9 | Wisley | 18
1980-09-11 | 1980 | 9 | Wisley | 19.4
1980-09-12 | 1980 | 9 | Wisley | 18.1
1980-09-13 | 1980 | 9 | Wisley | 19.9
1980-09-14 | 1980 | 9 | Wisley | 18.5
1980-09-15 | 1980 | 9 | Wisley | 18.9
1980-09-16 | 1980 | 9 | Wisley | 18.4
1980-09-17 | 1980 | 9 | Wisley | 18
1980-09-18 | 1980 | 9 | Wisley | 20.6
1980-09-19 | 1980 | 9 | Wisley | 19.9
1980-09-20 | 1980 | 9 | Wisley | 19.6
1980-09-21 | 1980 | 9 | Wisley | 19.5
1980-09-22 | 1980 | 9 | Wisley | 19.8
1980-09-23 | 1980 | 9 | Wisley | 18.6
1980-09-24 | 1980 | 9 | Wisley | 20
1980-09-25 | 1980 | 9 | Wisley | 20
1980-09-26 | 1980 | 9 | Wisley | 18.5
1980-09-27 | 1980 | 9 | Wisley | 16.6
1980-09-28 | 1980 | 9 | Wisley | 17.6
1980-09-29 | 1980 | 9 | Wisley | 19
1980-09-30 | 1980 | 9 | Wisley | 18.6
1981-05-02 | 1981 | 5 | Wisley | 9
1981-05-03 | 1981 | 5 | Wisley | 12
1981-05-04 | 1981 | 5 | Wisley | 13.5
1981-05-05 | 1981 | 5 | Wisley | 17.4
1981-05-06 | 1981 | 5 | Wisley | 19.7
1981-05-07 | 1981 | 5 | Wisley | 17.9
1981-05-08 | 1981 | 5 | Wisley | 16.5
1981-05-09 | 1981 | 5 | Wisley | 16.2
1981-05-10 | 1981 | 5 | Wisley | 21.4
1981-05-11 | 1981 | 5 | Wisley | 17.6
1981-05-13 | 1981 | 5 | Wisley | 15.9
1981-05-14 | 1981 | 5 | Wisley | 17.7
1981-05-15 | 1981 | 5 | Wisley | 14.4
1981-05-16 | 1981 | 5 | Wisley | 14.7
1981-05-17 | 1981 | 5 | Wisley | 15.5
1981-05-18 | 1981 | 5 | Wisley | 18.9
1981-05-19 | 1981 | 5 | Wisley | 20.6
1981-05-20 | 1981 | 5 | Wisley | 17.5
1981-05-21 | 1981 | 5 | Wisley | 16.3
1981-05-22 | 1981 | 5 | Wisley | 14.1
1981-05-23 | 1981 | 5 | Wisley | 15.6
1981-05-24 | 1981 | 5 | Wisley | 13
1981-05-25 | 1981 | 5 | Wisley | 15
1981-05-26 | 1981 | 5 | Wisley | 17.1
1981-05-27 | 1981 | 5 | Wisley | 14.4
1981-05-28 | 1981 | 5 | Wisley | 17.2
1981-05-29 | 1981 | 5 | Wisley | 19.4
1981-05-30 | 1981 | 5 | Wisley | 21.2
1981-05-31 | 1981 | 5 | Wisley | 22.6
1981-06-01 | 1981 | 6 | Wisley | 18.8
1981-06-02 | 1981 | 6 | Wisley | 19.4
1981-06-03 | 1981 | 6 | Wisley | 16.6
1981-06-04 | 1981 | 6 | Wisley | 17
1981-06-05 | 1981 | 6 | Wisley | 17.1
1981-06-06 | 1981 | 6 | Wisley | 17.1
1981-06-07 | 1981 | 6 | Wisley | 18.2
1981-06-08 | 1981 | 6 | Wisley | 17
1981-06-09 | 1981 | 6 | Wisley | 16.5
1981-06-10 | 1981 | 6 | Wisley | 17.7
1981-06-11 | 1981 | 6 | Wisley | 18.4
1981-06-12 | 1981 | 6 | Wisley | 21.3
1981-06-13 | 1981 | 6 | Wisley | 26.4
1981-06-14 | 1981 | 6 | Wisley | 20
1981-06-16 | 1981 | 6 | Wisley | 15
1981-06-17 | 1981 | 6 | Wisley | 16.9
1981-06-18 | 1981 | 6 | Wisley | 15.6
1981-06-19 | 1981 | 6 | Wisley | 18.8
1981-06-20 | 1981 | 6 | Wisley | 18.1
1981-06-21 | 1981 | 6 | Wisley | 22.6
1981-06-22 | 1981 | 6 | Wisley | 21
1981-06-23 | 1981 | 6 | Wisley | 18.5
1981-06-26 | 1981 | 6 | Wisley | 15.6
1981-06-27 | 1981 | 6 | Wisley | 14.3
1981-06-28 | 1981 | 6 | Wisley | 19
1981-06-29 | 1981 | 6 | Wisley | 21.1
1981-06-30 | 1981 | 6 | Wisley | 19.3
1981-07-01 | 1981 | 7 | Wisley | 17.7
1981-07-02 | 1981 | 7 | Wisley | 17.4
1981-07-03 | 1981 | 7 | Wisley | 18.9
1981-07-04 | 1981 | 7 | Wisley | 20.2
1981-07-05 | 1981 | 7 | Wisley | 20.6
1981-07-06 | 1981 | 7 | Wisley | 23.6
1981-07-07 | 1981 | 7 | Wisley | 26.6
1981-07-08 | 1981 | 7 | Wisley | 26.4
1981-07-09 | 1981 | 7 | Wisley | 21.9
1981-07-10 | 1981 | 7 | Wisley | 21.9
1981-07-11 | 1981 | 7 | Wisley | 22
1981-07-12 | 1981 | 7 | Wisley | 22.1
1981-07-13 | 1981 | 7 | Wisley | 22.4
1981-07-14 | 1981 | 7 | Wisley | 22.7
1981-07-15 | 1981 | 7 | Wisley | 20.4
1981-07-16 | 1981 | 7 | Wisley | 18
1981-07-17 | 1981 | 7 | Wisley | 19.6
1981-07-18 | 1981 | 7 | Wisley | 22.5
1981-07-19 | 1981 | 7 | Wisley | 23.5
1981-07-20 | 1981 | 7 | Wisley | 23.9
1981-07-23 | 1981 | 7 | Wisley | 17
1981-07-24 | 1981 | 7 | Wisley | 18
1981-07-25 | 1981 | 7 | Wisley | 24
1981-07-26 | 1981 | 7 | Wisley | 23.9
1981-07-27 | 1981 | 7 | Wisley | 26
1981-07-28 | 1981 | 7 | Wisley | 24.4
1981-07-29 | 1981 | 7 | Wisley | 23.4
1981-07-30 | 1981 | 7 | Wisley | 21.6
1981-07-31 | 1981 | 7 | Wisley | 17.3
1981-08-01 | 1981 | 8 | Wisley | 21.1
1981-08-02 | 1981 | 8 | Wisley | 25.1
1981-08-03 | 1981 | 8 | Wisley | 27.2
1981-08-04 | 1981 | 8 | Wisley | 28.5
1981-08-07 | 1981 | 8 | Wisley | 19.4
1981-08-08 | 1981 | 8 | Wisley | 17.9
1981-08-09 | 1981 | 8 | Wisley | 20.2
1981-08-10 | 1981 | 8 | Wisley | 23.9
1981-08-11 | 1981 | 8 | Wisley | 25.2
1981-08-12 | 1981 | 8 | Wisley | 24.4
1981-08-13 | 1981 | 8 | Wisley | 25.7
1981-08-14 | 1981 | 8 | Wisley | 25.9
1981-08-16 | 1981 | 8 | Wisley | 22
1981-08-17 | 1981 | 8 | Wisley | 23.4
1981-08-18 | 1981 | 8 | Wisley | 21.6
1981-08-19 | 1981 | 8 | Wisley | 19.9
1981-08-20 | 1981 | 8 | Wisley | 20.1
1981-08-21 | 1981 | 8 | Wisley | 21.5
1981-08-22 | 1981 | 8 | Wisley | 21.1
1981-08-23 | 1981 | 8 | Wisley | 21.6
1981-08-24 | 1981 | 8 | Wisley | 24.8
1981-08-25 | 1981 | 8 | Wisley | 25.9
1981-08-26 | 1981 | 8 | Wisley | 27.4
1981-08-27 | 1981 | 8 | Wisley | 27.4
1981-08-28 | 1981 | 8 | Wisley | 23.2
1981-08-29 | 1981 | 8 | Wisley | 22.2
1981-08-30 | 1981 | 8 | Wisley | 20.4
1981-08-31 | 1981 | 8 | Wisley | 19.4
1981-09-01 | 1981 | 9 | Wisley | 20.9
1981-09-02 | 1981 | 9 | Wisley | 21.6
1981-09-03 | 1981 | 9 | Wisley | 23
1981-09-04 | 1981 | 9 | Wisley | 24.5
1981-09-05 | 1981 | 9 | Wisley | 25
1981-09-06 | 1981 | 9 | Wisley | 21.5
1981-09-07 | 1981 | 9 | Wisley | 23.3
1981-09-08 | 1981 | 9 | Wisley | 23.5
1981-09-09 | 1981 | 9 | Wisley | 24
1981-09-10 | 1981 | 9 | Wisley | 21
1981-09-11 | 1981 | 9 | Wisley | 18.4
1981-09-12 | 1981 | 9 | Wisley | 18.2
1981-09-13 | 1981 | 9 | Wisley | 18.5
1981-09-14 | 1981 | 9 | Wisley | 20.7
1981-09-15 | 1981 | 9 | Wisley | 18.6
1981-09-16 | 1981 | 9 | Wisley | 19.7
1981-09-17 | 1981 | 9 | Wisley | 19.5
1981-09-18 | 1981 | 9 | Wisley | 17.8
1981-09-19 | 1981 | 9 | Wisley | 17
1981-09-20 | 1981 | 9 | Wisley | 19
1981-09-21 | 1981 | 9 | Wisley | 19.5
1981-09-22 | 1981 | 9 | Wisley | 18
1981-09-23 | 1981 | 9 | Wisley | 17.7
1981-09-24 | 1981 | 9 | Wisley | 17.6
1981-09-25 | 1981 | 9 | Wisley | 15.4
1981-09-26 | 1981 | 9 | Wisley | 16.9
1981-09-27 | 1981 | 9 | Wisley | 18.1
1981-09-28 | 1981 | 9 | Wisley | 17
1981-09-29 | 1981 | 9 | Wisley | 19
1981-09-30 | 1981 | 9 | Wisley | 18.7
1982-05-01 | 1982 | 5 | Wisley | 12.9
1982-05-02 | 1982 | 5 | Wisley | 12.5
1982-05-03 | 1982 | 5 | Wisley | 12.4
1982-05-04 | 1982 | 5 | Wisley | 11
1982-05-05 | 1982 | 5 | Wisley | 10.2
1982-05-06 | 1982 | 5 | Wisley | 11.7
1982-05-07 | 1982 | 5 | Wisley | 13.7
1982-05-08 | 1982 | 5 | Wisley | 15.9
1982-05-09 | 1982 | 5 | Wisley | 16.8
1982-05-10 | 1982 | 5 | Wisley | 18.6
1982-05-11 | 1982 | 5 | Wisley | 20.5
1982-05-12 | 1982 | 5 | Wisley | 24.1
1982-05-13 | 1982 | 5 | Wisley | 24
1982-05-14 | 1982 | 5 | Wisley | 26.8
1982-05-15 | 1982 | 5 | Wisley | 23.2
1982-05-16 | 1982 | 5 | Wisley | 18.7
1982-05-17 | 1982 | 5 | Wisley | 20.7
1982-05-18 | 1982 | 5 | Wisley | 18
1982-05-19 | 1982 | 5 | Wisley | 16.4
1982-05-20 | 1982 | 5 | Wisley | 18.6
1982-05-21 | 1982 | 5 | Wisley | 16.6
1982-05-22 | 1982 | 5 | Wisley | 15.5
1982-05-23 | 1982 | 5 | Wisley | 16.6
1982-05-24 | 1982 | 5 | Wisley | 19.9
1982-05-25 | 1982 | 5 | Wisley | 24.6
1982-05-26 | 1982 | 5 | Wisley | 16
1982-05-27 | 1982 | 5 | Wisley | 20
1982-05-28 | 1982 | 5 | Wisley | 22.8
1982-05-29 | 1982 | 5 | Wisley | 22.1
1982-05-30 | 1982 | 5 | Wisley | 25.5
1982-05-31 | 1982 | 5 | Wisley | 25.4
1982-06-01 | 1982 | 6 | Wisley | 25.7
1982-06-02 | 1982 | 6 | Wisley | 23.5
1982-06-03 | 1982 | 6 | Wisley | 28.1
1982-06-04 | 1982 | 6 | Wisley | 28.1
1982-06-05 | 1982 | 6 | Wisley | 25.4
1982-06-06 | 1982 | 6 | Wisley | 25.1
1982-06-07 | 1982 | 6 | Wisley | 25
1982-06-08 | 1982 | 6 | Wisley | 23.2
1982-06-09 | 1982 | 6 | Wisley | 20
1982-06-10 | 1982 | 6 | Wisley | 19.8
1982-06-11 | 1982 | 6 | Wisley | 18.3
1982-06-12 | 1982 | 6 | Wisley | 15.2
1982-06-13 | 1982 | 6 | Wisley | 17.3
1982-06-14 | 1982 | 6 | Wisley | 17.9
1982-06-15 | 1982 | 6 | Wisley | 20.8
1982-06-16 | 1982 | 6 | Wisley | 21.9
1982-06-17 | 1982 | 6 | Wisley | 18
1982-06-18 | 1982 | 6 | Wisley | 19.6
1982-06-19 | 1982 | 6 | Wisley | 20.9
1982-06-20 | 1982 | 6 | Wisley | 20
1982-06-21 | 1982 | 6 | Wisley | 18.1
1982-06-22 | 1982 | 6 | Wisley | 18
1982-06-23 | 1982 | 6 | Wisley | 20.5
1982-06-24 | 1982 | 6 | Wisley | 17.6
1982-06-25 | 1982 | 6 | Wisley | 18.4
1982-06-26 | 1982 | 6 | Wisley | 19.7
1982-06-27 | 1982 | 6 | Wisley | 18.2
1982-06-28 | 1982 | 6 | Wisley | 19.7
1982-06-29 | 1982 | 6 | Wisley | 20.8
1982-06-30 | 1982 | 6 | Wisley | 19.6
1982-07-01 | 1982 | 7 | Wisley | 22.5
1982-07-02 | 1982 | 7 | Wisley | 19.8
1982-07-03 | 1982 | 7 | Wisley | 18.1
1982-07-04 | 1982 | 7 | Wisley | 21.6
1982-07-05 | 1982 | 7 | Wisley | 22.5
1982-07-06 | 1982 | 7 | Wisley | 23.6
1982-07-07 | 1982 | 7 | Wisley | 27.4
1982-07-08 | 1982 | 7 | Wisley | 26.1
1982-07-09 | 1982 | 7 | Wisley | 23.3
1982-07-10 | 1982 | 7 | Wisley | 26.2
1982-07-11 | 1982 | 7 | Wisley | 19.3
1982-07-12 | 1982 | 7 | Wisley | 27.1
1982-07-13 | 1982 | 7 | Wisley | 23.2
1982-07-15 | 1982 | 7 | Wisley | 20.2
1982-07-16 | 1982 | 7 | Wisley | 23.1
1982-07-17 | 1982 | 7 | Wisley | 24.4
1982-07-18 | 1982 | 7 | Wisley | 23
1982-07-19 | 1982 | 7 | Wisley | 22.5
1982-07-20 | 1982 | 7 | Wisley | 19.6
1982-07-21 | 1982 | 7 | Wisley | 22
1982-07-22 | 1982 | 7 | Wisley | 17.7
1982-07-23 | 1982 | 7 | Wisley | 18.9
1982-07-24 | 1982 | 7 | Wisley | 25
1982-07-25 | 1982 | 7 | Wisley | 22.1
1982-07-27 | 1982 | 7 | Wisley | 22.5
1982-07-28 | 1982 | 7 | Wisley | 23.9
1982-07-29 | 1982 | 7 | Wisley | 25.4
1982-07-30 | 1982 | 7 | Wisley | 25.3
1982-07-31 | 1982 | 7 | Wisley | 26.3
1982-08-01 | 1982 | 8 | Wisley | 27.4
1982-08-02 | 1982 | 8 | Wisley | 26.5
1982-08-03 | 1982 | 8 | Wisley | 24.9
1982-08-04 | 1982 | 8 | Wisley | 21.9
1982-08-05 | 1982 | 8 | Wisley | 24.7
1982-08-06 | 1982 | 8 | Wisley | 20
1982-08-07 | 1982 | 8 | Wisley | 25.3
1982-08-08 | 1982 | 8 | Wisley | 24.9
1982-08-09 | 1982 | 8 | Wisley | 25
1982-08-10 | 1982 | 8 | Wisley | 24
1982-08-11 | 1982 | 8 | Wisley | 23
1982-08-12 | 1982 | 8 | Wisley | 20.4
1982-08-13 | 1982 | 8 | Wisley | 20.8
1982-08-25 | 1982 | 8 | Wisley | 18.6
1982-08-26 | 1982 | 8 | Wisley | 19.2
1982-08-27 | 1982 | 8 | Wisley | 20.6
1982-08-28 | 1982 | 8 | Wisley | 21
1982-08-29 | 1982 | 8 | Wisley | 20.4
1982-08-31 | 1982 | 8 | Wisley | 18
1982-09-01 | 1982 | 9 | Wisley | 20.6
1982-09-02 | 1982 | 9 | Wisley | 22.5
1982-09-03 | 1982 | 9 | Wisley | 23.3
1982-09-04 | 1982 | 9 | Wisley | 24.4
1982-09-05 | 1982 | 9 | Wisley | 16.3
1982-09-06 | 1982 | 9 | Wisley | 21.6
1982-09-07 | 1982 | 9 | Wisley | 20
1982-09-08 | 1982 | 9 | Wisley | 21.4
1982-09-09 | 1982 | 9 | Wisley | 23.9
1982-09-10 | 1982 | 9 | Wisley | 21.9
1982-09-11 | 1982 | 9 | Wisley | 22.1
1982-09-12 | 1982 | 9 | Wisley | 21.7
1982-09-13 | 1982 | 9 | Wisley | 22
1982-09-14 | 1982 | 9 | Wisley | 27.6
1982-09-15 | 1982 | 9 | Wisley | 26.5
1982-09-16 | 1982 | 9 | Wisley | 25.1
1982-09-17 | 1982 | 9 | Wisley | 27.3
1982-09-18 | 1982 | 9 | Wisley | 19
1982-09-20 | 1982 | 9 | Wisley | 16.9
1982-09-22 | 1982 | 9 | Wisley | 16.6
1982-09-23 | 1982 | 9 | Wisley | 17
1982-09-24 | 1982 | 9 | Wisley | 20
1982-09-25 | 1982 | 9 | Wisley | 17.6
1982-09-26 | 1982 | 9 | Wisley | 15.7
1982-09-27 | 1982 | 9 | Wisley | 17.7
1982-09-28 | 1982 | 9 | Wisley | 13
1982-09-29 | 1982 | 9 | Wisley | 17.9
1982-09-30 | 1982 | 9 | Wisley | 18.1
1983-05-02 | 1983 | 5 | Wisley | 13.6
1983-05-03 | 1983 | 5 | Wisley | 14.5
1983-05-04 | 1983 | 5 | Wisley | 18
1983-05-05 | 1983 | 5 | Wisley | 18
1983-05-06 | 1983 | 5 | Wisley | 15.7
1983-05-07 | 1983 | 5 | Wisley | 16.5
1983-05-08 | 1983 | 5 | Wisley | 13.6
1983-05-09 | 1983 | 5 | Wisley | 12.2
1983-05-10 | 1983 | 5 | Wisley | 13.6
1983-05-11 | 1983 | 5 | Wisley | 14
1983-05-12 | 1983 | 5 | Wisley | 15
1983-05-13 | 1983 | 5 | Wisley | 16
1983-05-14 | 1983 | 5 | Wisley | 16.3
1983-05-15 | 1983 | 5 | Wisley | 18.4
1983-05-16 | 1983 | 5 | Wisley | 14.4
1983-05-17 | 1983 | 5 | Wisley | 15.4
1983-05-18 | 1983 | 5 | Wisley | 14.1
1983-05-19 | 1983 | 5 | Wisley | 14
1983-05-20 | 1983 | 5 | Wisley | 14.4
1983-05-21 | 1983 | 5 | Wisley | 15.3
1983-05-22 | 1983 | 5 | Wisley | 15.8
1983-05-23 | 1983 | 5 | Wisley | 16.7
1983-05-24 | 1983 | 5 | Wisley | 18.5
1983-05-25 | 1983 | 5 | Wisley | 14.6
1983-05-26 | 1983 | 5 | Wisley | 15.3
1983-05-27 | 1983 | 5 | Wisley | 11.7
1983-05-28 | 1983 | 5 | Wisley | 14.4
1983-05-29 | 1983 | 5 | Wisley | 17.6
1983-05-30 | 1983 | 5 | Wisley | 22.8
1983-05-31 | 1983 | 5 | Wisley | 20.4
1983-06-02 | 1983 | 6 | Wisley | 20
1983-06-03 | 1983 | 6 | Wisley | 22.2
1983-06-04 | 1983 | 6 | Wisley | 21.6
1983-06-05 | 1983 | 6 | Wisley | 19.9
1983-06-06 | 1983 | 6 | Wisley | 24.5
1983-06-07 | 1983 | 6 | Wisley | 22.9
1983-06-09 | 1983 | 6 | Wisley | 20.2
1983-06-10 | 1983 | 6 | Wisley | 19.2
1983-06-11 | 1983 | 6 | Wisley | 19.9
1983-06-12 | 1983 | 6 | Wisley | 18.1
1983-06-13 | 1983 | 6 | Wisley | 18.4
1983-06-14 | 1983 | 6 | Wisley | 17.4
1983-06-15 | 1983 | 6 | Wisley | 19.5
1983-06-16 | 1983 | 6 | Wisley | 17
1983-06-17 | 1983 | 6 | Wisley | 20.5
1983-06-18 | 1983 | 6 | Wisley | 23.8
1983-06-19 | 1983 | 6 | Wisley | 23.4
1983-06-20 | 1983 | 6 | Wisley | 24.5
1983-06-21 | 1983 | 6 | Wisley | 23.9
1983-06-22 | 1983 | 6 | Wisley | 23
1983-06-24 | 1983 | 6 | Wisley | 22.1
1983-06-25 | 1983 | 6 | Wisley | 24.4
1983-06-26 | 1983 | 6 | Wisley | 15.4
1983-06-27 | 1983 | 6 | Wisley | 20.5
1983-06-28 | 1983 | 6 | Wisley | 21
1983-06-29 | 1983 | 6 | Wisley | 18.6
1983-06-30 | 1983 | 6 | Wisley | 20.9
1983-07-01 | 1983 | 7 | Wisley | 24.1
1983-07-02 | 1983 | 7 | Wisley | 25.8
1983-07-03 | 1983 | 7 | Wisley | 28.1
1983-07-04 | 1983 | 7 | Wisley | 28.2
1983-07-05 | 1983 | 7 | Wisley | 26.3
1983-07-06 | 1983 | 7 | Wisley | 26
1983-07-07 | 1983 | 7 | Wisley | 28.1
1983-07-08 | 1983 | 7 | Wisley | 27.9
1983-07-09 | 1983 | 7 | Wisley | 27.3
1983-07-10 | 1983 | 7 | Wisley | 31
1983-07-11 | 1983 | 7 | Wisley | 31.5
1983-07-12 | 1983 | 7 | Wisley | 31.6
1983-07-13 | 1983 | 7 | Wisley | 30.4
1983-07-14 | 1983 | 7 | Wisley | 31.2
1983-07-15 | 1983 | 7 | Wisley | 32.1
1983-07-16 | 1983 | 7 | Wisley | 27
1983-07-17 | 1983 | 7 | Wisley | 27.5
1983-07-18 | 1983 | 7 | Wisley | 25.6
1983-07-19 | 1983 | 7 | Wisley | 22
1983-07-20 | 1983 | 7 | Wisley | 24.4
1983-07-21 | 1983 | 7 | Wisley | 29.4
1983-07-22 | 1983 | 7 | Wisley | 24.2
1983-07-24 | 1983 | 7 | Wisley | 26
1983-07-25 | 1983 | 7 | Wisley | 28.4
1983-07-26 | 1983 | 7 | Wisley | 27.4
1983-07-27 | 1983 | 7 | Wisley | 26.6
1983-07-28 | 1983 | 7 | Wisley | 30.6
1983-07-29 | 1983 | 7 | Wisley | 30.2
1983-07-30 | 1983 | 7 | Wisley | 28
1983-08-02 | 1983 | 8 | Wisley | 21.9
1983-08-03 | 1983 | 8 | Wisley | 23
1983-08-04 | 1983 | 8 | Wisley | 23.9
1983-08-05 | 1983 | 8 | Wisley | 21.2
1983-08-06 | 1983 | 8 | Wisley | 22.2
1983-08-07 | 1983 | 8 | Wisley | 25.3
1983-08-08 | 1983 | 8 | Wisley | 26.9
1983-08-09 | 1983 | 8 | Wisley | 25.5
1983-08-10 | 1983 | 8 | Wisley | 21.6
1983-08-11 | 1983 | 8 | Wisley | 24.5
1983-08-12 | 1983 | 8 | Wisley | 23.6
1983-08-13 | 1983 | 8 | Wisley | 28
1983-08-14 | 1983 | 8 | Wisley | 26
1983-08-15 | 1983 | 8 | Wisley | 24.5
1983-08-16 | 1983 | 8 | Wisley | 25
1983-08-17 | 1983 | 8 | Wisley | 26
1983-08-18 | 1983 | 8 | Wisley | 29.4
1983-08-19 | 1983 | 8 | Wisley | 23.3
1983-08-21 | 1983 | 8 | Wisley | 23.5
1983-08-22 | 1983 | 8 | Wisley | 26
1983-08-23 | 1983 | 8 | Wisley | 22
1983-08-24 | 1983 | 8 | Wisley | 25.7
1983-08-25 | 1983 | 8 | Wisley | 26
1983-08-26 | 1983 | 8 | Wisley | 25.6
1983-08-27 | 1983 | 8 | Wisley | 21
1983-08-28 | 1983 | 8 | Wisley | 19
1983-08-29 | 1983 | 8 | Wisley | 21.8
1983-08-30 | 1983 | 8 | Wisley | 26.5
1983-08-31 | 1983 | 8 | Wisley | 22.4
1983-09-01 | 1983 | 9 | Wisley | 19.4
1983-09-02 | 1983 | 9 | Wisley | 17.8
1983-09-03 | 1983 | 9 | Wisley | 21.1
1983-09-04 | 1983 | 9 | Wisley | 20.5
1983-09-05 | 1983 | 9 | Wisley | 19.9
1983-09-06 | 1983 | 9 | Wisley | 20.5
1983-09-07 | 1983 | 9 | Wisley | 18.9
1983-09-08 | 1983 | 9 | Wisley | 18.1
1983-09-09 | 1983 | 9 | Wisley | 17.5
1983-09-11 | 1983 | 9 | Wisley | 15.6
1983-09-12 | 1983 | 9 | Wisley | 16.1
1983-09-13 | 1983 | 9 | Wisley | 19.6
1983-09-14 | 1983 | 9 | Wisley | 18
1983-09-15 | 1983 | 9 | Wisley | 16.5
1983-09-16 | 1983 | 9 | Wisley | 17.8
1983-09-17 | 1983 | 9 | Wisley | 17.6
1983-09-18 | 1983 | 9 | Wisley | 18.1
1983-09-19 | 1983 | 9 | Wisley | 16.3
1983-09-20 | 1983 | 9 | Wisley | 15.9
1983-09-21 | 1983 | 9 | Wisley | 17.4
1983-09-22 | 1983 | 9 | Wisley | 22
1983-09-23 | 1983 | 9 | Wisley | 22.5
1983-09-24 | 1983 | 9 | Wisley | 20.6
1983-09-25 | 1983 | 9 | Wisley | 23.3
1983-09-26 | 1983 | 9 | Wisley | 18.3
1983-09-27 | 1983 | 9 | Wisley | 21.2
1983-09-28 | 1983 | 9 | Wisley | 19.3
1983-09-29 | 1983 | 9 | Wisley | 18.4
1983-09-30 | 1983 | 9 | Wisley | 16.5
1984-05-01 | 1984 | 5 | Wisley | 17.2
1984-05-02 | 1984 | 5 | Wisley | 13.4
1984-05-03 | 1984 | 5 | Wisley | 16.6
1984-05-04 | 1984 | 5 | Wisley | 16.7
1984-05-05 | 1984 | 5 | Wisley | 12.3
1984-05-06 | 1984 | 5 | Wisley | 13.4
1984-05-07 | 1984 | 5 | Wisley | 11
1984-05-08 | 1984 | 5 | Wisley | 15.5
1984-05-09 | 1984 | 5 | Wisley | 11.4
1984-05-10 | 1984 | 5 | Wisley | 14.4
1984-05-11 | 1984 | 5 | Wisley | 14.5
1984-05-12 | 1984 | 5 | Wisley | 16.4
1984-05-13 | 1984 | 5 | Wisley | 16.1
1984-05-14 | 1984 | 5 | Wisley | 13
1984-05-15 | 1984 | 5 | Wisley | 16.5
1984-05-16 | 1984 | 5 | Wisley | 13.9
1984-05-17 | 1984 | 5 | Wisley | 14.4
1984-05-18 | 1984 | 5 | Wisley | 16
1984-05-19 | 1984 | 5 | Wisley | 11.3
1984-05-20 | 1984 | 5 | Wisley | 13
1984-05-21 | 1984 | 5 | Wisley | 13.6
1984-05-22 | 1984 | 5 | Wisley | 18
1984-05-23 | 1984 | 5 | Wisley | 22.6
1984-05-27 | 1984 | 5 | Wisley | 10.2
1984-05-28 | 1984 | 5 | Wisley | 17
1984-05-29 | 1984 | 5 | Wisley | 20
1984-05-30 | 1984 | 5 | Wisley | 19.3
1984-05-31 | 1984 | 5 | Wisley | 15.4
1984-06-01 | 1984 | 6 | Wisley | 16
1984-06-02 | 1984 | 6 | Wisley | 15.6
1984-06-03 | 1984 | 6 | Wisley | 17.4
1984-06-04 | 1984 | 6 | Wisley | 15
1984-06-05 | 1984 | 6 | Wisley | 18
1984-06-06 | 1984 | 6 | Wisley | 21.1
1984-06-07 | 1984 | 6 | Wisley | 21.9
1984-06-08 | 1984 | 6 | Wisley | 23
1984-06-09 | 1984 | 6 | Wisley | 24.1
1984-06-10 | 1984 | 6 | Wisley | 18.1
1984-06-11 | 1984 | 6 | Wisley | 18.5
1984-06-12 | 1984 | 6 | Wisley | 20
1984-06-13 | 1984 | 6 | Wisley | 23.5
1984-06-14 | 1984 | 6 | Wisley | 23.6
1984-06-15 | 1984 | 6 | Wisley | 24.1
1984-06-16 | 1984 | 6 | Wisley | 25.9
1984-06-17 | 1984 | 6 | Wisley | 26
1984-06-18 | 1984 | 6 | Wisley | 25.9
1984-06-19 | 1984 | 6 | Wisley | 26.6
1984-06-20 | 1984 | 6 | Wisley | 22
1984-06-22 | 1984 | 6 | Wisley | 20
1984-06-23 | 1984 | 6 | Wisley | 21.1
1984-06-24 | 1984 | 6 | Wisley | 22.9
1984-06-25 | 1984 | 6 | Wisley | 25.2
1984-06-26 | 1984 | 6 | Wisley | 24.2
1984-06-27 | 1984 | 6 | Wisley | 17.5
1984-06-28 | 1984 | 6 | Wisley | 18.2
1984-06-29 | 1984 | 6 | Wisley | 19.5
1984-06-30 | 1984 | 6 | Wisley | 21.2
1984-07-01 | 1984 | 7 | Wisley | 17.9
1984-07-02 | 1984 | 7 | Wisley | 21.5
1984-07-03 | 1984 | 7 | Wisley | 22.1
1984-07-04 | 1984 | 7 | Wisley | 26
1984-07-05 | 1984 | 7 | Wisley | 27.4
1984-07-06 | 1984 | 7 | Wisley | 26.5
1984-07-07 | 1984 | 7 | Wisley | 29.9
1984-07-08 | 1984 | 7 | Wisley | 23.5
1984-07-09 | 1984 | 7 | Wisley | 22.6
1984-07-10 | 1984 | 7 | Wisley | 22.1
1984-07-11 | 1984 | 7 | Wisley | 19.4
1984-07-12 | 1984 | 7 | Wisley | 20.7
1984-07-13 | 1984 | 7 | Wisley | 19.3
1984-07-14 | 1984 | 7 | Wisley | 19
1984-07-15 | 1984 | 7 | Wisley | 21.2
1984-07-16 | 1984 | 7 | Wisley | 22.5
1984-07-17 | 1984 | 7 | Wisley | 24
1984-07-18 | 1984 | 7 | Wisley | 20.5
1984-07-19 | 1984 | 7 | Wisley | 19
1984-07-20 | 1984 | 7 | Wisley | 27.1
1984-07-21 | 1984 | 7 | Wisley | 24.9
1984-07-22 | 1984 | 7 | Wisley | 27
1984-07-23 | 1984 | 7 | Wisley | 23.1
1984-07-25 | 1984 | 7 | Wisley | 23
1984-07-26 | 1984 | 7 | Wisley | 28
1984-07-27 | 1984 | 7 | Wisley | 29.1
1984-07-28 | 1984 | 7 | Wisley | 26.5
1984-07-29 | 1984 | 7 | Wisley | 28.2
1984-07-30 | 1984 | 7 | Wisley | 23.2
1984-07-31 | 1984 | 7 | Wisley | 23.6
1984-08-01 | 1984 | 8 | Wisley | 20.8
1984-08-02 | 1984 | 8 | Wisley | 21.5
1984-08-03 | 1984 | 8 | Wisley | 21.5
1984-08-04 | 1984 | 8 | Wisley | 21.4
1984-08-05 | 1984 | 8 | Wisley | 21.9
1984-08-06 | 1984 | 8 | Wisley | 18.6
1984-08-07 | 1984 | 8 | Wisley | 19.8
1984-08-08 | 1984 | 8 | Wisley | 24.1
1984-08-09 | 1984 | 8 | Wisley | 18.9
1984-08-10 | 1984 | 8 | Wisley | 22.1
1984-08-11 | 1984 | 8 | Wisley | 22.5
1984-08-12 | 1984 | 8 | Wisley | 23.5
1984-08-13 | 1984 | 8 | Wisley | 25
1984-08-14 | 1984 | 8 | Wisley | 24
1984-08-15 | 1984 | 8 | Wisley | 24
1984-08-16 | 1984 | 8 | Wisley | 23.1
1984-08-17 | 1984 | 8 | Wisley | 25.2
1984-08-18 | 1984 | 8 | Wisley | 27.5
1984-08-19 | 1984 | 8 | Wisley | 28.5
1984-08-20 | 1984 | 8 | Wisley | 29
1984-08-21 | 1984 | 8 | Wisley | 22.4
1984-08-22 | 1984 | 8 | Wisley | 26
1984-08-23 | 1984 | 8 | Wisley | 23
1984-08-24 | 1984 | 8 | Wisley | 23
1984-08-25 | 1984 | 8 | Wisley | 21.9
1984-08-26 | 1984 | 8 | Wisley | 26.2
1984-08-27 | 1984 | 8 | Wisley | 24.4
1984-08-28 | 1984 | 8 | Wisley | 24.5
1984-08-29 | 1984 | 8 | Wisley | 24
1984-08-30 | 1984 | 8 | Wisley | 23.9
1984-08-31 | 1984 | 8 | Wisley | 22.2
1984-09-01 | 1984 | 9 | Wisley | 23.4
1984-09-02 | 1984 | 9 | Wisley | 23.8
1984-09-05 | 1984 | 9 | Wisley | 17.5
1984-09-06 | 1984 | 9 | Wisley | 17.4
1984-09-07 | 1984 | 9 | Wisley | 19.7
1984-09-08 | 1984 | 9 | Wisley | 19.5
1984-09-09 | 1984 | 9 | Wisley | 16.8
1984-09-10 | 1984 | 9 | Wisley | 19.9
1984-09-11 | 1984 | 9 | Wisley | 21.8
1984-09-12 | 1984 | 9 | Wisley | 21.9
1984-09-13 | 1984 | 9 | Wisley | 18.4
1984-09-15 | 1984 | 9 | Wisley | 18.1
1984-09-16 | 1984 | 9 | Wisley | 15.9
1984-09-17 | 1984 | 9 | Wisley | 17.4
1984-09-18 | 1984 | 9 | Wisley | 17.4
1984-09-19 | 1984 | 9 | Wisley | 16.5
1984-09-20 | 1984 | 9 | Wisley | 14.9
1984-09-21 | 1984 | 9 | Wisley | 15.8
1984-09-22 | 1984 | 9 | Wisley | 13.1
1984-09-23 | 1984 | 9 | Wisley | 13
1984-09-24 | 1984 | 9 | Wisley | 15.7
1984-09-25 | 1984 | 9 | Wisley | 17.2
1984-09-26 | 1984 | 9 | Wisley | 17.9
1984-09-27 | 1984 | 9 | Wisley | 19.7
1984-09-28 | 1984 | 9 | Wisley | 19.1
1984-09-29 | 1984 | 9 | Wisley | 19
1984-09-30 | 1984 | 9 | Wisley | 16.3
1985-05-01 | 1985 | 5 | Wisley | 13.4
1985-05-02 | 1985 | 5 | Wisley | 10
1985-05-03 | 1985 | 5 | Wisley | 13.4
1985-05-04 | 1985 | 5 | Wisley | 11.9
1985-05-05 | 1985 | 5 | Wisley | 16.3
1985-05-06 | 1985 | 5 | Wisley | 19
1985-05-07 | 1985 | 5 | Wisley | 15.8
1985-05-08 | 1985 | 5 | Wisley | 15.1
1985-05-09 | 1985 | 5 | Wisley | 12.9
1985-05-10 | 1985 | 5 | Wisley | 10
1985-05-11 | 1985 | 5 | Wisley | 12.4
1985-05-12 | 1985 | 5 | Wisley | 15
1985-05-13 | 1985 | 5 | Wisley | 12.6
1985-05-14 | 1985 | 5 | Wisley | 15.9
1985-05-15 | 1985 | 5 | Wisley | 20.6
1985-05-16 | 1985 | 5 | Wisley | 21.6
1985-05-17 | 1985 | 5 | Wisley | 21.5
1985-05-18 | 1985 | 5 | Wisley | 15.4
1985-05-19 | 1985 | 5 | Wisley | 19.4
1985-05-20 | 1985 | 5 | Wisley | 16.2
1985-05-22 | 1985 | 5 | Wisley | 16.5
1985-05-23 | 1985 | 5 | Wisley | 16.4
1985-05-24 | 1985 | 5 | Wisley | 19.8
1985-05-25 | 1985 | 5 | Wisley | 21
1985-05-26 | 1985 | 5 | Wisley | 18.9
1985-05-27 | 1985 | 5 | Wisley | 18.3
1985-05-28 | 1985 | 5 | Wisley | 18.5
1985-05-29 | 1985 | 5 | Wisley | 18.4
1985-05-30 | 1985 | 5 | Wisley | 19.4
1985-05-31 | 1985 | 5 | Wisley | 22.2
1985-06-01 | 1985 | 6 | Wisley | 22.6
1985-06-02 | 1985 | 6 | Wisley | 23.7
1985-06-03 | 1985 | 6 | Wisley | 22.6
1985-06-04 | 1985 | 6 | Wisley | 20.7
1985-06-07 | 1985 | 6 | Wisley | 15.4
1985-06-08 | 1985 | 6 | Wisley | 17.6
1985-06-09 | 1985 | 6 | Wisley | 16.7
1985-06-10 | 1985 | 6 | Wisley | 16.4
1985-06-11 | 1985 | 6 | Wisley | 15.7
1985-06-12 | 1985 | 6 | Wisley | 16.5
1985-06-13 | 1985 | 6 | Wisley | 16
1985-06-14 | 1985 | 6 | Wisley | 17.2
1985-06-15 | 1985 | 6 | Wisley | 17.9
1985-06-16 | 1985 | 6 | Wisley | 18.6
1985-06-17 | 1985 | 6 | Wisley | 17.3
1985-06-18 | 1985 | 6 | Wisley | 19.1
1985-06-19 | 1985 | 6 | Wisley | 20
1985-06-20 | 1985 | 6 | Wisley | 15.2
1985-06-21 | 1985 | 6 | Wisley | 16.4
1985-06-22 | 1985 | 6 | Wisley | 18.5
1985-06-23 | 1985 | 6 | Wisley | 18
1985-06-24 | 1985 | 6 | Wisley | 16.1
1985-06-25 | 1985 | 6 | Wisley | 17.4
1985-06-26 | 1985 | 6 | Wisley | 18.3
1985-06-27 | 1985 | 6 | Wisley | 17
1985-06-28 | 1985 | 6 | Wisley | 20
1985-06-29 | 1985 | 6 | Wisley | 22.2
1985-06-30 | 1985 | 6 | Wisley | 22.4
1985-07-01 | 1985 | 7 | Wisley | 24.1
1985-07-02 | 1985 | 7 | Wisley | 24.4
1985-07-03 | 1985 | 7 | Wisley | 26.5
1985-07-04 | 1985 | 7 | Wisley | 26.2
1985-07-06 | 1985 | 7 | Wisley | 21.4
1985-07-07 | 1985 | 7 | Wisley | 24.9
1985-07-08 | 1985 | 7 | Wisley | 21.4
1985-07-09 | 1985 | 7 | Wisley | 22.2
1985-07-10 | 1985 | 7 | Wisley | 19.8
1985-07-11 | 1985 | 7 | Wisley | 22.8
1985-07-12 | 1985 | 7 | Wisley | 27.9
1985-07-13 | 1985 | 7 | Wisley | 23
1985-07-15 | 1985 | 7 | Wisley | 21.2
1985-07-16 | 1985 | 7 | Wisley | 19.6
1985-07-17 | 1985 | 7 | Wisley | 18.5
1985-07-18 | 1985 | 7 | Wisley | 19.4
1985-07-19 | 1985 | 7 | Wisley | 18.2
1985-07-20 | 1985 | 7 | Wisley | 20.1
1985-07-21 | 1985 | 7 | Wisley | 19.5
1985-07-22 | 1985 | 7 | Wisley | 24
1985-07-23 | 1985 | 7 | Wisley | 25.2
1985-07-24 | 1985 | 7 | Wisley | 28.6
1985-07-25 | 1985 | 7 | Wisley | 19
1985-07-27 | 1985 | 7 | Wisley | 18.3
1985-07-29 | 1985 | 7 | Wisley | 19.2
1985-07-30 | 1985 | 7 | Wisley | 22.9
1985-07-31 | 1985 | 7 | Wisley | 19.9
1985-08-02 | 1985 | 8 | Wisley | 18.1
1985-08-03 | 1985 | 8 | Wisley | 16.6
1985-08-04 | 1985 | 8 | Wisley | 19.3
1985-08-05 | 1985 | 8 | Wisley | 19
1985-08-06 | 1985 | 8 | Wisley | 16.2
1985-08-07 | 1985 | 8 | Wisley | 19.4
1985-08-08 | 1985 | 8 | Wisley | 17.9
1985-08-09 | 1985 | 8 | Wisley | 18.9
1985-08-10 | 1985 | 8 | Wisley | 17.8
1985-08-11 | 1985 | 8 | Wisley | 18.6
1985-08-12 | 1985 | 8 | Wisley | 19.6
1985-08-13 | 1985 | 8 | Wisley | 19.4
1985-08-14 | 1985 | 8 | Wisley | 18.6
1985-08-15 | 1985 | 8 | Wisley | 19.2
1985-08-16 | 1985 | 8 | Wisley | 22
1985-08-17 | 1985 | 8 | Wisley | 19.5
1985-08-18 | 1985 | 8 | Wisley | 20.6
1985-08-19 | 1985 | 8 | Wisley | 19.1
1985-08-20 | 1985 | 8 | Wisley | 21.6
1985-08-21 | 1985 | 8 | Wisley | 19.8
1985-08-22 | 1985 | 8 | Wisley | 17.5
1985-08-23 | 1985 | 8 | Wisley | 17.7
1985-08-24 | 1985 | 8 | Wisley | 18.3
1985-08-25 | 1985 | 8 | Wisley | 18.2
1985-08-26 | 1985 | 8 | Wisley | 19.6
1985-08-27 | 1985 | 8 | Wisley | 23
1985-08-28 | 1985 | 8 | Wisley | 24.6
1985-08-29 | 1985 | 8 | Wisley | 24.4
1985-08-30 | 1985 | 8 | Wisley | 19.5
1985-09-01 | 1985 | 9 | Wisley | 16.6
1985-09-02 | 1985 | 9 | Wisley | 18.5
1985-09-03 | 1985 | 9 | Wisley | 16.4
1985-09-04 | 1985 | 9 | Wisley | 18.6
1985-09-05 | 1985 | 9 | Wisley | 17.1
1985-09-06 | 1985 | 9 | Wisley | 19.1
1985-09-07 | 1985 | 9 | Wisley | 19.3
1985-09-08 | 1985 | 9 | Wisley | 19.1
1985-09-09 | 1985 | 9 | Wisley | 21.1
1985-09-10 | 1985 | 9 | Wisley | 24.1
1985-09-11 | 1985 | 9 | Wisley | 25.4
1985-09-12 | 1985 | 9 | Wisley | 18.2
1985-09-14 | 1985 | 9 | Wisley | 20
1985-09-15 | 1985 | 9 | Wisley | 18.8
1985-09-16 | 1985 | 9 | Wisley | 22.4
1985-09-17 | 1985 | 9 | Wisley | 19
1985-09-18 | 1985 | 9 | Wisley | 19.5
1985-09-19 | 1985 | 9 | Wisley | 18.9
1985-09-20 | 1985 | 9 | Wisley | 19
1985-09-21 | 1985 | 9 | Wisley | 22.4
1985-09-22 | 1985 | 9 | Wisley | 21
1985-09-23 | 1985 | 9 | Wisley | 18.1
1985-09-24 | 1985 | 9 | Wisley | 19.4
1985-09-25 | 1985 | 9 | Wisley | 22.3
1985-09-26 | 1985 | 9 | Wisley | 22.1
1985-09-27 | 1985 | 9 | Wisley | 23
1985-09-28 | 1985 | 9 | Wisley | 23.6
1985-09-29 | 1985 | 9 | Wisley | 24
1985-09-30 | 1985 | 9 | Wisley | 26.3
1986-05-01 | 1986 | 5 | Wisley | 20.9
1986-05-02 | 1986 | 5 | Wisley | 13.5
1986-05-04 | 1986 | 5 | Wisley | 13.6
1986-05-05 | 1986 | 5 | Wisley | 15.6
1986-05-06 | 1986 | 5 | Wisley | 12.4
1986-05-07 | 1986 | 5 | Wisley | 14
1986-05-08 | 1986 | 5 | Wisley | 15.1
1986-05-09 | 1986 | 5 | Wisley | 16.5
1986-05-10 | 1986 | 5 | Wisley | 15.4
1986-05-11 | 1986 | 5 | Wisley | 14.1
1986-05-12 | 1986 | 5 | Wisley | 15.1
1986-05-13 | 1986 | 5 | Wisley | 14.6
1986-05-14 | 1986 | 5 | Wisley | 14.5
1986-05-15 | 1986 | 5 | Wisley | 17
1986-05-16 | 1986 | 5 | Wisley | 15
1986-05-17 | 1986 | 5 | Wisley | 17.1
1986-05-18 | 1986 | 5 | Wisley | 21
1986-05-19 | 1986 | 5 | Wisley | 17.5
1986-05-21 | 1986 | 5 | Wisley | 16.1
1986-05-22 | 1986 | 5 | Wisley | 15.4
1986-05-23 | 1986 | 5 | Wisley | 15.2
1986-05-24 | 1986 | 5 | Wisley | 16.9
1986-05-25 | 1986 | 5 | Wisley | 18.9
1986-05-26 | 1986 | 5 | Wisley | 16.5
1986-05-27 | 1986 | 5 | Wisley | 14.8
1986-05-28 | 1986 | 5 | Wisley | 15.7
1986-05-29 | 1986 | 5 | Wisley | 16.1
1986-05-30 | 1986 | 5 | Wisley | 13.7
1986-05-31 | 1986 | 5 | Wisley | 16.9
1986-06-01 | 1986 | 6 | Wisley | 20
1986-06-02 | 1986 | 6 | Wisley | 15.4
1986-06-04 | 1986 | 6 | Wisley | 14.4
1986-06-05 | 1986 | 6 | Wisley | 15.1
1986-06-06 | 1986 | 6 | Wisley | 18.9
1986-06-07 | 1986 | 6 | Wisley | 16.6
1986-06-08 | 1986 | 6 | Wisley | 18.2
1986-06-09 | 1986 | 6 | Wisley | 16.4
1986-06-10 | 1986 | 6 | Wisley | 16.1
1986-06-11 | 1986 | 6 | Wisley | 19.9
1986-06-12 | 1986 | 6 | Wisley | 23.1
1986-06-13 | 1986 | 6 | Wisley | 24.2
1986-06-14 | 1986 | 6 | Wisley | 25.9
1986-06-15 | 1986 | 6 | Wisley | 27.7
1986-06-16 | 1986 | 6 | Wisley | 22.2
1986-06-17 | 1986 | 6 | Wisley | 21
1986-06-18 | 1986 | 6 | Wisley | 23.2
1986-06-19 | 1986 | 6 | Wisley | 21
1986-06-20 | 1986 | 6 | Wisley | 21.9
1986-06-21 | 1986 | 6 | Wisley | 17
1986-06-22 | 1986 | 6 | Wisley | 17.9
1986-06-23 | 1986 | 6 | Wisley | 20.5
1986-06-24 | 1986 | 6 | Wisley | 24.6
1986-06-25 | 1986 | 6 | Wisley | 27.2
1986-06-26 | 1986 | 6 | Wisley | 29.6
1986-06-27 | 1986 | 6 | Wisley | 29
1986-06-28 | 1986 | 6 | Wisley | 28.4
1986-06-29 | 1986 | 6 | Wisley | 28
1986-06-30 | 1986 | 6 | Wisley | 25.6
1986-07-01 | 1986 | 7 | Wisley | 26.6
1986-07-02 | 1986 | 7 | Wisley | 24
1986-07-03 | 1986 | 7 | Wisley | 23.4
1986-07-04 | 1986 | 7 | Wisley | 19
1986-07-05 | 1986 | 7 | Wisley | 21.2
1986-07-06 | 1986 | 7 | Wisley | 20.7
1986-07-07 | 1986 | 7 | Wisley | 20.8
1986-07-08 | 1986 | 7 | Wisley | 20
1986-07-09 | 1986 | 7 | Wisley | 22.4
1986-07-10 | 1986 | 7 | Wisley | 21.4
1986-07-11 | 1986 | 7 | Wisley | 19.3
1986-07-12 | 1986 | 7 | Wisley | 21
1986-07-13 | 1986 | 7 | Wisley | 24.9
1986-07-14 | 1986 | 7 | Wisley | 28.9
1986-07-15 | 1986 | 7 | Wisley | 26.3
1986-07-18 | 1986 | 7 | Wisley | 19.4
1986-07-19 | 1986 | 7 | Wisley | 22.6
1986-07-20 | 1986 | 7 | Wisley | 21.5
1986-07-21 | 1986 | 7 | Wisley | 21.1
1986-07-23 | 1986 | 7 | Wisley | 21.2
1986-07-24 | 1986 | 7 | Wisley | 21.3
1986-07-25 | 1986 | 7 | Wisley | 22.7
1986-07-26 | 1986 | 7 | Wisley | 22.6
1986-07-27 | 1986 | 7 | Wisley | 20.3
1986-07-28 | 1986 | 7 | Wisley | 20.4
1986-07-29 | 1986 | 7 | Wisley | 19.9
1986-07-30 | 1986 | 7 | Wisley | 19.6
1986-07-31 | 1986 | 7 | Wisley | 20.3
1986-08-01 | 1986 | 8 | Wisley | 21
1986-08-03 | 1986 | 8 | Wisley | 18.8
1986-08-04 | 1986 | 8 | Wisley | 20.3
1986-08-05 | 1986 | 8 | Wisley | 22.4
1986-08-06 | 1986 | 8 | Wisley | 20
1986-08-07 | 1986 | 8 | Wisley | 21.1
1986-08-08 | 1986 | 8 | Wisley | 22.2
1986-08-09 | 1986 | 8 | Wisley | 24.9
1986-08-10 | 1986 | 8 | Wisley | 21.3
1986-08-11 | 1986 | 8 | Wisley | 19.6
1986-08-12 | 1986 | 8 | Wisley | 21.6
1986-08-13 | 1986 | 8 | Wisley | 20.9
1986-08-14 | 1986 | 8 | Wisley | 21.1
1986-08-15 | 1986 | 8 | Wisley | 21.5
1986-08-16 | 1986 | 8 | Wisley | 20.8
1986-08-17 | 1986 | 8 | Wisley | 18
1986-08-18 | 1986 | 8 | Wisley | 18.9
1986-08-19 | 1986 | 8 | Wisley | 19.5
1986-08-20 | 1986 | 8 | Wisley | 18.6
1986-08-21 | 1986 | 8 | Wisley | 20
1986-08-22 | 1986 | 8 | Wisley | 17.9
1986-08-23 | 1986 | 8 | Wisley | 18.9
1986-08-24 | 1986 | 8 | Wisley | 15.6
1986-08-25 | 1986 | 8 | Wisley | 16.2
1986-08-26 | 1986 | 8 | Wisley | 17.1
1986-08-27 | 1986 | 8 | Wisley | 16.6
1986-08-28 | 1986 | 8 | Wisley | 17.2
1986-08-29 | 1986 | 8 | Wisley | 15.5
1986-08-30 | 1986 | 8 | Wisley | 17.9
1986-08-31 | 1986 | 8 | Wisley | 17
1986-09-01 | 1986 | 9 | Wisley | 20.6
1986-09-02 | 1986 | 9 | Wisley | 16.8
1986-09-03 | 1986 | 9 | Wisley | 19.2
1986-09-04 | 1986 | 9 | Wisley | 19.4
1986-09-05 | 1986 | 9 | Wisley | 17
1986-09-06 | 1986 | 9 | Wisley | 19
1986-09-07 | 1986 | 9 | Wisley | 16.1
1986-09-08 | 1986 | 9 | Wisley | 17
1986-09-09 | 1986 | 9 | Wisley | 17.1
1986-09-10 | 1986 | 9 | Wisley | 17
1986-09-11 | 1986 | 9 | Wisley | 16.8
1986-09-12 | 1986 | 9 | Wisley | 14
1986-09-13 | 1986 | 9 | Wisley | 15.7
1986-09-14 | 1986 | 9 | Wisley | 11
1986-09-15 | 1986 | 9 | Wisley | 14.9
1986-09-16 | 1986 | 9 | Wisley | 13
1986-09-17 | 1986 | 9 | Wisley | 15.6
1986-09-18 | 1986 | 9 | Wisley | 16.2
1986-09-19 | 1986 | 9 | Wisley | 20.4
1986-09-20 | 1986 | 9 | Wisley | 19.6
1986-09-21 | 1986 | 9 | Wisley | 19.9
1986-09-22 | 1986 | 9 | Wisley | 19.2
1986-09-23 | 1986 | 9 | Wisley | 14.5
1986-09-24 | 1986 | 9 | Wisley | 16.5
1986-09-25 | 1986 | 9 | Wisley | 16.9
1986-09-26 | 1986 | 9 | Wisley | 18.3
1986-09-27 | 1986 | 9 | Wisley | 19
1986-09-28 | 1986 | 9 | Wisley | 15.6
1986-09-29 | 1986 | 9 | Wisley | 16.3
1986-09-30 | 1986 | 9 | Wisley | 15.9
1987-05-01 | 1987 | 5 | Wisley | 13.8
1987-05-02 | 1987 | 5 | Wisley | 10.3
1987-05-03 | 1987 | 5 | Wisley | 12.5
1987-05-04 | 1987 | 5 | Wisley | 13.9
1987-05-05 | 1987 | 5 | Wisley | 16.7
1987-05-06 | 1987 | 5 | Wisley | 18.2
1987-05-07 | 1987 | 5 | Wisley | 19.7
1987-05-08 | 1987 | 5 | Wisley | 23.6
1987-05-09 | 1987 | 5 | Wisley | 14.6
1987-05-11 | 1987 | 5 | Wisley | 14.5
1987-05-12 | 1987 | 5 | Wisley | 13.6
1987-05-13 | 1987 | 5 | Wisley | 13.9
1987-05-14 | 1987 | 5 | Wisley | 12.2
1987-05-15 | 1987 | 5 | Wisley | 14.5
1987-05-16 | 1987 | 5 | Wisley | 13.8
1987-05-17 | 1987 | 5 | Wisley | 12.1
1987-05-18 | 1987 | 5 | Wisley | 17.2
1987-05-19 | 1987 | 5 | Wisley | 14
1987-05-20 | 1987 | 5 | Wisley | 14.7
1987-05-21 | 1987 | 5 | Wisley | 13
1987-05-22 | 1987 | 5 | Wisley | 12.5
1987-05-23 | 1987 | 5 | Wisley | 18.4
1987-05-24 | 1987 | 5 | Wisley | 17.5
1987-05-25 | 1987 | 5 | Wisley | 22.6
1987-05-26 | 1987 | 5 | Wisley | 19.5
1987-05-27 | 1987 | 5 | Wisley | 18.7
1987-05-28 | 1987 | 5 | Wisley | 18.9
1987-05-29 | 1987 | 5 | Wisley | 19.6
1987-05-30 | 1987 | 5 | Wisley | 21.1
1987-05-31 | 1987 | 5 | Wisley | 20.3
1987-06-01 | 1987 | 6 | Wisley | 15.6
1987-06-02 | 1987 | 6 | Wisley | 18.7
1987-06-03 | 1987 | 6 | Wisley | 19.5
1987-06-04 | 1987 | 6 | Wisley | 16.8
1987-06-05 | 1987 | 6 | Wisley | 16.7
1987-06-06 | 1987 | 6 | Wisley | 15.7
1987-06-07 | 1987 | 6 | Wisley | 16.4
1987-06-08 | 1987 | 6 | Wisley | 13.4
1987-06-09 | 1987 | 6 | Wisley | 15.9
1987-06-10 | 1987 | 6 | Wisley | 18.1
1987-06-11 | 1987 | 6 | Wisley | 18.7
1987-06-12 | 1987 | 6 | Wisley | 17
1987-06-13 | 1987 | 6 | Wisley | 17.2
1987-06-14 | 1987 | 6 | Wisley | 18.2
1987-06-15 | 1987 | 6 | Wisley | 17.9
1987-06-16 | 1987 | 6 | Wisley | 16.2
1987-06-17 | 1987 | 6 | Wisley | 18.3
1987-06-18 | 1987 | 6 | Wisley | 17.2
1987-06-19 | 1987 | 6 | Wisley | 20
1987-06-20 | 1987 | 6 | Wisley | 18.9
1987-06-21 | 1987 | 6 | Wisley | 15.9
1987-06-22 | 1987 | 6 | Wisley | 19.9
1987-06-23 | 1987 | 6 | Wisley | 19
1987-06-24 | 1987 | 6 | Wisley | 17.6
1987-06-25 | 1987 | 6 | Wisley | 21.5
1987-06-26 | 1987 | 6 | Wisley | 21.9
1987-06-27 | 1987 | 6 | Wisley | 24.5
1987-06-28 | 1987 | 6 | Wisley | 27.6
1987-06-29 | 1987 | 6 | Wisley | 24
1987-07-01 | 1987 | 7 | Wisley | 22.3
1987-07-02 | 1987 | 7 | Wisley | 23.1
1987-07-03 | 1987 | 7 | Wisley | 25.7
1987-07-04 | 1987 | 7 | Wisley | 28
1987-07-05 | 1987 | 7 | Wisley | 28.4
1987-07-06 | 1987 | 7 | Wisley | 24.4
1987-07-07 | 1987 | 7 | Wisley | 22.9
1987-07-08 | 1987 | 7 | Wisley | 22.3
1987-07-09 | 1987 | 7 | Wisley | 26.1
1987-07-10 | 1987 | 7 | Wisley | 26.2
1987-07-11 | 1987 | 7 | Wisley | 23.4
1987-07-12 | 1987 | 7 | Wisley | 25
1987-07-13 | 1987 | 7 | Wisley | 22.9
1987-07-14 | 1987 | 7 | Wisley | 22.4
1987-07-17 | 1987 | 7 | Wisley | 16.3
1987-07-18 | 1987 | 7 | Wisley | 17.4
1987-07-19 | 1987 | 7 | Wisley | 19.1
1987-07-21 | 1987 | 7 | Wisley | 17
1987-07-22 | 1987 | 7 | Wisley | 16.4
1987-07-23 | 1987 | 7 | Wisley | 21
1987-07-24 | 1987 | 7 | Wisley | 18.1
1987-07-25 | 1987 | 7 | Wisley | 19.8
1987-07-26 | 1987 | 7 | Wisley | 21.1
1987-07-27 | 1987 | 7 | Wisley | 22.2
1987-07-28 | 1987 | 7 | Wisley | 21.5
1987-07-29 | 1987 | 7 | Wisley | 19.5
1987-07-30 | 1987 | 7 | Wisley | 24.7
1987-07-31 | 1987 | 7 | Wisley | 20.8
1987-08-01 | 1987 | 8 | Wisley | 21
1987-08-02 | 1987 | 8 | Wisley | 20.9
1987-08-03 | 1987 | 8 | Wisley | 18.8
1987-08-04 | 1987 | 8 | Wisley | 19.5
1987-08-05 | 1987 | 8 | Wisley | 19
1987-08-06 | 1987 | 8 | Wisley | 19.6
1987-08-07 | 1987 | 8 | Wisley | 17.4
1987-08-08 | 1987 | 8 | Wisley | 19.3
1987-08-09 | 1987 | 8 | Wisley | 20.5
1987-08-10 | 1987 | 8 | Wisley | 19.2
1987-08-11 | 1987 | 8 | Wisley | 21
1987-08-12 | 1987 | 8 | Wisley | 22.5
1987-08-13 | 1987 | 8 | Wisley | 23.2
1987-08-14 | 1987 | 8 | Wisley | 26.4
1987-08-15 | 1987 | 8 | Wisley | 27.6
1987-08-16 | 1987 | 8 | Wisley | 23
1987-08-17 | 1987 | 8 | Wisley | 23.4
1987-08-18 | 1987 | 8 | Wisley | 25.2
1987-08-19 | 1987 | 8 | Wisley | 28.3
1987-08-20 | 1987 | 8 | Wisley | 29.2
1987-08-21 | 1987 | 8 | Wisley | 24.5
1987-08-23 | 1987 | 8 | Wisley | 19.4
1987-08-25 | 1987 | 8 | Wisley | 17.9
1987-08-26 | 1987 | 8 | Wisley | 18.1
1987-08-27 | 1987 | 8 | Wisley | 24.4
1987-08-28 | 1987 | 8 | Wisley | 20.9
1987-08-29 | 1987 | 8 | Wisley | 22.5
1987-08-30 | 1987 | 8 | Wisley | 20.6
1987-08-31 | 1987 | 8 | Wisley | 25.2
1987-09-01 | 1987 | 9 | Wisley | 21.3
1987-09-02 | 1987 | 9 | Wisley | 21.6
1987-09-03 | 1987 | 9 | Wisley | 20.9
1987-09-04 | 1987 | 9 | Wisley | 20.5
1987-09-05 | 1987 | 9 | Wisley | 18.2
1987-09-06 | 1987 | 9 | Wisley | 19
1987-09-07 | 1987 | 9 | Wisley | 20.3
1987-09-08 | 1987 | 9 | Wisley | 19.6
1987-09-09 | 1987 | 9 | Wisley | 19.8
1987-09-10 | 1987 | 9 | Wisley | 19.4
1987-09-11 | 1987 | 9 | Wisley | 20.6
1987-09-13 | 1987 | 9 | Wisley | 20.5
1987-09-14 | 1987 | 9 | Wisley | 19.6
1987-09-15 | 1987 | 9 | Wisley | 22
1987-09-16 | 1987 | 9 | Wisley | 24.6
1987-09-17 | 1987 | 9 | Wisley | 20.9
1987-09-19 | 1987 | 9 | Wisley | 22.6
1987-09-20 | 1987 | 9 | Wisley | 20.4
1987-09-22 | 1987 | 9 | Wisley | 19.5
1987-09-23 | 1987 | 9 | Wisley | 15.9
1987-09-24 | 1987 | 9 | Wisley | 16.2
1987-09-25 | 1987 | 9 | Wisley | 15.5
1987-09-26 | 1987 | 9 | Wisley | 14.6
1987-09-27 | 1987 | 9 | Wisley | 14.3
1987-09-28 | 1987 | 9 | Wisley | 16
1987-09-29 | 1987 | 9 | Wisley | 16.5
1987-09-30 | 1987 | 9 | Wisley | 17.7
1988-05-01 | 1988 | 5 | Wisley | 15.5
1988-05-02 | 1988 | 5 | Wisley | 14.9
1988-05-03 | 1988 | 5 | Wisley | 14.6
1988-05-04 | 1988 | 5 | Wisley | 16.9
1988-05-05 | 1988 | 5 | Wisley | 20.5
1988-05-06 | 1988 | 5 | Wisley | 19
1988-05-07 | 1988 | 5 | Wisley | 22.5
1988-05-09 | 1988 | 5 | Wisley | 17.3
1988-05-10 | 1988 | 5 | Wisley | 15.4
1988-05-11 | 1988 | 5 | Wisley | 19
1988-05-12 | 1988 | 5 | Wisley | 20.9
1988-05-13 | 1988 | 5 | Wisley | 24
1988-05-14 | 1988 | 5 | Wisley | 22.9
1988-05-15 | 1988 | 5 | Wisley | 22.1
1988-05-16 | 1988 | 5 | Wisley | 21
1988-05-19 | 1988 | 5 | Wisley | 15.8
1988-05-20 | 1988 | 5 | Wisley | 17.1
1988-05-21 | 1988 | 5 | Wisley | 18.4
1988-05-22 | 1988 | 5 | Wisley | 17.2
1988-05-23 | 1988 | 5 | Wisley | 18
1988-05-24 | 1988 | 5 | Wisley | 20.4
1988-05-25 | 1988 | 5 | Wisley | 17.9
1988-05-26 | 1988 | 5 | Wisley | 19.8
1988-05-27 | 1988 | 5 | Wisley | 18.2
1988-05-28 | 1988 | 5 | Wisley | 15.3
1988-05-29 | 1988 | 5 | Wisley | 15.1
1988-05-30 | 1988 | 5 | Wisley | 16.8
1988-05-31 | 1988 | 5 | Wisley | 18
1988-06-01 | 1988 | 6 | Wisley | 17.2
1988-06-02 | 1988 | 6 | Wisley | 15.6
1988-06-03 | 1988 | 6 | Wisley | 15.4
1988-06-04 | 1988 | 6 | Wisley | 16.5
1988-06-05 | 1988 | 6 | Wisley | 17.9
1988-06-06 | 1988 | 6 | Wisley | 18.4
1988-06-07 | 1988 | 6 | Wisley | 15.9
1988-06-09 | 1988 | 6 | Wisley | 14
1988-06-10 | 1988 | 6 | Wisley | 15.7
1988-06-11 | 1988 | 6 | Wisley | 19
1988-06-12 | 1988 | 6 | Wisley | 23.1
1988-06-13 | 1988 | 6 | Wisley | 23.6
1988-06-14 | 1988 | 6 | Wisley | 20.5
1988-06-15 | 1988 | 6 | Wisley | 20.8
1988-06-17 | 1988 | 6 | Wisley | 20.2
1988-06-18 | 1988 | 6 | Wisley | 25.4
1988-06-19 | 1988 | 6 | Wisley | 23.5
1988-06-20 | 1988 | 6 | Wisley | 23.3
1988-06-21 | 1988 | 6 | Wisley | 21.6
1988-06-22 | 1988 | 6 | Wisley | 24.6
1988-06-23 | 1988 | 6 | Wisley | 20.9
1988-06-24 | 1988 | 6 | Wisley | 23
1988-06-25 | 1988 | 6 | Wisley | 20.7
1988-06-27 | 1988 | 6 | Wisley | 18.1
1988-06-28 | 1988 | 6 | Wisley | 20.6
1988-06-29 | 1988 | 6 | Wisley | 24.5
1988-06-30 | 1988 | 6 | Wisley | 18.2
1988-07-02 | 1988 | 7 | Wisley | 16.8
1988-07-03 | 1988 | 7 | Wisley | 17
1988-07-04 | 1988 | 7 | Wisley | 21.1
1988-07-05 | 1988 | 7 | Wisley | 18.4
1988-07-06 | 1988 | 7 | Wisley | 18.4
1988-07-07 | 1988 | 7 | Wisley | 19
1988-07-08 | 1988 | 7 | Wisley | 19.8
1988-07-09 | 1988 | 7 | Wisley | 18
1988-07-10 | 1988 | 7 | Wisley | 19.5
1988-07-11 | 1988 | 7 | Wisley | 20.3
1988-07-12 | 1988 | 7 | Wisley | 19
1988-07-13 | 1988 | 7 | Wisley | 17.6
1988-07-14 | 1988 | 7 | Wisley | 19.4
1988-07-15 | 1988 | 7 | Wisley | 17.6
1988-07-16 | 1988 | 7 | Wisley | 20
1988-07-17 | 1988 | 7 | Wisley | 22
1988-07-18 | 1988 | 7 | Wisley | 21.1
1988-07-19 | 1988 | 7 | Wisley | 21
1988-07-20 | 1988 | 7 | Wisley | 21.1
1988-07-21 | 1988 | 7 | Wisley | 20.4
1988-07-22 | 1988 | 7 | Wisley | 21
1988-07-23 | 1988 | 7 | Wisley | 19.6
1988-07-24 | 1988 | 7 | Wisley | 19.5
1988-07-25 | 1988 | 7 | Wisley | 19.9
1988-07-26 | 1988 | 7 | Wisley | 19.9
1988-07-27 | 1988 | 7 | Wisley | 17.1
1988-07-28 | 1988 | 7 | Wisley | 18.4
1988-07-29 | 1988 | 7 | Wisley | 18.2
1988-07-30 | 1988 | 7 | Wisley | 20.4
1988-07-31 | 1988 | 7 | Wisley | 19.7
1988-08-01 | 1988 | 8 | Wisley | 18.9
1988-08-02 | 1988 | 8 | Wisley | 20
1988-08-03 | 1988 | 8 | Wisley | 21
1988-08-04 | 1988 | 8 | Wisley | 22.4
1988-08-05 | 1988 | 8 | Wisley | 27.4
1988-08-06 | 1988 | 8 | Wisley | 29
1988-08-07 | 1988 | 8 | Wisley | 26.5
1988-08-08 | 1988 | 8 | Wisley | 23.9
1988-08-10 | 1988 | 8 | Wisley | 19.2
1988-08-11 | 1988 | 8 | Wisley | 20.4
1988-08-12 | 1988 | 8 | Wisley | 20.2
1988-08-13 | 1988 | 8 | Wisley | 21.4
1988-08-14 | 1988 | 8 | Wisley | 22.6
1988-08-15 | 1988 | 8 | Wisley | 24
1988-08-16 | 1988 | 8 | Wisley | 26.4
1988-08-17 | 1988 | 8 | Wisley | 24.1
1988-08-18 | 1988 | 8 | Wisley | 21
1988-08-19 | 1988 | 8 | Wisley | 20.3
1988-08-21 | 1988 | 8 | Wisley | 18.9
1988-08-22 | 1988 | 8 | Wisley | 18.3
1988-08-23 | 1988 | 8 | Wisley | 19.2
1988-08-24 | 1988 | 8 | Wisley | 17.6
1988-08-25 | 1988 | 8 | Wisley | 18.6
1988-08-26 | 1988 | 8 | Wisley | 21.1
1988-08-27 | 1988 | 8 | Wisley | 18
1988-08-28 | 1988 | 8 | Wisley | 19.9
1988-08-29 | 1988 | 8 | Wisley | 19
1988-08-30 | 1988 | 8 | Wisley | 19.5
1988-08-31 | 1988 | 8 | Wisley | 17.6
1988-09-01 | 1988 | 9 | Wisley | 17
1988-09-02 | 1988 | 9 | Wisley | 18.5
1988-09-03 | 1988 | 9 | Wisley | 19
1988-09-04 | 1988 | 9 | Wisley | 21.4
1988-09-05 | 1988 | 9 | Wisley | 23.8
1988-09-06 | 1988 | 9 | Wisley | 25.2
1988-09-07 | 1988 | 9 | Wisley | 24.6
1988-09-08 | 1988 | 9 | Wisley | 22.1
1988-09-09 | 1988 | 9 | Wisley | 23.7
1988-09-10 | 1988 | 9 | Wisley | 19.6
1988-09-12 | 1988 | 9 | Wisley | 15
1988-09-13 | 1988 | 9 | Wisley | 13.4
1988-09-14 | 1988 | 9 | Wisley | 16
1988-09-15 | 1988 | 9 | Wisley | 19.1
1988-09-16 | 1988 | 9 | Wisley | 18.2
1988-09-17 | 1988 | 9 | Wisley | 18
1988-09-18 | 1988 | 9 | Wisley | 17.6
1988-09-19 | 1988 | 9 | Wisley | 13.5
1988-09-20 | 1988 | 9 | Wisley | 17.5
1988-09-21 | 1988 | 9 | Wisley | 18.4
1988-09-22 | 1988 | 9 | Wisley | 16.6
1988-09-23 | 1988 | 9 | Wisley | 16.4
1988-09-24 | 1988 | 9 | Wisley | 19.9
1988-09-25 | 1988 | 9 | Wisley | 18.5
1988-09-28 | 1988 | 9 | Wisley | 15.2
1988-09-29 | 1988 | 9 | Wisley | 15
1988-09-30 | 1988 | 9 | Wisley | 15.8
1989-05-01 | 1989 | 5 | Wisley | 21
1989-05-02 | 1989 | 5 | Wisley | 22.9
1989-05-03 | 1989 | 5 | Wisley | 24
1989-05-04 | 1989 | 5 | Wisley | 25.1
1989-05-05 | 1989 | 5 | Wisley | 17.6
1989-05-06 | 1989 | 5 | Wisley | 18.5
1989-05-07 | 1989 | 5 | Wisley | 21.3
1989-05-08 | 1989 | 5 | Wisley | 20.8
1989-05-09 | 1989 | 5 | Wisley | 17.7
1989-05-10 | 1989 | 5 | Wisley | 17.1
1989-05-11 | 1989 | 5 | Wisley | 14.1
1989-05-12 | 1989 | 5 | Wisley | 15.6
1989-05-13 | 1989 | 5 | Wisley | 18
1989-05-14 | 1989 | 5 | Wisley | 19.9
1989-05-15 | 1989 | 5 | Wisley | 20.5
1989-05-16 | 1989 | 5 | Wisley | 21.4
1989-05-17 | 1989 | 5 | Wisley | 24.4
1989-05-18 | 1989 | 5 | Wisley | 24.5
1989-05-19 | 1989 | 5 | Wisley | 24.9
1989-05-20 | 1989 | 5 | Wisley | 26
1989-05-21 | 1989 | 5 | Wisley | 25.8
1989-05-22 | 1989 | 5 | Wisley | 27.8
1989-05-23 | 1989 | 5 | Wisley | 27.9
1989-05-25 | 1989 | 5 | Wisley | 20.1
1989-05-26 | 1989 | 5 | Wisley | 19.4
1989-05-27 | 1989 | 5 | Wisley | 21.1
1989-05-28 | 1989 | 5 | Wisley | 22.3
1989-05-29 | 1989 | 5 | Wisley | 17.2
1989-05-30 | 1989 | 5 | Wisley | 15.9
1989-05-31 | 1989 | 5 | Wisley | 14
1989-06-01 | 1989 | 6 | Wisley | 15.6
1989-06-02 | 1989 | 6 | Wisley | 15.6
1989-06-03 | 1989 | 6 | Wisley | 15.8
1989-06-04 | 1989 | 6 | Wisley | 17.3
1989-06-05 | 1989 | 6 | Wisley | 11.1
1989-06-06 | 1989 | 6 | Wisley | 15.7
1989-06-07 | 1989 | 6 | Wisley | 15.4
1989-06-08 | 1989 | 6 | Wisley | 18
1989-06-09 | 1989 | 6 | Wisley | 21.2
1989-06-10 | 1989 | 6 | Wisley | 23.4
1989-06-11 | 1989 | 6 | Wisley | 26.2
1989-06-12 | 1989 | 6 | Wisley | 25.7
1989-06-13 | 1989 | 6 | Wisley | 27.3
1989-06-14 | 1989 | 6 | Wisley | 26.4
1989-06-15 | 1989 | 6 | Wisley | 25.6
1989-06-16 | 1989 | 6 | Wisley | 26.5
1989-06-17 | 1989 | 6 | Wisley | 25.9
1989-06-18 | 1989 | 6 | Wisley | 27.9
1989-06-19 | 1989 | 6 | Wisley | 29
1989-06-20 | 1989 | 6 | Wisley | 26
1989-06-21 | 1989 | 6 | Wisley | 20.9
1989-06-22 | 1989 | 6 | Wisley | 24.4
1989-06-23 | 1989 | 6 | Wisley | 24.1
1989-06-24 | 1989 | 6 | Wisley | 24.8
1989-06-25 | 1989 | 6 | Wisley | 21.5
1989-06-26 | 1989 | 6 | Wisley | 18
1989-06-27 | 1989 | 6 | Wisley | 17
1989-06-28 | 1989 | 6 | Wisley | 17.6
1989-06-29 | 1989 | 6 | Wisley | 19.9
1989-06-30 | 1989 | 6 | Wisley | 20
1989-07-01 | 1989 | 7 | Wisley | 19.4
1989-07-02 | 1989 | 7 | Wisley | 23.4
1989-07-03 | 1989 | 7 | Wisley | 24.9
1989-07-04 | 1989 | 7 | Wisley | 27.4
1989-07-05 | 1989 | 7 | Wisley | 30.1
1989-07-08 | 1989 | 7 | Wisley | 18.3
1989-07-09 | 1989 | 7 | Wisley | 23
1989-07-10 | 1989 | 7 | Wisley | 25
1989-07-11 | 1989 | 7 | Wisley | 22.8
1989-07-12 | 1989 | 7 | Wisley | 24.1
1989-07-13 | 1989 | 7 | Wisley | 22
1989-07-14 | 1989 | 7 | Wisley | 27.4
1989-07-15 | 1989 | 7 | Wisley | 24.8
1989-07-16 | 1989 | 7 | Wisley | 26.7
1989-07-17 | 1989 | 7 | Wisley | 24.9
1989-07-18 | 1989 | 7 | Wisley | 26.5
1989-07-19 | 1989 | 7 | Wisley | 28.1
1989-07-20 | 1989 | 7 | Wisley | 30.3
1989-07-21 | 1989 | 7 | Wisley | 33.8
1989-07-22 | 1989 | 7 | Wisley | 31
1989-07-23 | 1989 | 7 | Wisley | 29.4
1989-07-24 | 1989 | 7 | Wisley | 28.5
1989-07-25 | 1989 | 7 | Wisley | 26
1989-07-26 | 1989 | 7 | Wisley | 24.8
1989-07-27 | 1989 | 7 | Wisley | 25.1
1989-07-28 | 1989 | 7 | Wisley | 25.5
1989-07-29 | 1989 | 7 | Wisley | 18.5
1989-07-31 | 1989 | 7 | Wisley | 21.4
1989-08-01 | 1989 | 8 | Wisley | 22.2
1989-08-02 | 1989 | 8 | Wisley | 25
1989-08-03 | 1989 | 8 | Wisley | 24.4
1989-08-04 | 1989 | 8 | Wisley | 26.2
1989-08-05 | 1989 | 8 | Wisley | 28.6
1989-08-06 | 1989 | 8 | Wisley | 25.6
1989-08-07 | 1989 | 8 | Wisley | 25.4
1989-08-08 | 1989 | 8 | Wisley | 24.4
1989-08-09 | 1989 | 8 | Wisley | 19.5
1989-08-10 | 1989 | 8 | Wisley | 23.2
1989-08-11 | 1989 | 8 | Wisley | 23.3
1989-08-12 | 1989 | 8 | Wisley | 20.5
1989-08-13 | 1989 | 8 | Wisley | 22.5
1989-08-14 | 1989 | 8 | Wisley | 22.6
1989-08-15 | 1989 | 8 | Wisley | 22.5
1989-08-16 | 1989 | 8 | Wisley | 21
1989-08-17 | 1989 | 8 | Wisley | 21.6
1989-08-18 | 1989 | 8 | Wisley | 25.8
1989-08-19 | 1989 | 8 | Wisley | 26.9
1989-08-20 | 1989 | 8 | Wisley | 24.9
1989-08-21 | 1989 | 8 | Wisley | 22.9
1989-08-22 | 1989 | 8 | Wisley | 23.6
1989-08-23 | 1989 | 8 | Wisley | 25.1
1989-08-24 | 1989 | 8 | Wisley | 20.2
1989-08-25 | 1989 | 8 | Wisley | 22.8
1989-08-26 | 1989 | 8 | Wisley | 19
1989-08-27 | 1989 | 8 | Wisley | 19.1
1989-08-28 | 1989 | 8 | Wisley | 19
1989-08-29 | 1989 | 8 | Wisley | 24.2
1989-08-30 | 1989 | 8 | Wisley | 19.9
1989-08-31 | 1989 | 8 | Wisley | 19.6
1989-09-01 | 1989 | 9 | Wisley | 19
1989-09-02 | 1989 | 9 | Wisley | 18
1989-09-03 | 1989 | 9 | Wisley | 21.2
1989-09-04 | 1989 | 9 | Wisley | 23
1989-09-05 | 1989 | 9 | Wisley | 25.6
1989-09-06 | 1989 | 9 | Wisley | 26.3
1989-09-07 | 1989 | 9 | Wisley | 23
1989-09-09 | 1989 | 9 | Wisley | 19.4
1989-09-10 | 1989 | 9 | Wisley | 19
1989-09-11 | 1989 | 9 | Wisley | 21.1
1989-09-12 | 1989 | 9 | Wisley | 19.7
1989-09-14 | 1989 | 9 | Wisley | 20.6
1989-09-15 | 1989 | 9 | Wisley | 20.9
1989-09-16 | 1989 | 9 | Wisley | 19.8
1989-09-17 | 1989 | 9 | Wisley | 22.5
1989-09-18 | 1989 | 9 | Wisley | 21.4
1989-09-19 | 1989 | 9 | Wisley | 21.5
1989-09-20 | 1989 | 9 | Wisley | 25.6
1989-09-21 | 1989 | 9 | Wisley | 17.9
1989-09-23 | 1989 | 9 | Wisley | 22.3
1989-09-24 | 1989 | 9 | Wisley | 22.6
1989-09-25 | 1989 | 9 | Wisley | 19.2
1989-09-26 | 1989 | 9 | Wisley | 18.5
1989-09-28 | 1989 | 9 | Wisley | 18.4
1989-09-29 | 1989 | 9 | Wisley | 14.8
1989-09-30 | 1989 | 9 | Wisley | 15
1990-05-01 | 1990 | 5 | Wisley | 25.3
1990-05-02 | 1990 | 5 | Wisley | 27.9
1990-05-03 | 1990 | 5 | Wisley | 26.2
1990-05-04 | 1990 | 5 | Wisley | 26.7
1990-05-05 | 1990 | 5 | Wisley | 25.8
1990-05-06 | 1990 | 5 | Wisley | 18.4
1990-05-07 | 1990 | 5 | Wisley | 18.7
1990-05-08 | 1990 | 5 | Wisley | 15
1990-05-09 | 1990 | 5 | Wisley | 14.5
1990-05-10 | 1990 | 5 | Wisley | 14
1990-05-11 | 1990 | 5 | Wisley | 15.6
1990-05-12 | 1990 | 5 | Wisley | 17.5
1990-05-13 | 1990 | 5 | Wisley | 19.5
1990-05-14 | 1990 | 5 | Wisley | 20
1990-05-15 | 1990 | 5 | Wisley | 19.7
1990-05-16 | 1990 | 5 | Wisley | 21.8
1990-05-17 | 1990 | 5 | Wisley | 14.5
1990-05-18 | 1990 | 5 | Wisley | 16.4
1990-05-19 | 1990 | 5 | Wisley | 19.6
1990-05-20 | 1990 | 5 | Wisley | 20.3
1990-05-21 | 1990 | 5 | Wisley | 18.6
1990-05-22 | 1990 | 5 | Wisley | 22.3
1990-05-23 | 1990 | 5 | Wisley | 19.1
1990-05-24 | 1990 | 5 | Wisley | 17.6
1990-05-25 | 1990 | 5 | Wisley | 17.3
1990-05-26 | 1990 | 5 | Wisley | 21.2
1990-05-27 | 1990 | 5 | Wisley | 21.5
1990-05-28 | 1990 | 5 | Wisley | 19.6
1990-05-29 | 1990 | 5 | Wisley | 18.5
1990-05-30 | 1990 | 5 | Wisley | 23.4
1990-05-31 | 1990 | 5 | Wisley | 22.3
1990-06-01 | 1990 | 6 | Wisley | 17.8
1990-06-02 | 1990 | 6 | Wisley | 16.4
1990-06-03 | 1990 | 6 | Wisley | 18.4
1990-06-04 | 1990 | 6 | Wisley | 16.2
1990-06-05 | 1990 | 6 | Wisley | 15.7
1990-06-06 | 1990 | 6 | Wisley | 16.5
1990-06-07 | 1990 | 6 | Wisley | 12.8
1990-06-08 | 1990 | 6 | Wisley | 18.8
1990-06-09 | 1990 | 6 | Wisley | 20
1990-06-12 | 1990 | 6 | Wisley | 14.1
1990-06-13 | 1990 | 6 | Wisley | 17.5
1990-06-14 | 1990 | 6 | Wisley | 20
1990-06-15 | 1990 | 6 | Wisley | 21
1990-06-16 | 1990 | 6 | Wisley | 22
1990-06-17 | 1990 | 6 | Wisley | 19.8
1990-06-18 | 1990 | 6 | Wisley | 20.7
1990-06-19 | 1990 | 6 | Wisley | 19.4
1990-06-20 | 1990 | 6 | Wisley | 15.9
1990-06-21 | 1990 | 6 | Wisley | 19.5
1990-06-22 | 1990 | 6 | Wisley | 17.9
1990-06-23 | 1990 | 6 | Wisley | 18.3
1990-06-24 | 1990 | 6 | Wisley | 22
1990-06-25 | 1990 | 6 | Wisley | 22.8
1990-06-26 | 1990 | 6 | Wisley | 23.1
1990-06-27 | 1990 | 6 | Wisley | 19.7
1990-06-28 | 1990 | 6 | Wisley | 22
1990-06-29 | 1990 | 6 | Wisley | 19.8
1990-07-01 | 1990 | 7 | Wisley | 19
1990-07-02 | 1990 | 7 | Wisley | 18.4
1990-07-03 | 1990 | 7 | Wisley | 17.4
1990-07-04 | 1990 | 7 | Wisley | 17.4
1990-07-05 | 1990 | 7 | Wisley | 19.6
1990-07-06 | 1990 | 7 | Wisley | 22.4
1990-07-07 | 1990 | 7 | Wisley | 24.5
1990-07-09 | 1990 | 7 | Wisley | 19.4
1990-07-10 | 1990 | 7 | Wisley | 26
1990-07-11 | 1990 | 7 | Wisley | 27.9
1990-07-12 | 1990 | 7 | Wisley | 26
1990-07-13 | 1990 | 7 | Wisley | 24.6
1990-07-14 | 1990 | 7 | Wisley | 30.5
1990-07-15 | 1990 | 7 | Wisley | 24
1990-07-16 | 1990 | 7 | Wisley | 26.1
1990-07-17 | 1990 | 7 | Wisley | 27.1
1990-07-18 | 1990 | 7 | Wisley | 28.4
1990-07-19 | 1990 | 7 | Wisley | 30.9
1990-07-20 | 1990 | 7 | Wisley | 32.2
1990-07-21 | 1990 | 7 | Wisley | 23.4
1990-07-23 | 1990 | 7 | Wisley | 24.4
1990-07-24 | 1990 | 7 | Wisley | 25.5
1990-07-25 | 1990 | 7 | Wisley | 23.9
1990-07-26 | 1990 | 7 | Wisley | 24.6
1990-07-27 | 1990 | 7 | Wisley | 24.6
1990-07-28 | 1990 | 7 | Wisley | 24.9
1990-07-29 | 1990 | 7 | Wisley | 23.7
1990-07-30 | 1990 | 7 | Wisley | 27
1990-07-31 | 1990 | 7 | Wisley | 32.2
1990-08-01 | 1990 | 8 | Wisley | 33.1
1990-08-02 | 1990 | 8 | Wisley | 35.4
1990-08-03 | 1990 | 8 | Wisley | 33.7
1990-08-06 | 1990 | 8 | Wisley | 22
1990-08-07 | 1990 | 8 | Wisley | 25.5
1990-08-08 | 1990 | 8 | Wisley | 27
1990-08-09 | 1990 | 8 | Wisley | 27.6
1990-08-10 | 1990 | 8 | Wisley | 27.1
1990-08-11 | 1990 | 8 | Wisley | 29.1
1990-08-12 | 1990 | 8 | Wisley | 26
1990-08-13 | 1990 | 8 | Wisley | 22.9
1990-08-14 | 1990 | 8 | Wisley | 21.6
1990-08-15 | 1990 | 8 | Wisley | 20.6
1990-08-16 | 1990 | 8 | Wisley | 20.3
1990-08-17 | 1990 | 8 | Wisley | 18.6
1990-08-18 | 1990 | 8 | Wisley | 21.9
1990-08-19 | 1990 | 8 | Wisley | 21.3
1990-08-20 | 1990 | 8 | Wisley | 22.5
1990-08-21 | 1990 | 8 | Wisley | 27
1990-08-22 | 1990 | 8 | Wisley | 27.2
1990-08-23 | 1990 | 8 | Wisley | 27.3
1990-08-24 | 1990 | 8 | Wisley | 27.1
1990-08-25 | 1990 | 8 | Wisley | 26.2
1990-08-26 | 1990 | 8 | Wisley | 23.9
1990-08-27 | 1990 | 8 | Wisley | 27.3
1990-08-28 | 1990 | 8 | Wisley | 29.2
1990-08-29 | 1990 | 8 | Wisley | 22.7
1990-08-31 | 1990 | 8 | Wisley | 23.1
1990-09-01 | 1990 | 9 | Wisley | 25.1
1990-09-02 | 1990 | 9 | Wisley | 24.3
1990-09-03 | 1990 | 9 | Wisley | 19.5
1990-09-04 | 1990 | 9 | Wisley | 20.2
1990-09-05 | 1990 | 9 | Wisley | 18.9
1990-09-06 | 1990 | 9 | Wisley | 19.6
1990-09-07 | 1990 | 9 | Wisley | 18.6
1990-09-08 | 1990 | 9 | Wisley | 21.5
1990-09-09 | 1990 | 9 | Wisley | 20.6
1990-09-10 | 1990 | 9 | Wisley | 21.9
1990-09-11 | 1990 | 9 | Wisley | 22
1990-09-12 | 1990 | 9 | Wisley | 22.1
1990-09-13 | 1990 | 9 | Wisley | 21.2
1990-09-14 | 1990 | 9 | Wisley | 19.6
1990-09-15 | 1990 | 9 | Wisley | 17.5
1990-09-16 | 1990 | 9 | Wisley | 15.6
1990-09-17 | 1990 | 9 | Wisley | 21.1
1990-09-18 | 1990 | 9 | Wisley | 17.4
1990-09-20 | 1990 | 9 | Wisley | 16.5
1990-09-21 | 1990 | 9 | Wisley | 15.1
1990-09-22 | 1990 | 9 | Wisley | 15.5
1990-09-23 | 1990 | 9 | Wisley | 17.1
1990-09-24 | 1990 | 9 | Wisley | 16.7
1990-09-25 | 1990 | 9 | Wisley | 17.9
1990-09-26 | 1990 | 9 | Wisley | 17.2
1990-09-27 | 1990 | 9 | Wisley | 21.1
1990-09-28 | 1990 | 9 | Wisley | 19
1990-09-29 | 1990 | 9 | Wisley | 19.6
1990-09-30 | 1990 | 9 | Wisley | 17.9
1991-05-01 | 1991 | 5 | Wisley | 11.4
1991-05-02 | 1991 | 5 | Wisley | 11.1
1991-05-03 | 1991 | 5 | Wisley | 11.8
1991-05-04 | 1991 | 5 | Wisley | 10.7
1991-05-05 | 1991 | 5 | Wisley | 9.8
1991-05-06 | 1991 | 5 | Wisley | 12.2
1991-05-07 | 1991 | 5 | Wisley | 14.4
1991-05-08 | 1991 | 5 | Wisley | 14.6
1991-05-09 | 1991 | 5 | Wisley | 17.3
1991-05-10 | 1991 | 5 | Wisley | 15.5
1991-05-11 | 1991 | 5 | Wisley | 19.2
1991-05-12 | 1991 | 5 | Wisley | 19.6
1991-05-13 | 1991 | 5 | Wisley | 16.4
1991-05-14 | 1991 | 5 | Wisley | 15
1991-05-15 | 1991 | 5 | Wisley | 12
1991-05-16 | 1991 | 5 | Wisley | 12
1991-05-17 | 1991 | 5 | Wisley | 14.4
1991-05-18 | 1991 | 5 | Wisley | 16.6
1991-05-19 | 1991 | 5 | Wisley | 21.1
1991-05-20 | 1991 | 5 | Wisley | 24
1991-05-21 | 1991 | 5 | Wisley | 21.6
1991-05-22 | 1991 | 5 | Wisley | 18.1
1991-05-23 | 1991 | 5 | Wisley | 17.8
1991-05-24 | 1991 | 5 | Wisley | 20.7
1991-05-25 | 1991 | 5 | Wisley | 16.8
1991-05-26 | 1991 | 5 | Wisley | 20.2
1991-05-27 | 1991 | 5 | Wisley | 13.4
1991-05-28 | 1991 | 5 | Wisley | 16
1991-05-29 | 1991 | 5 | Wisley | 16.9
1991-05-30 | 1991 | 5 | Wisley | 14.2
1991-05-31 | 1991 | 5 | Wisley | 14.4
1991-06-01 | 1991 | 6 | Wisley | 15.6
1991-06-02 | 1991 | 6 | Wisley | 14.8
1991-06-03 | 1991 | 6 | Wisley | 16
1991-06-04 | 1991 | 6 | Wisley | 15.5
1991-06-05 | 1991 | 6 | Wisley | 18.5
1991-06-06 | 1991 | 6 | Wisley | 15.2
1991-06-07 | 1991 | 6 | Wisley | 16
1991-06-08 | 1991 | 6 | Wisley | 17.6
1991-06-09 | 1991 | 6 | Wisley | 18.2
1991-06-10 | 1991 | 6 | Wisley | 16.9
1991-06-11 | 1991 | 6 | Wisley | 18.2
1991-06-12 | 1991 | 6 | Wisley | 16.5
1991-06-13 | 1991 | 6 | Wisley | 17.7
1991-06-14 | 1991 | 6 | Wisley | 16.7
1991-06-15 | 1991 | 6 | Wisley | 16.6
1991-06-16 | 1991 | 6 | Wisley | 15.8
1991-06-17 | 1991 | 6 | Wisley | 14.6
1991-06-18 | 1991 | 6 | Wisley | 15.9
1991-06-19 | 1991 | 6 | Wisley | 19.1
1991-06-20 | 1991 | 6 | Wisley | 21
1991-06-21 | 1991 | 6 | Wisley | 15.9
1991-06-23 | 1991 | 6 | Wisley | 16.4
1991-06-24 | 1991 | 6 | Wisley | 18
1991-06-25 | 1991 | 6 | Wisley | 18.4
1991-06-26 | 1991 | 6 | Wisley | 19.1
1991-06-27 | 1991 | 6 | Wisley | 20.3
1991-06-28 | 1991 | 6 | Wisley | 20.3
1991-06-29 | 1991 | 6 | Wisley | 20.5
1991-06-30 | 1991 | 6 | Wisley | 20.6
1991-07-01 | 1991 | 7 | Wisley | 19.6
1991-07-02 | 1991 | 7 | Wisley | 23.7
1991-07-03 | 1991 | 7 | Wisley | 27
1991-07-04 | 1991 | 7 | Wisley | 27
1991-07-05 | 1991 | 7 | Wisley | 22.4
1991-07-06 | 1991 | 7 | Wisley | 24.8
1991-07-07 | 1991 | 7 | Wisley | 19.5
1991-07-08 | 1991 | 7 | Wisley | 22.1
1991-07-09 | 1991 | 7 | Wisley | 23.9
1991-07-10 | 1991 | 7 | Wisley | 25.9
1991-07-13 | 1991 | 7 | Wisley | 23
1991-07-14 | 1991 | 7 | Wisley | 20.5
1991-07-15 | 1991 | 7 | Wisley | 20.1
1991-07-16 | 1991 | 7 | Wisley | 20.5
1991-07-17 | 1991 | 7 | Wisley | 22.9
1991-07-18 | 1991 | 7 | Wisley | 19.6
1991-07-19 | 1991 | 7 | Wisley | 22.8
1991-07-20 | 1991 | 7 | Wisley | 20.9
1991-07-21 | 1991 | 7 | Wisley | 23.6
1991-07-22 | 1991 | 7 | Wisley | 25.9
1991-07-24 | 1991 | 7 | Wisley | 21.2
1991-07-25 | 1991 | 7 | Wisley | 24
1991-07-26 | 1991 | 7 | Wisley | 25.1
1991-07-27 | 1991 | 7 | Wisley | 25.1
1991-07-28 | 1991 | 7 | Wisley | 28.2
1991-07-29 | 1991 | 7 | Wisley | 20.4
1991-07-30 | 1991 | 7 | Wisley | 22.4
1991-07-31 | 1991 | 7 | Wisley | 23.3
1991-08-01 | 1991 | 8 | Wisley | 23.5
1991-08-02 | 1991 | 8 | Wisley | 22.5
1991-08-03 | 1991 | 8 | Wisley | 24.1
1991-08-04 | 1991 | 8 | Wisley | 22.9
1991-08-05 | 1991 | 8 | Wisley | 21.8
1991-08-07 | 1991 | 8 | Wisley | 23
1991-08-08 | 1991 | 8 | Wisley | 23.9
1991-08-09 | 1991 | 8 | Wisley | 26.7
1991-08-10 | 1991 | 8 | Wisley | 21.5
1991-08-11 | 1991 | 8 | Wisley | 23.2
1991-08-12 | 1991 | 8 | Wisley | 23.8
1991-08-13 | 1991 | 8 | Wisley | 25
1991-08-14 | 1991 | 8 | Wisley | 25.2
1991-08-15 | 1991 | 8 | Wisley | 24
1991-08-16 | 1991 | 8 | Wisley | 23.3
1991-08-17 | 1991 | 8 | Wisley | 22.2
1991-08-18 | 1991 | 8 | Wisley | 24.6
1991-08-19 | 1991 | 8 | Wisley | 25.2
1991-08-20 | 1991 | 8 | Wisley | 26.7
1991-08-21 | 1991 | 8 | Wisley | 23.8
1991-08-23 | 1991 | 8 | Wisley | 23.1
1991-08-24 | 1991 | 8 | Wisley | 23.8
1991-08-25 | 1991 | 8 | Wisley | 26.3
1991-08-26 | 1991 | 8 | Wisley | 26.2
1991-08-27 | 1991 | 8 | Wisley | 24.1
1991-08-28 | 1991 | 8 | Wisley | 22.6
1991-08-29 | 1991 | 8 | Wisley | 25.2
1991-08-30 | 1991 | 8 | Wisley | 26.9
1991-08-31 | 1991 | 8 | Wisley | 28.8
1991-09-01 | 1991 | 9 | Wisley | 25.6
1991-09-02 | 1991 | 9 | Wisley | 25.7
1991-09-03 | 1991 | 9 | Wisley | 26.6
1991-09-04 | 1991 | 9 | Wisley | 24.3
1991-09-05 | 1991 | 9 | Wisley | 20.7
1991-09-06 | 1991 | 9 | Wisley | 20.7
1991-09-07 | 1991 | 9 | Wisley | 24
1991-09-08 | 1991 | 9 | Wisley | 23.7
1991-09-09 | 1991 | 9 | Wisley | 24.3
1991-09-10 | 1991 | 9 | Wisley | 19
1991-09-11 | 1991 | 9 | Wisley | 21.5
1991-09-12 | 1991 | 9 | Wisley | 23.3
1991-09-13 | 1991 | 9 | Wisley | 23.8
1991-09-14 | 1991 | 9 | Wisley | 22.5
1991-09-15 | 1991 | 9 | Wisley | 20
1991-09-16 | 1991 | 9 | Wisley | 21.2
1991-09-17 | 1991 | 9 | Wisley | 20.7
1991-09-18 | 1991 | 9 | Wisley | 19.6
1991-09-19 | 1991 | 9 | Wisley | 20.5
1991-09-20 | 1991 | 9 | Wisley | 24
1991-09-21 | 1991 | 9 | Wisley | 18.9
1991-09-22 | 1991 | 9 | Wisley | 19.7
1991-09-23 | 1991 | 9 | Wisley | 18.8
1991-09-24 | 1991 | 9 | Wisley | 18.3
1991-09-25 | 1991 | 9 | Wisley | 18
1991-09-27 | 1991 | 9 | Wisley | 14.1
1991-09-28 | 1991 | 9 | Wisley | 16.2
1991-09-29 | 1991 | 9 | Wisley | 15.2
1991-09-30 | 1991 | 9 | Wisley | 16.7
1992-05-01 | 1992 | 5 | Wisley | 12.5
1992-05-02 | 1992 | 5 | Wisley | 16
1992-05-03 | 1992 | 5 | Wisley | 17.8
1992-05-04 | 1992 | 5 | Wisley | 14.8
1992-05-05 | 1992 | 5 | Wisley | 20.8
1992-05-06 | 1992 | 5 | Wisley | 20.2
1992-05-08 | 1992 | 5 | Wisley | 15.8
1992-05-09 | 1992 | 5 | Wisley | 15.8
1992-05-10 | 1992 | 5 | Wisley | 15
1992-05-11 | 1992 | 5 | Wisley | 16.6
1992-05-12 | 1992 | 5 | Wisley | 22
1992-05-13 | 1992 | 5 | Wisley | 25
1992-05-14 | 1992 | 5 | Wisley | 19.9
1992-05-15 | 1992 | 5 | Wisley | 21
1992-05-16 | 1992 | 5 | Wisley | 17.6
1992-05-17 | 1992 | 5 | Wisley | 21.5
1992-05-18 | 1992 | 5 | Wisley | 26.2
1992-05-19 | 1992 | 5 | Wisley | 25.7
1992-05-20 | 1992 | 5 | Wisley | 26.2
1992-05-21 | 1992 | 5 | Wisley | 25.6
1992-05-22 | 1992 | 5 | Wisley | 26.8
1992-05-23 | 1992 | 5 | Wisley | 26.2
1992-05-24 | 1992 | 5 | Wisley | 25.7
1992-05-25 | 1992 | 5 | Wisley | 25.9
1992-05-26 | 1992 | 5 | Wisley | 22.7
1992-05-27 | 1992 | 5 | Wisley | 24.1
1992-05-28 | 1992 | 5 | Wisley | 19.1
1992-05-29 | 1992 | 5 | Wisley | 19.8
1992-05-30 | 1992 | 5 | Wisley | 23.2
1992-05-31 | 1992 | 5 | Wisley | 18.5
1992-06-01 | 1992 | 6 | Wisley | 20.4
1992-06-02 | 1992 | 6 | Wisley | 19.7
1992-06-03 | 1992 | 6 | Wisley | 16
1992-06-04 | 1992 | 6 | Wisley | 16.2
1992-06-05 | 1992 | 6 | Wisley | 21
1992-06-06 | 1992 | 6 | Wisley | 18.8
1992-06-07 | 1992 | 6 | Wisley | 21.3
1992-06-08 | 1992 | 6 | Wisley | 22.6
1992-06-09 | 1992 | 6 | Wisley | 23.6
1992-06-10 | 1992 | 6 | Wisley | 21.9
1992-06-11 | 1992 | 6 | Wisley | 23.4
1992-06-12 | 1992 | 6 | Wisley | 25.4
1992-06-13 | 1992 | 6 | Wisley | 26.3
1992-06-14 | 1992 | 6 | Wisley | 28
1992-06-15 | 1992 | 6 | Wisley | 21.2
1992-06-17 | 1992 | 6 | Wisley | 18.8
1992-06-18 | 1992 | 6 | Wisley | 16.1
1992-06-19 | 1992 | 6 | Wisley | 21
1992-06-20 | 1992 | 6 | Wisley | 22.5
1992-06-21 | 1992 | 6 | Wisley | 21.7
1992-06-22 | 1992 | 6 | Wisley | 21.1
1992-06-23 | 1992 | 6 | Wisley | 22
1992-06-24 | 1992 | 6 | Wisley | 23.3
1992-06-25 | 1992 | 6 | Wisley | 25.3
1992-06-26 | 1992 | 6 | Wisley | 25.7
1992-06-27 | 1992 | 6 | Wisley | 27
1992-06-28 | 1992 | 6 | Wisley | 29.7
1992-06-29 | 1992 | 6 | Wisley | 22.9
1992-07-02 | 1992 | 7 | Wisley | 17.8
1992-07-03 | 1992 | 7 | Wisley | 19.8
1992-07-04 | 1992 | 7 | Wisley | 19.4
1992-07-05 | 1992 | 7 | Wisley | 22.5
1992-07-06 | 1992 | 7 | Wisley | 21
1992-07-07 | 1992 | 7 | Wisley | 16.8
1992-07-08 | 1992 | 7 | Wisley | 19.7
1992-07-09 | 1992 | 7 | Wisley | 19.2
1992-07-10 | 1992 | 7 | Wisley | 18.2
1992-07-11 | 1992 | 7 | Wisley | 21.3
1992-07-12 | 1992 | 7 | Wisley | 19
1992-07-13 | 1992 | 7 | Wisley | 21.3
1992-07-14 | 1992 | 7 | Wisley | 22
1992-07-15 | 1992 | 7 | Wisley | 23.4
1992-07-16 | 1992 | 7 | Wisley | 23.4
1992-07-17 | 1992 | 7 | Wisley | 22.6
1992-07-18 | 1992 | 7 | Wisley | 23.2
1992-07-19 | 1992 | 7 | Wisley | 26
1992-07-20 | 1992 | 7 | Wisley | 22.9
1992-07-21 | 1992 | 7 | Wisley | 23
1992-07-22 | 1992 | 7 | Wisley | 23.5
1992-07-23 | 1992 | 7 | Wisley | 23.7
1992-07-24 | 1992 | 7 | Wisley | 22.4
1992-07-25 | 1992 | 7 | Wisley | 20.2
1992-07-26 | 1992 | 7 | Wisley | 21.6
1992-07-27 | 1992 | 7 | Wisley | 22
1992-07-28 | 1992 | 7 | Wisley | 25.9
1992-07-29 | 1992 | 7 | Wisley | 26.6
1992-07-30 | 1992 | 7 | Wisley | 26.8
1992-07-31 | 1992 | 7 | Wisley | 26.8
1992-08-01 | 1992 | 8 | Wisley | 21.2
1992-08-02 | 1992 | 8 | Wisley | 22.7
1992-08-03 | 1992 | 8 | Wisley | 22.3
1992-08-04 | 1992 | 8 | Wisley | 22.8
1992-08-05 | 1992 | 8 | Wisley | 24
1992-08-06 | 1992 | 8 | Wisley | 28
1992-08-07 | 1992 | 8 | Wisley | 26.5
1992-08-08 | 1992 | 8 | Wisley | 23.2
1992-08-09 | 1992 | 8 | Wisley | 22
1992-08-10 | 1992 | 8 | Wisley | 20.1
1992-08-11 | 1992 | 8 | Wisley | 17.9
1992-08-13 | 1992 | 8 | Wisley | 18.8
1992-08-14 | 1992 | 8 | Wisley | 20.7
1992-08-15 | 1992 | 8 | Wisley | 19.2
1992-08-16 | 1992 | 8 | Wisley | 19.4
1992-08-17 | 1992 | 8 | Wisley | 19.3
1992-08-18 | 1992 | 8 | Wisley | 22.5
1992-08-19 | 1992 | 8 | Wisley | 19.4
1992-08-20 | 1992 | 8 | Wisley | 22.9
1992-08-21 | 1992 | 8 | Wisley | 19.6
1992-08-22 | 1992 | 8 | Wisley | 19.5
1992-08-23 | 1992 | 8 | Wisley | 19.4
1992-08-24 | 1992 | 8 | Wisley | 22.5
1992-08-25 | 1992 | 8 | Wisley | 19.2
1992-08-26 | 1992 | 8 | Wisley | 20.2
1992-08-27 | 1992 | 8 | Wisley | 19.5
1992-08-28 | 1992 | 8 | Wisley | 18.4
1992-08-29 | 1992 | 8 | Wisley | 17.9
1992-08-30 | 1992 | 8 | Wisley | 17.3
1992-08-31 | 1992 | 8 | Wisley | 16.2
1992-09-01 | 1992 | 9 | Wisley | 20.3
1992-09-02 | 1992 | 9 | Wisley | 16.2
1992-09-03 | 1992 | 9 | Wisley | 16.2
1992-09-04 | 1992 | 9 | Wisley | 17.1
1992-09-05 | 1992 | 9 | Wisley | 17
1992-09-06 | 1992 | 9 | Wisley | 17.2
1992-09-07 | 1992 | 9 | Wisley | 15.7
1992-09-08 | 1992 | 9 | Wisley | 17.2
1992-09-09 | 1992 | 9 | Wisley | 20.1
1992-09-10 | 1992 | 9 | Wisley | 18.3
1992-09-11 | 1992 | 9 | Wisley | 16.9
1992-09-12 | 1992 | 9 | Wisley | 15.1
1992-09-13 | 1992 | 9 | Wisley | 18.4
1992-09-14 | 1992 | 9 | Wisley | 18.5
1992-09-15 | 1992 | 9 | Wisley | 19.5
1992-09-16 | 1992 | 9 | Wisley | 23
1992-09-17 | 1992 | 9 | Wisley | 18.4
1992-09-18 | 1992 | 9 | Wisley | 18.7
1992-09-19 | 1992 | 9 | Wisley | 19.2
1992-09-20 | 1992 | 9 | Wisley | 18.6
1992-09-21 | 1992 | 9 | Wisley | 17.2
1992-09-22 | 1992 | 9 | Wisley | 16.5
1992-09-23 | 1992 | 9 | Wisley | 17.9
1992-09-24 | 1992 | 9 | Wisley | 19
1992-09-25 | 1992 | 9 | Wisley | 23.1
1992-09-26 | 1992 | 9 | Wisley | 22.3
1992-09-27 | 1992 | 9 | Wisley | 21.8
1992-09-28 | 1992 | 9 | Wisley | 20.2
1992-09-29 | 1992 | 9 | Wisley | 17.2
1992-09-30 | 1992 | 9 | Wisley | 16.7
1993-05-02 | 1993 | 5 | Wisley | 13.9
1993-05-03 | 1993 | 5 | Wisley | 16
1993-05-04 | 1993 | 5 | Wisley | 14.7
1993-05-05 | 1993 | 5 | Wisley | 14.6
1993-05-06 | 1993 | 5 | Wisley | 16.3
1993-05-07 | 1993 | 5 | Wisley | 18
1993-05-08 | 1993 | 5 | Wisley | 17.7
1993-05-09 | 1993 | 5 | Wisley | 20.9
1993-05-10 | 1993 | 5 | Wisley | 24.7
1993-05-11 | 1993 | 5 | Wisley | 18.6
1993-05-12 | 1993 | 5 | Wisley | 17
1993-05-13 | 1993 | 5 | Wisley | 15.1
1993-05-14 | 1993 | 5 | Wisley | 13.9
1993-05-15 | 1993 | 5 | Wisley | 17.4
1993-05-16 | 1993 | 5 | Wisley | 21.5
1993-05-17 | 1993 | 5 | Wisley | 18
1993-05-18 | 1993 | 5 | Wisley | 17.8
1993-05-19 | 1993 | 5 | Wisley | 12.6
1993-05-20 | 1993 | 5 | Wisley | 17.3
1993-05-21 | 1993 | 5 | Wisley | 19.6
1993-05-22 | 1993 | 5 | Wisley | 23.2
1993-05-23 | 1993 | 5 | Wisley | 24.7
1993-05-24 | 1993 | 5 | Wisley | 18.9
1993-05-27 | 1993 | 5 | Wisley | 17.9
1993-05-28 | 1993 | 5 | Wisley | 16.4
1993-05-29 | 1993 | 5 | Wisley | 16.2
1993-05-30 | 1993 | 5 | Wisley | 17.6
1993-05-31 | 1993 | 5 | Wisley | 19.4
1993-06-01 | 1993 | 6 | Wisley | 18.2
1993-06-02 | 1993 | 6 | Wisley | 18.7
1993-06-03 | 1993 | 6 | Wisley | 21.9
1993-06-04 | 1993 | 6 | Wisley | 23.8
1993-06-05 | 1993 | 6 | Wisley | 24.9
1993-06-06 | 1993 | 6 | Wisley | 25.4
1993-06-07 | 1993 | 6 | Wisley | 27.2
1993-06-08 | 1993 | 6 | Wisley | 26.5
1993-06-09 | 1993 | 6 | Wisley | 22.7
1993-06-12 | 1993 | 6 | Wisley | 18.6
1993-06-13 | 1993 | 6 | Wisley | 18.9
1993-06-14 | 1993 | 6 | Wisley | 20.3
1993-06-15 | 1993 | 6 | Wisley | 17.4
1993-06-16 | 1993 | 6 | Wisley | 20.9
1993-06-17 | 1993 | 6 | Wisley | 17.6
1993-06-18 | 1993 | 6 | Wisley | 18
1993-06-19 | 1993 | 6 | Wisley | 20.8
1993-06-20 | 1993 | 6 | Wisley | 19
1993-06-21 | 1993 | 6 | Wisley | 19.3
1993-06-22 | 1993 | 6 | Wisley | 19.2
1993-06-23 | 1993 | 6 | Wisley | 20.5
1993-06-24 | 1993 | 6 | Wisley | 21.5
1993-06-25 | 1993 | 6 | Wisley | 23.1
1993-06-26 | 1993 | 6 | Wisley | 25
1993-06-27 | 1993 | 6 | Wisley | 24
1993-06-28 | 1993 | 6 | Wisley | 23.7
1993-06-29 | 1993 | 6 | Wisley | 26.8
1993-06-30 | 1993 | 6 | Wisley | 24.2
1993-07-01 | 1993 | 7 | Wisley | 25.4
1993-07-02 | 1993 | 7 | Wisley | 26.8
1993-07-03 | 1993 | 7 | Wisley | 27.3
1993-07-05 | 1993 | 7 | Wisley | 23.3
1993-07-06 | 1993 | 7 | Wisley | 22.6
1993-07-07 | 1993 | 7 | Wisley | 21.8
1993-07-08 | 1993 | 7 | Wisley | 17.7
1993-07-10 | 1993 | 7 | Wisley | 18.3
1993-07-11 | 1993 | 7 | Wisley | 17.8
1993-07-12 | 1993 | 7 | Wisley | 18.7
1993-07-13 | 1993 | 7 | Wisley | 23.9
1993-07-14 | 1993 | 7 | Wisley | 20.2
1993-07-15 | 1993 | 7 | Wisley | 20.8
1993-07-16 | 1993 | 7 | Wisley | 21.4
1993-07-17 | 1993 | 7 | Wisley | 19.5
1993-07-18 | 1993 | 7 | Wisley | 20.9
1993-07-19 | 1993 | 7 | Wisley | 19.6
1993-07-20 | 1993 | 7 | Wisley | 17.9
1993-07-21 | 1993 | 7 | Wisley | 21.7
1993-07-22 | 1993 | 7 | Wisley | 24.9
1993-07-23 | 1993 | 7 | Wisley | 19.1
1993-07-25 | 1993 | 7 | Wisley | 18.5
1993-07-26 | 1993 | 7 | Wisley | 20.2
1993-07-27 | 1993 | 7 | Wisley | 23.3
1993-07-28 | 1993 | 7 | Wisley | 19.9
1993-07-29 | 1993 | 7 | Wisley | 21
1993-07-30 | 1993 | 7 | Wisley | 19.5
1993-07-31 | 1993 | 7 | Wisley | 21.3
1993-08-01 | 1993 | 8 | Wisley | 21.8
1993-08-02 | 1993 | 8 | Wisley | 20.9
1993-08-03 | 1993 | 8 | Wisley | 18.8
1993-08-04 | 1993 | 8 | Wisley | 20.3
1993-08-05 | 1993 | 8 | Wisley | 21.1
1993-08-06 | 1993 | 8 | Wisley | 23.4
1993-08-07 | 1993 | 8 | Wisley | 21.5
1993-08-08 | 1993 | 8 | Wisley | 22.3
1993-08-09 | 1993 | 8 | Wisley | 18.6
1993-08-10 | 1993 | 8 | Wisley | 20.6
1993-08-11 | 1993 | 8 | Wisley | 19.5
1993-08-12 | 1993 | 8 | Wisley | 21
1993-08-13 | 1993 | 8 | Wisley | 25.1
1993-08-14 | 1993 | 8 | Wisley | 22.6
1993-08-15 | 1993 | 8 | Wisley | 22.4
1993-08-16 | 1993 | 8 | Wisley | 22.6
1993-08-17 | 1993 | 8 | Wisley | 23.3
1993-08-18 | 1993 | 8 | Wisley | 25.2
1993-08-19 | 1993 | 8 | Wisley | 25.4
1993-08-20 | 1993 | 8 | Wisley | 24.6
1993-08-23 | 1993 | 8 | Wisley | 17.4
1993-08-24 | 1993 | 8 | Wisley | 18.3
1993-08-25 | 1993 | 8 | Wisley | 18.6
1993-08-26 | 1993 | 8 | Wisley | 18.1
1993-08-27 | 1993 | 8 | Wisley | 20.2
1993-08-28 | 1993 | 8 | Wisley | 22.2
1993-08-29 | 1993 | 8 | Wisley | 23.3
1993-08-30 | 1993 | 8 | Wisley | 19
1993-08-31 | 1993 | 8 | Wisley | 24.2
1993-09-01 | 1993 | 9 | Wisley | 21
1993-09-02 | 1993 | 9 | Wisley | 19.4
1993-09-03 | 1993 | 9 | Wisley | 17.1
1993-09-04 | 1993 | 9 | Wisley | 18
1993-09-05 | 1993 | 9 | Wisley | 19.1
1993-09-06 | 1993 | 9 | Wisley | 22
1993-09-07 | 1993 | 9 | Wisley | 20.7
1993-09-08 | 1993 | 9 | Wisley | 19.7
1993-09-10 | 1993 | 9 | Wisley | 18
1993-09-11 | 1993 | 9 | Wisley | 15.2
1993-09-12 | 1993 | 9 | Wisley | 16.5
1993-09-13 | 1993 | 9 | Wisley | 15
1993-09-14 | 1993 | 9 | Wisley | 15.6
1993-09-15 | 1993 | 9 | Wisley | 14.8
1993-09-16 | 1993 | 9 | Wisley | 16.8
1993-09-17 | 1993 | 9 | Wisley | 17.3
1993-09-18 | 1993 | 9 | Wisley | 21.1
1993-09-19 | 1993 | 9 | Wisley | 17.2
1993-09-20 | 1993 | 9 | Wisley | 19
1993-09-21 | 1993 | 9 | Wisley | 18.7
1993-09-22 | 1993 | 9 | Wisley | 16.3
1993-09-23 | 1993 | 9 | Wisley | 16.7
1993-09-24 | 1993 | 9 | Wisley | 12.5
1993-09-25 | 1993 | 9 | Wisley | 14
1993-09-26 | 1993 | 9 | Wisley | 9.4
1993-09-27 | 1993 | 9 | Wisley | 11.6
1993-09-28 | 1993 | 9 | Wisley | 14.9
1993-09-29 | 1993 | 9 | Wisley | 14.2
1993-09-30 | 1993 | 9 | Wisley | 13.4
1994-05-01 | 1994 | 5 | Wisley | 18.3
1994-05-02 | 1994 | 5 | Wisley | 19
1994-05-03 | 1994 | 5 | Wisley | 13.6
1994-05-05 | 1994 | 5 | Wisley | 14.9
1994-05-06 | 1994 | 5 | Wisley | 13.4
1994-05-07 | 1994 | 5 | Wisley | 16.6
1994-05-08 | 1994 | 5 | Wisley | 16.4
1994-05-09 | 1994 | 5 | Wisley | 18.2
1994-05-10 | 1994 | 5 | Wisley | 18.2
1994-05-11 | 1994 | 5 | Wisley | 17.6
1994-05-12 | 1994 | 5 | Wisley | 19.7
1994-05-13 | 1994 | 5 | Wisley | 19.1
1994-05-14 | 1994 | 5 | Wisley | 20.3
1994-05-17 | 1994 | 5 | Wisley | 13.3
1994-05-18 | 1994 | 5 | Wisley | 13.2
1994-05-19 | 1994 | 5 | Wisley | 15
1994-05-20 | 1994 | 5 | Wisley | 14.5
1994-05-21 | 1994 | 5 | Wisley | 16.5
1994-05-22 | 1994 | 5 | Wisley | 16.6
1994-05-23 | 1994 | 5 | Wisley | 13.6
1994-05-24 | 1994 | 5 | Wisley | 16.4
1994-05-25 | 1994 | 5 | Wisley | 12.6
1994-05-27 | 1994 | 5 | Wisley | 13.5
1994-05-28 | 1994 | 5 | Wisley | 16.5
1994-05-29 | 1994 | 5 | Wisley | 17.3
1994-05-30 | 1994 | 5 | Wisley | 21
1994-05-31 | 1994 | 5 | Wisley | 24.6
1994-06-01 | 1994 | 6 | Wisley | 18.6
1994-06-04 | 1994 | 6 | Wisley | 17
1994-06-05 | 1994 | 6 | Wisley | 20.9
1994-06-06 | 1994 | 6 | Wisley | 20.2
1994-06-07 | 1994 | 6 | Wisley | 16.8
1994-06-08 | 1994 | 6 | Wisley | 16
1994-06-09 | 1994 | 6 | Wisley | 16.5
1994-06-10 | 1994 | 6 | Wisley | 18.6
1994-06-11 | 1994 | 6 | Wisley | 20.8
1994-06-12 | 1994 | 6 | Wisley | 23
1994-06-13 | 1994 | 6 | Wisley | 24.2
1994-06-14 | 1994 | 6 | Wisley | 22.6
1994-06-15 | 1994 | 6 | Wisley | 23.6
1994-06-16 | 1994 | 6 | Wisley | 24.3
1994-06-17 | 1994 | 6 | Wisley | 22.5
1994-06-18 | 1994 | 6 | Wisley | 20.3
1994-06-20 | 1994 | 6 | Wisley | 18
1994-06-21 | 1994 | 6 | Wisley | 21.2
1994-06-22 | 1994 | 6 | Wisley | 23.6
1994-06-23 | 1994 | 6 | Wisley | 28.4
1994-06-24 | 1994 | 6 | Wisley | 21.9
1994-06-26 | 1994 | 6 | Wisley | 23.9
1994-06-27 | 1994 | 6 | Wisley | 26.5
1994-06-28 | 1994 | 6 | Wisley | 21.5
1994-06-29 | 1994 | 6 | Wisley | 23.7
1994-06-30 | 1994 | 6 | Wisley | 26.6
1994-07-01 | 1994 | 7 | Wisley | 26.8
1994-07-02 | 1994 | 7 | Wisley | 28
1994-07-03 | 1994 | 7 | Wisley | 22.9
1994-07-05 | 1994 | 7 | Wisley | 19.9
1994-07-06 | 1994 | 7 | Wisley | 21.5
1994-07-07 | 1994 | 7 | Wisley | 17.7
1994-07-08 | 1994 | 7 | Wisley | 23.9
1994-07-09 | 1994 | 7 | Wisley | 24.8
1994-07-10 | 1994 | 7 | Wisley | 28.8
1994-07-11 | 1994 | 7 | Wisley | 31.2
1994-07-12 | 1994 | 7 | Wisley | 21.1
1994-07-13 | 1994 | 7 | Wisley | 26.2
1994-07-14 | 1994 | 7 | Wisley | 23.9
1994-07-15 | 1994 | 7 | Wisley | 25.5
1994-07-16 | 1994 | 7 | Wisley | 24.3
1994-07-17 | 1994 | 7 | Wisley | 23.8
1994-07-18 | 1994 | 7 | Wisley | 25.7
1994-07-19 | 1994 | 7 | Wisley | 27.6
1994-07-20 | 1994 | 7 | Wisley | 28.2
1994-07-21 | 1994 | 7 | Wisley | 27
1994-07-22 | 1994 | 7 | Wisley | 27.5
1994-07-23 | 1994 | 7 | Wisley | 31.4
1994-07-24 | 1994 | 7 | Wisley | 28.7
1994-07-26 | 1994 | 7 | Wisley | 27
1994-07-27 | 1994 | 7 | Wisley | 20.7
1994-07-28 | 1994 | 7 | Wisley | 25
1994-07-29 | 1994 | 7 | Wisley | 30.4
1994-07-30 | 1994 | 7 | Wisley | 25.4
1994-08-01 | 1994 | 8 | Wisley | 24.2
1994-08-02 | 1994 | 8 | Wisley | 30
1994-08-03 | 1994 | 8 | Wisley | 24
1994-08-04 | 1994 | 8 | Wisley | 27.1
1994-08-05 | 1994 | 8 | Wisley | 25.6
1994-08-06 | 1994 | 8 | Wisley | 22.4
1994-08-07 | 1994 | 8 | Wisley | 24.2
1994-08-08 | 1994 | 8 | Wisley | 23.4
1994-08-09 | 1994 | 8 | Wisley | 19
1994-08-11 | 1994 | 8 | Wisley | 19
1994-08-12 | 1994 | 8 | Wisley | 21.5
1994-08-13 | 1994 | 8 | Wisley | 20
1994-08-14 | 1994 | 8 | Wisley | 23.5
1994-08-15 | 1994 | 8 | Wisley | 24.6
1994-08-16 | 1994 | 8 | Wisley | 19.2
1994-08-17 | 1994 | 8 | Wisley | 21.5
1994-08-18 | 1994 | 8 | Wisley | 21.9
1994-08-19 | 1994 | 8 | Wisley | 21.2
1994-08-20 | 1994 | 8 | Wisley | 22.5
1994-08-21 | 1994 | 8 | Wisley | 25.8
1994-08-22 | 1994 | 8 | Wisley | 22.6
1994-08-23 | 1994 | 8 | Wisley | 21.6
1994-08-24 | 1994 | 8 | Wisley | 19.5
1994-08-25 | 1994 | 8 | Wisley | 23.2
1994-08-26 | 1994 | 8 | Wisley | 21.7
1994-08-27 | 1994 | 8 | Wisley | 20
1994-08-28 | 1994 | 8 | Wisley | 20.4
1994-08-29 | 1994 | 8 | Wisley | 19
1994-08-30 | 1994 | 8 | Wisley | 18.2
1994-08-31 | 1994 | 8 | Wisley | 17.5
1994-09-01 | 1994 | 9 | Wisley | 21.1
1994-09-02 | 1994 | 9 | Wisley | 18.1
1994-09-03 | 1994 | 9 | Wisley | 20.1
1994-09-04 | 1994 | 9 | Wisley | 18.9
1994-09-05 | 1994 | 9 | Wisley | 15.9
1994-09-06 | 1994 | 9 | Wisley | 19.3
1994-09-07 | 1994 | 9 | Wisley | 18
1994-09-08 | 1994 | 9 | Wisley | 18
1994-09-09 | 1994 | 9 | Wisley | 16.5
1994-09-10 | 1994 | 9 | Wisley | 17
1994-09-11 | 1994 | 9 | Wisley | 17.5
1994-09-12 | 1994 | 9 | Wisley | 19.3
1994-09-13 | 1994 | 9 | Wisley | 18.2
1994-09-16 | 1994 | 9 | Wisley | 14.1
1994-09-17 | 1994 | 9 | Wisley | 13.7
1994-09-18 | 1994 | 9 | Wisley | 13.7
1994-09-19 | 1994 | 9 | Wisley | 16.2
1994-09-20 | 1994 | 9 | Wisley | 19
1994-09-21 | 1994 | 9 | Wisley | 19
1994-09-22 | 1994 | 9 | Wisley | 18.3
1994-09-23 | 1994 | 9 | Wisley | 17.7
1994-09-24 | 1994 | 9 | Wisley | 17.3
1994-09-25 | 1994 | 9 | Wisley | 18
1994-09-26 | 1994 | 9 | Wisley | 19.1
1994-09-27 | 1994 | 9 | Wisley | 17.8
1994-09-28 | 1994 | 9 | Wisley | 14.8
1994-09-29 | 1994 | 9 | Wisley | 14.1
1994-09-30 | 1994 | 9 | Wisley | 16.3
1995-05-01 | 1995 | 5 | Wisley | 22.8
1995-05-02 | 1995 | 5 | Wisley | 24.6
1995-05-03 | 1995 | 5 | Wisley | 26.4
1995-05-04 | 1995 | 5 | Wisley | 26.7
1995-05-05 | 1995 | 5 | Wisley | 26.4
1995-05-06 | 1995 | 5 | Wisley | 26.2
1995-05-09 | 1995 | 5 | Wisley | 16.6
1995-05-10 | 1995 | 5 | Wisley | 10.2
1995-05-12 | 1995 | 5 | Wisley | 12.7
1995-05-13 | 1995 | 5 | Wisley | 13.8
1995-05-14 | 1995 | 5 | Wisley | 14.9
1995-05-15 | 1995 | 5 | Wisley | 13.9
1995-05-16 | 1995 | 5 | Wisley | 10.3
1995-05-17 | 1995 | 5 | Wisley | 14.1
1995-05-18 | 1995 | 5 | Wisley | 15.8
1995-05-19 | 1995 | 5 | Wisley | 15
1995-05-20 | 1995 | 5 | Wisley | 16
1995-05-21 | 1995 | 5 | Wisley | 17.9
1995-05-22 | 1995 | 5 | Wisley | 22.2
1995-05-23 | 1995 | 5 | Wisley | 17.9
1995-05-24 | 1995 | 5 | Wisley | 18.9
1995-05-25 | 1995 | 5 | Wisley | 19
1995-05-26 | 1995 | 5 | Wisley | 19.5
1995-05-27 | 1995 | 5 | Wisley | 19.2
1995-05-28 | 1995 | 5 | Wisley | 18.5
1995-05-29 | 1995 | 5 | Wisley | 18.5
1995-05-30 | 1995 | 5 | Wisley | 19.8
1995-05-31 | 1995 | 5 | Wisley | 17.3
1995-06-01 | 1995 | 6 | Wisley | 17.4
1995-06-02 | 1995 | 6 | Wisley | 14.6
1995-06-03 | 1995 | 6 | Wisley | 15.2
1995-06-04 | 1995 | 6 | Wisley | 18
1995-06-05 | 1995 | 6 | Wisley | 17.2
1995-06-06 | 1995 | 6 | Wisley | 19.2
1995-06-07 | 1995 | 6 | Wisley | 16.3
1995-06-08 | 1995 | 6 | Wisley | 17.6
1995-06-09 | 1995 | 6 | Wisley | 14.6
1995-06-10 | 1995 | 6 | Wisley | 15
1995-06-11 | 1995 | 6 | Wisley | 13.5
1995-06-12 | 1995 | 6 | Wisley | 14.2
1995-06-13 | 1995 | 6 | Wisley | 15.7
1995-06-14 | 1995 | 6 | Wisley | 16.2
1995-06-15 | 1995 | 6 | Wisley | 21.1
1995-06-16 | 1995 | 6 | Wisley | 17.1
1995-06-17 | 1995 | 6 | Wisley | 21.4
1995-06-18 | 1995 | 6 | Wisley | 22.9
1995-06-19 | 1995 | 6 | Wisley | 23.7
1995-06-20 | 1995 | 6 | Wisley | 22.2
1995-06-21 | 1995 | 6 | Wisley | 21.6
1995-06-22 | 1995 | 6 | Wisley | 21.4
1995-06-23 | 1995 | 6 | Wisley | 16.3
1995-06-24 | 1995 | 6 | Wisley | 23.8
1995-06-25 | 1995 | 6 | Wisley | 24.9
1995-06-26 | 1995 | 6 | Wisley | 27.2
1995-06-27 | 1995 | 6 | Wisley | 28.8
1995-06-28 | 1995 | 6 | Wisley | 27.6
1995-06-29 | 1995 | 6 | Wisley | 31.3
1995-06-30 | 1995 | 6 | Wisley | 21.4
1995-07-02 | 1995 | 7 | Wisley | 19.9
1995-07-03 | 1995 | 7 | Wisley | 22.1
1995-07-04 | 1995 | 7 | Wisley | 22.7
1995-07-05 | 1995 | 7 | Wisley | 24.5
1995-07-06 | 1995 | 7 | Wisley | 23.5
1995-07-07 | 1995 | 7 | Wisley | 28.1
1995-07-08 | 1995 | 7 | Wisley | 27.7
1995-07-09 | 1995 | 7 | Wisley | 30.6
1995-07-10 | 1995 | 7 | Wisley | 27
1995-07-11 | 1995 | 7 | Wisley | 24.7
1995-07-12 | 1995 | 7 | Wisley | 22.6
1995-07-13 | 1995 | 7 | Wisley | 22.5
1995-07-14 | 1995 | 7 | Wisley | 21.5
1995-07-15 | 1995 | 7 | Wisley | 20.7
1995-07-16 | 1995 | 7 | Wisley | 20.5
1995-07-17 | 1995 | 7 | Wisley | 23.5
1995-07-18 | 1995 | 7 | Wisley | 25.1
1995-07-19 | 1995 | 7 | Wisley | 29.9
1995-07-20 | 1995 | 7 | Wisley | 29
1995-07-22 | 1995 | 7 | Wisley | 24.6
1995-07-23 | 1995 | 7 | Wisley | 27.6
1995-07-24 | 1995 | 7 | Wisley | 28.4
1995-07-25 | 1995 | 7 | Wisley | 25
1995-07-27 | 1995 | 7 | Wisley | 24.6
1995-07-28 | 1995 | 7 | Wisley | 28.1
1995-07-29 | 1995 | 7 | Wisley | 30.3
1995-07-30 | 1995 | 7 | Wisley | 30.6
1995-07-31 | 1995 | 7 | Wisley | 32.5
1995-08-01 | 1995 | 8 | Wisley | 30.4
1995-08-02 | 1995 | 8 | Wisley | 30.4
1995-08-03 | 1995 | 8 | Wisley | 26.5
1995-08-04 | 1995 | 8 | Wisley | 26.3
1995-08-05 | 1995 | 8 | Wisley | 25.9
1995-08-06 | 1995 | 8 | Wisley | 21.1
1995-08-07 | 1995 | 8 | Wisley | 21.1
1995-08-08 | 1995 | 8 | Wisley | 25
1995-08-09 | 1995 | 8 | Wisley | 29
1995-08-10 | 1995 | 8 | Wisley | 31.2
1995-08-11 | 1995 | 8 | Wisley | 30
1995-08-12 | 1995 | 8 | Wisley | 25.9
1995-08-13 | 1995 | 8 | Wisley | 25.2
1995-08-14 | 1995 | 8 | Wisley | 29
1995-08-15 | 1995 | 8 | Wisley | 30.3
1995-08-16 | 1995 | 8 | Wisley | 26.3
1995-08-17 | 1995 | 8 | Wisley | 29.1
1995-08-18 | 1995 | 8 | Wisley | 30
1995-08-19 | 1995 | 8 | Wisley | 29.6
1995-08-20 | 1995 | 8 | Wisley | 29.4
1995-08-21 | 1995 | 8 | Wisley | 28
1995-08-22 | 1995 | 8 | Wisley | 21.8
1995-08-23 | 1995 | 8 | Wisley | 23.5
1995-08-24 | 1995 | 8 | Wisley | 24.2
1995-08-25 | 1995 | 8 | Wisley | 25
1995-08-26 | 1995 | 8 | Wisley | 21.2
1995-08-27 | 1995 | 8 | Wisley | 20.4
1995-08-28 | 1995 | 8 | Wisley | 17.5
1995-08-29 | 1995 | 8 | Wisley | 22.1
1995-08-30 | 1995 | 8 | Wisley | 21
1995-08-31 | 1995 | 8 | Wisley | 19
1995-09-01 | 1995 | 9 | Wisley | 19.5
1995-09-02 | 1995 | 9 | Wisley | 19.7
1995-09-03 | 1995 | 9 | Wisley | 21.6
1995-09-04 | 1995 | 9 | Wisley | 20.4
1995-09-05 | 1995 | 9 | Wisley | 20.2
1995-09-06 | 1995 | 9 | Wisley | 18.7
1995-09-07 | 1995 | 9 | Wisley | 19.6
1995-09-08 | 1995 | 9 | Wisley | 20.1
1995-09-09 | 1995 | 9 | Wisley | 16.5
1995-09-10 | 1995 | 9 | Wisley | 20.4
1995-09-11 | 1995 | 9 | Wisley | 17.5
1995-09-12 | 1995 | 9 | Wisley | 18.2
1995-09-13 | 1995 | 9 | Wisley | 17.7
1995-09-14 | 1995 | 9 | Wisley | 17.4
1995-09-15 | 1995 | 9 | Wisley | 16.7
1995-09-16 | 1995 | 9 | Wisley | 19
1995-09-17 | 1995 | 9 | Wisley | 18.3
1995-09-18 | 1995 | 9 | Wisley | 17.8
1995-09-19 | 1995 | 9 | Wisley | 17.8
1995-09-20 | 1995 | 9 | Wisley | 19.1
1995-09-21 | 1995 | 9 | Wisley | 19
1995-09-22 | 1995 | 9 | Wisley | 18
1995-09-23 | 1995 | 9 | Wisley | 16.2
1995-09-24 | 1995 | 9 | Wisley | 16.4
1995-09-25 | 1995 | 9 | Wisley | 17.6
1995-09-26 | 1995 | 9 | Wisley | 15.2
1995-09-27 | 1995 | 9 | Wisley | 14.4
1995-09-28 | 1995 | 9 | Wisley | 17
1995-09-29 | 1995 | 9 | Wisley | 17.5
1995-09-30 | 1995 | 9 | Wisley | 19.1
1996-05-01 | 1996 | 5 | Wisley | 11.3
1996-05-02 | 1996 | 5 | Wisley | 12.4
1996-05-03 | 1996 | 5 | Wisley | 12.1
1996-05-04 | 1996 | 5 | Wisley | 12.9
1996-05-05 | 1996 | 5 | Wisley | 15.3
1996-05-06 | 1996 | 5 | Wisley | 15.9
1996-05-07 | 1996 | 5 | Wisley | 14
1996-05-08 | 1996 | 5 | Wisley | 13.1
1996-05-09 | 1996 | 5 | Wisley | 11.5
1996-05-10 | 1996 | 5 | Wisley | 12.5
1996-05-11 | 1996 | 5 | Wisley | 14.8
1996-05-12 | 1996 | 5 | Wisley | 18
1996-05-13 | 1996 | 5 | Wisley | 15.1
1996-05-14 | 1996 | 5 | Wisley | 16.8
1996-05-15 | 1996 | 5 | Wisley | 10.8
1996-05-17 | 1996 | 5 | Wisley | 10
1996-05-18 | 1996 | 5 | Wisley | 12.6
1996-05-19 | 1996 | 5 | Wisley | 15.5
1996-05-20 | 1996 | 5 | Wisley | 16.3
1996-05-21 | 1996 | 5 | Wisley | 13.9
1996-05-22 | 1996 | 5 | Wisley | 15.9
1996-05-23 | 1996 | 5 | Wisley | 13.5
1996-05-24 | 1996 | 5 | Wisley | 17.4
1996-05-25 | 1996 | 5 | Wisley | 15.5
1996-05-26 | 1996 | 5 | Wisley | 16.2
1996-05-27 | 1996 | 5 | Wisley | 16.5
1996-05-28 | 1996 | 5 | Wisley | 21.2
1996-05-29 | 1996 | 5 | Wisley | 24.4
1996-05-30 | 1996 | 5 | Wisley | 19
1996-06-01 | 1996 | 6 | Wisley | 18.8
1996-06-02 | 1996 | 6 | Wisley | 18.8
1996-06-03 | 1996 | 6 | Wisley | 21.7
1996-06-04 | 1996 | 6 | Wisley | 26
1996-06-05 | 1996 | 6 | Wisley | 29.1
1996-06-06 | 1996 | 6 | Wisley | 30.4
1996-06-09 | 1996 | 6 | Wisley | 23.3
1996-06-10 | 1996 | 6 | Wisley | 22.4
1996-06-11 | 1996 | 6 | Wisley | 20.9
1996-06-12 | 1996 | 6 | Wisley | 22.3
1996-06-13 | 1996 | 6 | Wisley | 21.9
1996-06-14 | 1996 | 6 | Wisley | 22.9
1996-06-15 | 1996 | 6 | Wisley | 26.1
1996-06-16 | 1996 | 6 | Wisley | 27.5
1996-06-17 | 1996 | 6 | Wisley | 23.1
1996-06-18 | 1996 | 6 | Wisley | 21.4
1996-06-19 | 1996 | 6 | Wisley | 16.1
1996-06-20 | 1996 | 6 | Wisley | 17.3
1996-06-21 | 1996 | 6 | Wisley | 16.8
1996-06-22 | 1996 | 6 | Wisley | 21.5
1996-06-23 | 1996 | 6 | Wisley | 22.2
1996-06-24 | 1996 | 6 | Wisley | 25.7
1996-06-25 | 1996 | 6 | Wisley | 25.9
1996-06-26 | 1996 | 6 | Wisley | 23.8
1996-06-29 | 1996 | 6 | Wisley | 21.3
1996-06-30 | 1996 | 6 | Wisley | 18.9
1996-07-01 | 1996 | 7 | Wisley | 18.9
1996-07-02 | 1996 | 7 | Wisley | 17.1
1996-07-03 | 1996 | 7 | Wisley | 18.3
1996-07-04 | 1996 | 7 | Wisley | 20.8
1996-07-05 | 1996 | 7 | Wisley | 18
1996-07-06 | 1996 | 7 | Wisley | 20.3
1996-07-07 | 1996 | 7 | Wisley | 19.5
1996-07-08 | 1996 | 7 | Wisley | 19.9
1996-07-09 | 1996 | 7 | Wisley | 25.3
1996-07-10 | 1996 | 7 | Wisley | 23.9
1996-07-11 | 1996 | 7 | Wisley | 23.5
1996-07-12 | 1996 | 7 | Wisley | 23.3
1996-07-13 | 1996 | 7 | Wisley | 24.3
1996-07-14 | 1996 | 7 | Wisley | 25.1
1996-07-15 | 1996 | 7 | Wisley | 21.2
1996-07-16 | 1996 | 7 | Wisley | 23.8
1996-07-17 | 1996 | 7 | Wisley | 26.7
1996-07-18 | 1996 | 7 | Wisley | 26.2
1996-07-19 | 1996 | 7 | Wisley | 27.8
1996-07-20 | 1996 | 7 | Wisley | 29.6
1996-07-21 | 1996 | 7 | Wisley | 30.5
1996-07-22 | 1996 | 7 | Wisley | 28.3
1996-07-24 | 1996 | 7 | Wisley | 25.2
1996-07-25 | 1996 | 7 | Wisley | 29
1996-07-26 | 1996 | 7 | Wisley | 23
1996-07-27 | 1996 | 7 | Wisley | 23.5
1996-07-28 | 1996 | 7 | Wisley | 23.5
1996-07-29 | 1996 | 7 | Wisley | 24.1
1996-07-30 | 1996 | 7 | Wisley | 23.7
1996-07-31 | 1996 | 7 | Wisley | 22.5
1996-08-01 | 1996 | 8 | Wisley | 20.6
1996-08-02 | 1996 | 8 | Wisley | 23.3
1996-08-03 | 1996 | 8 | Wisley | 24.6
1996-08-04 | 1996 | 8 | Wisley | 26.6
1996-08-05 | 1996 | 8 | Wisley | 21.1
1996-08-06 | 1996 | 8 | Wisley | 22.2
1996-08-07 | 1996 | 8 | Wisley | 22.1
1996-08-08 | 1996 | 8 | Wisley | 20.6
1996-08-09 | 1996 | 8 | Wisley | 21.8
1996-08-10 | 1996 | 8 | Wisley | 20.3
1996-08-11 | 1996 | 8 | Wisley | 21.4
1996-08-12 | 1996 | 8 | Wisley | 23.2
1996-08-13 | 1996 | 8 | Wisley | 21.9
1996-08-14 | 1996 | 8 | Wisley | 21.4
1996-08-15 | 1996 | 8 | Wisley | 25.8
1996-08-16 | 1996 | 8 | Wisley | 27.4
1996-08-17 | 1996 | 8 | Wisley | 29.3
1996-08-18 | 1996 | 8 | Wisley | 31.1
1996-08-19 | 1996 | 8 | Wisley | 23.8
1996-08-20 | 1996 | 8 | Wisley | 24.5
1996-08-21 | 1996 | 8 | Wisley | 21.7
1996-08-22 | 1996 | 8 | Wisley | 20.6
1996-08-23 | 1996 | 8 | Wisley | 20.8
1996-08-24 | 1996 | 8 | Wisley | 19.4
1996-08-25 | 1996 | 8 | Wisley | 20.5
1996-08-26 | 1996 | 8 | Wisley | 20.1
1996-08-27 | 1996 | 8 | Wisley | 20.4
1996-08-28 | 1996 | 8 | Wisley | 16.9
1996-08-29 | 1996 | 8 | Wisley | 17.5
1996-08-30 | 1996 | 8 | Wisley | 19.2
1996-08-31 | 1996 | 8 | Wisley | 21.3
1996-09-01 | 1996 | 9 | Wisley | 21.6
1996-09-02 | 1996 | 9 | Wisley | 21.3
1996-09-03 | 1996 | 9 | Wisley | 18.5
1996-09-04 | 1996 | 9 | Wisley | 22.6
1996-09-05 | 1996 | 9 | Wisley | 21.5
1996-09-06 | 1996 | 9 | Wisley | 20.4
1996-09-07 | 1996 | 9 | Wisley | 19.9
1996-09-08 | 1996 | 9 | Wisley | 18.8
1996-09-09 | 1996 | 9 | Wisley | 17.1
1996-09-10 | 1996 | 9 | Wisley | 18.9
1996-09-11 | 1996 | 9 | Wisley | 18
1996-09-12 | 1996 | 9 | Wisley | 17.8
1996-09-13 | 1996 | 9 | Wisley | 19.4
1996-09-14 | 1996 | 9 | Wisley | 22.9
1996-09-15 | 1996 | 9 | Wisley | 21.4
1996-09-16 | 1996 | 9 | Wisley | 19.4
1996-09-17 | 1996 | 9 | Wisley | 16.8
1996-09-18 | 1996 | 9 | Wisley | 14
1996-09-19 | 1996 | 9 | Wisley | 15.5
1996-09-20 | 1996 | 9 | Wisley | 17
1996-09-21 | 1996 | 9 | Wisley | 17.1
1996-09-22 | 1996 | 9 | Wisley | 17.1
1996-09-23 | 1996 | 9 | Wisley | 18.8
1996-09-24 | 1996 | 9 | Wisley | 18.4
1996-09-25 | 1996 | 9 | Wisley | 17.4
1996-09-26 | 1996 | 9 | Wisley | 19.8
1996-09-27 | 1996 | 9 | Wisley | 19.4
1996-09-28 | 1996 | 9 | Wisley | 17.5
1996-09-30 | 1996 | 9 | Wisley | 16.5
1997-05-01 | 1997 | 5 | Wisley | 24.9
1997-05-02 | 1997 | 5 | Wisley | 25.2
1997-05-03 | 1997 | 5 | Wisley | 18.4
1997-05-06 | 1997 | 5 | Wisley | 11.9
1997-05-07 | 1997 | 5 | Wisley | 12.6
1997-05-08 | 1997 | 5 | Wisley | 14
1997-05-09 | 1997 | 5 | Wisley | 14.1
1997-05-10 | 1997 | 5 | Wisley | 14.6
1997-05-11 | 1997 | 5 | Wisley | 15.7
1997-05-12 | 1997 | 5 | Wisley | 17
1997-05-13 | 1997 | 5 | Wisley | 19.6
1997-05-14 | 1997 | 5 | Wisley | 19.9
1997-05-15 | 1997 | 5 | Wisley | 22.1
1997-05-16 | 1997 | 5 | Wisley | 25.8
1997-05-17 | 1997 | 5 | Wisley | 19.8
1997-05-19 | 1997 | 5 | Wisley | 15.8
1997-05-20 | 1997 | 5 | Wisley | 14.1
1997-05-21 | 1997 | 5 | Wisley | 14.2
1997-05-22 | 1997 | 5 | Wisley | 15.4
1997-05-23 | 1997 | 5 | Wisley | 16.1
1997-05-24 | 1997 | 5 | Wisley | 19.3
1997-05-25 | 1997 | 5 | Wisley | 23.2
1997-05-26 | 1997 | 5 | Wisley | 20.1
1997-05-28 | 1997 | 5 | Wisley | 23.5
1997-05-29 | 1997 | 5 | Wisley | 24.8
1997-05-30 | 1997 | 5 | Wisley | 22.6
1997-05-31 | 1997 | 5 | Wisley | 19.6
1997-06-01 | 1997 | 6 | Wisley | 20.8
1997-06-02 | 1997 | 6 | Wisley | 22.1
1997-06-03 | 1997 | 6 | Wisley | 23.4
1997-06-04 | 1997 | 6 | Wisley | 26.4
1997-06-05 | 1997 | 6 | Wisley | 24.6
1997-06-06 | 1997 | 6 | Wisley | 22.8
1997-06-07 | 1997 | 6 | Wisley | 20.7
1997-06-08 | 1997 | 6 | Wisley | 21.5
1997-06-09 | 1997 | 6 | Wisley | 26.1
1997-06-10 | 1997 | 6 | Wisley | 23.5
1997-06-12 | 1997 | 6 | Wisley | 21.5
1997-06-13 | 1997 | 6 | Wisley | 18
1997-06-14 | 1997 | 6 | Wisley | 19.4
1997-06-15 | 1997 | 6 | Wisley | 21.2
1997-06-16 | 1997 | 6 | Wisley | 20.7
1997-06-17 | 1997 | 6 | Wisley | 20.1
1997-06-18 | 1997 | 6 | Wisley | 16
1997-06-19 | 1997 | 6 | Wisley | 15.5
1997-06-20 | 1997 | 6 | Wisley | 16.8
1997-06-21 | 1997 | 6 | Wisley | 17.2
1997-06-22 | 1997 | 6 | Wisley | 20.1
1997-06-23 | 1997 | 6 | Wisley | 18.7
1997-06-24 | 1997 | 6 | Wisley | 16.1
1997-06-25 | 1997 | 6 | Wisley | 16.9
1997-06-27 | 1997 | 6 | Wisley | 17.6
1997-06-28 | 1997 | 6 | Wisley | 18.6
1997-06-29 | 1997 | 6 | Wisley | 16.2
1997-06-30 | 1997 | 6 | Wisley | 17.8
1997-07-01 | 1997 | 7 | Wisley | 17.6
1997-07-02 | 1997 | 7 | Wisley | 16.6
1997-07-03 | 1997 | 7 | Wisley | 18.1
1997-07-04 | 1997 | 7 | Wisley | 22.3
1997-07-05 | 1997 | 7 | Wisley | 24.2
1997-07-06 | 1997 | 7 | Wisley | 26.8
1997-07-07 | 1997 | 7 | Wisley | 27.2
1997-07-08 | 1997 | 7 | Wisley | 25.3
1997-07-10 | 1997 | 7 | Wisley | 23.9
1997-07-11 | 1997 | 7 | Wisley | 23.7
1997-07-12 | 1997 | 7 | Wisley | 23.2
1997-07-13 | 1997 | 7 | Wisley | 23.4
1997-07-14 | 1997 | 7 | Wisley | 24.3
1997-07-15 | 1997 | 7 | Wisley | 21.3
1997-07-16 | 1997 | 7 | Wisley | 21.1
1997-07-17 | 1997 | 7 | Wisley | 19.8
1997-07-18 | 1997 | 7 | Wisley | 24.2
1997-07-19 | 1997 | 7 | Wisley | 24.4
1997-07-20 | 1997 | 7 | Wisley | 25.2
1997-07-21 | 1997 | 7 | Wisley | 26.3
1997-07-22 | 1997 | 7 | Wisley | 27.2
1997-07-23 | 1997 | 7 | Wisley | 23.6
1997-07-24 | 1997 | 7 | Wisley | 23.8
1997-07-25 | 1997 | 7 | Wisley | 20.7
1997-07-26 | 1997 | 7 | Wisley | 24.3
1997-07-27 | 1997 | 7 | Wisley | 25.8
1997-07-28 | 1997 | 7 | Wisley | 26.4
1997-07-29 | 1997 | 7 | Wisley | 23.4
1997-07-31 | 1997 | 7 | Wisley | 24.1
1997-08-01 | 1997 | 8 | Wisley | 23.7
1997-08-02 | 1997 | 8 | Wisley | 21.4
1997-08-03 | 1997 | 8 | Wisley | 21
1997-08-04 | 1997 | 8 | Wisley | 21.4
1997-08-05 | 1997 | 8 | Wisley | 23.8
1997-08-06 | 1997 | 8 | Wisley | 26.2
1997-08-07 | 1997 | 8 | Wisley | 30.2
1997-08-08 | 1997 | 8 | Wisley | 28.4
1997-08-09 | 1997 | 8 | Wisley | 29.9
1997-08-10 | 1997 | 8 | Wisley | 28.3
1997-08-11 | 1997 | 8 | Wisley | 27.5
1997-08-12 | 1997 | 8 | Wisley | 28.5
1997-08-13 | 1997 | 8 | Wisley | 25.7
1997-08-14 | 1997 | 8 | Wisley | 28.3
1997-08-15 | 1997 | 8 | Wisley | 28.9
1997-08-16 | 1997 | 8 | Wisley | 24.2
1997-08-17 | 1997 | 8 | Wisley | 29.2
1997-08-18 | 1997 | 8 | Wisley | 29.5
1997-08-19 | 1997 | 8 | Wisley | 28.6
1997-08-20 | 1997 | 8 | Wisley | 27
1997-08-21 | 1997 | 8 | Wisley | 22.4
1997-08-22 | 1997 | 8 | Wisley | 26.3
1997-08-23 | 1997 | 8 | Wisley | 23.2
1997-08-25 | 1997 | 8 | Wisley | 22.4
1997-08-26 | 1997 | 8 | Wisley | 19.1
1997-08-27 | 1997 | 8 | Wisley | 19.3
1997-08-28 | 1997 | 8 | Wisley | 20.1
1997-08-29 | 1997 | 8 | Wisley | 21.2
1997-08-30 | 1997 | 8 | Wisley | 23.9
1997-08-31 | 1997 | 8 | Wisley | 21.6
1997-09-01 | 1997 | 9 | Wisley | 21
1997-09-02 | 1997 | 9 | Wisley | 18.7
1997-09-03 | 1997 | 9 | Wisley | 21.1
1997-09-04 | 1997 | 9 | Wisley | 20.5
1997-09-05 | 1997 | 9 | Wisley | 20.8
1997-09-06 | 1997 | 9 | Wisley | 22.1
1997-09-07 | 1997 | 9 | Wisley | 21.7
1997-09-08 | 1997 | 9 | Wisley | 21.7
1997-09-09 | 1997 | 9 | Wisley | 21
1997-09-10 | 1997 | 9 | Wisley | 20.4
1997-09-11 | 1997 | 9 | Wisley | 18.1
1997-09-13 | 1997 | 9 | Wisley | 18
1997-09-14 | 1997 | 9 | Wisley | 19.9
1997-09-15 | 1997 | 9 | Wisley | 21.4
1997-09-16 | 1997 | 9 | Wisley | 23.2
1997-09-17 | 1997 | 9 | Wisley | 25.4
1997-09-18 | 1997 | 9 | Wisley | 16.5
1997-09-20 | 1997 | 9 | Wisley | 19.4
1997-09-21 | 1997 | 9 | Wisley | 20.7
1997-09-22 | 1997 | 9 | Wisley | 20.9
1997-09-23 | 1997 | 9 | Wisley | 20.7
1997-09-24 | 1997 | 9 | Wisley | 19.5
1997-09-25 | 1997 | 9 | Wisley | 21.7
1997-09-26 | 1997 | 9 | Wisley | 20
1997-09-27 | 1997 | 9 | Wisley | 19.1
1997-09-28 | 1997 | 9 | Wisley | 23.1
1997-09-29 | 1997 | 9 | Wisley | 22.3
1997-09-30 | 1997 | 9 | Wisley | 25
1998-05-01 | 1998 | 5 | Wisley | 16.4
1998-05-02 | 1998 | 5 | Wisley | 12.2
1998-05-03 | 1998 | 5 | Wisley | 16.6
1998-05-04 | 1998 | 5 | Wisley | 14.2
1998-05-05 | 1998 | 5 | Wisley | 17
1998-05-06 | 1998 | 5 | Wisley | 18.2
1998-05-07 | 1998 | 5 | Wisley | 21.5
1998-05-08 | 1998 | 5 | Wisley | 21.5
1998-05-18 | 1998 | 5 | Wisley | 23.5
1998-05-19 | 1998 | 5 | Wisley | 24.1
1998-05-20 | 1998 | 5 | Wisley | 18.2
1998-05-22 | 1998 | 5 | Wisley | 17.1
1998-05-23 | 1998 | 5 | Wisley | 17.4
1998-05-24 | 1998 | 5 | Wisley | 19.7
1998-05-25 | 1998 | 5 | Wisley | 16.4
1998-05-27 | 1998 | 5 | Wisley | 17.5
1998-05-28 | 1998 | 5 | Wisley | 17.9
1998-05-29 | 1998 | 5 | Wisley | 22
1998-05-30 | 1998 | 5 | Wisley | 18.5
1998-05-31 | 1998 | 5 | Wisley | 20
1998-06-01 | 1998 | 6 | Wisley | 17.9
1998-06-02 | 1998 | 6 | Wisley | 17.5
1998-06-03 | 1998 | 6 | Wisley | 17.4
1998-06-04 | 1998 | 6 | Wisley | 19
1998-06-05 | 1998 | 6 | Wisley | 22
1998-06-06 | 1998 | 6 | Wisley | 19.5
1998-06-07 | 1998 | 6 | Wisley | 16.4
1998-06-08 | 1998 | 6 | Wisley | 18
1998-06-09 | 1998 | 6 | Wisley | 17.5
1998-06-11 | 1998 | 6 | Wisley | 16.4
1998-06-12 | 1998 | 6 | Wisley | 14.6
1998-06-13 | 1998 | 6 | Wisley | 18
1998-06-14 | 1998 | 6 | Wisley | 16.6
1998-06-15 | 1998 | 6 | Wisley | 18.2
1998-06-16 | 1998 | 6 | Wisley | 17.5
1998-06-17 | 1998 | 6 | Wisley | 19
1998-06-18 | 1998 | 6 | Wisley | 24
1998-06-19 | 1998 | 6 | Wisley | 27.7
1998-06-20 | 1998 | 6 | Wisley | 24.7
1998-06-22 | 1998 | 6 | Wisley | 20
1998-06-23 | 1998 | 6 | Wisley | 22.6
1998-06-24 | 1998 | 6 | Wisley | 19.3
1998-06-26 | 1998 | 6 | Wisley | 19.2
1998-06-27 | 1998 | 6 | Wisley | 20.5
1998-06-28 | 1998 | 6 | Wisley | 17.7
1998-06-29 | 1998 | 6 | Wisley | 20.2
1998-06-30 | 1998 | 6 | Wisley | 19.8
1998-07-01 | 1998 | 7 | Wisley | 16.9
1998-07-02 | 1998 | 7 | Wisley | 18.8
1998-07-03 | 1998 | 7 | Wisley | 19.7
1998-07-04 | 1998 | 7 | Wisley | 22.9
1998-07-05 | 1998 | 7 | Wisley | 18
1998-07-06 | 1998 | 7 | Wisley | 19.6
1998-07-07 | 1998 | 7 | Wisley | 22.1
1998-07-08 | 1998 | 7 | Wisley | 21.8
1998-07-09 | 1998 | 7 | Wisley | 19.9
1998-07-11 | 1998 | 7 | Wisley | 17.3
1998-07-12 | 1998 | 7 | Wisley | 18.8
1998-07-13 | 1998 | 7 | Wisley | 19.4
1998-07-14 | 1998 | 7 | Wisley | 18.4
1998-07-15 | 1998 | 7 | Wisley | 21.1
1998-07-16 | 1998 | 7 | Wisley | 21.7
1998-07-17 | 1998 | 7 | Wisley | 20.2
1998-07-18 | 1998 | 7 | Wisley | 21.6
1998-07-19 | 1998 | 7 | Wisley | 24.5
1998-07-20 | 1998 | 7 | Wisley | 21
1998-07-21 | 1998 | 7 | Wisley | 21.5
1998-07-22 | 1998 | 7 | Wisley | 22.1
1998-07-23 | 1998 | 7 | Wisley | 21.4
1998-07-24 | 1998 | 7 | Wisley | 22
1998-07-25 | 1998 | 7 | Wisley | 20.6
1998-07-26 | 1998 | 7 | Wisley | 21.7
1998-07-27 | 1998 | 7 | Wisley | 19.5
1998-07-28 | 1998 | 7 | Wisley | 20.6
1998-07-29 | 1998 | 7 | Wisley | 21.4
1998-07-30 | 1998 | 7 | Wisley | 22
1998-07-31 | 1998 | 7 | Wisley | 22
1998-08-01 | 1998 | 8 | Wisley | 20.5
1998-08-02 | 1998 | 8 | Wisley | 17.1
1998-08-03 | 1998 | 8 | Wisley | 22
1998-08-04 | 1998 | 8 | Wisley | 25.6
1998-08-05 | 1998 | 8 | Wisley | 26.2
1998-08-06 | 1998 | 8 | Wisley | 27.8
1998-08-07 | 1998 | 8 | Wisley | 29.4
1998-08-08 | 1998 | 8 | Wisley | 25
1998-08-09 | 1998 | 8 | Wisley | 30.6
1998-08-10 | 1998 | 8 | Wisley | 29.6
1998-08-11 | 1998 | 8 | Wisley | 22.9
1998-08-12 | 1998 | 8 | Wisley | 22.6
1998-08-13 | 1998 | 8 | Wisley | 26.1
1998-08-14 | 1998 | 8 | Wisley | 22.5
1998-08-15 | 1998 | 8 | Wisley | 24
1998-08-16 | 1998 | 8 | Wisley | 24.6
1998-08-17 | 1998 | 8 | Wisley | 22.5
1998-08-18 | 1998 | 8 | Wisley | 24.6
1998-08-19 | 1998 | 8 | Wisley | 20.8
1998-08-20 | 1998 | 8 | Wisley | 23.2
1998-08-21 | 1998 | 8 | Wisley | 21.4
1998-08-22 | 1998 | 8 | Wisley | 18.6
1998-08-23 | 1998 | 8 | Wisley | 18.4
1998-08-24 | 1998 | 8 | Wisley | 21.9
1998-08-25 | 1998 | 8 | Wisley | 18.5
1998-08-26 | 1998 | 8 | Wisley | 20
1998-08-27 | 1998 | 8 | Wisley | 19.5
1998-08-28 | 1998 | 8 | Wisley | 22.3
1998-08-29 | 1998 | 8 | Wisley | 22.7
1998-08-30 | 1998 | 8 | Wisley | 22.4
1998-08-31 | 1998 | 8 | Wisley | 24.9
1998-09-01 | 1998 | 9 | Wisley | 23
1998-09-02 | 1998 | 9 | Wisley | 21
1998-09-03 | 1998 | 9 | Wisley | 19
1998-09-04 | 1998 | 9 | Wisley | 21
1998-09-05 | 1998 | 9 | Wisley | 20.3
1998-09-06 | 1998 | 9 | Wisley | 22.2
1998-09-07 | 1998 | 9 | Wisley | 21.8
1998-09-08 | 1998 | 9 | Wisley | 20.2
1998-09-09 | 1998 | 9 | Wisley | 19.9
1998-09-12 | 1998 | 9 | Wisley | 16
1998-09-13 | 1998 | 9 | Wisley | 16.6
1998-09-14 | 1998 | 9 | Wisley | 17.5
1998-09-15 | 1998 | 9 | Wisley | 17.7
1998-09-16 | 1998 | 9 | Wisley | 18.8
1998-09-17 | 1998 | 9 | Wisley | 19.7
1998-09-18 | 1998 | 9 | Wisley | 23
1998-09-19 | 1998 | 9 | Wisley | 21.3
1998-09-20 | 1998 | 9 | Wisley | 21.1
1998-09-21 | 1998 | 9 | Wisley | 18.6
1998-09-22 | 1998 | 9 | Wisley | 22.3
1998-09-23 | 1998 | 9 | Wisley | 22.4
1998-09-24 | 1998 | 9 | Wisley | 22.2
1998-09-25 | 1998 | 9 | Wisley | 19.4
1998-09-26 | 1998 | 9 | Wisley | 20.5
1998-09-27 | 1998 | 9 | Wisley | 18.1
1998-09-29 | 1998 | 9 | Wisley | 18.1
1998-09-30 | 1998 | 9 | Wisley | 16.9
1999-05-01 | 1999 | 5 | Wisley | 21.2
1999-05-02 | 1999 | 5 | Wisley | 22.2
1999-05-03 | 1999 | 5 | Wisley | 18.2
1999-05-04 | 1999 | 5 | Wisley | 17.2
1999-05-05 | 1999 | 5 | Wisley | 17.4
1999-05-06 | 1999 | 5 | Wisley | 16.3
1999-05-07 | 1999 | 5 | Wisley | 15.8
1999-05-08 | 1999 | 5 | Wisley | 19.6
1999-05-09 | 1999 | 5 | Wisley | 17.3
1999-05-10 | 1999 | 5 | Wisley | 17.5
1999-05-11 | 1999 | 5 | Wisley | 16.3
1999-05-12 | 1999 | 5 | Wisley | 17
1999-05-13 | 1999 | 5 | Wisley | 17.8
1999-05-14 | 1999 | 5 | Wisley | 15.2
1999-05-15 | 1999 | 5 | Wisley | 16.3
1999-05-16 | 1999 | 5 | Wisley | 15.5
1999-05-17 | 1999 | 5 | Wisley | 16.9
1999-05-18 | 1999 | 5 | Wisley | 23.1
1999-05-19 | 1999 | 5 | Wisley | 21.9
1999-05-20 | 1999 | 5 | Wisley | 18
1999-05-21 | 1999 | 5 | Wisley | 16.5
1999-05-22 | 1999 | 5 | Wisley | 19.4
1999-05-23 | 1999 | 5 | Wisley | 18.4
1999-05-24 | 1999 | 5 | Wisley | 17.6
1999-05-25 | 1999 | 5 | Wisley | 22
1999-05-26 | 1999 | 5 | Wisley | 25.9
1999-05-27 | 1999 | 5 | Wisley | 21.5
1999-05-28 | 1999 | 5 | Wisley | 24.3
1999-05-31 | 1999 | 5 | Wisley | 22.5
1999-06-01 | 1999 | 6 | Wisley | 20.4
1999-06-02 | 1999 | 6 | Wisley | 17.8
1999-06-03 | 1999 | 6 | Wisley | 17.5
1999-06-04 | 1999 | 6 | Wisley | 16.4
1999-06-05 | 1999 | 6 | Wisley | 18.8
1999-06-06 | 1999 | 6 | Wisley | 17.2
1999-06-07 | 1999 | 6 | Wisley | 17.2
1999-06-08 | 1999 | 6 | Wisley | 18.8
1999-06-09 | 1999 | 6 | Wisley | 17.4
1999-06-10 | 1999 | 6 | Wisley | 17.6
1999-06-11 | 1999 | 6 | Wisley | 16
1999-06-12 | 1999 | 6 | Wisley | 20.6
1999-06-13 | 1999 | 6 | Wisley | 23.4
1999-06-14 | 1999 | 6 | Wisley | 24.3
1999-06-15 | 1999 | 6 | Wisley | 25
1999-06-16 | 1999 | 6 | Wisley | 21.8
1999-06-17 | 1999 | 6 | Wisley | 23.1
1999-06-18 | 1999 | 6 | Wisley | 21.9
1999-06-19 | 1999 | 6 | Wisley | 19.8
1999-06-21 | 1999 | 6 | Wisley | 19
1999-06-22 | 1999 | 6 | Wisley | 21.4
1999-06-23 | 1999 | 6 | Wisley | 22.5
1999-06-24 | 1999 | 6 | Wisley | 22.5
1999-06-25 | 1999 | 6 | Wisley | 26.2
1999-06-26 | 1999 | 6 | Wisley | 18.3
1999-06-28 | 1999 | 6 | Wisley | 18.1
1999-06-29 | 1999 | 6 | Wisley | 20.5
1999-06-30 | 1999 | 6 | Wisley | 21.6
1999-07-01 | 1999 | 7 | Wisley | 25
1999-07-02 | 1999 | 7 | Wisley | 22.9
1999-07-03 | 1999 | 7 | Wisley | 21.6
1999-07-04 | 1999 | 7 | Wisley | 22.4
1999-07-05 | 1999 | 7 | Wisley | 24.9
1999-07-06 | 1999 | 7 | Wisley | 24.7
1999-07-07 | 1999 | 7 | Wisley | 27.4
1999-07-08 | 1999 | 7 | Wisley | 26
1999-07-09 | 1999 | 7 | Wisley | 27
1999-07-10 | 1999 | 7 | Wisley | 27.5
1999-07-11 | 1999 | 7 | Wisley | 25.5
1999-07-12 | 1999 | 7 | Wisley | 26
1999-07-13 | 1999 | 7 | Wisley | 19.1
1999-07-14 | 1999 | 7 | Wisley | 21
1999-07-15 | 1999 | 7 | Wisley | 21.5
1999-07-16 | 1999 | 7 | Wisley | 26.1
1999-07-17 | 1999 | 7 | Wisley | 27.9
1999-07-18 | 1999 | 7 | Wisley | 24.8
1999-07-19 | 1999 | 7 | Wisley | 23.4
1999-07-20 | 1999 | 7 | Wisley | 20.6
1999-07-22 | 1999 | 7 | Wisley | 25.3
1999-07-23 | 1999 | 7 | Wisley | 28.6
1999-07-24 | 1999 | 7 | Wisley | 29.5
1999-07-25 | 1999 | 7 | Wisley | 23.2
1999-07-26 | 1999 | 7 | Wisley | 22.5
1999-07-27 | 1999 | 7 | Wisley | 24.8
1999-07-28 | 1999 | 7 | Wisley | 28.6
1999-07-29 | 1999 | 7 | Wisley | 29.8
1999-07-30 | 1999 | 7 | Wisley | 31.4
1999-07-31 | 1999 | 7 | Wisley | 31.7
1999-08-01 | 1999 | 8 | Wisley | 30.9
1999-08-03 | 1999 | 8 | Wisley | 26.6
1999-08-04 | 1999 | 8 | Wisley | 25
1999-08-05 | 1999 | 8 | Wisley | 26.1
1999-08-06 | 1999 | 8 | Wisley | 24.6
1999-08-07 | 1999 | 8 | Wisley | 22.6
1999-08-08 | 1999 | 8 | Wisley | 21.3
1999-08-10 | 1999 | 8 | Wisley | 20.2
1999-08-11 | 1999 | 8 | Wisley | 21.5
1999-08-12 | 1999 | 8 | Wisley | 22
1999-08-13 | 1999 | 8 | Wisley | 21.1
1999-08-14 | 1999 | 8 | Wisley | 20.1
1999-08-15 | 1999 | 8 | Wisley | 19.5
1999-08-16 | 1999 | 8 | Wisley | 17.2
1999-08-17 | 1999 | 8 | Wisley | 19.5
1999-08-18 | 1999 | 8 | Wisley | 20.7
1999-08-19 | 1999 | 8 | Wisley | 21.3
1999-08-20 | 1999 | 8 | Wisley | 19.5
1999-08-21 | 1999 | 8 | Wisley | 18.6
1999-08-22 | 1999 | 8 | Wisley | 20.1
1999-08-23 | 1999 | 8 | Wisley | 20.6
1999-08-24 | 1999 | 8 | Wisley | 24.2
1999-08-25 | 1999 | 8 | Wisley | 22.8
1999-08-26 | 1999 | 8 | Wisley | 21.6
1999-08-27 | 1999 | 8 | Wisley | 24.8
1999-08-28 | 1999 | 8 | Wisley | 23.3
1999-08-29 | 1999 | 8 | Wisley | 22.8
1999-08-30 | 1999 | 8 | Wisley | 23
1999-08-31 | 1999 | 8 | Wisley | 25
1999-09-01 | 1999 | 9 | Wisley | 26
1999-09-02 | 1999 | 9 | Wisley | 26.9
1999-09-03 | 1999 | 9 | Wisley | 26.9
1999-09-04 | 1999 | 9 | Wisley | 27.7
1999-09-05 | 1999 | 9 | Wisley | 26.6
1999-09-06 | 1999 | 9 | Wisley | 23
1999-09-07 | 1999 | 9 | Wisley | 23
1999-09-08 | 1999 | 9 | Wisley | 21.4
1999-09-09 | 1999 | 9 | Wisley | 25.3
1999-09-10 | 1999 | 9 | Wisley | 28.4
1999-09-11 | 1999 | 9 | Wisley | 21.3
1999-09-12 | 1999 | 9 | Wisley | 19.3
1999-09-14 | 1999 | 9 | Wisley | 17.6
1999-09-15 | 1999 | 9 | Wisley | 18.2
1999-09-16 | 1999 | 9 | Wisley | 19.4
1999-09-17 | 1999 | 9 | Wisley | 18.8
1999-09-18 | 1999 | 9 | Wisley | 18.4
1999-09-19 | 1999 | 9 | Wisley | 16.8
1999-09-20 | 1999 | 9 | Wisley | 20.2
1999-09-21 | 1999 | 9 | Wisley | 20.2
1999-09-22 | 1999 | 9 | Wisley | 19.6
1999-09-23 | 1999 | 9 | Wisley | 19.3
1999-09-24 | 1999 | 9 | Wisley | 19.7
1999-09-25 | 1999 | 9 | Wisley | 17.3
1999-09-26 | 1999 | 9 | Wisley | 18.2
1999-09-27 | 1999 | 9 | Wisley | 18.2
1999-09-28 | 1999 | 9 | Wisley | 17.8
1999-09-29 | 1999 | 9 | Wisley | 18
1999-09-30 | 1999 | 9 | Wisley | 15.9
2000-05-01 | 2000 | 5 | Wisley | 15.5
2000-05-03 | 2000 | 5 | Wisley | 13.2
2000-05-04 | 2000 | 5 | Wisley | 21.6
2000-05-05 | 2000 | 5 | Wisley | 25.2
2000-05-06 | 2000 | 5 | Wisley | 24.3
2000-05-07 | 2000 | 5 | Wisley | 19.8
2000-05-08 | 2000 | 5 | Wisley | 24.4
2000-05-09 | 2000 | 5 | Wisley | 18.2
2000-05-11 | 2000 | 5 | Wisley | 19.6
2000-05-12 | 2000 | 5 | Wisley | 24.5
2000-05-13 | 2000 | 5 | Wisley | 24.5
2000-05-14 | 2000 | 5 | Wisley | 25.5
2000-05-15 | 2000 | 5 | Wisley | 20.7
2000-05-18 | 2000 | 5 | Wisley | 14.9
2000-05-19 | 2000 | 5 | Wisley | 16
2000-05-20 | 2000 | 5 | Wisley | 16.3
2000-05-21 | 2000 | 5 | Wisley | 18.6
2000-05-22 | 2000 | 5 | Wisley | 14.5
2000-05-23 | 2000 | 5 | Wisley | 16.4
2000-05-24 | 2000 | 5 | Wisley | 15.9
2000-05-25 | 2000 | 5 | Wisley | 13
2000-05-26 | 2000 | 5 | Wisley | 14.2
2000-05-27 | 2000 | 5 | Wisley | 15.5
2000-05-28 | 2000 | 5 | Wisley | 17.1
2000-05-29 | 2000 | 5 | Wisley | 15.4
2000-05-30 | 2000 | 5 | Wisley | 18.5
2000-05-31 | 2000 | 5 | Wisley | 15.7
2000-06-01 | 2000 | 6 | Wisley | 18.5
2000-06-02 | 2000 | 6 | Wisley | 23
2000-06-03 | 2000 | 6 | Wisley | 19.1
2000-06-05 | 2000 | 6 | Wisley | 18.5
2000-06-06 | 2000 | 6 | Wisley | 20.1
2000-06-07 | 2000 | 6 | Wisley | 21.5
2000-06-08 | 2000 | 6 | Wisley | 17.8
2000-06-09 | 2000 | 6 | Wisley | 19
2000-06-10 | 2000 | 6 | Wisley | 18.8
2000-06-11 | 2000 | 6 | Wisley | 23.5
2000-06-12 | 2000 | 6 | Wisley | 22.5
2000-06-13 | 2000 | 6 | Wisley | 20.6
2000-06-14 | 2000 | 6 | Wisley | 20.2
2000-06-15 | 2000 | 6 | Wisley | 22
2000-06-16 | 2000 | 6 | Wisley | 24.8
2000-06-17 | 2000 | 6 | Wisley | 29.4
2000-06-18 | 2000 | 6 | Wisley | 29.6
2000-06-22 | 2000 | 6 | Wisley | 18.6
2000-06-23 | 2000 | 6 | Wisley | 15.9
2000-06-24 | 2000 | 6 | Wisley | 18.2
2000-06-25 | 2000 | 6 | Wisley | 19.5
2000-06-26 | 2000 | 6 | Wisley | 22.1
2000-06-27 | 2000 | 6 | Wisley | 21.9
2000-06-28 | 2000 | 6 | Wisley | 22.1
2000-06-29 | 2000 | 6 | Wisley | 21.6
2000-06-30 | 2000 | 6 | Wisley | 21.2
2000-07-01 | 2000 | 7 | Wisley | 22.4
2000-07-02 | 2000 | 7 | Wisley | 22.9
2000-07-03 | 2000 | 7 | Wisley | 19.8
2000-07-04 | 2000 | 7 | Wisley | 17.2
2000-07-05 | 2000 | 7 | Wisley | 22.3
2000-07-06 | 2000 | 7 | Wisley | 17.8
2000-07-07 | 2000 | 7 | Wisley | 17.8
2000-07-08 | 2000 | 7 | Wisley | 18.2
2000-07-09 | 2000 | 7 | Wisley | 16.6
2000-07-10 | 2000 | 7 | Wisley | 16.9
2000-07-11 | 2000 | 7 | Wisley | 19.3
2000-07-12 | 2000 | 7 | Wisley | 20.9
2000-07-13 | 2000 | 7 | Wisley | 17.4
2000-07-14 | 2000 | 7 | Wisley | 18.4
2000-07-15 | 2000 | 7 | Wisley | 18.6
2000-07-16 | 2000 | 7 | Wisley | 22
2000-07-17 | 2000 | 7 | Wisley | 24.2
2000-07-18 | 2000 | 7 | Wisley | 25.4
2000-07-19 | 2000 | 7 | Wisley | 25.2
2000-07-20 | 2000 | 7 | Wisley | 26.2
2000-07-21 | 2000 | 7 | Wisley | 21.9
2000-07-22 | 2000 | 7 | Wisley | 19.1
2000-07-23 | 2000 | 7 | Wisley | 16.8
2000-07-24 | 2000 | 7 | Wisley | 19.5
2000-07-25 | 2000 | 7 | Wisley | 23
2000-07-26 | 2000 | 7 | Wisley | 23.7
2000-07-27 | 2000 | 7 | Wisley | 21.2
2000-07-28 | 2000 | 7 | Wisley | 25
2000-07-29 | 2000 | 7 | Wisley | 24.2
2000-07-30 | 2000 | 7 | Wisley | 24.1
2000-07-31 | 2000 | 7 | Wisley | 24.3
2000-08-01 | 2000 | 8 | Wisley | 21.8
2000-08-02 | 2000 | 8 | Wisley | 19.5
2000-08-03 | 2000 | 8 | Wisley | 22.4
2000-08-04 | 2000 | 8 | Wisley | 23.9
2000-08-05 | 2000 | 8 | Wisley | 24.7
2000-08-06 | 2000 | 8 | Wisley | 23.9
2000-08-07 | 2000 | 8 | Wisley | 23.9
2000-08-08 | 2000 | 8 | Wisley | 22.8
2000-08-09 | 2000 | 8 | Wisley | 25.2
2000-08-10 | 2000 | 8 | Wisley | 25.3
2000-08-11 | 2000 | 8 | Wisley | 28.8
2000-08-12 | 2000 | 8 | Wisley | 23
2000-08-13 | 2000 | 8 | Wisley | 22.8
2000-08-14 | 2000 | 8 | Wisley | 23.3
2000-08-15 | 2000 | 8 | Wisley | 22.7
2000-08-16 | 2000 | 8 | Wisley | 22
2000-08-17 | 2000 | 8 | Wisley | 19.7
2000-08-18 | 2000 | 8 | Wisley | 22.8
2000-08-19 | 2000 | 8 | Wisley | 21.2
2000-08-20 | 2000 | 8 | Wisley | 21.3
2000-08-21 | 2000 | 8 | Wisley | 22
2000-08-22 | 2000 | 8 | Wisley | 23.9
2000-08-23 | 2000 | 8 | Wisley | 27.5
2000-08-24 | 2000 | 8 | Wisley | 28.2
2000-08-26 | 2000 | 8 | Wisley | 21.8
2000-08-27 | 2000 | 8 | Wisley | 21.6
2000-08-28 | 2000 | 8 | Wisley | 22.2
2000-08-29 | 2000 | 8 | Wisley | 22
2000-08-30 | 2000 | 8 | Wisley | 21.7
2000-08-31 | 2000 | 8 | Wisley | 18
2000-09-01 | 2000 | 9 | Wisley | 20.5
2000-09-02 | 2000 | 9 | Wisley | 18.1
2000-09-03 | 2000 | 9 | Wisley | 20
2000-09-04 | 2000 | 9 | Wisley | 20.5
2000-09-05 | 2000 | 9 | Wisley | 19.5
2000-09-06 | 2000 | 9 | Wisley | 19.8
2000-09-07 | 2000 | 9 | Wisley | 19.8
2000-09-08 | 2000 | 9 | Wisley | 22
2000-09-09 | 2000 | 9 | Wisley | 25.7
2000-09-10 | 2000 | 9 | Wisley | 26.6
2000-09-11 | 2000 | 9 | Wisley | 22.8
2000-09-12 | 2000 | 9 | Wisley | 19.9
2000-09-13 | 2000 | 9 | Wisley | 20.9
2000-09-14 | 2000 | 9 | Wisley | 17.7
2000-09-15 | 2000 | 9 | Wisley | 17.1
2000-09-16 | 2000 | 9 | Wisley | 21
2000-09-18 | 2000 | 9 | Wisley | 15.1
2000-09-19 | 2000 | 9 | Wisley | 16.6
2000-09-20 | 2000 | 9 | Wisley | 18
2000-09-21 | 2000 | 9 | Wisley | 21.8
2000-09-22 | 2000 | 9 | Wisley | 23.5
2000-09-23 | 2000 | 9 | Wisley | 21.2
2000-09-24 | 2000 | 9 | Wisley | 18.3
2000-09-25 | 2000 | 9 | Wisley | 20.2
2000-09-26 | 2000 | 9 | Wisley | 17.5
2000-09-27 | 2000 | 9 | Wisley | 18.3
2000-09-28 | 2000 | 9 | Wisley | 18.2
2000-09-29 | 2000 | 9 | Wisley | 18.4
2000-09-30 | 2000 | 9 | Wisley | 18.5
2001-05-01 | 2001 | 5 | Wisley | 15.6
2001-05-02 | 2001 | 5 | Wisley | 17.9
2001-05-03 | 2001 | 5 | Wisley | 14
2001-05-04 | 2001 | 5 | Wisley | 13.9
2001-05-05 | 2001 | 5 | Wisley | 13.1
2001-05-06 | 2001 | 5 | Wisley | 16.2
2001-05-07 | 2001 | 5 | Wisley | 17.8
2001-05-08 | 2001 | 5 | Wisley | 17.2
2001-05-09 | 2001 | 5 | Wisley | 23.7
2001-05-10 | 2001 | 5 | Wisley | 26.5
2001-05-11 | 2001 | 5 | Wisley | 25.4
2001-05-12 | 2001 | 5 | Wisley | 26.2
2001-05-14 | 2001 | 5 | Wisley | 19.2
2001-05-15 | 2001 | 5 | Wisley | 15.8
2001-05-17 | 2001 | 5 | Wisley | 16.6
2001-05-18 | 2001 | 5 | Wisley | 17.4
2001-05-19 | 2001 | 5 | Wisley | 19.4
2001-05-20 | 2001 | 5 | Wisley | 18.5
2001-05-21 | 2001 | 5 | Wisley | 19.9
2001-05-22 | 2001 | 5 | Wisley | 22.9
2001-05-23 | 2001 | 5 | Wisley | 23.6
2001-05-24 | 2001 | 5 | Wisley | 21.6
2001-05-25 | 2001 | 5 | Wisley | 24
2001-05-26 | 2001 | 5 | Wisley | 20.8
2001-05-27 | 2001 | 5 | Wisley | 23.6
2001-05-28 | 2001 | 5 | Wisley | 23
2001-05-29 | 2001 | 5 | Wisley | 23.5
2001-05-30 | 2001 | 5 | Wisley | 18.9
2001-05-31 | 2001 | 5 | Wisley | 19
2001-06-01 | 2001 | 6 | Wisley | 17.4
2001-06-02 | 2001 | 6 | Wisley | 16.9
2001-06-03 | 2001 | 6 | Wisley | 20.5
2001-06-04 | 2001 | 6 | Wisley | 21.3
2001-06-05 | 2001 | 6 | Wisley | 19
2001-06-06 | 2001 | 6 | Wisley | 17.4
2001-06-07 | 2001 | 6 | Wisley | 16.9
2001-06-08 | 2001 | 6 | Wisley | 17.6
2001-06-09 | 2001 | 6 | Wisley | 15.3
2001-06-10 | 2001 | 6 | Wisley | 18.6
2001-06-11 | 2001 | 6 | Wisley | 19.3
2001-06-12 | 2001 | 6 | Wisley | 21.7
2001-06-13 | 2001 | 6 | Wisley | 20.2
2001-06-14 | 2001 | 6 | Wisley | 19.9
2001-06-15 | 2001 | 6 | Wisley | 17.6
2001-06-16 | 2001 | 6 | Wisley | 15.8
2001-06-17 | 2001 | 6 | Wisley | 18.6
2001-06-18 | 2001 | 6 | Wisley | 21.2
2001-06-19 | 2001 | 6 | Wisley | 25
2001-06-20 | 2001 | 6 | Wisley | 22
2001-06-21 | 2001 | 6 | Wisley | 22.7
2001-06-22 | 2001 | 6 | Wisley | 24.1
2001-06-23 | 2001 | 6 | Wisley | 27.9
2001-06-24 | 2001 | 6 | Wisley | 29.3
2001-06-25 | 2001 | 6 | Wisley | 32
2001-06-26 | 2001 | 6 | Wisley | 24.7
2001-06-27 | 2001 | 6 | Wisley | 22.4
2001-06-28 | 2001 | 6 | Wisley | 20.3
2001-06-29 | 2001 | 6 | Wisley | 23.3
2001-06-30 | 2001 | 6 | Wisley | 25.7
2001-07-01 | 2001 | 7 | Wisley | 27.8
2001-07-02 | 2001 | 7 | Wisley | 28.9
2001-07-03 | 2001 | 7 | Wisley | 29.5
2001-07-04 | 2001 | 7 | Wisley | 28.6
2001-07-05 | 2001 | 7 | Wisley | 25.8
2001-07-07 | 2001 | 7 | Wisley | 20.7
2001-07-08 | 2001 | 7 | Wisley | 20.8
2001-07-09 | 2001 | 7 | Wisley | 19.1
2001-07-10 | 2001 | 7 | Wisley | 20.3
2001-07-11 | 2001 | 7 | Wisley | 19.8
2001-07-12 | 2001 | 7 | Wisley | 20
2001-07-13 | 2001 | 7 | Wisley | 19.2
2001-07-14 | 2001 | 7 | Wisley | 19.6
2001-07-15 | 2001 | 7 | Wisley | 22.1
2001-07-16 | 2001 | 7 | Wisley | 20.7
2001-07-17 | 2001 | 7 | Wisley | 21
2001-07-18 | 2001 | 7 | Wisley | 18.1
2001-07-19 | 2001 | 7 | Wisley | 20.9
2001-07-20 | 2001 | 7 | Wisley | 22.1
2001-07-21 | 2001 | 7 | Wisley | 21.1
2001-07-22 | 2001 | 7 | Wisley | 24.9
2001-07-23 | 2001 | 7 | Wisley | 23.6
2001-07-24 | 2001 | 7 | Wisley | 25.4
2001-07-25 | 2001 | 7 | Wisley | 27.9
2001-07-26 | 2001 | 7 | Wisley | 29.6
2001-07-27 | 2001 | 7 | Wisley | 30.8
2001-07-28 | 2001 | 7 | Wisley | 30.8
2001-07-29 | 2001 | 7 | Wisley | 30.8
2001-07-30 | 2001 | 7 | Wisley | 27.2
2001-07-31 | 2001 | 7 | Wisley | 26.4
2001-08-02 | 2001 | 8 | Wisley | 23
2001-08-03 | 2001 | 8 | Wisley | 21.3
2001-08-04 | 2001 | 8 | Wisley | 22.5
2001-08-05 | 2001 | 8 | Wisley | 22.7
2001-08-06 | 2001 | 8 | Wisley | 20.1
2001-08-07 | 2001 | 8 | Wisley | 21
2001-08-08 | 2001 | 8 | Wisley | 19.2
2001-08-09 | 2001 | 8 | Wisley | 20.6
2001-08-10 | 2001 | 8 | Wisley | 21.3
2001-08-11 | 2001 | 8 | Wisley | 22.4
2001-08-12 | 2001 | 8 | Wisley | 27.6
2001-08-13 | 2001 | 8 | Wisley | 26.5
2001-08-14 | 2001 | 8 | Wisley | 29.4
2001-08-16 | 2001 | 8 | Wisley | 22.5
2001-08-17 | 2001 | 8 | Wisley | 23.7
2001-08-18 | 2001 | 8 | Wisley | 21.9
2001-08-19 | 2001 | 8 | Wisley | 22.4
2001-08-20 | 2001 | 8 | Wisley | 23.5
2001-08-21 | 2001 | 8 | Wisley | 25.5
2001-08-22 | 2001 | 8 | Wisley | 24.2
2001-08-23 | 2001 | 8 | Wisley | 27.9
2001-08-24 | 2001 | 8 | Wisley | 30.7
2001-08-26 | 2001 | 8 | Wisley | 22.4
2001-08-27 | 2001 | 8 | Wisley | 22.3
2001-08-28 | 2001 | 8 | Wisley | 22.7
2001-08-29 | 2001 | 8 | Wisley | 20
2001-08-30 | 2001 | 8 | Wisley | 18.1
2001-08-31 | 2001 | 8 | Wisley | 20.1
2001-09-01 | 2001 | 9 | Wisley | 22.1
2001-09-02 | 2001 | 9 | Wisley | 19.4
2001-09-03 | 2001 | 9 | Wisley | 17.6
2001-09-04 | 2001 | 9 | Wisley | 19.5
2001-09-05 | 2001 | 9 | Wisley | 19.2
2001-09-06 | 2001 | 9 | Wisley | 20.3
2001-09-07 | 2001 | 9 | Wisley | 18
2001-09-08 | 2001 | 9 | Wisley | 16.6
2001-09-09 | 2001 | 9 | Wisley | 17.2
2001-09-10 | 2001 | 9 | Wisley | 17.6
2001-09-11 | 2001 | 9 | Wisley | 18.3
2001-09-12 | 2001 | 9 | Wisley | 15.7
2001-09-13 | 2001 | 9 | Wisley | 18.9
2001-09-14 | 2001 | 9 | Wisley | 17.8
2001-09-15 | 2001 | 9 | Wisley | 17.1
2001-09-16 | 2001 | 9 | Wisley | 13.8
2001-09-17 | 2001 | 9 | Wisley | 15.1
2001-09-18 | 2001 | 9 | Wisley | 14.6
2001-09-19 | 2001 | 9 | Wisley | 18.7
2001-09-20 | 2001 | 9 | Wisley | 16.1
2001-09-21 | 2001 | 9 | Wisley | 18.3
2001-09-22 | 2001 | 9 | Wisley | 15.3
2001-09-23 | 2001 | 9 | Wisley | 17.1
2001-09-24 | 2001 | 9 | Wisley | 17.6
2001-09-25 | 2001 | 9 | Wisley | 17.2
2001-09-26 | 2001 | 9 | Wisley | 20
2001-09-27 | 2001 | 9 | Wisley | 22.9
2001-09-28 | 2001 | 9 | Wisley | 19.6
2001-09-30 | 2001 | 9 | Wisley | 18.8
2002-05-01 | 2002 | 5 | Wisley | 16.1
2002-05-02 | 2002 | 5 | Wisley | 17
2002-05-03 | 2002 | 5 | Wisley | 14.8
2002-05-04 | 2002 | 5 | Wisley | 12.4
2002-05-05 | 2002 | 5 | Wisley | 16.2
2002-05-06 | 2002 | 5 | Wisley | 16.8
2002-05-07 | 2002 | 5 | Wisley | 17.3
2002-05-08 | 2002 | 5 | Wisley | 13.5
2002-05-09 | 2002 | 5 | Wisley | 16.1
2002-05-10 | 2002 | 5 | Wisley | 18.3
2002-05-11 | 2002 | 5 | Wisley | 16.8
2002-05-12 | 2002 | 5 | Wisley | 14.7
2002-05-13 | 2002 | 5 | Wisley | 16.2
2002-05-14 | 2002 | 5 | Wisley | 19.5
2002-05-15 | 2002 | 5 | Wisley | 25.3
2002-05-16 | 2002 | 5 | Wisley | 25.6
2002-05-18 | 2002 | 5 | Wisley | 19
2002-05-19 | 2002 | 5 | Wisley | 19
2002-05-20 | 2002 | 5 | Wisley | 17.6
2002-05-21 | 2002 | 5 | Wisley | 17.5
2002-05-22 | 2002 | 5 | Wisley | 17.7
2002-05-23 | 2002 | 5 | Wisley | 17.5
2002-05-24 | 2002 | 5 | Wisley | 16.4
2002-05-26 | 2002 | 5 | Wisley | 17.2
2002-05-27 | 2002 | 5 | Wisley | 15.7
2002-05-28 | 2002 | 5 | Wisley | 16.4
2002-05-29 | 2002 | 5 | Wisley | 17.9
2002-05-30 | 2002 | 5 | Wisley | 19.9
2002-05-31 | 2002 | 5 | Wisley | 22.2
2002-06-01 | 2002 | 6 | Wisley | 25.9
2002-06-02 | 2002 | 6 | Wisley | 17.6
2002-06-03 | 2002 | 6 | Wisley | 16.5
2002-06-04 | 2002 | 6 | Wisley | 15.6
2002-06-05 | 2002 | 6 | Wisley | 18.9
2002-06-07 | 2002 | 6 | Wisley | 18.9
2002-06-08 | 2002 | 6 | Wisley | 15.4
2002-06-09 | 2002 | 6 | Wisley | 16.7
2002-06-10 | 2002 | 6 | Wisley | 18
2002-06-11 | 2002 | 6 | Wisley | 17.5
2002-06-12 | 2002 | 6 | Wisley | 19.5
2002-06-13 | 2002 | 6 | Wisley | 21.6
2002-06-14 | 2002 | 6 | Wisley | 20.3
2002-06-15 | 2002 | 6 | Wisley | 22.5
2002-06-16 | 2002 | 6 | Wisley | 26.4
2002-06-17 | 2002 | 6 | Wisley | 22.3
2002-06-18 | 2002 | 6 | Wisley | 22
2002-06-19 | 2002 | 6 | Wisley | 22.1
2002-06-20 | 2002 | 6 | Wisley | 20.8
2002-06-21 | 2002 | 6 | Wisley | 19.6
2002-06-22 | 2002 | 6 | Wisley | 20.3
2002-06-23 | 2002 | 6 | Wisley | 21.9
2002-06-24 | 2002 | 6 | Wisley | 21.3
2002-06-25 | 2002 | 6 | Wisley | 23.7
2002-06-26 | 2002 | 6 | Wisley | 19.2
2002-06-27 | 2002 | 6 | Wisley | 19.3
2002-06-28 | 2002 | 6 | Wisley | 19.8
2002-06-29 | 2002 | 6 | Wisley | 19.7
2002-06-30 | 2002 | 6 | Wisley | 17.9
2002-07-01 | 2002 | 7 | Wisley | 17.3
2002-07-02 | 2002 | 7 | Wisley | 18
2002-07-03 | 2002 | 7 | Wisley | 20.5
2002-07-04 | 2002 | 7 | Wisley | 19.9
2002-07-05 | 2002 | 7 | Wisley | 20.5
2002-07-06 | 2002 | 7 | Wisley | 19.4
2002-07-07 | 2002 | 7 | Wisley | 19.2
2002-07-08 | 2002 | 7 | Wisley | 20.3
2002-07-09 | 2002 | 7 | Wisley | 19.3
2002-07-10 | 2002 | 7 | Wisley | 19.8
2002-07-11 | 2002 | 7 | Wisley | 18
2002-07-12 | 2002 | 7 | Wisley | 22.7
2002-07-13 | 2002 | 7 | Wisley | 25
2002-07-14 | 2002 | 7 | Wisley | 25.9
2002-07-15 | 2002 | 7 | Wisley | 25.8
2002-07-16 | 2002 | 7 | Wisley | 23.1
2002-07-17 | 2002 | 7 | Wisley | 23.4
2002-07-18 | 2002 | 7 | Wisley | 23.4
2002-07-19 | 2002 | 7 | Wisley | 22.7
2002-07-20 | 2002 | 7 | Wisley | 20.4
2002-07-21 | 2002 | 7 | Wisley | 22.1
2002-07-22 | 2002 | 7 | Wisley | 20.4
2002-07-23 | 2002 | 7 | Wisley | 21.2
2002-07-24 | 2002 | 7 | Wisley | 21.3
2002-07-25 | 2002 | 7 | Wisley | 27
2002-07-26 | 2002 | 7 | Wisley | 24.2
2002-07-27 | 2002 | 7 | Wisley | 29.8
2002-07-28 | 2002 | 7 | Wisley | 31.8
2002-07-29 | 2002 | 7 | Wisley | 24.8
2002-07-30 | 2002 | 7 | Wisley | 23.1
2002-07-31 | 2002 | 7 | Wisley | 22
2002-08-01 | 2002 | 8 | Wisley | 23
2002-08-02 | 2002 | 8 | Wisley | 21
2002-08-03 | 2002 | 8 | Wisley | 22.1
2002-08-04 | 2002 | 8 | Wisley | 22.3
2002-08-05 | 2002 | 8 | Wisley | 24.1
2002-08-06 | 2002 | 8 | Wisley | 27.2
2002-08-07 | 2002 | 8 | Wisley | 20.6
2002-08-08 | 2002 | 8 | Wisley | 20.4
2002-08-09 | 2002 | 8 | Wisley | 21.9
2002-08-10 | 2002 | 8 | Wisley | 21.3
2002-08-11 | 2002 | 8 | Wisley | 22.5
2002-08-12 | 2002 | 8 | Wisley | 25.7
2002-08-13 | 2002 | 8 | Wisley | 25.1
2002-08-14 | 2002 | 8 | Wisley | 29
2002-08-15 | 2002 | 8 | Wisley | 27
2002-08-16 | 2002 | 8 | Wisley | 28.6
2002-08-17 | 2002 | 8 | Wisley | 26.2
2002-08-18 | 2002 | 8 | Wisley | 25.5
2002-08-19 | 2002 | 8 | Wisley | 22.8
2002-08-20 | 2002 | 8 | Wisley | 23.9
2002-08-21 | 2002 | 8 | Wisley | 24.1
2002-08-22 | 2002 | 8 | Wisley | 22.8
2002-08-23 | 2002 | 8 | Wisley | 24.4
2002-08-24 | 2002 | 8 | Wisley | 22.1
2002-08-25 | 2002 | 8 | Wisley | 17.4
2002-08-26 | 2002 | 8 | Wisley | 21.9
2002-08-27 | 2002 | 8 | Wisley | 23.8
2002-08-28 | 2002 | 8 | Wisley | 23.7
2002-08-29 | 2002 | 8 | Wisley | 21.5
2002-08-30 | 2002 | 8 | Wisley | 20.9
2002-08-31 | 2002 | 8 | Wisley | 21
2002-09-01 | 2002 | 9 | Wisley | 22.5
2002-09-02 | 2002 | 9 | Wisley | 24.6
2002-09-03 | 2002 | 9 | Wisley | 22.4
2002-09-04 | 2002 | 9 | Wisley | 22.9
2002-09-05 | 2002 | 9 | Wisley | 22.1
2002-09-06 | 2002 | 9 | Wisley | 19.9
2002-09-07 | 2002 | 9 | Wisley | 20.6
2002-09-08 | 2002 | 9 | Wisley | 16.3
2002-09-09 | 2002 | 9 | Wisley | 20.9
2002-09-10 | 2002 | 9 | Wisley | 22.1
2002-09-11 | 2002 | 9 | Wisley | 24
2002-09-12 | 2002 | 9 | Wisley | 24.7
2002-09-13 | 2002 | 9 | Wisley | 19.7
2002-09-14 | 2002 | 9 | Wisley | 18.4
2002-09-15 | 2002 | 9 | Wisley | 20.4
2002-09-16 | 2002 | 9 | Wisley | 19.4
2002-09-17 | 2002 | 9 | Wisley | 19.4
2002-09-18 | 2002 | 9 | Wisley | 20.7
2002-09-19 | 2002 | 9 | Wisley | 18.7
2002-09-20 | 2002 | 9 | Wisley | 19
2002-09-21 | 2002 | 9 | Wisley | 18
2002-09-22 | 2002 | 9 | Wisley | 19.4
2002-09-23 | 2002 | 9 | Wisley | 18.4
2002-09-24 | 2002 | 9 | Wisley | 19.2
2002-09-25 | 2002 | 9 | Wisley | 18.3
2002-09-26 | 2002 | 9 | Wisley | 16.8
2002-09-27 | 2002 | 9 | Wisley | 19.9
2002-09-28 | 2002 | 9 | Wisley | 20.9
2002-09-29 | 2002 | 9 | Wisley | 20.8
2002-09-30 | 2002 | 9 | Wisley | 21.9
2003-05-01 | 2003 | 5 | Wisley | 14.1
2003-05-02 | 2003 | 5 | Wisley | 17.5
2003-05-03 | 2003 | 5 | Wisley | 21.7
2003-05-04 | 2003 | 5 | Wisley | 17.3
2003-05-05 | 2003 | 5 | Wisley | 18
2003-05-06 | 2003 | 5 | Wisley | 19.8
2003-05-07 | 2003 | 5 | Wisley | 17.5
2003-05-08 | 2003 | 5 | Wisley | 18.5
2003-05-09 | 2003 | 5 | Wisley | 15.3
2003-05-10 | 2003 | 5 | Wisley | 16.4
2003-05-11 | 2003 | 5 | Wisley | 13.7
2003-05-12 | 2003 | 5 | Wisley | 14.1
2003-05-13 | 2003 | 5 | Wisley | 16.1
2003-05-14 | 2003 | 5 | Wisley | 16.8
2003-05-15 | 2003 | 5 | Wisley | 13.2
2003-05-16 | 2003 | 5 | Wisley | 17
2003-05-17 | 2003 | 5 | Wisley | 17
2003-05-18 | 2003 | 5 | Wisley | 16.7
2003-05-19 | 2003 | 5 | Wisley | 15.8
2003-05-20 | 2003 | 5 | Wisley | 17.4
2003-05-21 | 2003 | 5 | Wisley | 19.2
2003-05-22 | 2003 | 5 | Wisley | 17.6
2003-05-23 | 2003 | 5 | Wisley | 18.1
2003-05-24 | 2003 | 5 | Wisley | 18
2003-05-25 | 2003 | 5 | Wisley | 19.3
2003-05-26 | 2003 | 5 | Wisley | 19.3
2003-05-27 | 2003 | 5 | Wisley | 24.1
2003-05-28 | 2003 | 5 | Wisley | 26.2
2003-05-29 | 2003 | 5 | Wisley | 26.9
2003-05-30 | 2003 | 5 | Wisley | 27.6
2003-06-30 | 2003 | 6 | Wisley | 20.7
2003-07-02 | 2003 | 7 | Wisley | 20.6
2003-07-03 | 2003 | 7 | Wisley | 21.2
2003-07-04 | 2003 | 7 | Wisley | 20.3
2003-07-05 | 2003 | 7 | Wisley | 22.6
2003-07-06 | 2003 | 7 | Wisley | 22.1
2003-07-07 | 2003 | 7 | Wisley | 24
2003-07-08 | 2003 | 7 | Wisley | 27.9
2003-07-09 | 2003 | 7 | Wisley | 29
2003-07-10 | 2003 | 7 | Wisley | 25.1
2003-07-11 | 2003 | 7 | Wisley | 26.8
2003-07-12 | 2003 | 7 | Wisley | 28.8
2003-07-13 | 2003 | 7 | Wisley | 31.1
2003-07-14 | 2003 | 7 | Wisley | 33.6
2003-07-15 | 2003 | 7 | Wisley | 22.7
2003-07-17 | 2003 | 7 | Wisley | 24.3
2003-07-18 | 2003 | 7 | Wisley | 28
2003-07-19 | 2003 | 7 | Wisley | 23.6
2003-07-20 | 2003 | 7 | Wisley | 24
2003-07-21 | 2003 | 7 | Wisley | 24.2
2003-07-22 | 2003 | 7 | Wisley | 23.2
2003-07-23 | 2003 | 7 | Wisley | 22.6
2003-07-24 | 2003 | 7 | Wisley | 21.2
2003-07-25 | 2003 | 7 | Wisley | 20.6
2003-07-26 | 2003 | 7 | Wisley | 23
2003-07-27 | 2003 | 7 | Wisley | 22.3
2003-07-28 | 2003 | 7 | Wisley | 20.7
2003-07-29 | 2003 | 7 | Wisley | 23.5
2003-07-30 | 2003 | 7 | Wisley | 22.5
2003-07-31 | 2003 | 7 | Wisley | 19.3
2003-08-01 | 2003 | 8 | Wisley | 26
2003-08-02 | 2003 | 8 | Wisley | 30.3
2003-08-03 | 2003 | 8 | Wisley | 32.5
2003-08-04 | 2003 | 8 | Wisley | 33.9
2003-08-05 | 2003 | 8 | Wisley | 36.1
2003-08-06 | 2003 | 8 | Wisley | 30.6
2003-08-07 | 2003 | 8 | Wisley | 32.3
2003-08-08 | 2003 | 8 | Wisley | 35.7
2003-08-09 | 2003 | 8 | Wisley | 37.8
2003-08-10 | 2003 | 8 | Wisley | 34.5
2003-08-11 | 2003 | 8 | Wisley | 31.1
2003-08-12 | 2003 | 8 | Wisley | 29.2
2003-08-13 | 2003 | 8 | Wisley | 26.4
2003-08-14 | 2003 | 8 | Wisley | 25
2003-08-15 | 2003 | 8 | Wisley | 24.7
2003-08-16 | 2003 | 8 | Wisley | 28.2
2003-08-17 | 2003 | 8 | Wisley | 24.8
2003-08-18 | 2003 | 8 | Wisley | 22.9
2003-08-19 | 2003 | 8 | Wisley | 24.3
2003-08-20 | 2003 | 8 | Wisley | 23.8
2003-08-21 | 2003 | 8 | Wisley | 26.5
2003-08-22 | 2003 | 8 | Wisley | 28.3
2003-08-23 | 2003 | 8 | Wisley | 27
2003-08-25 | 2003 | 8 | Wisley | 24.4
2003-08-26 | 2003 | 8 | Wisley | 24.2
2003-08-29 | 2003 | 8 | Wisley | 20.3
2003-08-30 | 2003 | 8 | Wisley | 20.6
2003-08-31 | 2003 | 8 | Wisley | 19.8
2003-09-01 | 2003 | 9 | Wisley | 21.1
2003-09-02 | 2003 | 9 | Wisley | 23.1
2003-09-03 | 2003 | 9 | Wisley | 24.7
2003-09-04 | 2003 | 9 | Wisley | 27.3
2003-09-05 | 2003 | 9 | Wisley | 21.6
2003-09-07 | 2003 | 9 | Wisley | 22.1
2003-09-08 | 2003 | 9 | Wisley | 20.9
2003-09-09 | 2003 | 9 | Wisley | 23.1
2003-09-10 | 2003 | 9 | Wisley | 18.6
2003-09-11 | 2003 | 9 | Wisley | 21.7
2003-09-12 | 2003 | 9 | Wisley | 24.2
2003-09-13 | 2003 | 9 | Wisley | 26
2003-09-14 | 2003 | 9 | Wisley | 26.7
2003-09-15 | 2003 | 9 | Wisley | 27.8
2003-09-16 | 2003 | 9 | Wisley | 28.2
2003-09-17 | 2003 | 9 | Wisley | 21.9
2003-09-18 | 2003 | 9 | Wisley | 23.4
2003-09-19 | 2003 | 9 | Wisley | 27.7
2003-09-20 | 2003 | 9 | Wisley | 27.3
2003-09-22 | 2003 | 9 | Wisley | 15.8
2003-09-23 | 2003 | 9 | Wisley | 17.9
2003-09-24 | 2003 | 9 | Wisley | 20.3
2003-09-25 | 2003 | 9 | Wisley | 20.6
2003-09-26 | 2003 | 9 | Wisley | 18
2003-09-27 | 2003 | 9 | Wisley | 15.8
2003-09-28 | 2003 | 9 | Wisley | 19.7
2003-09-29 | 2003 | 9 | Wisley | 20.8
2005-05-01 | 2005 | 5 | Wisley | 20.4
2005-05-04 | 2005 | 5 | Wisley | 18.6
2005-05-05 | 2005 | 5 | Wisley | 17.2
2005-05-06 | 2005 | 5 | Wisley | 15.6
2005-05-07 | 2005 | 5 | Wisley | 14.7
2005-05-08 | 2005 | 5 | Wisley | 13.5
2005-05-09 | 2005 | 5 | Wisley | 13.1
2005-05-10 | 2005 | 5 | Wisley | 13.9
2005-05-11 | 2005 | 5 | Wisley | 14.9
2005-05-12 | 2005 | 5 | Wisley | 17.2
2005-05-13 | 2005 | 5 | Wisley | 15.7
2005-05-14 | 2005 | 5 | Wisley | 17.9
2005-05-15 | 2005 | 5 | Wisley | 17.3
2005-05-16 | 2005 | 5 | Wisley | 12.9
2005-05-17 | 2005 | 5 | Wisley | 15.6
2005-05-18 | 2005 | 5 | Wisley | 14.2
2005-05-19 | 2005 | 5 | Wisley | 17.6
2005-05-20 | 2005 | 5 | Wisley | 15.7
2005-05-21 | 2005 | 5 | Wisley | 16.8
2005-05-22 | 2005 | 5 | Wisley | 17
2005-05-23 | 2005 | 5 | Wisley | 17.5
2005-05-24 | 2005 | 5 | Wisley | 21.4
2005-05-25 | 2005 | 5 | Wisley | 23.7
2005-05-26 | 2005 | 5 | Wisley | 29.6
2005-05-27 | 2005 | 5 | Wisley | 19.9
2005-05-29 | 2005 | 5 | Wisley | 19
2005-05-30 | 2005 | 5 | Wisley | 20.1
2005-05-31 | 2005 | 5 | Wisley | 16.3
2005-06-01 | 2005 | 6 | Wisley | 17.3
2005-06-02 | 2005 | 6 | Wisley | 21.5
2005-06-03 | 2005 | 6 | Wisley | 19.1
2005-06-04 | 2005 | 6 | Wisley | 17.5
2005-06-05 | 2005 | 6 | Wisley | 17.1
2005-06-06 | 2005 | 6 | Wisley | 18.4
2005-06-07 | 2005 | 6 | Wisley | 21.5
2005-06-08 | 2005 | 6 | Wisley | 23
2005-06-09 | 2005 | 6 | Wisley | 21.2
2005-06-10 | 2005 | 6 | Wisley | 18.4
2005-06-11 | 2005 | 6 | Wisley | 19.8
2005-06-12 | 2005 | 6 | Wisley | 19.9
2005-06-13 | 2005 | 6 | Wisley | 20.1
2005-06-14 | 2005 | 6 | Wisley | 20.4
2005-06-15 | 2005 | 6 | Wisley | 20.8
2005-06-16 | 2005 | 6 | Wisley | 25.5
2005-06-17 | 2005 | 6 | Wisley | 28.2
2005-06-18 | 2005 | 6 | Wisley | 31
2005-06-19 | 2005 | 6 | Wisley | 28.1
2005-06-20 | 2005 | 6 | Wisley | 26
2005-06-21 | 2005 | 6 | Wisley | 28.2
2005-06-22 | 2005 | 6 | Wisley | 30.6
2005-06-23 | 2005 | 6 | Wisley | 26.9
2005-06-25 | 2005 | 6 | Wisley | 21.4
2005-06-26 | 2005 | 6 | Wisley | 26.2
2005-06-27 | 2005 | 6 | Wisley | 26.1
2005-06-28 | 2005 | 6 | Wisley | 24.9
2005-06-30 | 2005 | 6 | Wisley | 21.4
2005-07-01 | 2005 | 7 | Wisley | 21.2
2005-07-02 | 2005 | 7 | Wisley | 20.2
2005-07-03 | 2005 | 7 | Wisley | 16.8
2005-07-04 | 2005 | 7 | Wisley | 16.9
2005-07-05 | 2005 | 7 | Wisley | 19.5
2005-07-06 | 2005 | 7 | Wisley | 21
2005-07-07 | 2005 | 7 | Wisley | 20.4
2005-07-08 | 2005 | 7 | Wisley | 22.4
2005-07-09 | 2005 | 7 | Wisley | 29.4
2005-07-10 | 2005 | 7 | Wisley | 28.3
2005-07-11 | 2005 | 7 | Wisley | 27.6
2005-07-12 | 2005 | 7 | Wisley | 30.3
2005-07-13 | 2005 | 7 | Wisley | 30
2005-07-14 | 2005 | 7 | Wisley | 27.5
2005-07-15 | 2005 | 7 | Wisley | 25.2
2005-07-16 | 2005 | 7 | Wisley | 28.6
2005-07-17 | 2005 | 7 | Wisley | 25.6
2005-07-18 | 2005 | 7 | Wisley | 22.6
2005-07-19 | 2005 | 7 | Wisley | 24.7
2005-07-20 | 2005 | 7 | Wisley | 24.5
2005-07-21 | 2005 | 7 | Wisley | 24
2005-07-22 | 2005 | 7 | Wisley | 23.2
2005-07-23 | 2005 | 7 | Wisley | 21.6
2005-07-24 | 2005 | 7 | Wisley | 18.8
2005-07-25 | 2005 | 7 | Wisley | 19.3
2005-07-26 | 2005 | 7 | Wisley | 18.7
2005-07-27 | 2005 | 7 | Wisley | 24.1
2005-07-28 | 2005 | 7 | Wisley | 22.6
2005-07-29 | 2005 | 7 | Wisley | 19.5
2005-07-30 | 2005 | 7 | Wisley | 20.7
2005-07-31 | 2005 | 7 | Wisley | 20.4
2005-08-01 | 2005 | 8 | Wisley | 23.9
2005-08-02 | 2005 | 8 | Wisley | 23.5
2005-08-03 | 2005 | 8 | Wisley | 22.5
2005-08-04 | 2005 | 8 | Wisley | 21.8
2005-08-05 | 2005 | 8 | Wisley | 20
2005-08-06 | 2005 | 8 | Wisley | 21.6
2005-08-07 | 2005 | 8 | Wisley | 22.9
2005-08-08 | 2005 | 8 | Wisley | 25.3
2005-08-09 | 2005 | 8 | Wisley | 24.5
2005-08-10 | 2005 | 8 | Wisley | 26.6
2005-08-11 | 2005 | 8 | Wisley | 21.7
2005-08-12 | 2005 | 8 | Wisley | 21.3
2005-08-13 | 2005 | 8 | Wisley | 20.2
2005-08-14 | 2005 | 8 | Wisley | 23.4
2005-08-15 | 2005 | 8 | Wisley | 24.9
2005-08-16 | 2005 | 8 | Wisley | 26.1
2005-08-17 | 2005 | 8 | Wisley | 28.2
2005-08-20 | 2005 | 8 | Wisley | 24.6
2005-08-21 | 2005 | 8 | Wisley | 19.1
2005-08-22 | 2005 | 8 | Wisley | 22.1
2005-08-23 | 2005 | 8 | Wisley | 16.4
2005-08-24 | 2005 | 8 | Wisley | 19
2005-08-25 | 2005 | 8 | Wisley | 19.4
2005-08-26 | 2005 | 8 | Wisley | 20.8
2005-08-27 | 2005 | 8 | Wisley | 23.9
2005-08-28 | 2005 | 8 | Wisley | 25.3
2005-08-29 | 2005 | 8 | Wisley | 26.3
2005-08-30 | 2005 | 8 | Wisley | 30.4
2005-08-31 | 2005 | 8 | Wisley | 23.5
2005-09-01 | 2005 | 9 | Wisley | 23.8
2005-09-02 | 2005 | 9 | Wisley | 26
2005-09-03 | 2005 | 9 | Wisley | 28.2
2005-09-04 | 2005 | 9 | Wisley | 22
2005-09-06 | 2005 | 9 | Wisley | 25.7
2005-09-07 | 2005 | 9 | Wisley | 24.4
2005-09-08 | 2005 | 9 | Wisley | 25.4
2005-09-09 | 2005 | 9 | Wisley | 24.7
2005-09-11 | 2005 | 9 | Wisley | 21.8
2005-09-12 | 2005 | 9 | Wisley | 22.7
2005-09-13 | 2005 | 9 | Wisley | 23.4
2005-09-14 | 2005 | 9 | Wisley | 20.7
2005-09-16 | 2005 | 9 | Wisley | 16.7
2005-09-17 | 2005 | 9 | Wisley | 16.6
2005-09-18 | 2005 | 9 | Wisley | 19.6
2005-09-19 | 2005 | 9 | Wisley | 21.9
2005-09-20 | 2005 | 9 | Wisley | 21.4
2005-09-21 | 2005 | 9 | Wisley | 21.4
2005-09-22 | 2005 | 9 | Wisley | 18.4
2005-09-23 | 2005 | 9 | Wisley | 18.2
2005-09-24 | 2005 | 9 | Wisley | 20.9
2005-09-25 | 2005 | 9 | Wisley | 17.4
2005-09-26 | 2005 | 9 | Wisley | 20.1
2005-09-27 | 2005 | 9 | Wisley | 15.5
2005-09-28 | 2005 | 9 | Wisley | 16.7
2005-09-29 | 2005 | 9 | Wisley | 19.7
2005-09-30 | 2005 | 9 | Wisley | 16.5
2006-05-01 | 2006 | 5 | Wisley | 16
2006-05-02 | 2006 | 5 | Wisley | 19.9
2006-05-03 | 2006 | 5 | Wisley | 27
2006-05-04 | 2006 | 5 | Wisley | 21.5
2006-05-06 | 2006 | 5 | Wisley | 18.3
2006-05-07 | 2006 | 5 | Wisley | 15.1
2006-05-08 | 2006 | 5 | Wisley | 18.9
2006-05-09 | 2006 | 5 | Wisley | 23
2006-05-10 | 2006 | 5 | Wisley | 24.2
2006-05-11 | 2006 | 5 | Wisley | 24.3
2006-05-12 | 2006 | 5 | Wisley | 17.9
2006-05-13 | 2006 | 5 | Wisley | 17
2006-05-14 | 2006 | 5 | Wisley | 19.4
2006-05-15 | 2006 | 5 | Wisley | 17.6
2006-05-16 | 2006 | 5 | Wisley | 17
2006-05-17 | 2006 | 5 | Wisley | 18
2006-05-18 | 2006 | 5 | Wisley | 16.3
2006-05-19 | 2006 | 5 | Wisley | 15.6
2006-05-20 | 2006 | 5 | Wisley | 13.8
2006-05-21 | 2006 | 5 | Wisley | 15.8
2006-05-22 | 2006 | 5 | Wisley | 15.1
2006-05-29 | 2006 | 5 | Wisley | 13.8
2006-05-30 | 2006 | 5 | Wisley | 15.5
2006-05-31 | 2006 | 5 | Wisley | 16
2006-06-01 | 2006 | 6 | Wisley | 19.5
2006-06-02 | 2006 | 6 | Wisley | 24.4
2006-06-03 | 2006 | 6 | Wisley | 23.5
2006-06-04 | 2006 | 6 | Wisley | 20.5
2006-06-05 | 2006 | 6 | Wisley | 21.1
2006-06-06 | 2006 | 6 | Wisley | 25.9
2006-06-07 | 2006 | 6 | Wisley | 26.1
2006-06-08 | 2006 | 6 | Wisley | 25.8
2006-06-09 | 2006 | 6 | Wisley | 27.6
2006-06-10 | 2006 | 6 | Wisley | 27.5
2006-06-11 | 2006 | 6 | Wisley | 30.2
2006-06-12 | 2006 | 6 | Wisley | 24.4
2006-06-14 | 2006 | 6 | Wisley | 21.2
2006-06-15 | 2006 | 6 | Wisley | 24.3
2006-06-16 | 2006 | 6 | Wisley | 27
2006-06-17 | 2006 | 6 | Wisley | 25.6
2006-06-18 | 2006 | 6 | Wisley | 20.3
2006-06-19 | 2006 | 6 | Wisley | 22.5
2006-06-20 | 2006 | 6 | Wisley | 19.9
2006-06-21 | 2006 | 6 | Wisley | 20.1
2006-06-22 | 2006 | 6 | Wisley | 22
2006-06-23 | 2006 | 6 | Wisley | 25.1
2006-06-24 | 2006 | 6 | Wisley | 23.9
2006-06-26 | 2006 | 6 | Wisley | 19.7
2006-06-27 | 2006 | 6 | Wisley | 22.5
2006-06-28 | 2006 | 6 | Wisley | 25.3
2006-06-29 | 2006 | 6 | Wisley | 27.6
2006-06-30 | 2006 | 6 | Wisley | 30
2006-07-01 | 2006 | 7 | Wisley | 31.3
2006-07-02 | 2006 | 7 | Wisley | 31
2006-07-03 | 2006 | 7 | Wisley | 30.2
2006-07-05 | 2006 | 7 | Wisley | 23.7
2006-07-06 | 2006 | 7 | Wisley | 21.1
2006-07-07 | 2006 | 7 | Wisley | 22.4
2006-07-08 | 2006 | 7 | Wisley | 23
2006-07-09 | 2006 | 7 | Wisley | 21.3
2006-07-10 | 2006 | 7 | Wisley | 25.2
2006-07-11 | 2006 | 7 | Wisley | 26.7
2006-07-12 | 2006 | 7 | Wisley | 23.5
2006-07-13 | 2006 | 7 | Wisley | 22.9
2006-07-14 | 2006 | 7 | Wisley | 25.1
2006-07-15 | 2006 | 7 | Wisley | 30.1
2006-07-16 | 2006 | 7 | Wisley | 32.6
2006-07-17 | 2006 | 7 | Wisley | 33.3
2006-07-18 | 2006 | 7 | Wisley | 36.5
2006-07-19 | 2006 | 7 | Wisley | 30.3
2006-07-20 | 2006 | 7 | Wisley | 31.4
2006-07-21 | 2006 | 7 | Wisley | 29
2006-07-22 | 2006 | 7 | Wisley | 26.5
2006-07-23 | 2006 | 7 | Wisley | 29.7
2006-07-24 | 2006 | 7 | Wisley | 32.9
2006-07-25 | 2006 | 7 | Wisley | 31.8
2006-07-26 | 2006 | 7 | Wisley | 29.9
2006-07-27 | 2006 | 7 | Wisley | 28.2
2006-07-28 | 2006 | 7 | Wisley | 25.5
2006-07-29 | 2006 | 7 | Wisley | 25.3
2006-07-30 | 2006 | 7 | Wisley | 24.2
2006-07-31 | 2006 | 7 | Wisley | 22.3
2006-08-01 | 2006 | 8 | Wisley | 22.7
2006-08-02 | 2006 | 8 | Wisley | 20.8
2006-08-03 | 2006 | 8 | Wisley | 23
2006-08-04 | 2006 | 8 | Wisley | 27
2006-08-05 | 2006 | 8 | Wisley | 27.8
2006-08-06 | 2006 | 8 | Wisley | 22.2
2006-08-07 | 2006 | 8 | Wisley | 26.1
2006-08-08 | 2006 | 8 | Wisley | 23
2006-08-09 | 2006 | 8 | Wisley | 21.4
2006-08-10 | 2006 | 8 | Wisley | 20.8
2006-08-11 | 2006 | 8 | Wisley | 18.6
2006-08-12 | 2006 | 8 | Wisley | 18.6
2006-08-13 | 2006 | 8 | Wisley | 18.4
2006-08-14 | 2006 | 8 | Wisley | 21.2
2006-08-15 | 2006 | 8 | Wisley | 21
2006-08-16 | 2006 | 8 | Wisley | 22.5
2006-08-17 | 2006 | 8 | Wisley | 19.7
2006-08-18 | 2006 | 8 | Wisley | 21
2006-08-19 | 2006 | 8 | Wisley | 20.7
2006-08-20 | 2006 | 8 | Wisley | 22.4
2006-08-21 | 2006 | 8 | Wisley | 21.8
2006-08-22 | 2006 | 8 | Wisley | 19.1
2006-08-23 | 2006 | 8 | Wisley | 21.3
2006-08-24 | 2006 | 8 | Wisley | 22.4
2006-08-25 | 2006 | 8 | Wisley | 21.9
2006-08-26 | 2006 | 8 | Wisley | 22.2
2006-08-27 | 2006 | 8 | Wisley | 20
2006-08-28 | 2006 | 8 | Wisley | 19.3
2006-08-29 | 2006 | 8 | Wisley | 20.6
2006-08-30 | 2006 | 8 | Wisley | 22.7
2006-08-31 | 2006 | 8 | Wisley | 23.4
2006-09-01 | 2006 | 9 | Wisley | 20.2
2006-09-02 | 2006 | 9 | Wisley | 25.6
2006-09-03 | 2006 | 9 | Wisley | 24.2
2006-09-04 | 2006 | 9 | Wisley | 25.9
2006-09-05 | 2006 | 9 | Wisley | 26.6
2006-09-06 | 2006 | 9 | Wisley | 21.4
2006-09-07 | 2006 | 9 | Wisley | 21.8
2006-09-08 | 2006 | 9 | Wisley | 23.1
2006-09-09 | 2006 | 9 | Wisley | 26.7
2006-09-10 | 2006 | 9 | Wisley | 29.6
2006-09-11 | 2006 | 9 | Wisley | 21.3
2006-09-12 | 2006 | 9 | Wisley | 22.8
2006-09-13 | 2006 | 9 | Wisley | 20.4
2006-09-14 | 2006 | 9 | Wisley | 22.2
2006-09-15 | 2006 | 9 | Wisley | 20.9
2006-09-16 | 2006 | 9 | Wisley | 24.2
2006-09-17 | 2006 | 9 | Wisley | 21.2
2006-09-18 | 2006 | 9 | Wisley | 20.3
2006-09-19 | 2006 | 9 | Wisley | 22.1
2006-09-20 | 2006 | 9 | Wisley | 27.4
2006-09-22 | 2006 | 9 | Wisley | 23.4
2006-09-23 | 2006 | 9 | Wisley | 22.2
2006-09-25 | 2006 | 9 | Wisley | 21.7
2006-09-26 | 2006 | 9 | Wisley | 19.9
2007-05-01 | 2007 | 5 | Wisley | 21.8
2007-05-02 | 2007 | 5 | Wisley | 15.9
2007-05-03 | 2007 | 5 | Wisley | 18
2007-05-04 | 2007 | 5 | Wisley | 15.5
2007-05-05 | 2007 | 5 | Wisley | 19.6
2007-05-06 | 2007 | 5 | Wisley | 18.7
2007-05-07 | 2007 | 5 | Wisley | 18.9
2007-05-08 | 2007 | 5 | Wisley | 14.7
2007-05-16 | 2007 | 5 | Wisley | 19.3
2007-05-17 | 2007 | 5 | Wisley | 20.5
2007-05-18 | 2007 | 5 | Wisley | 17.5
2007-05-19 | 2007 | 5 | Wisley | 19.5
2007-05-21 | 2007 | 5 | Wisley | 22
2007-05-22 | 2007 | 5 | Wisley | 24
2007-05-23 | 2007 | 5 | Wisley | 24.8
2007-05-24 | 2007 | 5 | Wisley | 23.3
2007-05-27 | 2007 | 5 | Wisley | 11.5
2007-05-28 | 2007 | 5 | Wisley | 15.8
2007-05-30 | 2007 | 5 | Wisley | 18.5
2007-05-31 | 2007 | 5 | Wisley | 21.6
2007-06-01 | 2007 | 6 | Wisley | 24.6
2007-06-02 | 2007 | 6 | Wisley | 25
2007-06-03 | 2007 | 6 | Wisley | 18.7
2007-06-04 | 2007 | 6 | Wisley | 21.5
2007-06-05 | 2007 | 6 | Wisley | 18.8
2007-06-06 | 2007 | 6 | Wisley | 19.6
2007-06-07 | 2007 | 6 | Wisley | 21.8
2007-06-08 | 2007 | 6 | Wisley | 25.1
2007-06-09 | 2007 | 6 | Wisley | 24.6
2007-06-10 | 2007 | 6 | Wisley | 21.8
2007-06-11 | 2007 | 6 | Wisley | 23.3
2007-06-12 | 2007 | 6 | Wisley | 24.1
2007-06-13 | 2007 | 6 | Wisley | 21.8
2007-06-14 | 2007 | 6 | Wisley | 19.7
2007-06-15 | 2007 | 6 | Wisley | 19.1
2007-06-16 | 2007 | 6 | Wisley | 21.3
2007-06-17 | 2007 | 6 | Wisley | 20.4
2007-06-19 | 2007 | 6 | Wisley | 21.2
2007-06-24 | 2007 | 6 | Wisley | 16.6
2007-06-25 | 2007 | 6 | Wisley | 16.7
2007-06-26 | 2007 | 6 | Wisley | 18.1
2007-06-27 | 2007 | 6 | Wisley | 19.3
2007-06-28 | 2007 | 6 | Wisley | 21.8
2007-06-29 | 2007 | 6 | Wisley | 18.3
2007-07-31 | 2007 | 7 | Wisley | 23.6
2007-08-01 | 2007 | 8 | Wisley | 20.5
2007-08-02 | 2007 | 8 | Wisley | 24
2007-08-03 | 2007 | 8 | Wisley | 25.5
2007-08-04 | 2007 | 8 | Wisley | 27.9
2007-08-05 | 2007 | 8 | Wisley | 23.1
2007-08-06 | 2007 | 8 | Wisley | 22.7
2007-08-07 | 2007 | 8 | Wisley | 21.1
2007-08-08 | 2007 | 8 | Wisley | 21.2
2007-08-09 | 2007 | 8 | Wisley | 23.9
2007-08-10 | 2007 | 8 | Wisley | 25
2007-08-11 | 2007 | 8 | Wisley | 21.2
2007-08-12 | 2007 | 8 | Wisley | 21.7
2007-08-13 | 2007 | 8 | Wisley | 19.1
2007-08-14 | 2007 | 8 | Wisley | 21
2007-08-15 | 2007 | 8 | Wisley | 19.6
2007-08-16 | 2007 | 8 | Wisley | 19.9
2007-08-17 | 2007 | 8 | Wisley | 19.1
2007-08-18 | 2007 | 8 | Wisley | 17.4
2007-08-20 | 2007 | 8 | Wisley | 16.7
2007-08-21 | 2007 | 8 | Wisley | 16.3
2007-08-22 | 2007 | 8 | Wisley | 16
2007-08-23 | 2007 | 8 | Wisley | 18.8
2007-08-24 | 2007 | 8 | Wisley | 26.4
2007-08-25 | 2007 | 8 | Wisley | 23.1
2007-08-27 | 2007 | 8 | Wisley | 20.2
2007-08-28 | 2007 | 8 | Wisley | 21.3
2007-08-29 | 2007 | 8 | Wisley | 19.5
2007-08-30 | 2007 | 8 | Wisley | 19.4
2007-08-31 | 2007 | 8 | Wisley | 20.6
2007-09-01 | 2007 | 9 | Wisley | 21.3
2007-09-02 | 2007 | 9 | Wisley | 19
2007-09-03 | 2007 | 9 | Wisley | 19.3
2007-09-04 | 2007 | 9 | Wisley | 23.9
2007-09-05 | 2007 | 9 | Wisley | 24.7
2007-09-06 | 2007 | 9 | Wisley | 24
2007-09-07 | 2007 | 9 | Wisley | 19.9
2007-09-08 | 2007 | 9 | Wisley | 21.7
2007-09-09 | 2007 | 9 | Wisley | 21.7
2007-09-10 | 2007 | 9 | Wisley | 20.3
2007-09-11 | 2007 | 9 | Wisley | 21.5
2007-09-12 | 2007 | 9 | Wisley | 22.2
2007-09-13 | 2007 | 9 | Wisley | 21.3
2007-09-14 | 2007 | 9 | Wisley | 21.1
2007-09-15 | 2007 | 9 | Wisley | 20.7
2007-09-16 | 2007 | 9 | Wisley | 17.5
2007-09-18 | 2007 | 9 | Wisley | 18.7
2007-09-19 | 2007 | 9 | Wisley | 19.6
2007-09-20 | 2007 | 9 | Wisley | 19.2
2007-09-21 | 2007 | 9 | Wisley | 21.1
2007-09-22 | 2007 | 9 | Wisley | 20.9
2007-09-23 | 2007 | 9 | Wisley | 17.5
2007-09-24 | 2007 | 9 | Wisley | 17.3
2007-09-25 | 2007 | 9 | Wisley | 14.2
2007-09-26 | 2007 | 9 | Wisley | 13.8
2007-09-27 | 2007 | 9 | Wisley | 14.1
2007-09-28 | 2007 | 9 | Wisley | 17.4
2007-09-29 | 2007 | 9 | Wisley | 17
2007-09-30 | 2007 | 9 | Wisley | 14.4
2008-05-01 | 2008 | 5 | Wisley | 15.8
2008-05-02 | 2008 | 5 | Wisley | 20.2
2008-05-03 | 2008 | 5 | Wisley | 22.3
2008-05-04 | 2008 | 5 | Wisley | 22.8
2008-05-05 | 2008 | 5 | Wisley | 23.3
2008-05-06 | 2008 | 5 | Wisley | 25.4
2008-05-07 | 2008 | 5 | Wisley | 24.9
2008-05-08 | 2008 | 5 | Wisley | 25.3
2008-05-09 | 2008 | 5 | Wisley | 26.5
2008-05-10 | 2008 | 5 | Wisley | 26.9
2008-05-11 | 2008 | 5 | Wisley | 25.2
2008-05-12 | 2008 | 5 | Wisley | 22.9
2008-05-13 | 2008 | 5 | Wisley | 20.9
2008-05-16 | 2008 | 5 | Wisley | 13.7
2008-05-17 | 2008 | 5 | Wisley | 16.5
2008-05-18 | 2008 | 5 | Wisley | 15.6
2008-05-19 | 2008 | 5 | Wisley | 16.5
2008-05-20 | 2008 | 5 | Wisley | 20.1
2008-05-21 | 2008 | 5 | Wisley | 21.7
2008-05-22 | 2008 | 5 | Wisley | 20.3
2008-05-23 | 2008 | 5 | Wisley | 22.4
2008-05-24 | 2008 | 5 | Wisley | 20.7
2008-05-26 | 2008 | 5 | Wisley | 19.4
2008-05-27 | 2008 | 5 | Wisley | 17.1
2008-05-28 | 2008 | 5 | Wisley | 22.1
2008-05-29 | 2008 | 5 | Wisley | 19.3
2008-05-30 | 2008 | 5 | Wisley | 21.6
2008-05-31 | 2008 | 5 | Wisley | 19.5
2008-06-01 | 2008 | 6 | Wisley | 18.7
2008-06-02 | 2008 | 6 | Wisley | 16.6
2008-06-03 | 2008 | 6 | Wisley | 20.6
2008-06-04 | 2008 | 6 | Wisley | 20.7
2008-06-05 | 2008 | 6 | Wisley | 19.8
2008-06-06 | 2008 | 6 | Wisley | 20.8
2008-06-07 | 2008 | 6 | Wisley | 25.7
2008-06-08 | 2008 | 6 | Wisley | 26.5
2008-06-09 | 2008 | 6 | Wisley | 23.1
2008-06-10 | 2008 | 6 | Wisley | 20.4
2008-06-11 | 2008 | 6 | Wisley | 16.1
2008-06-12 | 2008 | 6 | Wisley | 17.5
2008-06-13 | 2008 | 6 | Wisley | 18.9
2008-06-14 | 2008 | 6 | Wisley | 18.4
2008-06-15 | 2008 | 6 | Wisley | 19.9
2008-06-16 | 2008 | 6 | Wisley | 20.3
2008-06-17 | 2008 | 6 | Wisley | 17.5
2008-06-18 | 2008 | 6 | Wisley | 21.1
2008-06-19 | 2008 | 6 | Wisley | 19.9
2008-06-20 | 2008 | 6 | Wisley | 19.4
2008-06-21 | 2008 | 6 | Wisley | 21.1
2008-06-22 | 2008 | 6 | Wisley | 21.6
2008-06-23 | 2008 | 6 | Wisley | 23
2008-06-24 | 2008 | 6 | Wisley | 22.2
2008-06-25 | 2008 | 6 | Wisley | 21.6
2008-06-26 | 2008 | 6 | Wisley | 21.2
2008-06-27 | 2008 | 6 | Wisley | 23.1
2008-06-28 | 2008 | 6 | Wisley | 22.4
2008-06-29 | 2008 | 6 | Wisley | 22.5
2008-06-30 | 2008 | 6 | Wisley | 26.4
2008-07-01 | 2008 | 7 | Wisley | 19.3
2008-07-02 | 2008 | 7 | Wisley | 21.9
2008-07-03 | 2008 | 7 | Wisley | 20.8
2008-07-04 | 2008 | 7 | Wisley | 21.5
2008-07-05 | 2008 | 7 | Wisley | 18.8
2008-07-06 | 2008 | 7 | Wisley | 19.1
2008-07-07 | 2008 | 7 | Wisley | 19.1
2008-07-08 | 2008 | 7 | Wisley | 17.5
2008-07-09 | 2008 | 7 | Wisley | 20
2008-07-10 | 2008 | 7 | Wisley | 20.3
2008-07-11 | 2008 | 7 | Wisley | 18.5
2008-07-12 | 2008 | 7 | Wisley | 20.5
2008-07-13 | 2008 | 7 | Wisley | 22.7
2008-07-14 | 2008 | 7 | Wisley | 25.2
2008-07-15 | 2008 | 7 | Wisley | 21
2008-07-17 | 2008 | 7 | Wisley | 19.3
2008-07-18 | 2008 | 7 | Wisley | 20.9
2008-07-19 | 2008 | 7 | Wisley | 18.7
2008-07-20 | 2008 | 7 | Wisley | 21.1
2008-07-21 | 2008 | 7 | Wisley | 24.3
2008-07-22 | 2008 | 7 | Wisley | 25.7
2008-07-23 | 2008 | 7 | Wisley | 27.5
2008-07-24 | 2008 | 7 | Wisley | 24.6
2008-07-25 | 2008 | 7 | Wisley | 27
2008-07-26 | 2008 | 7 | Wisley | 29.4
2008-07-27 | 2008 | 7 | Wisley | 29.3
2008-07-28 | 2008 | 7 | Wisley | 22.3
2008-07-29 | 2008 | 7 | Wisley | 25.5
2008-07-30 | 2008 | 7 | Wisley | 26
2008-07-31 | 2008 | 7 | Wisley | 22
2008-08-01 | 2008 | 8 | Wisley | 22.8
2008-08-02 | 2008 | 8 | Wisley | 21.3
2008-08-03 | 2008 | 8 | Wisley | 20.5
2008-08-04 | 2008 | 8 | Wisley | 20.1
2008-08-05 | 2008 | 8 | Wisley | 25
2008-08-06 | 2008 | 8 | Wisley | 23.7
2008-08-09 | 2008 | 8 | Wisley | 21.2
2008-08-10 | 2008 | 8 | Wisley | 19.3
2008-08-11 | 2008 | 8 | Wisley | 19.8
2008-08-12 | 2008 | 8 | Wisley | 18.2
2008-08-13 | 2008 | 8 | Wisley | 20.7
2008-08-14 | 2008 | 8 | Wisley | 22
2008-08-15 | 2008 | 8 | Wisley | 21.4
2008-08-16 | 2008 | 8 | Wisley | 20
2008-08-17 | 2008 | 8 | Wisley | 20.1
2008-08-18 | 2008 | 8 | Wisley | 20.7
2008-08-19 | 2008 | 8 | Wisley | 21.1
2008-08-20 | 2008 | 8 | Wisley | 22
2008-08-21 | 2008 | 8 | Wisley | 20.7
2008-08-22 | 2008 | 8 | Wisley | 20.9
2008-08-23 | 2008 | 8 | Wisley | 22
2008-08-24 | 2008 | 8 | Wisley | 19.4
2008-08-25 | 2008 | 8 | Wisley | 19
2008-08-26 | 2008 | 8 | Wisley | 19.4
2008-08-27 | 2008 | 8 | Wisley | 20.2
2008-08-28 | 2008 | 8 | Wisley | 22
2008-08-29 | 2008 | 8 | Wisley | 26.1
2008-08-30 | 2008 | 8 | Wisley | 23.3
2008-08-31 | 2008 | 8 | Wisley | 20.5
2008-09-01 | 2008 | 9 | Wisley | 18.1
2008-09-02 | 2008 | 9 | Wisley | 19.1
2008-09-03 | 2008 | 9 | Wisley | 18.5
2008-09-04 | 2008 | 9 | Wisley | 17.5
2008-09-05 | 2008 | 9 | Wisley | 16.2
2008-09-06 | 2008 | 9 | Wisley | 16.2
2008-09-07 | 2008 | 9 | Wisley | 17.2
2008-09-08 | 2008 | 9 | Wisley | 18.6
2008-09-09 | 2008 | 9 | Wisley | 19.2
2008-09-10 | 2008 | 9 | Wisley | 19.1
2008-09-11 | 2008 | 9 | Wisley | 19.2
2008-09-12 | 2008 | 9 | Wisley | 19.3
2008-09-13 | 2008 | 9 | Wisley | 19.9
2008-09-14 | 2008 | 9 | Wisley | 18.8
2008-09-15 | 2008 | 9 | Wisley | 16.6
2008-09-16 | 2008 | 9 | Wisley | 17.3
2008-09-17 | 2008 | 9 | Wisley | 19.4
2008-09-18 | 2008 | 9 | Wisley | 20.7
2008-09-19 | 2008 | 9 | Wisley | 20.5
2008-09-20 | 2008 | 9 | Wisley | 20.2
2008-09-21 | 2008 | 9 | Wisley | 19.3
2008-09-22 | 2008 | 9 | Wisley | 17.9
2008-09-23 | 2008 | 9 | Wisley | 16
2008-09-24 | 2008 | 9 | Wisley | 19.1
2008-09-25 | 2008 | 9 | Wisley | 20
2008-09-26 | 2008 | 9 | Wisley | 19.6
2008-09-27 | 2008 | 9 | Wisley | 19.6
2008-09-28 | 2008 | 9 | Wisley | 17
2008-09-29 | 2008 | 9 | Wisley | 15.5
2008-09-30 | 2008 | 9 | Wisley | 15.6
2009-05-31 | 2009 | 5 | Wisley | 26
2009-06-01 | 2009 | 6 | Wisley | 25.9
2009-06-02 | 2009 | 6 | Wisley | 21.3
2009-06-03 | 2009 | 6 | Wisley | 19.4
2009-06-04 | 2009 | 6 | Wisley | 14.6
2009-06-05 | 2009 | 6 | Wisley | 14.4
2009-06-06 | 2009 | 6 | Wisley | 16.8
2009-06-07 | 2009 | 6 | Wisley | 16.8
2009-06-08 | 2009 | 6 | Wisley | 15.9
2009-06-09 | 2009 | 6 | Wisley | 16.9
2009-06-11 | 2009 | 6 | Wisley | 21.1
2009-06-12 | 2009 | 6 | Wisley | 23.5
2009-06-13 | 2009 | 6 | Wisley | 23.5
2009-06-14 | 2009 | 6 | Wisley | 24
2009-06-15 | 2009 | 6 | Wisley | 23.3
2009-06-16 | 2009 | 6 | Wisley | 22.2
2009-06-17 | 2009 | 6 | Wisley | 19.3
2009-06-18 | 2009 | 6 | Wisley | 19.8
2009-06-19 | 2009 | 6 | Wisley | 19.8
2009-06-20 | 2009 | 6 | Wisley | 21
2009-06-21 | 2009 | 6 | Wisley | 21.8
2009-06-22 | 2009 | 6 | Wisley | 24.1
2009-06-23 | 2009 | 6 | Wisley | 24.2
2009-06-24 | 2009 | 6 | Wisley | 26.9
2009-06-25 | 2009 | 6 | Wisley | 22.5
2009-06-26 | 2009 | 6 | Wisley | 26.8
2009-06-27 | 2009 | 6 | Wisley | 27.4
2009-06-28 | 2009 | 6 | Wisley | 31.3
2009-06-29 | 2009 | 6 | Wisley | 31.8
2009-06-30 | 2009 | 6 | Wisley | 30.8
2009-07-01 | 2009 | 7 | Wisley | 30.7
2009-07-02 | 2009 | 7 | Wisley | 26.3
2009-07-03 | 2009 | 7 | Wisley | 25
2009-07-04 | 2009 | 7 | Wisley | 24.6
2009-07-05 | 2009 | 7 | Wisley | 21.9
2009-07-06 | 2009 | 7 | Wisley | 19.6
2009-07-07 | 2009 | 7 | Wisley | 20.1
2009-07-08 | 2009 | 7 | Wisley | 19.2
2009-07-09 | 2009 | 7 | Wisley | 20.3
2009-07-10 | 2009 | 7 | Wisley | 19.2
2009-07-11 | 2009 | 7 | Wisley | 23.3
2009-07-12 | 2009 | 7 | Wisley | 22.7
2009-07-13 | 2009 | 7 | Wisley | 22.3
2009-07-14 | 2009 | 7 | Wisley | 21.8
2009-07-15 | 2009 | 7 | Wisley | 23.4
2009-07-16 | 2009 | 7 | Wisley | 19.8
2009-07-17 | 2009 | 7 | Wisley | 20.4
2009-07-18 | 2009 | 7 | Wisley | 20
2009-07-19 | 2009 | 7 | Wisley | 20.9
2009-07-20 | 2009 | 7 | Wisley | 22.1
2009-07-21 | 2009 | 7 | Wisley | 21.8
2009-07-22 | 2009 | 7 | Wisley | 22.3
2009-07-23 | 2009 | 7 | Wisley | 19.7
2009-07-24 | 2009 | 7 | Wisley | 23.3
2009-07-25 | 2009 | 7 | Wisley | 20.8
2009-07-26 | 2009 | 7 | Wisley | 20.1
2009-07-27 | 2009 | 7 | Wisley | 21.2
2009-07-28 | 2009 | 7 | Wisley | 21.4
2009-07-29 | 2009 | 7 | Wisley | 19.5
2009-07-30 | 2009 | 7 | Wisley | 21.5
2009-07-31 | 2009 | 7 | Wisley | 20.4
2009-08-01 | 2009 | 8 | Wisley | 21.1
2009-08-02 | 2009 | 8 | Wisley | 22.4
2009-08-03 | 2009 | 8 | Wisley | 23.5
2009-08-04 | 2009 | 8 | Wisley | 26.9
2009-08-05 | 2009 | 8 | Wisley | 23.8
2009-08-06 | 2009 | 8 | Wisley | 23
2009-08-07 | 2009 | 8 | Wisley | 25.5
2009-08-08 | 2009 | 8 | Wisley | 24.6
2009-08-09 | 2009 | 8 | Wisley | 21.7
2009-08-10 | 2009 | 8 | Wisley | 24.9
2009-08-11 | 2009 | 8 | Wisley | 22.5
2009-08-12 | 2009 | 8 | Wisley | 23.3
2009-08-13 | 2009 | 8 | Wisley | 24.2
2009-08-14 | 2009 | 8 | Wisley | 22.7
2009-08-15 | 2009 | 8 | Wisley | 25.1
2009-08-16 | 2009 | 8 | Wisley | 23.7
2009-08-17 | 2009 | 8 | Wisley | 24.6
2009-08-18 | 2009 | 8 | Wisley | 28.3
2009-08-19 | 2009 | 8 | Wisley | 23.1
2009-08-20 | 2009 | 8 | Wisley | 21.2
2009-08-21 | 2009 | 8 | Wisley | 22.3
2009-08-22 | 2009 | 8 | Wisley | 26.9
2009-08-23 | 2009 | 8 | Wisley | 24.5
2009-08-24 | 2009 | 8 | Wisley | 21.7
2009-08-25 | 2009 | 8 | Wisley | 22.4
2009-08-26 | 2009 | 8 | Wisley | 22.9
2009-08-27 | 2009 | 8 | Wisley | 19.5
2009-08-28 | 2009 | 8 | Wisley | 20.5
2009-08-29 | 2009 | 8 | Wisley | 19.1
2009-08-30 | 2009 | 8 | Wisley | 25.8
2009-08-31 | 2009 | 8 | Wisley | 21.5
2009-09-01 | 2009 | 9 | Wisley | 19.7
2009-09-02 | 2009 | 9 | Wisley | 18.5
2009-09-03 | 2009 | 9 | Wisley | 19.3
2009-09-04 | 2009 | 9 | Wisley | 19.4
2009-09-05 | 2009 | 9 | Wisley | 20.1
2009-09-06 | 2009 | 9 | Wisley | 21.3
2009-09-07 | 2009 | 9 | Wisley | 27.5
2009-09-08 | 2009 | 9 | Wisley | 19.6
2009-09-10 | 2009 | 9 | Wisley | 20.8
2009-09-11 | 2009 | 9 | Wisley | 22.3
2009-09-12 | 2009 | 9 | Wisley | 17.5
2009-09-13 | 2009 | 9 | Wisley | 20
2009-09-15 | 2009 | 9 | Wisley | 19.6
2009-09-16 | 2009 | 9 | Wisley | 16.9
2009-09-17 | 2009 | 9 | Wisley | 20.4
2009-09-18 | 2009 | 9 | Wisley | 24.1
2009-09-19 | 2009 | 9 | Wisley | 20.6
2009-09-20 | 2009 | 9 | Wisley | 21.4
2009-09-21 | 2009 | 9 | Wisley | 20.5
2009-09-22 | 2009 | 9 | Wisley | 18.1
2009-09-23 | 2009 | 9 | Wisley | 19.6
2009-09-24 | 2009 | 9 | Wisley | 19.9
2009-09-25 | 2009 | 9 | Wisley | 19.1
2009-09-26 | 2009 | 9 | Wisley | 20.9
2009-09-27 | 2009 | 9 | Wisley | 19.3
2009-09-28 | 2009 | 9 | Wisley | 21.5
2009-09-29 | 2009 | 9 | Wisley | 18.8
2009-09-30 | 2009 | 9 | Wisley | 17.5
2010-05-02 | 2010 | 5 | Wisley | 11.8
2010-05-03 | 2010 | 5 | Wisley | 12.2
2010-05-04 | 2010 | 5 | Wisley | 15.9
2010-05-05 | 2010 | 5 | Wisley | 15.6
2010-05-06 | 2010 | 5 | Wisley | 13.5
2010-05-08 | 2010 | 5 | Wisley | 11.1
2010-05-09 | 2010 | 5 | Wisley | 14
2010-05-10 | 2010 | 5 | Wisley | 10.8
2010-05-11 | 2010 | 5 | Wisley | 12.7
2010-05-12 | 2010 | 5 | Wisley | 13.8
2010-05-13 | 2010 | 5 | Wisley | 15.1
2010-05-14 | 2010 | 5 | Wisley | 18
2010-05-15 | 2010 | 5 | Wisley | 15.1
2010-05-16 | 2010 | 5 | Wisley | 18.3
2010-05-17 | 2010 | 5 | Wisley | 18.7
2010-05-18 | 2010 | 5 | Wisley | 20.9
2010-05-19 | 2010 | 5 | Wisley | 22
2010-05-20 | 2010 | 5 | Wisley | 25
2010-05-21 | 2010 | 5 | Wisley | 24.5
2010-05-22 | 2010 | 5 | Wisley | 28
2010-05-23 | 2010 | 5 | Wisley | 28.4
2010-05-24 | 2010 | 5 | Wisley | 20.3
2010-05-26 | 2010 | 5 | Wisley | 17.4
2010-05-27 | 2010 | 5 | Wisley | 19.6
2010-05-28 | 2010 | 5 | Wisley | 15.7
2010-05-29 | 2010 | 5 | Wisley | 19.5
2010-05-30 | 2010 | 5 | Wisley | 16.4
2010-05-31 | 2010 | 5 | Wisley | 15.7
2010-06-01 | 2010 | 6 | Wisley | 22.8
2010-06-02 | 2010 | 6 | Wisley | 22.9
2010-06-03 | 2010 | 6 | Wisley | 27.7
2010-06-04 | 2010 | 6 | Wisley | 27.6
2010-06-05 | 2010 | 6 | Wisley | 23.4
2010-06-07 | 2010 | 6 | Wisley | 19.9
2010-06-08 | 2010 | 6 | Wisley | 21.7
2010-06-09 | 2010 | 6 | Wisley | 18.4
2010-06-10 | 2010 | 6 | Wisley | 20.5
2010-06-11 | 2010 | 6 | Wisley | 20.4
2010-06-12 | 2010 | 6 | Wisley | 21.1
2010-06-13 | 2010 | 6 | Wisley | 21
2010-06-14 | 2010 | 6 | Wisley | 18.6
2010-06-15 | 2010 | 6 | Wisley | 20.3
2010-06-16 | 2010 | 6 | Wisley | 23.7
2010-06-17 | 2010 | 6 | Wisley | 20.5
2010-06-19 | 2010 | 6 | Wisley | 19.7
2010-06-20 | 2010 | 6 | Wisley | 23.6
2010-06-21 | 2010 | 6 | Wisley | 27
2010-06-22 | 2010 | 6 | Wisley | 27.6
2010-06-23 | 2010 | 6 | Wisley | 26
2010-06-24 | 2010 | 6 | Wisley | 27.1
2010-06-25 | 2010 | 6 | Wisley | 28
2010-06-26 | 2010 | 6 | Wisley | 30.5
2010-06-27 | 2010 | 6 | Wisley | 28.9
2010-06-28 | 2010 | 6 | Wisley | 27.3
2010-06-29 | 2010 | 6 | Wisley | 26.1
2010-06-30 | 2010 | 6 | Wisley | 25.9
2010-07-01 | 2010 | 7 | Wisley | 26.2
2010-07-02 | 2010 | 7 | Wisley | 26.1
2010-07-03 | 2010 | 7 | Wisley | 23.6
2010-07-04 | 2010 | 7 | Wisley | 24
2010-07-05 | 2010 | 7 | Wisley | 23.2
2010-07-06 | 2010 | 7 | Wisley | 22.7
2010-07-07 | 2010 | 7 | Wisley | 26.6
2010-07-08 | 2010 | 7 | Wisley | 30.7
2010-07-09 | 2010 | 7 | Wisley | 28.7
2010-07-10 | 2010 | 7 | Wisley | 27.8
2010-07-11 | 2010 | 7 | Wisley | 23.2
2010-07-13 | 2010 | 7 | Wisley | 21.3
2010-07-14 | 2010 | 7 | Wisley | 20.1
2010-07-15 | 2010 | 7 | Wisley | 21.1
2010-07-16 | 2010 | 7 | Wisley | 21.6
2010-07-17 | 2010 | 7 | Wisley | 24.1
2010-07-18 | 2010 | 7 | Wisley | 28.4
2010-07-19 | 2010 | 7 | Wisley | 28.1
2010-07-20 | 2010 | 7 | Wisley | 24.7
2010-07-21 | 2010 | 7 | Wisley | 22.3
2010-07-22 | 2010 | 7 | Wisley | 21.6
2010-07-23 | 2010 | 7 | Wisley | 24.9
2010-07-24 | 2010 | 7 | Wisley | 26.7
2010-07-25 | 2010 | 7 | Wisley | 24
2010-07-26 | 2010 | 7 | Wisley | 25
2010-07-27 | 2010 | 7 | Wisley | 24.2
2010-07-28 | 2010 | 7 | Wisley | 22.2
2010-07-29 | 2010 | 7 | Wisley | 22.5
2010-07-30 | 2010 | 7 | Wisley | 24.1
2010-07-31 | 2010 | 7 | Wisley | 23.9
2010-08-01 | 2010 | 8 | Wisley | 23.3
2010-08-02 | 2010 | 8 | Wisley | 22
2010-08-03 | 2010 | 8 | Wisley | 21.7
2010-08-04 | 2010 | 8 | Wisley | 21.8
2010-08-05 | 2010 | 8 | Wisley | 20.4
2010-08-06 | 2010 | 8 | Wisley | 21.2
2010-08-07 | 2010 | 8 | Wisley | 24.1
2010-08-08 | 2010 | 8 | Wisley | 24.1
2010-08-09 | 2010 | 8 | Wisley | 18.9
2010-08-10 | 2010 | 8 | Wisley | 21.7
2010-08-11 | 2010 | 8 | Wisley | 20.2
2010-08-12 | 2010 | 8 | Wisley | 17.1
2010-08-13 | 2010 | 8 | Wisley | 18.3
2010-08-14 | 2010 | 8 | Wisley | 22.6
2010-08-15 | 2010 | 8 | Wisley | 24.5
2010-08-16 | 2010 | 8 | Wisley | 20
2010-08-17 | 2010 | 8 | Wisley | 21.9
2010-08-18 | 2010 | 8 | Wisley | 21.5
2010-08-19 | 2010 | 8 | Wisley | 21.9
2010-08-20 | 2010 | 8 | Wisley | 21.9
2010-08-21 | 2010 | 8 | Wisley | 21.3
2010-08-22 | 2010 | 8 | Wisley | 21.2
2010-08-23 | 2010 | 8 | Wisley | 20
2010-08-24 | 2010 | 8 | Wisley | 18.6
2010-08-25 | 2010 | 8 | Wisley | 21.1
2010-08-26 | 2010 | 8 | Wisley | 18.2
2010-08-27 | 2010 | 8 | Wisley | 20.2
2010-08-28 | 2010 | 8 | Wisley | 18.6
2010-08-29 | 2010 | 8 | Wisley | 19.4
2010-08-30 | 2010 | 8 | Wisley | 20.2
2010-08-31 | 2010 | 8 | Wisley | 21.1
2010-09-01 | 2010 | 9 | Wisley | 21.6
2010-09-02 | 2010 | 9 | Wisley | 22.1
2010-09-03 | 2010 | 9 | Wisley | 21.5
2010-09-04 | 2010 | 9 | Wisley | 20.3
2010-09-05 | 2010 | 9 | Wisley | 19.8
2010-09-06 | 2010 | 9 | Wisley | 19.8
2010-09-07 | 2010 | 9 | Wisley | 19.7
2010-09-08 | 2010 | 9 | Wisley | 21.9
2010-09-09 | 2010 | 9 | Wisley | 21.1
2010-09-10 | 2010 | 9 | Wisley | 21.4
2010-09-11 | 2010 | 9 | Wisley | 20.2
2010-09-12 | 2010 | 9 | Wisley | 18.4
2010-09-13 | 2010 | 9 | Wisley | 19.5
2010-09-14 | 2010 | 9 | Wisley | 17.2
2010-09-15 | 2010 | 9 | Wisley | 17.9
2010-09-16 | 2010 | 9 | Wisley | 16.1
2010-09-17 | 2010 | 9 | Wisley | 17.7
2010-09-18 | 2010 | 9 | Wisley | 18.3
2010-09-19 | 2010 | 9 | Wisley | 21.5
2010-09-20 | 2010 | 9 | Wisley | 22
2010-09-21 | 2010 | 9 | Wisley | 23.1
2010-09-22 | 2010 | 9 | Wisley | 17.6
2010-09-25 | 2010 | 9 | Wisley | 13
2010-09-26 | 2010 | 9 | Wisley | 15.9
2010-09-27 | 2010 | 9 | Wisley | 17.1
2010-09-28 | 2010 | 9 | Wisley | 17.2
2010-09-29 | 2010 | 9 | Wisley | 16.2
2010-09-30 | 2010 | 9 | Wisley | 16.1
2011-05-01 | 2011 | 5 | Wisley | 16.5
2011-05-02 | 2011 | 5 | Wisley | 15.3
2011-05-03 | 2011 | 5 | Wisley | 18.3
2011-05-04 | 2011 | 5 | Wisley | 20.3
2011-05-05 | 2011 | 5 | Wisley | 24.5
2011-05-06 | 2011 | 5 | Wisley | 22.4
2011-05-07 | 2011 | 5 | Wisley | 19.3
2011-05-08 | 2011 | 5 | Wisley | 19.5
2011-05-09 | 2011 | 5 | Wisley | 20.7
2011-05-10 | 2011 | 5 | Wisley | 17.6
2011-05-11 | 2011 | 5 | Wisley | 18.2
2011-05-12 | 2011 | 5 | Wisley | 18.7
2011-05-13 | 2011 | 5 | Wisley | 17.3
2011-05-14 | 2011 | 5 | Wisley | 15.5
2011-05-15 | 2011 | 5 | Wisley | 18.6
2011-05-16 | 2011 | 5 | Wisley | 18.3
2011-05-17 | 2011 | 5 | Wisley | 19.4
2011-05-18 | 2011 | 5 | Wisley | 20.6
2011-05-19 | 2011 | 5 | Wisley | 18.8
2011-05-20 | 2011 | 5 | Wisley | 20.7
2011-05-21 | 2011 | 5 | Wisley | 18.5
2011-05-22 | 2011 | 5 | Wisley | 18.7
2011-05-23 | 2011 | 5 | Wisley | 18.9
2011-05-24 | 2011 | 5 | Wisley | 19.5
2011-05-25 | 2011 | 5 | Wisley | 17.9
2011-05-26 | 2011 | 5 | Wisley | 16.1
2011-05-27 | 2011 | 5 | Wisley | 16.5
2011-05-28 | 2011 | 5 | Wisley | 18.7
2011-05-29 | 2011 | 5 | Wisley | 20.8
2011-05-30 | 2011 | 5 | Wisley | 18.2
2011-05-31 | 2011 | 5 | Wisley | 21.2
2011-06-01 | 2011 | 6 | Wisley | 24
2011-06-02 | 2011 | 6 | Wisley | 25.3
2011-06-03 | 2011 | 6 | Wisley | 27.4
2011-06-06 | 2011 | 6 | Wisley | 19
2011-06-07 | 2011 | 6 | Wisley | 18.2
2011-06-08 | 2011 | 6 | Wisley | 17.5
2011-06-09 | 2011 | 6 | Wisley | 16.2
2011-06-10 | 2011 | 6 | Wisley | 18.7
2011-06-11 | 2011 | 6 | Wisley | 17.2
2011-06-12 | 2011 | 6 | Wisley | 22.3
2011-06-13 | 2011 | 6 | Wisley | 22.3
2011-06-14 | 2011 | 6 | Wisley | 20.4
2011-06-15 | 2011 | 6 | Wisley | 18.2
2011-06-17 | 2011 | 6 | Wisley | 17.4
2011-06-18 | 2011 | 6 | Wisley | 18.8
2011-06-19 | 2011 | 6 | Wisley | 20
2011-06-20 | 2011 | 6 | Wisley | 20.4
2011-06-21 | 2011 | 6 | Wisley | 17
2011-06-22 | 2011 | 6 | Wisley | 19
2011-06-23 | 2011 | 6 | Wisley | 19.7
2011-06-24 | 2011 | 6 | Wisley | 23.7
2011-06-25 | 2011 | 6 | Wisley | 27.7
2011-06-26 | 2011 | 6 | Wisley | 31.1
2011-06-29 | 2011 | 6 | Wisley | 19.5
2011-06-30 | 2011 | 6 | Wisley | 20.5
2011-07-01 | 2011 | 7 | Wisley | 22.2
2011-07-02 | 2011 | 7 | Wisley | 23.8
2011-07-03 | 2011 | 7 | Wisley | 25.4
2011-07-04 | 2011 | 7 | Wisley | 25.6
2011-07-05 | 2011 | 7 | Wisley | 19.6
2011-07-06 | 2011 | 7 | Wisley | 18.8
2011-07-07 | 2011 | 7 | Wisley | 17.8
2011-07-08 | 2011 | 7 | Wisley | 20.4
2011-07-09 | 2011 | 7 | Wisley | 21.5
2011-07-10 | 2011 | 7 | Wisley | 23.8
2011-07-11 | 2011 | 7 | Wisley | 19.3
2011-07-13 | 2011 | 7 | Wisley | 22.7
2011-07-14 | 2011 | 7 | Wisley | 23.6
2011-07-15 | 2011 | 7 | Wisley | 19.4
2011-07-17 | 2011 | 7 | Wisley | 18.1
2011-07-18 | 2011 | 7 | Wisley | 19.9
2011-07-19 | 2011 | 7 | Wisley | 18.4
2011-07-20 | 2011 | 7 | Wisley | 19.1
2011-07-21 | 2011 | 7 | Wisley | 20.5
2011-07-22 | 2011 | 7 | Wisley | 18.6
2011-07-23 | 2011 | 7 | Wisley | 22.7
2011-07-24 | 2011 | 7 | Wisley | 23.8
2011-07-25 | 2011 | 7 | Wisley | 20.2
2011-07-26 | 2011 | 7 | Wisley | 20.2
2011-07-27 | 2011 | 7 | Wisley | 24.5
2011-07-28 | 2011 | 7 | Wisley | 21.6
2011-07-29 | 2011 | 7 | Wisley | 22.2
2011-07-30 | 2011 | 7 | Wisley | 24.3
2011-07-31 | 2011 | 7 | Wisley | 27.6
2011-08-01 | 2011 | 8 | Wisley | 27.8
2011-08-02 | 2011 | 8 | Wisley | 29.3
2011-08-03 | 2011 | 8 | Wisley | 21.4
2011-08-04 | 2011 | 8 | Wisley | 24.8
2011-08-05 | 2011 | 8 | Wisley | 19.3
2011-08-06 | 2011 | 8 | Wisley | 21.1
2011-08-07 | 2011 | 8 | Wisley | 20.1
2011-08-08 | 2011 | 8 | Wisley | 20.7
2011-08-09 | 2011 | 8 | Wisley | 22.2
2011-08-10 | 2011 | 8 | Wisley | 22
2011-08-11 | 2011 | 8 | Wisley | 23.5
2011-08-12 | 2011 | 8 | Wisley | 22.4
2011-08-13 | 2011 | 8 | Wisley | 22.7
2011-08-14 | 2011 | 8 | Wisley | 21.5
2011-08-15 | 2011 | 8 | Wisley | 21
2011-08-16 | 2011 | 8 | Wisley | 19.9
2011-08-17 | 2011 | 8 | Wisley | 16.7
2011-08-18 | 2011 | 8 | Wisley | 21.9
2011-08-19 | 2011 | 8 | Wisley | 21.8
2011-08-20 | 2011 | 8 | Wisley | 23.2
2011-08-21 | 2011 | 8 | Wisley | 22.4
2011-08-23 | 2011 | 8 | Wisley | 20.9
2011-08-24 | 2011 | 8 | Wisley | 20.3
2011-08-25 | 2011 | 8 | Wisley | 18.3
2011-08-26 | 2011 | 8 | Wisley | 19.5
2011-08-27 | 2011 | 8 | Wisley | 19.7
2011-08-28 | 2011 | 8 | Wisley | 18.3
2011-08-29 | 2011 | 8 | Wisley | 16.9
2011-08-30 | 2011 | 8 | Wisley | 18.8
2011-08-31 | 2011 | 8 | Wisley | 22
2011-09-01 | 2011 | 9 | Wisley | 26.6
2011-09-02 | 2011 | 9 | Wisley | 22.8
2011-09-04 | 2011 | 9 | Wisley | 19.5
2011-09-05 | 2011 | 9 | Wisley | 17.9
2011-09-06 | 2011 | 9 | Wisley | 16.9
2011-09-07 | 2011 | 9 | Wisley | 20.2
2011-09-08 | 2011 | 9 | Wisley | 21.3
2011-09-09 | 2011 | 9 | Wisley | 23.2
2011-09-10 | 2011 | 9 | Wisley | 20.6
2011-09-11 | 2011 | 9 | Wisley | 21.1
2011-09-12 | 2011 | 9 | Wisley | 18.5
2011-09-13 | 2011 | 9 | Wisley | 19.2
2011-09-14 | 2011 | 9 | Wisley | 20.2
2011-09-15 | 2011 | 9 | Wisley | 22.1
2011-09-16 | 2011 | 9 | Wisley | 19
2011-09-18 | 2011 | 9 | Wisley | 18.3
2011-09-19 | 2011 | 9 | Wisley | 18
2011-09-20 | 2011 | 9 | Wisley | 18
2011-09-21 | 2011 | 9 | Wisley | 18.9
2011-09-22 | 2011 | 9 | Wisley | 18.7
2011-09-23 | 2011 | 9 | Wisley | 20.7
2011-09-24 | 2011 | 9 | Wisley | 21.2
2011-09-25 | 2011 | 9 | Wisley | 22.7
2011-09-26 | 2011 | 9 | Wisley | 22.3
2011-09-27 | 2011 | 9 | Wisley | 25.9
2011-09-28 | 2011 | 9 | Wisley | 27.6
2011-09-29 | 2011 | 9 | Wisley | 28.1
2011-09-30 | 2011 | 9 | Wisley | 28.7
2012-05-04 | 2012 | 5 | Wisley | 9.6
2012-05-05 | 2012 | 5 | Wisley | 10.1
2012-05-06 | 2012 | 5 | Wisley | 15.1
2012-05-07 | 2012 | 5 | Wisley | 17.9
2012-05-08 | 2012 | 5 | Wisley | 15.7
2012-05-09 | 2012 | 5 | Wisley | 17
2012-05-10 | 2012 | 5 | Wisley | 16.1
2012-05-11 | 2012 | 5 | Wisley | 15.4
2012-05-12 | 2012 | 5 | Wisley | 17.3
2012-05-13 | 2012 | 5 | Wisley | 11.8
2012-05-14 | 2012 | 5 | Wisley | 12.7
2012-05-15 | 2012 | 5 | Wisley | 14.9
2012-05-16 | 2012 | 5 | Wisley | 15.6
2012-05-17 | 2012 | 5 | Wisley | 15.4
2012-05-18 | 2012 | 5 | Wisley | 18.1
2012-05-20 | 2012 | 5 | Wisley | 18
2012-05-21 | 2012 | 5 | Wisley | 25.5
2012-05-22 | 2012 | 5 | Wisley | 27.1
2012-05-23 | 2012 | 5 | Wisley | 27.5
2012-05-24 | 2012 | 5 | Wisley | 26.1
2012-05-25 | 2012 | 5 | Wisley | 25.7
2012-05-26 | 2012 | 5 | Wisley | 27.7
2012-05-27 | 2012 | 5 | Wisley | 26.5
2012-05-28 | 2012 | 5 | Wisley | 24.7
2012-05-29 | 2012 | 5 | Wisley | 25.2
2012-05-30 | 2012 | 5 | Wisley | 19.4
2012-05-31 | 2012 | 5 | Wisley | 21.7
2012-06-01 | 2012 | 6 | Wisley | 19.9
2012-06-04 | 2012 | 6 | Wisley | 16.8
2012-06-05 | 2012 | 6 | Wisley | 18.8
2012-06-06 | 2012 | 6 | Wisley | 17.3
2012-06-07 | 2012 | 6 | Wisley | 15.7
2012-06-08 | 2012 | 6 | Wisley | 18.9
2012-06-09 | 2012 | 6 | Wisley | 16.4
2012-06-10 | 2012 | 6 | Wisley | 12.7
2012-06-11 | 2012 | 6 | Wisley | 14.9
2012-06-12 | 2012 | 6 | Wisley | 19.1
2012-06-13 | 2012 | 6 | Wisley | 18.1
2012-06-14 | 2012 | 6 | Wisley | 18.1
2012-06-15 | 2012 | 6 | Wisley | 17.9
2012-06-16 | 2012 | 6 | Wisley | 20.2
2012-06-17 | 2012 | 6 | Wisley | 19.7
2012-06-18 | 2012 | 6 | Wisley | 21.6
2012-06-19 | 2012 | 6 | Wisley | 22.7
2012-06-20 | 2012 | 6 | Wisley | 20.3
2012-06-22 | 2012 | 6 | Wisley | 19.4
2012-06-23 | 2012 | 6 | Wisley | 20.7
2012-06-24 | 2012 | 6 | Wisley | 21.9
2012-06-25 | 2012 | 6 | Wisley | 22.1
2012-06-26 | 2012 | 6 | Wisley | 22
2012-06-27 | 2012 | 6 | Wisley | 26.8
2012-06-28 | 2012 | 6 | Wisley | 20.6
2012-06-29 | 2012 | 6 | Wisley | 19.9
2012-06-30 | 2012 | 6 | Wisley | 18.1
2012-07-01 | 2012 | 7 | Wisley | 17.7
2012-07-02 | 2012 | 7 | Wisley | 18.4
2012-07-03 | 2012 | 7 | Wisley | 21.3
2012-07-04 | 2012 | 7 | Wisley | 21.8
2012-07-05 | 2012 | 7 | Wisley | 19.9
2012-07-06 | 2012 | 7 | Wisley | 18.1
2012-07-07 | 2012 | 7 | Wisley | 21
2012-07-08 | 2012 | 7 | Wisley | 18.8
2012-07-09 | 2012 | 7 | Wisley | 19.1
2012-07-10 | 2012 | 7 | Wisley | 20
2012-07-11 | 2012 | 7 | Wisley | 19.1
2012-07-12 | 2012 | 7 | Wisley | 19.8
2012-07-13 | 2012 | 7 | Wisley | 17.9
2012-07-14 | 2012 | 7 | Wisley | 19.2
2012-07-15 | 2012 | 7 | Wisley | 18.7
2012-07-16 | 2012 | 7 | Wisley | 22.8
2012-07-17 | 2012 | 7 | Wisley | 18.7
2012-07-18 | 2012 | 7 | Wisley | 20.3
2012-07-19 | 2012 | 7 | Wisley | 19.8
2012-07-20 | 2012 | 7 | Wisley | 20
2012-07-21 | 2012 | 7 | Wisley | 22.7
2012-07-22 | 2012 | 7 | Wisley | 26.8
2012-07-23 | 2012 | 7 | Wisley | 29.1
2012-07-24 | 2012 | 7 | Wisley | 30.3
2012-07-25 | 2012 | 7 | Wisley | 28.1
2012-07-26 | 2012 | 7 | Wisley | 24.2
2012-07-27 | 2012 | 7 | Wisley | 21.8
2012-07-28 | 2012 | 7 | Wisley | 19.5
2012-07-29 | 2012 | 7 | Wisley | 20.3
2012-07-30 | 2012 | 7 | Wisley | 20.7
2012-07-31 | 2012 | 7 | Wisley | 23
2012-08-01 | 2012 | 8 | Wisley | 21.2
2012-08-02 | 2012 | 8 | Wisley | 21.9
2012-08-03 | 2012 | 8 | Wisley | 20.9
2012-08-04 | 2012 | 8 | Wisley | 21.6
2012-08-05 | 2012 | 8 | Wisley | 22
2012-08-06 | 2012 | 8 | Wisley | 20
2012-08-07 | 2012 | 8 | Wisley | 23.5
2012-08-08 | 2012 | 8 | Wisley | 26.4
2012-08-09 | 2012 | 8 | Wisley | 27.1
2012-08-10 | 2012 | 8 | Wisley | 23.6
2012-08-11 | 2012 | 8 | Wisley | 26.2
2012-08-12 | 2012 | 8 | Wisley | 23.2
2012-08-13 | 2012 | 8 | Wisley | 24.5
2012-08-14 | 2012 | 8 | Wisley | 22.8
2012-08-15 | 2012 | 8 | Wisley | 21.3
2012-08-16 | 2012 | 8 | Wisley | 27.6
2012-08-17 | 2012 | 8 | Wisley | 29.7
2012-08-18 | 2012 | 8 | Wisley | 29.9
2012-08-19 | 2012 | 8 | Wisley | 25.2
2012-08-20 | 2012 | 8 | Wisley | 22.6
2012-08-21 | 2012 | 8 | Wisley | 22.7
2012-08-22 | 2012 | 8 | Wisley | 21.9
2012-08-23 | 2012 | 8 | Wisley | 20.6
2012-08-24 | 2012 | 8 | Wisley | 22.5
2012-08-25 | 2012 | 8 | Wisley | 21.4
2012-08-26 | 2012 | 8 | Wisley | 21.3
2012-08-27 | 2012 | 8 | Wisley | 23.1
2012-08-28 | 2012 | 8 | Wisley | 20.4
2012-08-29 | 2012 | 8 | Wisley | 18.9
2012-08-30 | 2012 | 8 | Wisley | 18.6
2012-08-31 | 2012 | 8 | Wisley | 22.6
2012-09-01 | 2012 | 9 | Wisley | 18.6
2012-09-02 | 2012 | 9 | Wisley | 24.7
2012-09-03 | 2012 | 9 | Wisley | 25.3
2012-09-04 | 2012 | 9 | Wisley | 20.8
2012-09-05 | 2012 | 9 | Wisley | 21.9
2012-09-06 | 2012 | 9 | Wisley | 26.4
2012-09-07 | 2012 | 9 | Wisley | 27.3
2012-09-08 | 2012 | 9 | Wisley | 27.9
2012-09-09 | 2012 | 9 | Wisley | 20.9
2012-09-11 | 2012 | 9 | Wisley | 19.7
2012-09-12 | 2012 | 9 | Wisley | 19.6
2012-09-13 | 2012 | 9 | Wisley | 21.7
2012-09-14 | 2012 | 9 | Wisley | 22.5
2012-09-15 | 2012 | 9 | Wisley | 19
2012-09-16 | 2012 | 9 | Wisley | 19.1
2012-09-17 | 2012 | 9 | Wisley | 17.9
2012-09-18 | 2012 | 9 | Wisley | 17.2
2012-09-19 | 2012 | 9 | Wisley | 18.8
2012-09-20 | 2012 | 9 | Wisley | 16.8
2012-09-21 | 2012 | 9 | Wisley | 16.3
2012-09-22 | 2012 | 9 | Wisley | 15.3
2012-09-23 | 2012 | 9 | Wisley | 16.3
2012-09-24 | 2012 | 9 | Wisley | 16.2
2012-09-25 | 2012 | 9 | Wisley | 15.8
2012-09-26 | 2012 | 9 | Wisley | 17.3
2012-09-27 | 2012 | 9 | Wisley | 18.2
2012-09-28 | 2012 | 9 | Wisley | 16.9
2012-09-29 | 2012 | 9 | Wisley | 17.2
2012-09-30 | 2012 | 9 | Wisley | 17
2013-05-01 | 2013 | 5 | Wisley | 18.3
2013-05-02 | 2013 | 5 | Wisley | 19.9
2013-05-03 | 2013 | 5 | Wisley | 17.4
2013-05-04 | 2013 | 5 | Wisley | 18.6
2013-05-05 | 2013 | 5 | Wisley | 21.7
2013-05-06 | 2013 | 5 | Wisley | 23.1
2013-05-07 | 2013 | 5 | Wisley | 17.3
2013-05-09 | 2013 | 5 | Wisley | 17.8
2013-05-10 | 2013 | 5 | Wisley | 13.7
2013-05-11 | 2013 | 5 | Wisley | 15.7
2013-05-12 | 2013 | 5 | Wisley | 15.1
2013-05-14 | 2013 | 5 | Wisley | 14.8
2013-05-15 | 2013 | 5 | Wisley | 17
2013-05-16 | 2013 | 5 | Wisley | 12.7
2013-05-17 | 2013 | 5 | Wisley | 15.7
2013-05-18 | 2013 | 5 | Wisley | 19
2013-05-19 | 2013 | 5 | Wisley | 16.7
2013-05-21 | 2013 | 5 | Wisley | 14.9
2013-05-22 | 2013 | 5 | Wisley | 12.6
2013-05-23 | 2013 | 5 | Wisley | 10.7
2013-05-24 | 2013 | 5 | Wisley | 15.8
2013-05-25 | 2013 | 5 | Wisley | 19.4
2013-05-26 | 2013 | 5 | Wisley | 17.1
2013-05-27 | 2013 | 5 | Wisley | 12.7
2013-05-28 | 2013 | 5 | Wisley | 13.7
2013-05-29 | 2013 | 5 | Wisley | 15.7
2013-05-30 | 2013 | 5 | Wisley | 21.7
2013-05-31 | 2013 | 5 | Wisley | 18.9
2013-06-01 | 2013 | 6 | Wisley | 18.7
2013-06-02 | 2013 | 6 | Wisley | 19.1
2013-06-03 | 2013 | 6 | Wisley | 21.1
2013-06-04 | 2013 | 6 | Wisley | 21.6
2013-06-05 | 2013 | 6 | Wisley | 22.6
2013-06-06 | 2013 | 6 | Wisley | 21.1
2013-06-07 | 2013 | 6 | Wisley | 18.4
2013-06-08 | 2013 | 6 | Wisley | 14.9
2013-06-09 | 2013 | 6 | Wisley | 16.1
2013-06-10 | 2013 | 6 | Wisley | 16.8
2013-06-11 | 2013 | 6 | Wisley | 16.9
2013-06-12 | 2013 | 6 | Wisley | 17.7
2013-06-13 | 2013 | 6 | Wisley | 18.8
2013-06-14 | 2013 | 6 | Wisley | 16.8
2013-06-15 | 2013 | 6 | Wisley | 17.6
2013-06-16 | 2013 | 6 | Wisley | 21.1
2013-06-17 | 2013 | 6 | Wisley | 21.1
2013-06-18 | 2013 | 6 | Wisley | 26
2013-06-19 | 2013 | 6 | Wisley | 20.1
2013-06-20 | 2013 | 6 | Wisley | 21.7
2013-06-21 | 2013 | 6 | Wisley | 18.1
2013-06-22 | 2013 | 6 | Wisley | 17.3
2013-06-23 | 2013 | 6 | Wisley | 16.9
2013-06-24 | 2013 | 6 | Wisley | 20
2013-06-25 | 2013 | 6 | Wisley | 21
2013-06-26 | 2013 | 6 | Wisley | 19.7
2013-06-27 | 2013 | 6 | Wisley | 21.7
2013-06-28 | 2013 | 6 | Wisley | 22
2013-06-29 | 2013 | 6 | Wisley | 25.8
2013-06-30 | 2013 | 6 | Wisley | 20.7
2013-07-02 | 2013 | 7 | Wisley | 20.3
2013-07-03 | 2013 | 7 | Wisley | 23.3
2013-07-04 | 2013 | 7 | Wisley | 25.7
2013-07-05 | 2013 | 7 | Wisley | 27.3
2013-07-06 | 2013 | 7 | Wisley | 29.4
2013-07-07 | 2013 | 7 | Wisley | 27.6
2013-07-08 | 2013 | 7 | Wisley | 27
2013-07-09 | 2013 | 7 | Wisley | 25.1
2013-07-10 | 2013 | 7 | Wisley | 23.3
2013-07-11 | 2013 | 7 | Wisley | 25.3
2013-07-12 | 2013 | 7 | Wisley | 31.3
2013-07-13 | 2013 | 7 | Wisley | 29.5
2013-07-14 | 2013 | 7 | Wisley | 30.9
2013-07-15 | 2013 | 7 | Wisley | 30.9
2013-07-16 | 2013 | 7 | Wisley | 31.3
2013-07-17 | 2013 | 7 | Wisley | 29.4
2013-07-18 | 2013 | 7 | Wisley | 28.4
2013-07-19 | 2013 | 7 | Wisley | 24.3
2013-07-20 | 2013 | 7 | Wisley | 27.6
2013-07-21 | 2013 | 7 | Wisley | 33.1
2013-07-22 | 2013 | 7 | Wisley | 29.1
2013-07-23 | 2013 | 7 | Wisley | 27.3
2013-07-24 | 2013 | 7 | Wisley | 25.4
2013-07-25 | 2013 | 7 | Wisley | 27.1
2013-07-26 | 2013 | 7 | Wisley | 28.6
2013-07-27 | 2013 | 7 | Wisley | 23.7
2013-07-28 | 2013 | 7 | Wisley | 23
2013-07-29 | 2013 | 7 | Wisley | 21.3
2013-07-30 | 2013 | 7 | Wisley | 24.3
2013-07-31 | 2013 | 7 | Wisley | 32.5
2013-08-01 | 2013 | 8 | Wisley | 25.3
2013-08-03 | 2013 | 8 | Wisley | 23.6
2013-08-04 | 2013 | 8 | Wisley | 23.4
2013-08-05 | 2013 | 8 | Wisley | 23.7
2013-08-06 | 2013 | 8 | Wisley | 22.6
2013-08-07 | 2013 | 8 | Wisley | 24.7
2013-08-08 | 2013 | 8 | Wisley | 25
2013-08-09 | 2013 | 8 | Wisley | 22.3
2013-08-10 | 2013 | 8 | Wisley | 23.3
2013-08-11 | 2013 | 8 | Wisley | 21.6
2013-08-12 | 2013 | 8 | Wisley | 21.5
2013-08-13 | 2013 | 8 | Wisley | 23
2013-08-14 | 2013 | 8 | Wisley | 24.1
2013-08-15 | 2013 | 8 | Wisley | 22.1
2013-08-17 | 2013 | 8 | Wisley | 23.7
2013-08-18 | 2013 | 8 | Wisley | 23.1
2013-08-19 | 2013 | 8 | Wisley | 24.8
2013-08-20 | 2013 | 8 | Wisley | 26.2
2013-08-21 | 2013 | 8 | Wisley | 23.3
2013-08-22 | 2013 | 8 | Wisley | 27.4
2013-08-24 | 2013 | 8 | Wisley | 23.9
2013-08-25 | 2013 | 8 | Wisley | 25.4
2013-08-26 | 2013 | 8 | Wisley | 23.1
2013-08-27 | 2013 | 8 | Wisley | 24
2013-08-28 | 2013 | 8 | Wisley | 24.3
2013-08-29 | 2013 | 8 | Wisley | 24.8
2013-08-30 | 2013 | 8 | Wisley | 20.5
2013-08-31 | 2013 | 8 | Wisley | 21
2013-09-01 | 2013 | 9 | Wisley | 25.4
2013-09-02 | 2013 | 9 | Wisley | 25.5
2013-09-03 | 2013 | 9 | Wisley | 28.7
2013-09-04 | 2013 | 9 | Wisley | 28.8
2013-09-07 | 2013 | 9 | Wisley | 16.8
2013-09-08 | 2013 | 9 | Wisley | 14.9
2013-09-09 | 2013 | 9 | Wisley | 16.5
2013-09-10 | 2013 | 9 | Wisley | 16.7
2013-09-11 | 2013 | 9 | Wisley | 19.1
2013-09-12 | 2013 | 9 | Wisley | 20.2
2013-09-14 | 2013 | 9 | Wisley | 15.7
2013-09-15 | 2013 | 9 | Wisley | 15.4
2013-09-16 | 2013 | 9 | Wisley | 15.3
2013-09-17 | 2013 | 9 | Wisley | 15.7
2013-09-18 | 2013 | 9 | Wisley | 16.7
2013-09-19 | 2013 | 9 | Wisley | 19.1
2013-09-20 | 2013 | 9 | Wisley | 18.5
2013-09-21 | 2013 | 9 | Wisley | 19.5
2013-09-22 | 2013 | 9 | Wisley | 19.5
2013-09-23 | 2013 | 9 | Wisley | 22.2
2013-09-24 | 2013 | 9 | Wisley | 22.2
2013-09-25 | 2013 | 9 | Wisley | 19.2
2013-09-26 | 2013 | 9 | Wisley | 18
2013-09-27 | 2013 | 9 | Wisley | 18.3
2013-09-28 | 2013 | 9 | Wisley | 19.1
2013-09-29 | 2013 | 9 | Wisley | 18.9
2013-09-30 | 2013 | 9 | Wisley | 16.8
2014-05-02 | 2014 | 5 | Wisley | 14.6
2014-05-03 | 2014 | 5 | Wisley | 16.8
2014-05-04 | 2014 | 5 | Wisley | 18.6
2014-05-05 | 2014 | 5 | Wisley | 19.2
2014-05-06 | 2014 | 5 | Wisley | 16.5
2014-05-07 | 2014 | 5 | Wisley | 15.6
2014-05-08 | 2014 | 5 | Wisley | 17.4
2014-05-09 | 2014 | 5 | Wisley | 16.9
2014-05-10 | 2014 | 5 | Wisley | 15.3
2014-05-11 | 2014 | 5 | Wisley | 16.4
2014-05-12 | 2014 | 5 | Wisley | 16.6
2014-05-13 | 2014 | 5 | Wisley | 18.8
2014-05-14 | 2014 | 5 | Wisley | 21.1
2014-05-15 | 2014 | 5 | Wisley | 22.4
2014-05-16 | 2014 | 5 | Wisley | 23.4
2014-05-17 | 2014 | 5 | Wisley | 23.2
2014-05-18 | 2014 | 5 | Wisley | 25.4
2014-05-19 | 2014 | 5 | Wisley | 19.8
2014-05-21 | 2014 | 5 | Wisley | 17.8
2014-05-22 | 2014 | 5 | Wisley | 16
2014-05-23 | 2014 | 5 | Wisley | 16.5
2014-05-24 | 2014 | 5 | Wisley | 17.8
2014-05-25 | 2014 | 5 | Wisley | 13.1
2014-05-26 | 2014 | 5 | Wisley | 13.5
2014-05-27 | 2014 | 5 | Wisley | 15
2014-05-28 | 2014 | 5 | Wisley | 18.7
2014-05-29 | 2014 | 5 | Wisley | 16.1
2014-05-30 | 2014 | 5 | Wisley | 19.4
2014-05-31 | 2014 | 5 | Wisley | 22
2014-06-01 | 2014 | 6 | Wisley | 20.4
2014-06-02 | 2014 | 6 | Wisley | 20.8
2014-06-04 | 2014 | 6 | Wisley | 19.1
2014-06-05 | 2014 | 6 | Wisley | 23.2
2014-06-06 | 2014 | 6 | Wisley | 22.7
2014-06-07 | 2014 | 6 | Wisley | 24
2014-06-08 | 2014 | 6 | Wisley | 25.3
2014-06-09 | 2014 | 6 | Wisley | 22.1
2014-06-10 | 2014 | 6 | Wisley | 22.1
2014-06-11 | 2014 | 6 | Wisley | 25.3
2014-06-12 | 2014 | 6 | Wisley | 25
2014-06-13 | 2014 | 6 | Wisley | 22.2
2014-06-15 | 2014 | 6 | Wisley | 18
2014-06-16 | 2014 | 6 | Wisley | 21.3
2014-06-17 | 2014 | 6 | Wisley | 22.3
2014-06-18 | 2014 | 6 | Wisley | 21.5
2014-06-19 | 2014 | 6 | Wisley | 22.4
2014-06-20 | 2014 | 6 | Wisley | 23.4
2014-06-21 | 2014 | 6 | Wisley | 25.6
2014-06-22 | 2014 | 6 | Wisley | 25.9
2014-06-23 | 2014 | 6 | Wisley | 24.7
2014-06-24 | 2014 | 6 | Wisley | 21.2
2014-06-25 | 2014 | 6 | Wisley | 21.8
2014-06-26 | 2014 | 6 | Wisley | 22.6
2014-06-27 | 2014 | 6 | Wisley | 20
2014-06-28 | 2014 | 6 | Wisley | 19.7
2014-06-29 | 2014 | 6 | Wisley | 20
2014-06-30 | 2014 | 6 | Wisley | 22.6
2014-07-01 | 2014 | 7 | Wisley | 24
2014-07-02 | 2014 | 7 | Wisley | 25.3
2014-07-03 | 2014 | 7 | Wisley | 25.2
2014-07-04 | 2014 | 7 | Wisley | 20.6
2014-07-05 | 2014 | 7 | Wisley | 21
2014-07-06 | 2014 | 7 | Wisley | 21
2014-07-07 | 2014 | 7 | Wisley | 20.6
2014-07-08 | 2014 | 7 | Wisley | 22.3
2014-07-09 | 2014 | 7 | Wisley | 22
2014-07-10 | 2014 | 7 | Wisley | 19.9
2014-07-11 | 2014 | 7 | Wisley | 26.6
2014-07-12 | 2014 | 7 | Wisley | 24.1
2014-07-13 | 2014 | 7 | Wisley | 23.9
2014-07-14 | 2014 | 7 | Wisley | 26.1
2014-07-15 | 2014 | 7 | Wisley | 26.9
2014-07-16 | 2014 | 7 | Wisley | 28.5
2014-07-17 | 2014 | 7 | Wisley | 28.6
2014-07-18 | 2014 | 7 | Wisley | 26.8
2014-07-19 | 2014 | 7 | Wisley | 25.3
2014-07-20 | 2014 | 7 | Wisley | 25.8
2014-07-21 | 2014 | 7 | Wisley | 27.4
2014-07-22 | 2014 | 7 | Wisley | 28.7
2014-07-23 | 2014 | 7 | Wisley | 28.8
2014-07-24 | 2014 | 7 | Wisley | 26.9
2014-07-25 | 2014 | 7 | Wisley | 28.3
2014-07-26 | 2014 | 7 | Wisley | 24.9
2014-07-27 | 2014 | 7 | Wisley | 23.2
2014-07-28 | 2014 | 7 | Wisley | 26.5
2014-07-29 | 2014 | 7 | Wisley | 25.6
2014-07-30 | 2014 | 7 | Wisley | 25
2014-07-31 | 2014 | 7 | Wisley | 24.3
2014-08-01 | 2014 | 8 | Wisley | 23.2
2014-08-02 | 2014 | 8 | Wisley | 23.3
2014-08-03 | 2014 | 8 | Wisley | 23.8
2014-08-04 | 2014 | 8 | Wisley | 24
2014-08-05 | 2014 | 8 | Wisley | 25.4
2014-08-06 | 2014 | 8 | Wisley | 26.3
2014-08-07 | 2014 | 8 | Wisley | 24.1
2014-08-08 | 2014 | 8 | Wisley | 23.1
2014-08-09 | 2014 | 8 | Wisley | 22
2014-08-10 | 2014 | 8 | Wisley | 20.5
2014-08-11 | 2014 | 8 | Wisley | 20
2014-08-12 | 2014 | 8 | Wisley | 21.8
2014-08-13 | 2014 | 8 | Wisley | 22
2014-08-14 | 2014 | 8 | Wisley | 20.7
2014-08-15 | 2014 | 8 | Wisley | 21.4
2014-08-16 | 2014 | 8 | Wisley | 20.3
2014-08-17 | 2014 | 8 | Wisley | 20.5
2014-08-18 | 2014 | 8 | Wisley | 18.4
2014-08-19 | 2014 | 8 | Wisley | 18.1
2014-08-20 | 2014 | 8 | Wisley | 17.4
2014-08-21 | 2014 | 8 | Wisley | 20.3
2014-08-22 | 2014 | 8 | Wisley | 18.7
2014-08-23 | 2014 | 8 | Wisley | 19.3
2014-08-24 | 2014 | 8 | Wisley | 17.5
2014-08-25 | 2014 | 8 | Wisley | 17.1
2014-08-26 | 2014 | 8 | Wisley | 19.5
2014-08-27 | 2014 | 8 | Wisley | 22.3
2014-08-28 | 2014 | 8 | Wisley | 21
2014-08-29 | 2014 | 8 | Wisley | 20.2
2014-08-30 | 2014 | 8 | Wisley | 21.8
2014-08-31 | 2014 | 8 | Wisley | 18.8
2014-09-01 | 2014 | 9 | Wisley | 22.5
2014-09-02 | 2014 | 9 | Wisley | 23.1
2014-09-03 | 2014 | 9 | Wisley | 21.3
2014-09-04 | 2014 | 9 | Wisley | 20.5
2014-09-05 | 2014 | 9 | Wisley | 22.4
2014-09-06 | 2014 | 9 | Wisley | 21.5
2014-09-07 | 2014 | 9 | Wisley | 22.2
2014-09-08 | 2014 | 9 | Wisley | 22.2
2014-09-09 | 2014 | 9 | Wisley | 20.4
2014-09-10 | 2014 | 9 | Wisley | 18.4
2014-09-11 | 2014 | 9 | Wisley | 22.5
2014-09-12 | 2014 | 9 | Wisley | 22.1
2014-09-13 | 2014 | 9 | Wisley | 21.8
2014-09-14 | 2014 | 9 | Wisley | 22.2
2014-09-15 | 2014 | 9 | Wisley | 24.8
2014-09-16 | 2014 | 9 | Wisley | 20.9
2014-09-17 | 2014 | 9 | Wisley | 25.7
2014-09-18 | 2014 | 9 | Wisley | 24.3
2014-09-21 | 2014 | 9 | Wisley | 18.5
2014-09-22 | 2014 | 9 | Wisley | 18.8
2014-09-23 | 2014 | 9 | Wisley | 18.2
2014-09-24 | 2014 | 9 | Wisley | 20
2014-09-25 | 2014 | 9 | Wisley | 21
2014-09-26 | 2014 | 9 | Wisley | 21.1
2014-09-27 | 2014 | 9 | Wisley | 23.4
2014-09-28 | 2014 | 9 | Wisley | 18.6
2014-09-29 | 2014 | 9 | Wisley | 22.4
2014-09-30 | 2014 | 9 | Wisley | 20.1
2015-05-01 | 2015 | 5 | Wisley | 14.8
2015-05-02 | 2015 | 5 | Wisley | 19.5
2015-05-03 | 2015 | 5 | Wisley | 17.9
2015-05-04 | 2015 | 5 | Wisley | 15.5
2015-05-06 | 2015 | 5 | Wisley | 17.4
2015-05-07 | 2015 | 5 | Wisley | 18.1
2015-05-08 | 2015 | 5 | Wisley | 18.4
2015-05-09 | 2015 | 5 | Wisley | 18.7
2015-05-10 | 2015 | 5 | Wisley | 20.9
2015-05-11 | 2015 | 5 | Wisley | 18.2
2015-05-12 | 2015 | 5 | Wisley | 20.1
2015-05-13 | 2015 | 5 | Wisley | 11.4
2015-05-14 | 2015 | 5 | Wisley | 15.5
2015-05-15 | 2015 | 5 | Wisley | 18.4
2015-05-16 | 2015 | 5 | Wisley | 17.3
2015-05-17 | 2015 | 5 | Wisley | 15.6
2015-05-18 | 2015 | 5 | Wisley | 15.1
2015-05-19 | 2015 | 5 | Wisley | 15.7
2015-05-20 | 2015 | 5 | Wisley | 20
2015-05-21 | 2015 | 5 | Wisley | 18.8
2015-05-22 | 2015 | 5 | Wisley | 18.6
2015-05-23 | 2015 | 5 | Wisley | 20.7
2015-05-24 | 2015 | 5 | Wisley | 17.1
2015-05-25 | 2015 | 5 | Wisley | 19.3
2015-05-26 | 2015 | 5 | Wisley | 20.5
2015-05-27 | 2015 | 5 | Wisley | 17.1
2015-05-29 | 2015 | 5 | Wisley | 17.7
2015-05-30 | 2015 | 5 | Wisley | 16.4
2015-05-31 | 2015 | 5 | Wisley | 15.1
2015-06-01 | 2015 | 6 | Wisley | 18.5
2015-06-02 | 2015 | 6 | Wisley | 19.2
2015-06-03 | 2015 | 6 | Wisley | 22.6
2015-06-04 | 2015 | 6 | Wisley | 23.4
2015-06-05 | 2015 | 6 | Wisley | 19.2
2015-06-06 | 2015 | 6 | Wisley | 20.5
2015-06-07 | 2015 | 6 | Wisley | 18.9
2015-06-08 | 2015 | 6 | Wisley | 15.8
2015-06-09 | 2015 | 6 | Wisley | 19.1
2015-06-10 | 2015 | 6 | Wisley | 23.9
2015-06-11 | 2015 | 6 | Wisley | 24.4
2015-06-12 | 2015 | 6 | Wisley | 21
2015-06-14 | 2015 | 6 | Wisley | 19.8
2015-06-15 | 2015 | 6 | Wisley | 23.4
2015-06-16 | 2015 | 6 | Wisley | 24.8
2015-06-17 | 2015 | 6 | Wisley | 22.5
2015-06-18 | 2015 | 6 | Wisley | 22.3
2015-06-19 | 2015 | 6 | Wisley | 20.1
2015-06-20 | 2015 | 6 | Wisley | 20.3
2015-06-21 | 2015 | 6 | Wisley | 18.1
2015-06-22 | 2015 | 6 | Wisley | 20.8
2015-06-23 | 2015 | 6 | Wisley | 23.5
2015-06-24 | 2015 | 6 | Wisley | 24.6
2015-06-25 | 2015 | 6 | Wisley | 26
2015-06-26 | 2015 | 6 | Wisley | 24.8
2015-06-27 | 2015 | 6 | Wisley | 21.2
2015-06-28 | 2015 | 6 | Wisley | 25.7
2015-06-29 | 2015 | 6 | Wisley | 29.5
2015-06-30 | 2015 | 6 | Wisley | 34.9
2015-07-01 | 2015 | 7 | Wisley | 25.6
2015-07-02 | 2015 | 7 | Wisley | 27.7
2015-07-03 | 2015 | 7 | Wisley | 26.5
2015-07-04 | 2015 | 7 | Wisley | 23.9
2015-07-05 | 2015 | 7 | Wisley | 23.4
2015-07-06 | 2015 | 7 | Wisley | 22.5
2015-07-07 | 2015 | 7 | Wisley | 21.7
2015-07-08 | 2015 | 7 | Wisley | 23
2015-07-09 | 2015 | 7 | Wisley | 26
2015-07-10 | 2015 | 7 | Wisley | 25
2015-07-11 | 2015 | 7 | Wisley | 21.1
2015-07-12 | 2015 | 7 | Wisley | 20.8
2015-07-13 | 2015 | 7 | Wisley | 22.6
2015-07-14 | 2015 | 7 | Wisley | 22.6
2015-07-15 | 2015 | 7 | Wisley | 24.7
2015-07-16 | 2015 | 7 | Wisley | 24.3
2015-07-17 | 2015 | 7 | Wisley | 23.9
2015-07-18 | 2015 | 7 | Wisley | 24.8
2015-07-19 | 2015 | 7 | Wisley | 23.4
2015-07-20 | 2015 | 7 | Wisley | 25.7
2015-07-21 | 2015 | 7 | Wisley | 22.5
2015-07-22 | 2015 | 7 | Wisley | 22.2
2015-07-23 | 2015 | 7 | Wisley | 16
2015-07-24 | 2015 | 7 | Wisley | 21.3
2015-07-25 | 2015 | 7 | Wisley | 17.5
2015-07-26 | 2015 | 7 | Wisley | 20.4
2015-07-27 | 2015 | 7 | Wisley | 19.9
2015-07-28 | 2015 | 7 | Wisley | 18.5
2015-07-29 | 2015 | 7 | Wisley | 20
2015-07-30 | 2015 | 7 | Wisley | 22.6
2015-07-31 | 2015 | 7 | Wisley | 22.2
2015-08-01 | 2015 | 8 | Wisley | 25.3
2015-08-02 | 2015 | 8 | Wisley | 23.2
2015-08-03 | 2015 | 8 | Wisley | 21.4
2015-08-04 | 2015 | 8 | Wisley | 22.6
2015-08-05 | 2015 | 8 | Wisley | 23.5
2015-08-06 | 2015 | 8 | Wisley | 24.6
2015-08-07 | 2015 | 8 | Wisley | 26.8
2015-08-08 | 2015 | 8 | Wisley | 27
2015-08-09 | 2015 | 8 | Wisley | 21.9
2015-08-11 | 2015 | 8 | Wisley | 22.9
2015-08-12 | 2015 | 8 | Wisley | 21.3
2015-08-13 | 2015 | 8 | Wisley | 21.7
2015-08-14 | 2015 | 8 | Wisley | 20.7
2015-08-15 | 2015 | 8 | Wisley | 21.1
2015-08-16 | 2015 | 8 | Wisley | 21.3
2015-08-17 | 2015 | 8 | Wisley | 18.3
2015-08-18 | 2015 | 8 | Wisley | 21
2015-08-19 | 2015 | 8 | Wisley | 21.7
2015-08-20 | 2015 | 8 | Wisley | 25.5
2015-08-21 | 2015 | 8 | Wisley | 29.7
2015-08-22 | 2015 | 8 | Wisley | 20.5
2015-08-24 | 2015 | 8 | Wisley | 18.5
2015-08-25 | 2015 | 8 | Wisley | 19.3
2015-08-26 | 2015 | 8 | Wisley | 19
2015-08-27 | 2015 | 8 | Wisley | 20.8
2015-08-28 | 2015 | 8 | Wisley | 22
2015-08-29 | 2015 | 8 | Wisley | 20.1
2015-08-31 | 2015 | 8 | Wisley | 18.8
2015-09-01 | 2015 | 9 | Wisley | 18.2
2015-09-02 | 2015 | 9 | Wisley | 16.5
2015-09-03 | 2015 | 9 | Wisley | 16.9
2015-09-04 | 2015 | 9 | Wisley | 15.6
2015-09-05 | 2015 | 9 | Wisley | 18.9
2015-09-06 | 2015 | 9 | Wisley | 19.5
2015-09-07 | 2015 | 9 | Wisley | 17.4
2015-09-08 | 2015 | 9 | Wisley | 19.9
2015-09-09 | 2015 | 9 | Wisley | 22.1
2015-09-10 | 2015 | 9 | Wisley | 21.4
2015-09-11 | 2015 | 9 | Wisley | 21.3
2015-09-12 | 2015 | 9 | Wisley | 18.1
2015-09-13 | 2015 | 9 | Wisley | 19.1
2015-09-14 | 2015 | 9 | Wisley | 19.3
2015-09-15 | 2015 | 9 | Wisley | 15.1
2015-09-16 | 2015 | 9 | Wisley | 18.1
2015-09-17 | 2015 | 9 | Wisley | 18.3
2015-09-18 | 2015 | 9 | Wisley | 19.5
2015-09-19 | 2015 | 9 | Wisley | 20.2
2015-09-20 | 2015 | 9 | Wisley | 14.5
2015-09-22 | 2015 | 9 | Wisley | 17.4
2015-09-23 | 2015 | 9 | Wisley | 18.2
2015-09-24 | 2015 | 9 | Wisley | 18.3
2015-09-25 | 2015 | 9 | Wisley | 18.2
2015-09-26 | 2015 | 9 | Wisley | 18.9
2015-09-27 | 2015 | 9 | Wisley | 19.3
2015-09-28 | 2015 | 9 | Wisley | 18.9
2015-09-29 | 2015 | 9 | Wisley | 18.4
2015-09-30 | 2015 | 9 | Wisley | 18.4
2016-05-01 | 2016 | 5 | Wisley | 17.1
2016-05-02 | 2016 | 5 | Wisley | 15.7
2016-05-03 | 2016 | 5 | Wisley | 17.3
2016-05-04 | 2016 | 5 | Wisley | 20.6
2016-05-05 | 2016 | 5 | Wisley | 23.4
2016-05-06 | 2016 | 5 | Wisley | 23.1
2016-05-07 | 2016 | 5 | Wisley | 26.6
2016-05-08 | 2016 | 5 | Wisley | 23.8
2016-05-09 | 2016 | 5 | Wisley | 18.7
2016-05-10 | 2016 | 5 | Wisley | 19.2
2016-05-11 | 2016 | 5 | Wisley | 23.8
2016-05-12 | 2016 | 5 | Wisley | 18.5
2016-05-14 | 2016 | 5 | Wisley | 17.4
2016-05-15 | 2016 | 5 | Wisley | 18.5
2016-05-16 | 2016 | 5 | Wisley | 18.3
2016-05-17 | 2016 | 5 | Wisley | 14.4
2016-05-18 | 2016 | 5 | Wisley | 18.7
2016-05-19 | 2016 | 5 | Wisley | 20.3
2016-05-20 | 2016 | 5 | Wisley | 18.1
2016-05-21 | 2016 | 5 | Wisley | 19.5
2016-05-22 | 2016 | 5 | Wisley | 20
2016-05-23 | 2016 | 5 | Wisley | 17.5
2016-05-24 | 2016 | 5 | Wisley | 13.7
2016-05-25 | 2016 | 5 | Wisley | 21
2016-05-26 | 2016 | 5 | Wisley | 21.5
2016-05-27 | 2016 | 5 | Wisley | 20.9
2016-05-28 | 2016 | 5 | Wisley | 19.2
2016-05-29 | 2016 | 5 | Wisley | 17.1
2016-05-31 | 2016 | 5 | Wisley | 13.1
2016-06-01 | 2016 | 6 | Wisley | 13.9
2016-06-02 | 2016 | 6 | Wisley | 14.5
2016-06-03 | 2016 | 6 | Wisley | 19.5
2016-06-04 | 2016 | 6 | Wisley | 24.1
2016-06-05 | 2016 | 6 | Wisley | 25.2
2016-06-06 | 2016 | 6 | Wisley | 24.2
2016-06-07 | 2016 | 6 | Wisley | 25.1
2016-06-08 | 2016 | 6 | Wisley | 23.3
2016-06-09 | 2016 | 6 | Wisley | 23.5
2016-06-10 | 2016 | 6 | Wisley | 21.6
2016-06-11 | 2016 | 6 | Wisley | 20.9
2016-06-12 | 2016 | 6 | Wisley | 19.3
2016-06-13 | 2016 | 6 | Wisley | 19.2
2016-06-14 | 2016 | 6 | Wisley | 20.1
2016-06-15 | 2016 | 6 | Wisley | 19
2016-06-16 | 2016 | 6 | Wisley | 19.9
2016-06-17 | 2016 | 6 | Wisley | 18.1
2016-06-18 | 2016 | 6 | Wisley | 20.5
2016-06-19 | 2016 | 6 | Wisley | 22.5
2016-06-20 | 2016 | 6 | Wisley | 20.9
2016-06-21 | 2016 | 6 | Wisley | 22.2
2016-06-22 | 2016 | 6 | Wisley | 21.1
2016-06-23 | 2016 | 6 | Wisley | 21.9
2016-06-24 | 2016 | 6 | Wisley | 20.9
2016-06-25 | 2016 | 6 | Wisley | 21.1
2016-06-26 | 2016 | 6 | Wisley | 21.6
2016-06-27 | 2016 | 6 | Wisley | 21.5
2016-06-28 | 2016 | 6 | Wisley | 17
2016-06-29 | 2016 | 6 | Wisley | 19.7
2016-06-30 | 2016 | 6 | Wisley | 19.6
2016-07-01 | 2016 | 7 | Wisley | 18.3
2016-07-02 | 2016 | 7 | Wisley | 21.1
2016-07-03 | 2016 | 7 | Wisley | 20.6
2016-07-04 | 2016 | 7 | Wisley | 21.3
2016-07-05 | 2016 | 7 | Wisley | 22
2016-07-06 | 2016 | 7 | Wisley | 22.9
2016-07-07 | 2016 | 7 | Wisley | 22.8
2016-07-08 | 2016 | 7 | Wisley | 22.2
2016-07-09 | 2016 | 7 | Wisley | 22.1
2016-07-10 | 2016 | 7 | Wisley | 21.6
2016-07-11 | 2016 | 7 | Wisley | 18.8
2016-07-12 | 2016 | 7 | Wisley | 19
2016-07-13 | 2016 | 7 | Wisley | 21.6
2016-07-14 | 2016 | 7 | Wisley | 20.6
2016-07-15 | 2016 | 7 | Wisley | 26.8
2016-07-16 | 2016 | 7 | Wisley | 26.1
2016-07-17 | 2016 | 7 | Wisley | 28.6
2016-07-18 | 2016 | 7 | Wisley | 31.2
2016-07-19 | 2016 | 7 | Wisley | 29.9
2016-07-20 | 2016 | 7 | Wisley | 25.2
2016-07-21 | 2016 | 7 | Wisley | 23.8
2016-07-22 | 2016 | 7 | Wisley | 28
2016-07-23 | 2016 | 7 | Wisley | 23.7
2016-07-24 | 2016 | 7 | Wisley | 24.1
2016-07-25 | 2016 | 7 | Wisley | 23.5
2016-07-26 | 2016 | 7 | Wisley | 24
2016-07-27 | 2016 | 7 | Wisley | 22.1
2016-07-28 | 2016 | 7 | Wisley | 22.8
2016-07-29 | 2016 | 7 | Wisley | 22.5
2016-07-30 | 2016 | 7 | Wisley | 22.8
2016-07-31 | 2016 | 7 | Wisley | 18.5
2016-08-01 | 2016 | 8 | Wisley | 21.7
2016-08-02 | 2016 | 8 | Wisley | 23
2016-08-03 | 2016 | 8 | Wisley | 22.2
2016-08-04 | 2016 | 8 | Wisley | 23.9
2016-08-05 | 2016 | 8 | Wisley | 25.5
2016-08-06 | 2016 | 8 | Wisley | 26.1
2016-08-07 | 2016 | 8 | Wisley | 21.7
2016-08-08 | 2016 | 8 | Wisley | 20.3
2016-08-09 | 2016 | 8 | Wisley | 19.6
2016-08-10 | 2016 | 8 | Wisley | 23.6
2016-08-11 | 2016 | 8 | Wisley | 26.6
2016-08-12 | 2016 | 8 | Wisley | 24.6
2016-08-13 | 2016 | 8 | Wisley | 22.6
2016-08-14 | 2016 | 8 | Wisley | 23.7
2016-08-15 | 2016 | 8 | Wisley | 24.5
2016-08-16 | 2016 | 8 | Wisley | 26.9
2016-08-17 | 2016 | 8 | Wisley | 25.3
2016-08-19 | 2016 | 8 | Wisley | 20.9
2016-08-20 | 2016 | 8 | Wisley | 22.2
2016-08-21 | 2016 | 8 | Wisley | 25.1
2016-08-22 | 2016 | 8 | Wisley | 29.5
2016-08-23 | 2016 | 8 | Wisley | 32
2016-08-24 | 2016 | 8 | Wisley | 27.1
2016-08-25 | 2016 | 8 | Wisley | 26.7
2016-08-26 | 2016 | 8 | Wisley | 26.2
2016-08-27 | 2016 | 8 | Wisley | 21.9
2016-08-28 | 2016 | 8 | Wisley | 23.6
2016-08-29 | 2016 | 8 | Wisley | 26.6
2016-08-30 | 2016 | 8 | Wisley | 24.3
2016-08-31 | 2016 | 8 | Wisley | 23.8
2016-09-01 | 2016 | 9 | Wisley | 20.3
2016-09-02 | 2016 | 9 | Wisley | 20.7
2016-09-03 | 2016 | 9 | Wisley | 19.1
2016-09-04 | 2016 | 9 | Wisley | 23
2016-09-05 | 2016 | 9 | Wisley | 22.9
2016-09-06 | 2016 | 9 | Wisley | 27.5
2016-09-07 | 2016 | 9 | Wisley | 23.5
2016-09-08 | 2016 | 9 | Wisley | 22.1
2016-09-09 | 2016 | 9 | Wisley | 18.8
2016-09-10 | 2016 | 9 | Wisley | 21.4
2016-09-11 | 2016 | 9 | Wisley | 25.5
2016-09-12 | 2016 | 9 | Wisley | 30.3
2016-09-13 | 2016 | 9 | Wisley | 27.1
2016-09-14 | 2016 | 9 | Wisley | 28.9
2016-09-17 | 2016 | 9 | Wisley | 19
2016-09-18 | 2016 | 9 | Wisley | 19
2016-09-19 | 2016 | 9 | Wisley | 18.5
2016-09-20 | 2016 | 9 | Wisley | 21.7
2016-09-21 | 2016 | 9 | Wisley | 19.9
2016-09-22 | 2016 | 9 | Wisley | 20
2016-09-23 | 2016 | 9 | Wisley | 22.1
2016-09-24 | 2016 | 9 | Wisley | 19.7
2016-09-25 | 2016 | 9 | Wisley | 18.2
2016-09-26 | 2016 | 9 | Wisley | 18.6
2016-09-27 | 2016 | 9 | Wisley | 21.8
2016-09-28 | 2016 | 9 | Wisley | 20.1
2016-09-29 | 2016 | 9 | Wisley | 18.6
2016-09-30 | 2016 | 9 | Wisley | 16.1
2017-05-01 | 2017 | 5 | Wisley | 18.1
2017-05-02 | 2017 | 5 | Wisley | 12.2
2017-05-03 | 2017 | 5 | Wisley | 15
2017-05-04 | 2017 | 5 | Wisley | 16.7
2017-05-05 | 2017 | 5 | Wisley | 16.6
2017-05-06 | 2017 | 5 | Wisley | 18.7
2017-05-08 | 2017 | 5 | Wisley | 15.7
2017-05-09 | 2017 | 5 | Wisley | 19.1
2017-05-10 | 2017 | 5 | Wisley | 21.1
2017-05-11 | 2017 | 5 | Wisley | 19.2
2017-05-12 | 2017 | 5 | Wisley | 19
2017-05-13 | 2017 | 5 | Wisley | 20.1
2017-05-14 | 2017 | 5 | Wisley | 19.9
2017-05-15 | 2017 | 5 | Wisley | 24.4
2017-05-18 | 2017 | 5 | Wisley | 15.7
2017-05-19 | 2017 | 5 | Wisley | 17.1
2017-05-20 | 2017 | 5 | Wisley | 20.5
2017-05-21 | 2017 | 5 | Wisley | 24
2017-05-22 | 2017 | 5 | Wisley | 21.7
2017-05-23 | 2017 | 5 | Wisley | 25.9
2017-05-24 | 2017 | 5 | Wisley | 26.6
2017-05-25 | 2017 | 5 | Wisley | 27
2017-05-26 | 2017 | 5 | Wisley | 22.2
2017-05-27 | 2017 | 5 | Wisley | 24.2
2017-05-28 | 2017 | 5 | Wisley | 21.5
2017-05-29 | 2017 | 5 | Wisley | 20.1
2017-05-30 | 2017 | 5 | Wisley | 22.8
2017-05-31 | 2017 | 5 | Wisley | 25.1
2017-06-01 | 2017 | 6 | Wisley | 24.7
2017-06-02 | 2017 | 6 | Wisley | 21
2017-06-03 | 2017 | 6 | Wisley | 20.2
2017-06-04 | 2017 | 6 | Wisley | 17.7
2017-06-05 | 2017 | 6 | Wisley | 16.3
2017-06-06 | 2017 | 6 | Wisley | 20.1
2017-06-07 | 2017 | 6 | Wisley | 18.6
2017-06-08 | 2017 | 6 | Wisley | 20.3
2017-06-09 | 2017 | 6 | Wisley | 22.7
2017-06-10 | 2017 | 6 | Wisley | 22.6
2017-06-11 | 2017 | 6 | Wisley | 20.6
2017-06-12 | 2017 | 6 | Wisley | 24
2017-06-13 | 2017 | 6 | Wisley | 25.9
2017-06-14 | 2017 | 6 | Wisley | 23.8
2017-06-15 | 2017 | 6 | Wisley | 23.6
2017-06-16 | 2017 | 6 | Wisley | 29.6
2017-06-17 | 2017 | 6 | Wisley | 31.6
2017-06-18 | 2017 | 6 | Wisley | 31.4
2017-06-19 | 2017 | 6 | Wisley | 31.4
2017-06-20 | 2017 | 6 | Wisley | 33.3
2017-06-22 | 2017 | 6 | Wisley | 23.8
2017-06-23 | 2017 | 6 | Wisley | 23.2
2017-06-24 | 2017 | 6 | Wisley | 23.6
2017-06-25 | 2017 | 6 | Wisley | 25.2
2017-06-26 | 2017 | 6 | Wisley | 21.9
2017-06-28 | 2017 | 6 | Wisley | 18.3
2017-06-29 | 2017 | 6 | Wisley | 21.6
2017-06-30 | 2017 | 6 | Wisley | 22.6
2017-07-01 | 2017 | 7 | Wisley | 23.5
2017-07-02 | 2017 | 7 | Wisley | 24.4
2017-07-03 | 2017 | 7 | Wisley | 23.4
2017-07-04 | 2017 | 7 | Wisley | 29.5
2017-07-05 | 2017 | 7 | Wisley | 31
2017-07-06 | 2017 | 7 | Wisley | 29.8
2017-07-07 | 2017 | 7 | Wisley | 27
2017-07-08 | 2017 | 7 | Wisley | 28.1
2017-07-09 | 2017 | 7 | Wisley | 26.5
2017-07-11 | 2017 | 7 | Wisley | 21.5
2017-07-12 | 2017 | 7 | Wisley | 22.7
2017-07-13 | 2017 | 7 | Wisley | 21.3
2017-07-14 | 2017 | 7 | Wisley | 21.7
2017-07-15 | 2017 | 7 | Wisley | 26.1
2017-07-16 | 2017 | 7 | Wisley | 26.7
2017-07-17 | 2017 | 7 | Wisley | 27
2017-07-18 | 2017 | 7 | Wisley | 22
2017-07-19 | 2017 | 7 | Wisley | 20.8
2017-07-20 | 2017 | 7 | Wisley | 22.4
2017-07-21 | 2017 | 7 | Wisley | 19.7
2017-07-22 | 2017 | 7 | Wisley | 18.8
2017-07-23 | 2017 | 7 | Wisley | 20.3
2017-07-24 | 2017 | 7 | Wisley | 22.5
2017-07-25 | 2017 | 7 | Wisley | 22
2017-07-26 | 2017 | 7 | Wisley | 21.5
2017-07-27 | 2017 | 7 | Wisley | 20.4
2017-07-28 | 2017 | 7 | Wisley | 20.2
2017-07-29 | 2017 | 7 | Wisley | 21.1
2017-07-30 | 2017 | 7 | Wisley | 22.6
2017-07-31 | 2017 | 7 | Wisley | 22.8
2017-08-01 | 2017 | 8 | Wisley | 19.1
2017-08-02 | 2017 | 8 | Wisley | 20.4
2017-08-03 | 2017 | 8 | Wisley | 22.1
2017-08-04 | 2017 | 8 | Wisley | 21.5
2017-08-05 | 2017 | 8 | Wisley | 21.8
2017-08-06 | 2017 | 8 | Wisley | 19.9
2017-08-07 | 2017 | 8 | Wisley | 16.9
2017-08-08 | 2017 | 8 | Wisley | 15
2017-08-09 | 2017 | 8 | Wisley | 20.6
2017-08-10 | 2017 | 8 | Wisley | 21.9
2017-08-11 | 2017 | 8 | Wisley | 21.8
2017-08-12 | 2017 | 8 | Wisley | 22.1
2017-08-13 | 2017 | 8 | Wisley | 23.9
2017-08-14 | 2017 | 8 | Wisley | 23.5
2017-08-15 | 2017 | 8 | Wisley | 22.5
2017-08-16 | 2017 | 8 | Wisley | 23.9
2017-08-17 | 2017 | 8 | Wisley | 21.2
2017-08-18 | 2017 | 8 | Wisley | 20.5
2017-08-19 | 2017 | 8 | Wisley | 20.8
2017-08-20 | 2017 | 8 | Wisley | 19.6
2017-08-21 | 2017 | 8 | Wisley | 23.7
2017-08-22 | 2017 | 8 | Wisley | 21.8
2017-08-23 | 2017 | 8 | Wisley | 22.3
2017-08-24 | 2017 | 8 | Wisley | 23.3
2017-08-25 | 2017 | 8 | Wisley | 25.4
2017-08-26 | 2017 | 8 | Wisley | 25.4
2017-08-27 | 2017 | 8 | Wisley | 27.4
2017-08-28 | 2017 | 8 | Wisley | 25.1
2017-08-30 | 2017 | 8 | Wisley | 19.6
2017-08-31 | 2017 | 8 | Wisley | 21
2017-09-01 | 2017 | 9 | Wisley | 21.3
2017-09-02 | 2017 | 9 | Wisley | 17.9
2017-09-03 | 2017 | 9 | Wisley | 21.9
2017-09-04 | 2017 | 9 | Wisley | 20.4
2017-09-05 | 2017 | 9 | Wisley | 18.8
2017-09-06 | 2017 | 9 | Wisley | 19.4
2017-09-07 | 2017 | 9 | Wisley | 18.9
2017-09-08 | 2017 | 9 | Wisley | 19.2
2017-09-09 | 2017 | 9 | Wisley | 16.9
2017-09-10 | 2017 | 9 | Wisley | 18.4
2017-09-11 | 2017 | 9 | Wisley | 18.5
2017-09-12 | 2017 | 9 | Wisley | 18.5
2017-09-13 | 2017 | 9 | Wisley | 16.9
2017-09-14 | 2017 | 9 | Wisley | 16.9
2017-09-15 | 2017 | 9 | Wisley | 16.2
2017-09-16 | 2017 | 9 | Wisley | 16.8
2017-09-17 | 2017 | 9 | Wisley | 16
2017-09-18 | 2017 | 9 | Wisley | 16.1
2017-09-19 | 2017 | 9 | Wisley | 17.5
2017-09-20 | 2017 | 9 | Wisley | 18.1
2017-09-21 | 2017 | 9 | Wisley | 18.6
2017-09-22 | 2017 | 9 | Wisley | 19.2
2017-09-23 | 2017 | 9 | Wisley | 21.5
2017-09-24 | 2017 | 9 | Wisley | 17.6
2017-09-25 | 2017 | 9 | Wisley | 21.2
2017-09-26 | 2017 | 9 | Wisley | 20.3
2017-09-27 | 2017 | 9 | Wisley | 20.3
2017-09-28 | 2017 | 9 | Wisley | 18.7
2017-09-29 | 2017 | 9 | Wisley | 16.9
2017-09-30 | 2017 | 9 | Wisley | 17.9
2018-05-01 | 2018 | 5 | Wisley | 15.4
2018-05-02 | 2018 | 5 | Wisley | 17.6
2018-05-03 | 2018 | 5 | Wisley | 20.5
2018-05-04 | 2018 | 5 | Wisley | 22.7
2018-05-05 | 2018 | 5 | Wisley | 25.7
2018-05-06 | 2018 | 5 | Wisley | 28
2018-05-07 | 2018 | 5 | Wisley | 25.8
2018-05-08 | 2018 | 5 | Wisley | 20.5
2018-05-09 | 2018 | 5 | Wisley | 17
2018-05-10 | 2018 | 5 | Wisley | 17.7
2018-05-11 | 2018 | 5 | Wisley | 14.6
2018-05-12 | 2018 | 5 | Wisley | 18.5
2018-05-13 | 2018 | 5 | Wisley | 21.1
2018-05-14 | 2018 | 5 | Wisley | 23.4
2018-05-15 | 2018 | 5 | Wisley | 15.9
2018-05-16 | 2018 | 5 | Wisley | 17.8
2018-05-17 | 2018 | 5 | Wisley | 18.4
2018-05-18 | 2018 | 5 | Wisley | 21.9
2018-05-19 | 2018 | 5 | Wisley | 21.4
2018-05-20 | 2018 | 5 | Wisley | 22.4
2018-05-21 | 2018 | 5 | Wisley | 23.5
2018-05-22 | 2018 | 5 | Wisley | 20.7
2018-05-23 | 2018 | 5 | Wisley | 16.2
2018-05-24 | 2018 | 5 | Wisley | 18.5
2018-05-25 | 2018 | 5 | Wisley | 26.2
2018-05-26 | 2018 | 5 | Wisley | 27.5
2018-05-27 | 2018 | 5 | Wisley | 25.1
2018-05-29 | 2018 | 5 | Wisley | 19.2
2018-05-30 | 2018 | 5 | Wisley | 22.9
2018-05-31 | 2018 | 5 | Wisley | 23.5
2018-06-01 | 2018 | 6 | Wisley | 24
2018-06-02 | 2018 | 6 | Wisley | 26.5
2018-06-03 | 2018 | 6 | Wisley | 19.7
2018-06-04 | 2018 | 6 | Wisley | 19.3
2018-06-05 | 2018 | 6 | Wisley | 23.2
2018-06-06 | 2018 | 6 | Wisley | 20.1
2018-06-07 | 2018 | 6 | Wisley | 22.9
2018-06-08 | 2018 | 6 | Wisley | 22
2018-06-09 | 2018 | 6 | Wisley | 24.1
2018-06-10 | 2018 | 6 | Wisley | 24.8
2018-06-11 | 2018 | 6 | Wisley | 18.4
2018-06-12 | 2018 | 6 | Wisley | 21.8
2018-06-13 | 2018 | 6 | Wisley | 23
2018-06-14 | 2018 | 6 | Wisley | 23.3
2018-06-15 | 2018 | 6 | Wisley | 20.1
2018-06-16 | 2018 | 6 | Wisley | 19.4
2018-06-17 | 2018 | 6 | Wisley | 25.3
2018-06-18 | 2018 | 6 | Wisley | 23.9
2018-06-19 | 2018 | 6 | Wisley | 25.3
2018-06-20 | 2018 | 6 | Wisley | 20.4
2018-06-21 | 2018 | 6 | Wisley | 22.8
2018-06-22 | 2018 | 6 | Wisley | 23.5
2018-06-23 | 2018 | 6 | Wisley | 26.1
2018-06-24 | 2018 | 6 | Wisley | 29.7
2018-06-25 | 2018 | 6 | Wisley | 28.7
2018-06-26 | 2018 | 6 | Wisley | 26.8
2018-06-27 | 2018 | 6 | Wisley | 27.9
2018-06-28 | 2018 | 6 | Wisley | 28.1
2018-06-29 | 2018 | 6 | Wisley | 28.1
2018-06-30 | 2018 | 6 | Wisley | 30.7
2018-07-01 | 2018 | 7 | Wisley | 29.4
2018-07-02 | 2018 | 7 | Wisley | 26.2
2018-07-03 | 2018 | 7 | Wisley | 26
2018-07-04 | 2018 | 7 | Wisley | 30.3
2018-07-05 | 2018 | 7 | Wisley | 30.7
2018-07-06 | 2018 | 7 | Wisley | 31.3
2018-07-07 | 2018 | 7 | Wisley | 31
2018-07-08 | 2018 | 7 | Wisley | 30.3
2018-07-09 | 2018 | 7 | Wisley | 22.6
2018-07-10 | 2018 | 7 | Wisley | 24.2
2018-07-11 | 2018 | 7 | Wisley | 26.1
2018-07-12 | 2018 | 7 | Wisley | 26.9
2018-07-13 | 2018 | 7 | Wisley | 28.1
2018-07-14 | 2018 | 7 | Wisley | 30.4
2018-07-15 | 2018 | 7 | Wisley | 30.4
2018-07-16 | 2018 | 7 | Wisley | 24.4
2018-07-17 | 2018 | 7 | Wisley | 24.3
2018-07-18 | 2018 | 7 | Wisley | 28
2018-07-19 | 2018 | 7 | Wisley | 23.8
2018-07-20 | 2018 | 7 | Wisley | 28.4
2018-07-21 | 2018 | 7 | Wisley | 28.7
2018-07-22 | 2018 | 7 | Wisley | 32.5
2018-07-23 | 2018 | 7 | Wisley | 30.2
2018-07-24 | 2018 | 7 | Wisley | 32
2018-07-25 | 2018 | 7 | Wisley | 35.1
2018-07-26 | 2018 | 7 | Wisley | 32.4
2018-07-28 | 2018 | 7 | Wisley | 19.7
2018-07-29 | 2018 | 7 | Wisley | 23.2
2018-07-30 | 2018 | 7 | Wisley | 25.5
2018-07-31 | 2018 | 7 | Wisley | 26.3
2018-08-01 | 2018 | 8 | Wisley | 29.9
2018-08-02 | 2018 | 8 | Wisley | 32.9
2018-08-03 | 2018 | 8 | Wisley | 29.1
2018-08-04 | 2018 | 8 | Wisley | 29.5
2018-08-05 | 2018 | 8 | Wisley | 32.1
2018-08-06 | 2018 | 8 | Wisley | 31.5
2018-08-07 | 2018 | 8 | Wisley | 24.8
2018-08-09 | 2018 | 8 | Wisley | 19.9
2018-08-10 | 2018 | 8 | Wisley | 21.6
2018-08-11 | 2018 | 8 | Wisley | 21.2
2018-08-12 | 2018 | 8 | Wisley | 25.2
2018-08-13 | 2018 | 8 | Wisley | 25.7
2018-08-14 | 2018 | 8 | Wisley | 24.8
2018-08-16 | 2018 | 8 | Wisley | 22
2018-08-17 | 2018 | 8 | Wisley | 22
2018-08-18 | 2018 | 8 | Wisley | 27.3
2018-08-19 | 2018 | 8 | Wisley | 24.4
2018-08-20 | 2018 | 8 | Wisley | 25.9
2018-08-21 | 2018 | 8 | Wisley | 22.8
2018-08-22 | 2018 | 8 | Wisley | 22.4
2018-08-23 | 2018 | 8 | Wisley | 19.7
2018-08-24 | 2018 | 8 | Wisley | 19.8
2018-08-25 | 2018 | 8 | Wisley | 17.6
2018-08-26 | 2018 | 8 | Wisley | 18.7
2018-08-27 | 2018 | 8 | Wisley | 21.4
2018-08-28 | 2018 | 8 | Wisley | 20
2018-08-29 | 2018 | 8 | Wisley | 20.5
2018-08-30 | 2018 | 8 | Wisley | 22.3
2018-08-31 | 2018 | 8 | Wisley | 23.9
2018-09-01 | 2018 | 9 | Wisley | 24.2
2018-09-02 | 2018 | 9 | Wisley | 23.9
2018-09-03 | 2018 | 9 | Wisley | 19.8
2018-09-04 | 2018 | 9 | Wisley | 23
2018-09-05 | 2018 | 9 | Wisley | 22.1
2018-09-06 | 2018 | 9 | Wisley | 19.8
2018-09-07 | 2018 | 9 | Wisley | 19.7
2018-09-08 | 2018 | 9 | Wisley | 23.9
2018-09-09 | 2018 | 9 | Wisley | 22.1
2018-09-10 | 2018 | 9 | Wisley | 22.7
2018-09-12 | 2018 | 9 | Wisley | 20.5
2018-09-13 | 2018 | 9 | Wisley | 17.8
2018-09-14 | 2018 | 9 | Wisley | 21.7
2018-09-15 | 2018 | 9 | Wisley | 23.2
2018-09-16 | 2018 | 9 | Wisley | 24.7
2018-09-17 | 2018 | 9 | Wisley | 22.9
2018-09-18 | 2018 | 9 | Wisley | 22
2018-09-19 | 2018 | 9 | Wisley | 20.4
2018-09-21 | 2018 | 9 | Wisley | 13.7
2018-09-22 | 2018 | 9 | Wisley | 13.8
2018-09-23 | 2018 | 9 | Wisley | 15.5
2018-09-24 | 2018 | 9 | Wisley | 17.7
2018-09-25 | 2018 | 9 | Wisley | 22.3
2018-09-26 | 2018 | 9 | Wisley | 23
2018-09-27 | 2018 | 9 | Wisley | 17
2018-09-28 | 2018 | 9 | Wisley | 18.3
2018-09-29 | 2018 | 9 | Wisley | 15.4
2018-09-30 | 2018 | 9 | Wisley | 15.9
2019-05-01 | 2019 | 5 | Wisley | 15.8
2019-05-02 | 2019 | 5 | Wisley | 15.4
2019-05-03 | 2019 | 5 | Wisley | 11.6
2019-05-04 | 2019 | 5 | Wisley | 11.8
2019-05-05 | 2019 | 5 | Wisley | 12.9
2019-05-06 | 2019 | 5 | Wisley | 16.6
2019-05-07 | 2019 | 5 | Wisley | 15.9
2019-05-08 | 2019 | 5 | Wisley | 16
2019-05-09 | 2019 | 5 | Wisley | 16.2
2019-05-10 | 2019 | 5 | Wisley | 16.4
2019-05-11 | 2019 | 5 | Wisley | 18.1
2019-05-12 | 2019 | 5 | Wisley | 17.1
2019-05-13 | 2019 | 5 | Wisley | 17.7
2019-05-14 | 2019 | 5 | Wisley | 20.1
2019-05-15 | 2019 | 5 | Wisley | 18.3
2019-05-16 | 2019 | 5 | Wisley | 15.1
2019-05-17 | 2019 | 5 | Wisley | 18.7
2019-05-18 | 2019 | 5 | Wisley | 17.3
2019-05-19 | 2019 | 5 | Wisley | 20.4
2019-05-20 | 2019 | 5 | Wisley | 21
2019-05-21 | 2019 | 5 | Wisley | 22.2
2019-05-22 | 2019 | 5 | Wisley | 24.1
2019-05-23 | 2019 | 5 | Wisley | 22.7
2019-05-24 | 2019 | 5 | Wisley | 23.9
2019-05-25 | 2019 | 5 | Wisley | 20
2019-05-26 | 2019 | 5 | Wisley | 19.1
2019-05-27 | 2019 | 5 | Wisley | 17.9
2019-05-28 | 2019 | 5 | Wisley | 18.3
2019-05-29 | 2019 | 5 | Wisley | 22.7
2019-05-30 | 2019 | 5 | Wisley | 20.4
2019-05-31 | 2019 | 5 | Wisley | 26.4
2019-06-01 | 2019 | 6 | Wisley | 25.8
2019-06-02 | 2019 | 6 | Wisley | 20.5
2019-06-03 | 2019 | 6 | Wisley | 17.3
2019-06-04 | 2019 | 6 | Wisley | 19.3
2019-06-05 | 2019 | 6 | Wisley | 19.5
2019-06-06 | 2019 | 6 | Wisley | 17.7
2019-06-07 | 2019 | 6 | Wisley | 18.2
2019-06-08 | 2019 | 6 | Wisley | 19.7
2019-06-09 | 2019 | 6 | Wisley | 15.1
2019-06-10 | 2019 | 6 | Wisley | 19.2
2019-06-11 | 2019 | 6 | Wisley | 15.7
2019-06-12 | 2019 | 6 | Wisley | 16.5
2019-06-13 | 2019 | 6 | Wisley | 18.8
2019-06-14 | 2019 | 6 | Wisley | 19.6
2019-06-15 | 2019 | 6 | Wisley | 19.2
2019-06-16 | 2019 | 6 | Wisley | 21.8
2019-06-17 | 2019 | 6 | Wisley | 18.3
2019-06-18 | 2019 | 6 | Wisley | 18.4
2019-06-19 | 2019 | 6 | Wisley | 19.3
2019-06-20 | 2019 | 6 | Wisley | 22.2
2019-06-21 | 2019 | 6 | Wisley | 22.5
2019-06-22 | 2019 | 6 | Wisley | 24.1
2019-06-23 | 2019 | 6 | Wisley | 24.4
2019-06-24 | 2019 | 6 | Wisley | 23.6
2019-06-25 | 2019 | 6 | Wisley | 22.6
2019-06-26 | 2019 | 6 | Wisley | 23.5
2019-06-27 | 2019 | 6 | Wisley | 24.6
2019-06-28 | 2019 | 6 | Wisley | 32.6
2019-06-29 | 2019 | 6 | Wisley | 24.6
2019-06-30 | 2019 | 6 | Wisley | 22.4
2019-07-01 | 2019 | 7 | Wisley | 22.8
2019-07-02 | 2019 | 7 | Wisley | 23.1
2019-07-03 | 2019 | 7 | Wisley | 26.3
2019-07-04 | 2019 | 7 | Wisley | 26.9
2019-07-05 | 2019 | 7 | Wisley | 25.4
2019-07-06 | 2019 | 7 | Wisley | 20.9
2019-07-07 | 2019 | 7 | Wisley | 23.6
2019-07-08 | 2019 | 7 | Wisley | 25.7
2019-07-09 | 2019 | 7 | Wisley | 26
2019-07-10 | 2019 | 7 | Wisley | 26.4
2019-07-11 | 2019 | 7 | Wisley | 25
2019-07-12 | 2019 | 7 | Wisley | 24.7
2019-07-13 | 2019 | 7 | Wisley | 22
2019-07-14 | 2019 | 7 | Wisley | 22.3
2019-07-15 | 2019 | 7 | Wisley | 27.1
2019-07-16 | 2019 | 7 | Wisley | 25.7
2019-07-17 | 2019 | 7 | Wisley | 23.8
2019-07-18 | 2019 | 7 | Wisley | 19.9
2019-07-19 | 2019 | 7 | Wisley | 24.5
2019-07-20 | 2019 | 7 | Wisley | 23.2
2019-07-21 | 2019 | 7 | Wisley | 26.5
2019-07-22 | 2019 | 7 | Wisley | 32.5
2019-07-23 | 2019 | 7 | Wisley | 32.2
2019-07-24 | 2019 | 7 | Wisley | 36.7
2019-07-27 | 2019 | 7 | Wisley | 23.9
2019-07-28 | 2019 | 7 | Wisley | 24.7
2019-07-29 | 2019 | 7 | Wisley | 19.6
2019-07-30 | 2019 | 7 | Wisley | 23.2
2019-07-31 | 2019 | 7 | Wisley | 25.4
2019-08-01 | 2019 | 8 | Wisley | 25.6
2019-08-02 | 2019 | 8 | Wisley | 23.8
2019-08-03 | 2019 | 8 | Wisley | 25.7
2019-08-04 | 2019 | 8 | Wisley | 24.7
2019-08-05 | 2019 | 8 | Wisley | 23.9
2019-08-06 | 2019 | 8 | Wisley | 23.3
2019-08-07 | 2019 | 8 | Wisley | 23.7
2019-08-08 | 2019 | 8 | Wisley | 24.9
2019-08-09 | 2019 | 8 | Wisley | 21.5
2019-08-10 | 2019 | 8 | Wisley | 21.8
2019-08-11 | 2019 | 8 | Wisley | 19
2019-08-12 | 2019 | 8 | Wisley | 22.2
2019-08-13 | 2019 | 8 | Wisley | 18.8
2019-08-14 | 2019 | 8 | Wisley | 22.6
2019-08-15 | 2019 | 8 | Wisley | 18.5
2019-08-16 | 2019 | 8 | Wisley | 21.9
2019-08-17 | 2019 | 8 | Wisley | 22.1
2019-08-18 | 2019 | 8 | Wisley | 20.4
2019-08-19 | 2019 | 8 | Wisley | 21.7
2019-08-20 | 2019 | 8 | Wisley | 22.8
2019-08-21 | 2019 | 8 | Wisley | 23.8
2019-08-22 | 2019 | 8 | Wisley | 26.5
2019-08-23 | 2019 | 8 | Wisley | 29.3
2019-08-24 | 2019 | 8 | Wisley | 32.4
2019-08-25 | 2019 | 8 | Wisley | 31.3
2019-08-26 | 2019 | 8 | Wisley | 31.8
2019-08-27 | 2019 | 8 | Wisley | 24.9
2019-08-28 | 2019 | 8 | Wisley | 23.5
2019-08-29 | 2019 | 8 | Wisley | 23.9
2019-08-30 | 2019 | 8 | Wisley | 23.6
2019-08-31 | 2019 | 8 | Wisley | 21.1
2019-09-01 | 2019 | 9 | Wisley | 22.9
2019-09-02 | 2019 | 9 | Wisley | 20.4
2019-09-03 | 2019 | 9 | Wisley | 19.8
2019-09-04 | 2019 | 9 | Wisley | 17.9
2019-09-05 | 2019 | 9 | Wisley | 18.1
2019-09-06 | 2019 | 9 | Wisley | 17.8
2019-09-07 | 2019 | 9 | Wisley | 18.1
2019-09-08 | 2019 | 9 | Wisley | 15
2019-09-09 | 2019 | 9 | Wisley | 19.9
2019-09-10 | 2019 | 9 | Wisley | 21
2019-09-11 | 2019 | 9 | Wisley | 24.7
2019-09-12 | 2019 | 9 | Wisley | 21.8
2019-09-13 | 2019 | 9 | Wisley | 23.4
2019-09-14 | 2019 | 9 | Wisley | 26.4
2019-09-15 | 2019 | 9 | Wisley | 20.7
2019-09-16 | 2019 | 9 | Wisley | 19.8
2019-09-17 | 2019 | 9 | Wisley | 19.3
2019-09-18 | 2019 | 9 | Wisley | 21.1
2019-09-19 | 2019 | 9 | Wisley | 22.3
2019-09-20 | 2019 | 9 | Wisley | 25.3
2019-09-21 | 2019 | 9 | Wisley | 23
2019-09-22 | 2019 | 9 | Wisley | 20.8
2019-09-23 | 2019 | 9 | Wisley | 21.1
2019-09-24 | 2019 | 9 | Wisley | 20.6
2019-09-25 | 2019 | 9 | Wisley | 20.3
2019-09-26 | 2019 | 9 | Wisley | 18.1
2019-09-27 | 2019 | 9 | Wisley | 20
2019-09-28 | 2019 | 9 | Wisley | 19.7
2019-09-29 | 2019 | 9 | Wisley | 17.7
2019-09-30 | 2019 | 9 | Wisley | 20.4
2020-05-01 | 2020 | 5 | Wisley | 17.7
2020-05-02 | 2020 | 5 | Wisley | 14.6
2020-05-03 | 2020 | 5 | Wisley | 17.4
2020-05-04 | 2020 | 5 | Wisley | 14.9
2020-05-05 | 2020 | 5 | Wisley | 18.2
2020-05-06 | 2020 | 5 | Wisley | 22.2
2020-05-07 | 2020 | 5 | Wisley | 24
2020-05-08 | 2020 | 5 | Wisley | 24.2
2020-05-09 | 2020 | 5 | Wisley | 19.4
2020-05-11 | 2020 | 5 | Wisley | 15.2
2020-05-12 | 2020 | 5 | Wisley | 13
2020-05-13 | 2020 | 5 | Wisley | 14.1
2020-05-14 | 2020 | 5 | Wisley | 18.8
2020-05-15 | 2020 | 5 | Wisley | 18.8
2020-05-16 | 2020 | 5 | Wisley | 20.3
2020-05-17 | 2020 | 5 | Wisley | 23.3
2020-05-18 | 2020 | 5 | Wisley | 25.5
2020-05-19 | 2020 | 5 | Wisley | 26.9
2020-05-20 | 2020 | 5 | Wisley | 27.6
2020-05-21 | 2020 | 5 | Wisley | 21.9
2020-05-22 | 2020 | 5 | Wisley | 19.1
2020-05-23 | 2020 | 5 | Wisley | 22.4
2020-05-24 | 2020 | 5 | Wisley | 25.3
2020-05-25 | 2020 | 5 | Wisley | 26.2
2020-05-26 | 2020 | 5 | Wisley | 25.6
2020-05-27 | 2020 | 5 | Wisley | 21.9
2020-05-28 | 2020 | 5 | Wisley | 23.2
2020-05-29 | 2020 | 5 | Wisley | 23.9
2020-05-30 | 2020 | 5 | Wisley | 24
2020-05-31 | 2020 | 5 | Wisley | 25.5
2020-06-01 | 2020 | 6 | Wisley | 25.2
2020-06-02 | 2020 | 6 | Wisley | 18.9
2020-06-03 | 2020 | 6 | Wisley | 16.3
2020-06-04 | 2020 | 6 | Wisley | 17.6
2020-06-05 | 2020 | 6 | Wisley | 15.1
2020-06-06 | 2020 | 6 | Wisley | 20.3
2020-06-07 | 2020 | 6 | Wisley | 16.5
2020-06-08 | 2020 | 6 | Wisley | 20.8
2020-06-09 | 2020 | 6 | Wisley | 16
2020-06-10 | 2020 | 6 | Wisley | 20.3
2020-06-11 | 2020 | 6 | Wisley | 20.2
2020-06-12 | 2020 | 6 | Wisley | 23.7
2020-06-13 | 2020 | 6 | Wisley | 21.8
2020-06-14 | 2020 | 6 | Wisley | 24.7
2020-06-15 | 2020 | 6 | Wisley | 22.3
2020-06-16 | 2020 | 6 | Wisley | 23.3
2020-06-17 | 2020 | 6 | Wisley | 17.8
2020-06-18 | 2020 | 6 | Wisley | 19.7
2020-06-19 | 2020 | 6 | Wisley | 22.2
2020-06-20 | 2020 | 6 | Wisley | 22.7
2020-06-21 | 2020 | 6 | Wisley | 22.6
2020-06-22 | 2020 | 6 | Wisley | 27.5
2020-06-23 | 2020 | 6 | Wisley | 31.3
2020-06-24 | 2020 | 6 | Wisley | 31.4
2020-06-25 | 2020 | 6 | Wisley | 29.8
2020-06-27 | 2020 | 6 | Wisley | 20.2
2020-06-28 | 2020 | 6 | Wisley | 19.6
2020-06-29 | 2020 | 6 | Wisley | 19.3
2020-06-30 | 2020 | 6 | Wisley | 22
2020-07-01 | 2020 | 7 | Wisley | 20.3
2020-07-02 | 2020 | 7 | Wisley | 20.4
2020-07-03 | 2020 | 7 | Wisley | 19.7
2020-07-04 | 2020 | 7 | Wisley | 21
2020-07-05 | 2020 | 7 | Wisley | 20.2
2020-07-06 | 2020 | 7 | Wisley | 20.4
2020-07-07 | 2020 | 7 | Wisley | 20.6
2020-07-08 | 2020 | 7 | Wisley | 20.4
2020-07-09 | 2020 | 7 | Wisley | 19
2020-07-10 | 2020 | 7 | Wisley | 21.2
2020-07-11 | 2020 | 7 | Wisley | 24.1
2020-07-12 | 2020 | 7 | Wisley | 26.2
2020-07-13 | 2020 | 7 | Wisley | 22.1
2020-07-14 | 2020 | 7 | Wisley | 19.8
2020-07-15 | 2020 | 7 | Wisley | 24.5
2020-07-16 | 2020 | 7 | Wisley | 28
2020-07-17 | 2020 | 7 | Wisley | 26.3
2020-07-18 | 2020 | 7 | Wisley | 20.5
2020-07-19 | 2020 | 7 | Wisley | 22.2
2020-07-20 | 2020 | 7 | Wisley | 22.5
2020-07-21 | 2020 | 7 | Wisley | 25.4
2020-07-22 | 2020 | 7 | Wisley | 26.1
2020-07-23 | 2020 | 7 | Wisley | 25.1
2020-07-24 | 2020 | 7 | Wisley | 21.8
2020-07-25 | 2020 | 7 | Wisley | 23.2
2020-07-26 | 2020 | 7 | Wisley | 21
2020-07-27 | 2020 | 7 | Wisley | 21.4
2020-07-28 | 2020 | 7 | Wisley | 23.9
2020-07-29 | 2020 | 7 | Wisley | 28.7
2020-07-30 | 2020 | 7 | Wisley | 36.2
2020-07-31 | 2020 | 7 | Wisley | 27
2020-08-01 | 2020 | 8 | Wisley | 24.3
2020-08-02 | 2020 | 8 | Wisley | 23.3
2020-08-03 | 2020 | 8 | Wisley | 23.5
2020-08-04 | 2020 | 8 | Wisley | 25.7
2020-08-05 | 2020 | 8 | Wisley | 30.1
2020-08-06 | 2020 | 8 | Wisley | 36.1
2020-08-07 | 2020 | 8 | Wisley | 32.4
2020-08-08 | 2020 | 8 | Wisley | 32.8
2020-08-09 | 2020 | 8 | Wisley | 34.4
2020-08-10 | 2020 | 8 | Wisley | 35.4
2020-08-11 | 2020 | 8 | Wisley | 34.9
2020-08-12 | 2020 | 8 | Wisley | 28.6
2020-08-14 | 2020 | 8 | Wisley | 19.9
2020-08-15 | 2020 | 8 | Wisley | 23.2
2020-08-16 | 2020 | 8 | Wisley | 23.9
2020-08-17 | 2020 | 8 | Wisley | 24.2
2020-08-18 | 2020 | 8 | Wisley | 20.5
2020-08-19 | 2020 | 8 | Wisley | 24.7
2020-08-20 | 2020 | 8 | Wisley | 23
2020-08-21 | 2020 | 8 | Wisley | 22.9
2020-08-22 | 2020 | 8 | Wisley | 21.2
2020-08-23 | 2020 | 8 | Wisley | 22.8
2020-08-24 | 2020 | 8 | Wisley | 21.2
2020-08-25 | 2020 | 8 | Wisley | 22.5
2020-08-27 | 2020 | 8 | Wisley | 19.7
2020-08-28 | 2020 | 8 | Wisley | 15.9
2020-08-29 | 2020 | 8 | Wisley | 17.4
2020-08-30 | 2020 | 8 | Wisley | 17.6
2020-08-31 | 2020 | 8 | Wisley | 20.3
2020-09-01 | 2020 | 9 | Wisley | 20.4
2020-09-02 | 2020 | 9 | Wisley | 22.8
2020-09-03 | 2020 | 9 | Wisley | 19.5
2020-09-04 | 2020 | 9 | Wisley | 19.2
2020-09-05 | 2020 | 9 | Wisley | 20.2
2020-09-06 | 2020 | 9 | Wisley | 21.2
2020-09-07 | 2020 | 9 | Wisley | 24.7
2020-09-08 | 2020 | 9 | Wisley | 22.4
2020-09-09 | 2020 | 9 | Wisley | 19.1
2020-09-10 | 2020 | 9 | Wisley | 19.4
2020-09-11 | 2020 | 9 | Wisley | 21.9
2020-09-12 | 2020 | 9 | Wisley | 24.9
2020-09-13 | 2020 | 9 | Wisley | 28.4
2020-09-14 | 2020 | 9 | Wisley | 28.8
2020-09-15 | 2020 | 9 | Wisley | 25.6
2020-09-16 | 2020 | 9 | Wisley | 21.4
2020-09-17 | 2020 | 9 | Wisley | 20.5
2020-09-18 | 2020 | 9 | Wisley | 23.7
2020-09-19 | 2020 | 9 | Wisley | 24.1
2020-09-20 | 2020 | 9 | Wisley | 23.7
2020-09-21 | 2020 | 9 | Wisley | 24.5
2020-09-22 | 2020 | 9 | Wisley | 18.1
2020-09-23 | 2020 | 9 | Wisley | 16.4
2020-09-24 | 2020 | 9 | Wisley | 14.6
2020-09-25 | 2020 | 9 | Wisley | 13.2
2020-09-26 | 2020 | 9 | Wisley | 13.9
2020-09-27 | 2020 | 9 | Wisley | 17.5
2020-09-28 | 2020 | 9 | Wisley | 19.2
2020-09-29 | 2020 | 9 | Wisley | 17
2020-09-30 | 2020 | 9 | Wisley | 15.8
2021-05-01 | 2021 | 5 | Wisley | 14.2
2021-05-02 | 2021 | 5 | Wisley | 13.7
2021-05-03 | 2021 | 5 | Wisley | 14.4
2021-05-04 | 2021 | 5 | Wisley | 13.6
2021-05-05 | 2021 | 5 | Wisley | 12.1
2021-05-06 | 2021 | 5 | Wisley | 14.8
2021-05-07 | 2021 | 5 | Wisley | 17.7
2021-05-08 | 2021 | 5 | Wisley | 20.3
2021-05-09 | 2021 | 5 | Wisley | 16.6
2021-05-10 | 2021 | 5 | Wisley | 17.5
2021-05-11 | 2021 | 5 | Wisley | 16.9
2021-05-12 | 2021 | 5 | Wisley | 14.2
2021-05-13 | 2021 | 5 | Wisley | 13.2
2021-05-14 | 2021 | 5 | Wisley | 15.4
2021-05-15 | 2021 | 5 | Wisley | 14.3
2021-05-16 | 2021 | 5 | Wisley | 15.9
2021-05-17 | 2021 | 5 | Wisley | 16.4
2021-05-18 | 2021 | 5 | Wisley | 17.7
2021-05-19 | 2021 | 5 | Wisley | 14.1
2021-05-20 | 2021 | 5 | Wisley | 12.3
2021-05-21 | 2021 | 5 | Wisley | 15.2
2021-05-22 | 2021 | 5 | Wisley | 14.2
2021-05-23 | 2021 | 5 | Wisley | 13.7
2021-05-24 | 2021 | 5 | Wisley | 16.5
2021-05-25 | 2021 | 5 | Wisley | 17.5
2021-05-26 | 2021 | 5 | Wisley | 22
2021-05-27 | 2021 | 5 | Wisley | 19.5
2021-05-28 | 2021 | 5 | Wisley | 21.4
2021-05-29 | 2021 | 5 | Wisley | 20.9
2021-05-30 | 2021 | 5 | Wisley | 24.6
2021-05-31 | 2021 | 5 | Wisley | 25.7
2021-06-01 | 2021 | 6 | Wisley | 28
2021-06-02 | 2021 | 6 | Wisley | 23.9
2021-06-04 | 2021 | 6 | Wisley | 23.4
2021-06-05 | 2021 | 6 | Wisley | 23.4
2021-06-06 | 2021 | 6 | Wisley | 23.4
2021-06-07 | 2021 | 6 | Wisley | 24
2021-06-08 | 2021 | 6 | Wisley | 25.5
2021-06-09 | 2021 | 6 | Wisley | 24.4
2021-06-10 | 2021 | 6 | Wisley | 24.4
2021-06-11 | 2021 | 6 | Wisley | 24.2
2021-06-12 | 2021 | 6 | Wisley | 27.3
2021-06-13 | 2021 | 6 | Wisley | 28.7
2021-06-14 | 2021 | 6 | Wisley | 25.8
2021-06-15 | 2021 | 6 | Wisley | 29.1
2021-06-16 | 2021 | 6 | Wisley | 21.5
2021-06-18 | 2021 | 6 | Wisley | 15.8
2021-06-19 | 2021 | 6 | Wisley | 19.6
2021-06-21 | 2021 | 6 | Wisley | 16.8
2021-06-22 | 2021 | 6 | Wisley | 21.9
2021-06-23 | 2021 | 6 | Wisley | 20.9
2021-06-24 | 2021 | 6 | Wisley | 23.1
2021-06-25 | 2021 | 6 | Wisley | 21.7
2021-06-26 | 2021 | 6 | Wisley | 19.9
2021-06-27 | 2021 | 6 | Wisley | 21.3
2021-06-28 | 2021 | 6 | Wisley | 20.2
2021-06-29 | 2021 | 6 | Wisley | 19
2021-06-30 | 2021 | 6 | Wisley | 21.7
2021-07-01 | 2021 | 7 | Wisley | 24.1
2021-07-02 | 2021 | 7 | Wisley | 21.8
2021-07-03 | 2021 | 7 | Wisley | 21.4
2021-07-04 | 2021 | 7 | Wisley | 20.8
2021-07-05 | 2021 | 7 | Wisley | 20
2021-07-06 | 2021 | 7 | Wisley | 19.9
2021-07-07 | 2021 | 7 | Wisley | 21.4
2021-07-08 | 2021 | 7 | Wisley | 24.9
2021-07-09 | 2021 | 7 | Wisley | 19.6
2021-07-10 | 2021 | 7 | Wisley | 21.6
2021-07-11 | 2021 | 7 | Wisley | 20.9
2021-07-12 | 2021 | 7 | Wisley | 22.5
2021-07-13 | 2021 | 7 | Wisley | 24.7
2021-07-14 | 2021 | 7 | Wisley | 21.8
2021-07-15 | 2021 | 7 | Wisley | 26.3
2021-07-16 | 2021 | 7 | Wisley | 27.5
2021-07-17 | 2021 | 7 | Wisley | 31
2021-07-18 | 2021 | 7 | Wisley | 31.1
2021-07-19 | 2021 | 7 | Wisley | 31.2
2021-07-20 | 2021 | 7 | Wisley | 29.5
2021-07-21 | 2021 | 7 | Wisley | 29
2021-07-22 | 2021 | 7 | Wisley | 23.6
2021-07-23 | 2021 | 7 | Wisley | 22.7
2021-07-24 | 2021 | 7 | Wisley | 22
2021-07-25 | 2021 | 7 | Wisley | 25.8
2021-07-26 | 2021 | 7 | Wisley | 22.1
2021-07-27 | 2021 | 7 | Wisley | 21
2021-07-28 | 2021 | 7 | Wisley | 22.3
2021-07-29 | 2021 | 7 | Wisley | 20.5
2021-07-30 | 2021 | 7 | Wisley | 20.6
2021-07-31 | 2021 | 7 | Wisley | 21.7
2021-08-01 | 2021 | 8 | Wisley | 18.4
2021-08-02 | 2021 | 8 | Wisley | 22.8
2021-08-03 | 2021 | 8 | Wisley | 22.5
2021-08-04 | 2021 | 8 | Wisley | 20.9
2021-08-05 | 2021 | 8 | Wisley | 22
2021-08-06 | 2021 | 8 | Wisley | 20.2
2021-08-07 | 2021 | 8 | Wisley | 20.1
2021-08-08 | 2021 | 8 | Wisley | 22.2
2021-08-09 | 2021 | 8 | Wisley | 23.9
2021-08-10 | 2021 | 8 | Wisley | 24.2
2021-08-11 | 2021 | 8 | Wisley | 22.7
2021-08-12 | 2021 | 8 | Wisley | 22.6
2021-08-13 | 2021 | 8 | Wisley | 24.8
2021-08-14 | 2021 | 8 | Wisley | 22.8
2021-08-15 | 2021 | 8 | Wisley | 19
2021-08-16 | 2021 | 8 | Wisley | 18.3
2021-08-17 | 2021 | 8 | Wisley | 22.6
2021-08-18 | 2021 | 8 | Wisley | 21.6
2021-08-19 | 2021 | 8 | Wisley | 21.4
2021-08-20 | 2021 | 8 | Wisley | 20.6
2021-08-21 | 2021 | 8 | Wisley | 22.5
2021-08-22 | 2021 | 8 | Wisley | 21.2
2021-08-23 | 2021 | 8 | Wisley | 22.6
2021-08-24 | 2021 | 8 | Wisley | 22.3
2021-08-25 | 2021 | 8 | Wisley | 18.3
2021-08-26 | 2021 | 8 | Wisley | 19.4
2021-08-27 | 2021 | 8 | Wisley | 20.2
2021-08-28 | 2021 | 8 | Wisley | 20.5
2021-08-29 | 2021 | 8 | Wisley | 17.3
2021-08-30 | 2021 | 8 | Wisley | 19.4
2021-08-31 | 2021 | 8 | Wisley | 18
2021-09-01 | 2021 | 9 | Wisley | 18.7
2021-09-02 | 2021 | 9 | Wisley | 21.8
2021-09-03 | 2021 | 9 | Wisley | 19.3
2021-09-04 | 2021 | 9 | Wisley | 25.6
2021-09-05 | 2021 | 9 | Wisley | 26.8
2021-09-06 | 2021 | 9 | Wisley | 28.9
2021-09-07 | 2021 | 9 | Wisley | 29.1
2021-09-08 | 2021 | 9 | Wisley | 22.9
2021-09-09 | 2021 | 9 | Wisley | 21.6
2021-09-10 | 2021 | 9 | Wisley | 23.3
2021-09-11 | 2021 | 9 | Wisley | 22
2021-09-12 | 2021 | 9 | Wisley | 20.8
2021-09-13 | 2021 | 9 | Wisley | 20.3
2021-09-14 | 2021 | 9 | Wisley | 21.2
2021-09-15 | 2021 | 9 | Wisley | 23.1
2021-09-16 | 2021 | 9 | Wisley | 21.6
2021-09-17 | 2021 | 9 | Wisley | 23.6
2021-09-18 | 2021 | 9 | Wisley | 17.9
2021-09-19 | 2021 | 9 | Wisley | 19.7
2021-09-20 | 2021 | 9 | Wisley | 22.4
2021-09-21 | 2021 | 9 | Wisley | 22.8
2021-09-22 | 2021 | 9 | Wisley | 20.5
2021-09-23 | 2021 | 9 | Wisley | 23.8
2021-09-24 | 2021 | 9 | Wisley | 18.4
2021-09-25 | 2021 | 9 | Wisley | 22.3
2021-09-26 | 2021 | 9 | Wisley | 18.4
2021-09-27 | 2021 | 9 | Wisley | 18.4
2021-09-28 | 2021 | 9 | Wisley | 16
2021-09-29 | 2021 | 9 | Wisley | 16.4
2021-09-30 | 2021 | 9 | Wisley | 18
2022-05-01 | 2022 | 5 | Wisley | 15.5
2022-05-02 | 2022 | 5 | Wisley | 16.5
2022-05-03 | 2022 | 5 | Wisley | 19.6
2022-05-04 | 2022 | 5 | Wisley | 19.5
2022-05-05 | 2022 | 5 | Wisley | 22.5
2022-05-06 | 2022 | 5 | Wisley | 20.3
2022-05-07 | 2022 | 5 | Wisley | 19.2
2022-05-08 | 2022 | 5 | Wisley | 22.2
2022-05-09 | 2022 | 5 | Wisley | 20.2
2022-05-11 | 2022 | 5 | Wisley | 18.6
2022-05-12 | 2022 | 5 | Wisley | 20.6
2022-05-13 | 2022 | 5 | Wisley | 22.4
2022-05-14 | 2022 | 5 | Wisley | 17.5
2022-05-15 | 2022 | 5 | Wisley | 21.6
2022-05-16 | 2022 | 5 | Wisley | 25.4
2022-05-17 | 2022 | 5 | Wisley | 22.2
2022-05-18 | 2022 | 5 | Wisley | 22.1
2022-05-19 | 2022 | 5 | Wisley | 18.2
2022-05-20 | 2022 | 5 | Wisley | 20.9
2022-05-21 | 2022 | 5 | Wisley | 23.5
2022-05-22 | 2022 | 5 | Wisley | 19.4
2022-05-23 | 2022 | 5 | Wisley | 18.9
2022-05-24 | 2022 | 5 | Wisley | 18.9
2022-05-25 | 2022 | 5 | Wisley | 20.1
2022-05-26 | 2022 | 5 | Wisley | 20.4
2022-05-27 | 2022 | 5 | Wisley | 18.8
2022-05-28 | 2022 | 5 | Wisley | 17.6
2022-05-29 | 2022 | 5 | Wisley | 15.1
2022-05-30 | 2022 | 5 | Wisley | 17
2022-05-31 | 2022 | 5 | Wisley | 18.4
2022-06-01 | 2022 | 6 | Wisley | 21.5
2022-06-02 | 2022 | 6 | Wisley | 23.2
2022-06-03 | 2022 | 6 | Wisley | 20.2
2022-06-05 | 2022 | 6 | Wisley | 17.5
2022-06-06 | 2022 | 6 | Wisley | 20.8
2022-06-07 | 2022 | 6 | Wisley | 21.8
2022-06-08 | 2022 | 6 | Wisley | 20.7
2022-06-09 | 2022 | 6 | Wisley | 23.3
2022-06-10 | 2022 | 6 | Wisley | 22.9
2022-06-11 | 2022 | 6 | Wisley | 21.9
2022-06-12 | 2022 | 6 | Wisley | 21.1
2022-06-13 | 2022 | 6 | Wisley | 24.4
2022-06-14 | 2022 | 6 | Wisley | 27.8
2022-06-15 | 2022 | 6 | Wisley | 28.8
2022-06-16 | 2022 | 6 | Wisley | 32
2022-06-17 | 2022 | 6 | Wisley | 24.3
2022-06-18 | 2022 | 6 | Wisley | 19.9
2022-06-19 | 2022 | 6 | Wisley | 22.4
2022-06-20 | 2022 | 6 | Wisley | 25.8
2022-06-21 | 2022 | 6 | Wisley | 26.2
2022-06-22 | 2022 | 6 | Wisley | 26.1
2022-06-23 | 2022 | 6 | Wisley | 22.9
2022-06-24 | 2022 | 6 | Wisley | 20.9
2022-06-25 | 2022 | 6 | Wisley | 21.8
2022-06-26 | 2022 | 6 | Wisley | 20.3
2022-06-27 | 2022 | 6 | Wisley | 22.3
2022-06-28 | 2022 | 6 | Wisley | 21.5
2022-06-29 | 2022 | 6 | Wisley | 21.1
2022-06-30 | 2022 | 6 | Wisley | 22.8
2022-07-01 | 2022 | 7 | Wisley | 23
2022-07-02 | 2022 | 7 | Wisley | 23.4
2022-07-03 | 2022 | 7 | Wisley | 23
2022-07-04 | 2022 | 7 | Wisley | 22.1
2022-07-05 | 2022 | 7 | Wisley | 24.9
2022-07-06 | 2022 | 7 | Wisley | 24.7
2022-07-07 | 2022 | 7 | Wisley | 28.5
2022-07-08 | 2022 | 7 | Wisley | 27.2
2022-07-09 | 2022 | 7 | Wisley | 29.6
2022-07-10 | 2022 | 7 | Wisley | 31.4
2022-07-11 | 2022 | 7 | Wisley | 31.7
2022-07-12 | 2022 | 7 | Wisley | 28.9
2022-07-13 | 2022 | 7 | Wisley | 25.5
2022-07-14 | 2022 | 7 | Wisley | 27.1
2022-07-15 | 2022 | 7 | Wisley | 28.8
2022-07-16 | 2022 | 7 | Wisley | 30.3
2022-07-17 | 2022 | 7 | Wisley | 37.2
2022-07-18 | 2022 | 7 | Wisley | 39.3
2022-07-20 | 2022 | 7 | Wisley | 24.2
2022-07-21 | 2022 | 7 | Wisley | 23
2022-07-22 | 2022 | 7 | Wisley | 27.7
2022-07-23 | 2022 | 7 | Wisley | 28.2
2022-07-24 | 2022 | 7 | Wisley | 23.5
2022-07-25 | 2022 | 7 | Wisley | 22.3
2022-07-26 | 2022 | 7 | Wisley | 23.5
2022-07-27 | 2022 | 7 | Wisley | 24.7
2022-07-28 | 2022 | 7 | Wisley | 27.9
2022-07-29 | 2022 | 7 | Wisley | 26.4
2022-07-30 | 2022 | 7 | Wisley | 27.1
2022-07-31 | 2022 | 7 | Wisley | 27.6
2022-08-01 | 2022 | 8 | Wisley | 26.5
2022-08-02 | 2022 | 8 | Wisley | 27.5
2022-08-03 | 2022 | 8 | Wisley | 24.9
2022-08-04 | 2022 | 8 | Wisley | 23.1
2022-08-05 | 2022 | 8 | Wisley | 24.2
2022-08-06 | 2022 | 8 | Wisley | 27.7
2022-08-07 | 2022 | 8 | Wisley | 28.9
2022-08-08 | 2022 | 8 | Wisley | 28.4
2022-08-09 | 2022 | 8 | Wisley | 29.7
2022-08-10 | 2022 | 8 | Wisley | 32.3
2022-08-11 | 2022 | 8 | Wisley | 32.9
2022-08-12 | 2022 | 8 | Wisley | 34.2
2022-08-13 | 2022 | 8 | Wisley | 32.7
2022-08-14 | 2022 | 8 | Wisley | 29
2022-08-15 | 2022 | 8 | Wisley | 22.5
2022-08-16 | 2022 | 8 | Wisley | 24.7
2022-08-17 | 2022 | 8 | Wisley | 26.7
2022-08-18 | 2022 | 8 | Wisley | 24.9
2022-08-19 | 2022 | 8 | Wisley | 25.3
2022-08-20 | 2022 | 8 | Wisley | 25.4
2022-08-21 | 2022 | 8 | Wisley | 23
2022-08-22 | 2022 | 8 | Wisley | 26.6
2022-08-23 | 2022 | 8 | Wisley | 29.5
2022-08-25 | 2022 | 8 | Wisley | 24.9
2022-08-26 | 2022 | 8 | Wisley | 25.2
2022-08-27 | 2022 | 8 | Wisley | 24
2022-08-28 | 2022 | 8 | Wisley | 21.8
2022-08-29 | 2022 | 8 | Wisley | 24.1
2022-08-30 | 2022 | 8 | Wisley | 23.6
2022-08-31 | 2022 | 8 | Wisley | 22.7
2022-09-01 | 2022 | 9 | Wisley | 23.9
2022-09-02 | 2022 | 9 | Wisley | 23.8
2022-09-03 | 2022 | 9 | Wisley | 23.7
2022-09-04 | 2022 | 9 | Wisley | 22.4
2022-09-05 | 2022 | 9 | Wisley | 22.5
2022-09-06 | 2022 | 9 | Wisley | 21.6
2022-09-07 | 2022 | 9 | Wisley | 20.7
2022-09-08 | 2022 | 9 | Wisley | 19.6
2022-09-09 | 2022 | 9 | Wisley | 21.5
2022-09-10 | 2022 | 9 | Wisley | 23.4
2022-09-11 | 2022 | 9 | Wisley | 26.8
2022-09-13 | 2022 | 9 | Wisley | 21
2022-09-14 | 2022 | 9 | Wisley | 18.7
2022-09-15 | 2022 | 9 | Wisley | 16.8
2022-09-16 | 2022 | 9 | Wisley | 17.2
2022-09-17 | 2022 | 9 | Wisley | 17.8
2022-09-18 | 2022 | 9 | Wisley | 18
2022-09-19 | 2022 | 9 | Wisley | 20
2022-09-20 | 2022 | 9 | Wisley | 19.9
2022-09-21 | 2022 | 9 | Wisley | 20.7
2022-09-22 | 2022 | 9 | Wisley | 18.3
2022-09-23 | 2022 | 9 | Wisley | 18.5
2022-09-24 | 2022 | 9 | Wisley | 16.5
2022-09-25 | 2022 | 9 | Wisley | 15.3
2022-09-26 | 2022 | 9 | Wisley | 15.9
2022-09-27 | 2022 | 9 | Wisley | 14.9
2022-09-28 | 2022 | 9 | Wisley | 16.1
2022-09-29 | 2022 | 9 | Wisley | 16.3
2022-09-30 | 2022 | 9 | Wisley | 18.7
2023-05-01 | 2023 | 5 | Wisley | 15.9
2023-05-02 | 2023 | 5 | Wisley | 16
2023-05-03 | 2023 | 5 | Wisley | 19.7
2023-05-04 | 2023 | 5 | Wisley | 19.3
2023-05-06 | 2023 | 5 | Wisley | 20.9
2023-05-08 | 2023 | 5 | Wisley | 17.3
2023-05-09 | 2023 | 5 | Wisley | 18.9
2023-05-10 | 2023 | 5 | Wisley | 18
2023-05-11 | 2023 | 5 | Wisley | 13.9
2023-05-12 | 2023 | 5 | Wisley | 14.5
2023-05-13 | 2023 | 5 | Wisley | 21
2023-05-14 | 2023 | 5 | Wisley | 16.4
2023-05-15 | 2023 | 5 | Wisley | 17.4
2023-05-16 | 2023 | 5 | Wisley | 19.2
2023-05-17 | 2023 | 5 | Wisley | 20.4
2023-05-18 | 2023 | 5 | Wisley | 17.9
2023-05-19 | 2023 | 5 | Wisley | 20.1
2023-05-20 | 2023 | 5 | Wisley | 18.9
2023-05-21 | 2023 | 5 | Wisley | 19.4
2023-05-22 | 2023 | 5 | Wisley | 18.5
2023-05-23 | 2023 | 5 | Wisley | 21.8
2023-05-24 | 2023 | 5 | Wisley | 18.9
2023-05-25 | 2023 | 5 | Wisley | 19.2
2023-05-26 | 2023 | 5 | Wisley | 21.1
2023-05-27 | 2023 | 5 | Wisley | 22.4
2023-05-28 | 2023 | 5 | Wisley | 18.3
2023-05-29 | 2023 | 5 | Wisley | 18.3
2023-05-30 | 2023 | 5 | Wisley | 19.6
2023-05-31 | 2023 | 5 | Wisley | 19.7
2023-06-01 | 2023 | 6 | Wisley | 19
2023-06-02 | 2023 | 6 | Wisley | 22.3
2023-06-03 | 2023 | 6 | Wisley | 22.9
2023-06-04 | 2023 | 6 | Wisley | 18.6
2023-06-05 | 2023 | 6 | Wisley | 18.2
2023-06-06 | 2023 | 6 | Wisley | 22.1
2023-06-07 | 2023 | 6 | Wisley | 23
2023-06-08 | 2023 | 6 | Wisley | 25.9
2023-06-09 | 2023 | 6 | Wisley | 31.7
2023-06-10 | 2023 | 6 | Wisley | 30.8
2023-06-11 | 2023 | 6 | Wisley | 29.7
2023-06-12 | 2023 | 6 | Wisley | 28.7
2023-06-13 | 2023 | 6 | Wisley | 28.3
2023-06-14 | 2023 | 6 | Wisley | 27.5
2023-06-15 | 2023 | 6 | Wisley | 27.9
2023-06-16 | 2023 | 6 | Wisley | 26.6
2023-06-17 | 2023 | 6 | Wisley | 28.3
2023-06-18 | 2023 | 6 | Wisley | 25.6
2023-06-19 | 2023 | 6 | Wisley | 23.6
2023-06-20 | 2023 | 6 | Wisley | 26.3
2023-06-21 | 2023 | 6 | Wisley | 28.8
2023-06-22 | 2023 | 6 | Wisley | 28.1
2023-06-23 | 2023 | 6 | Wisley | 29
2023-06-24 | 2023 | 6 | Wisley | 31.4
2023-06-25 | 2023 | 6 | Wisley | 23.1
2023-06-26 | 2023 | 6 | Wisley | 24
2023-06-27 | 2023 | 6 | Wisley | 25
2023-06-28 | 2023 | 6 | Wisley | 23.2
2023-06-29 | 2023 | 6 | Wisley | 19.9
2023-06-30 | 2023 | 6 | Wisley | 23.8
2023-07-01 | 2023 | 7 | Wisley | 21.2
2023-07-02 | 2023 | 7 | Wisley | 22.3
2023-07-03 | 2023 | 7 | Wisley | 19.3
2023-07-04 | 2023 | 7 | Wisley | 21.8
2023-07-05 | 2023 | 7 | Wisley | 23.2
2023-07-06 | 2023 | 7 | Wisley | 29.8
2023-07-07 | 2023 | 7 | Wisley | 26.2
2023-07-08 | 2023 | 7 | Wisley | 24.4
2023-07-09 | 2023 | 7 | Wisley | 24.7
2023-07-10 | 2023 | 7 | Wisley | 24.8
2023-07-11 | 2023 | 7 | Wisley | 23.5
2023-07-12 | 2023 | 7 | Wisley | 22.2
2023-07-13 | 2023 | 7 | Wisley | 19.7
2023-07-14 | 2023 | 7 | Wisley | 21.3
2023-07-15 | 2023 | 7 | Wisley | 22.9
2023-07-16 | 2023 | 7 | Wisley | 23.1
2023-07-17 | 2023 | 7 | Wisley | 23.6
2023-07-18 | 2023 | 7 | Wisley | 24
2023-07-19 | 2023 | 7 | Wisley | 23.8
2023-07-20 | 2023 | 7 | Wisley | 21.7
2023-07-21 | 2023 | 7 | Wisley | 19.6
2023-07-22 | 2023 | 7 | Wisley | 24.7
2023-07-24 | 2023 | 7 | Wisley | 21.2
2023-07-25 | 2023 | 7 | Wisley | 23.7
2023-07-26 | 2023 | 7 | Wisley | 23.6
2023-07-27 | 2023 | 7 | Wisley | 24.6
2023-07-28 | 2023 | 7 | Wisley | 23.9
2023-07-29 | 2023 | 7 | Wisley | 21.2
2023-07-30 | 2023 | 7 | Wisley | 21.5
2023-07-31 | 2023 | 7 | Wisley | 23.9
2023-08-01 | 2023 | 8 | Wisley | 20.4
2023-08-02 | 2023 | 8 | Wisley | 21.8
2023-08-03 | 2023 | 8 | Wisley | 19.4
2023-08-04 | 2023 | 8 | Wisley | 18.9
2023-08-05 | 2023 | 8 | Wisley | 19.3
2023-08-06 | 2023 | 8 | Wisley | 22
2023-08-07 | 2023 | 8 | Wisley | 18.5
2023-08-08 | 2023 | 8 | Wisley | 25
2023-08-09 | 2023 | 8 | Wisley | 26.8
2023-08-10 | 2023 | 8 | Wisley | 25.1
2023-08-11 | 2023 | 8 | Wisley | 22.1
2023-08-12 | 2023 | 8 | Wisley | 23.5
2023-08-13 | 2023 | 8 | Wisley | 22.1
2023-08-14 | 2023 | 8 | Wisley | 25.8
2023-08-15 | 2023 | 8 | Wisley | 26.4
2023-08-16 | 2023 | 8 | Wisley | 23.9
2023-08-17 | 2023 | 8 | Wisley | 25.6
2023-08-18 | 2023 | 8 | Wisley | 24.5
2023-08-19 | 2023 | 8 | Wisley | 25.9
2023-08-20 | 2023 | 8 | Wisley | 25.1
2023-08-21 | 2023 | 8 | Wisley | 26.1
2023-08-22 | 2023 | 8 | Wisley | 27.9
2023-08-23 | 2023 | 8 | Wisley | 25
2023-08-24 | 2023 | 8 | Wisley | 23.1
2023-08-25 | 2023 | 8 | Wisley | 21.2
2023-08-26 | 2023 | 8 | Wisley | 21.1
2023-08-27 | 2023 | 8 | Wisley | 20.9
2023-08-28 | 2023 | 8 | Wisley | 21.9
2023-08-29 | 2023 | 8 | Wisley | 21.2
2023-08-30 | 2023 | 8 | Wisley | 17.6
2023-08-31 | 2023 | 8 | Wisley | 22.3
2023-09-01 | 2023 | 9 | Wisley | 24.7
2023-09-02 | 2023 | 9 | Wisley | 26.5
2023-09-03 | 2023 | 9 | Wisley | 30
2023-09-04 | 2023 | 9 | Wisley | 29.7
2023-09-05 | 2023 | 9 | Wisley | 31.1
2023-09-06 | 2023 | 9 | Wisley | 32.6
2023-09-07 | 2023 | 9 | Wisley | 30.8
2023-09-08 | 2023 | 9 | Wisley | 33.1
2023-09-09 | 2023 | 9 | Wisley | 28.9
2023-09-10 | 2023 | 9 | Wisley | 26.6
2023-09-11 | 2023 | 9 | Wisley | 23.4
2023-09-12 | 2023 | 9 | Wisley | 19.9
2023-09-13 | 2023 | 9 | Wisley | 24.9
2023-09-14 | 2023 | 9 | Wisley | 26.4
2023-09-15 | 2023 | 9 | Wisley | 27.4
2023-09-16 | 2023 | 9 | Wisley | 22.3
2023-09-17 | 2023 | 9 | Wisley | 19.8
2023-09-18 | 2023 | 9 | Wisley | 19.7
2023-09-19 | 2023 | 9 | Wisley | 21.3
2023-09-20 | 2023 | 9 | Wisley | 19.2
2023-09-21 | 2023 | 9 | Wisley | 19
2023-09-22 | 2023 | 9 | Wisley | 18.7
2023-09-23 | 2023 | 9 | Wisley | 21
2023-09-24 | 2023 | 9 | Wisley | 23
2023-09-25 | 2023 | 9 | Wisley | 23.5
2023-09-26 | 2023 | 9 | Wisley | 21.5
2023-09-27 | 2023 | 9 | Wisley | 20.3
2023-09-28 | 2023 | 9 | Wisley | 20.5
2023-09-29 | 2023 | 9 | Wisley | 20.3
2023-09-30 | 2023 | 9 | Wisley | 24.1
2024-05-01 | 2024 | 5 | Wisley | 16.2
2024-05-02 | 2024 | 5 | Wisley | 14.4
2024-05-03 | 2024 | 5 | Wisley | 17.8
2024-05-04 | 2024 | 5 | Wisley | 17.5
2024-05-05 | 2024 | 5 | Wisley | 15.6
2024-05-06 | 2024 | 5 | Wisley | 20
2024-05-07 | 2024 | 5 | Wisley | 21
2024-05-08 | 2024 | 5 | Wisley | 23.8
2024-05-09 | 2024 | 5 | Wisley | 24.2
2024-05-10 | 2024 | 5 | Wisley | 23.2
2024-05-11 | 2024 | 5 | Wisley | 26.9
2024-05-13 | 2024 | 5 | Wisley | 17.1
2024-05-14 | 2024 | 5 | Wisley | 19.7
2024-05-15 | 2024 | 5 | Wisley | 19.6
2024-05-16 | 2024 | 5 | Wisley | 22
2024-05-17 | 2024 | 5 | Wisley | 19.7
2024-05-18 | 2024 | 5 | Wisley | 23.3
2024-05-19 | 2024 | 5 | Wisley | 21.5
2024-05-21 | 2024 | 5 | Wisley | 15.1
2024-05-22 | 2024 | 5 | Wisley | 18.6
2024-05-23 | 2024 | 5 | Wisley | 18.9
2024-05-24 | 2024 | 5 | Wisley | 21.2
2024-05-25 | 2024 | 5 | Wisley | 19.9
2024-05-26 | 2024 | 5 | Wisley | 17.7
2024-05-27 | 2024 | 5 | Wisley | 17.9
2024-05-28 | 2024 | 5 | Wisley | 20
2024-05-29 | 2024 | 5 | Wisley | 18
2024-05-31 | 2024 | 5 | Wisley | 16.2
2024-06-01 | 2024 | 6 | Wisley | 23.2
2024-06-02 | 2024 | 6 | Wisley | 20.5
2024-06-03 | 2024 | 6 | Wisley | 20.2
2024-06-04 | 2024 | 6 | Wisley | 18.1
2024-06-05 | 2024 | 6 | Wisley | 19
2024-06-06 | 2024 | 6 | Wisley | 20.4
2024-06-07 | 2024 | 6 | Wisley | 19.6
2024-06-08 | 2024 | 6 | Wisley | 17.7
2024-06-09 | 2024 | 6 | Wisley | 16.9
2024-06-10 | 2024 | 6 | Wisley | 17
2024-06-11 | 2024 | 6 | Wisley | 16.9
2024-06-12 | 2024 | 6 | Wisley | 16.7
2024-06-13 | 2024 | 6 | Wisley | 19.9
2024-06-14 | 2024 | 6 | Wisley | 18.6
2024-06-15 | 2024 | 6 | Wisley | 21.6
2024-06-16 | 2024 | 6 | Wisley | 22.9
2024-06-17 | 2024 | 6 | Wisley | 22.7
2024-06-18 | 2024 | 6 | Wisley | 21.6
2024-06-19 | 2024 | 6 | Wisley | 23.7
2024-06-20 | 2024 | 6 | Wisley | 25.8
2024-06-21 | 2024 | 6 | Wisley | 23.4
2024-06-22 | 2024 | 6 | Wisley | 24.4
2024-06-23 | 2024 | 6 | Wisley | 28.3
2024-06-24 | 2024 | 6 | Wisley | 29.5
2024-06-25 | 2024 | 6 | Wisley | 30.5
2024-06-26 | 2024 | 6 | Wisley | 25
2024-06-27 | 2024 | 6 | Wisley | 20.9
2024-06-28 | 2024 | 6 | Wisley | 25.3
2024-06-29 | 2024 | 6 | Wisley | 21.2
2024-06-30 | 2024 | 6 | Wisley | 20.7
2024-07-01 | 2024 | 7 | Wisley | 19.8
2024-07-02 | 2024 | 7 | Wisley | 19.5
2024-07-03 | 2024 | 7 | Wisley | 20.7
2024-07-04 | 2024 | 7 | Wisley | 21.2
2024-07-05 | 2024 | 7 | Wisley | 17.8
2024-07-06 | 2024 | 7 | Wisley | 18.6
2024-07-07 | 2024 | 7 | Wisley | 19.7
2024-07-08 | 2024 | 7 | Wisley | 19.6
2024-07-09 | 2024 | 7 | Wisley | 22.9
2024-07-10 | 2024 | 7 | Wisley | 23.6
2024-07-11 | 2024 | 7 | Wisley | 19.6
2024-07-12 | 2024 | 7 | Wisley | 20.4
2024-07-13 | 2024 | 7 | Wisley | 22.9
2024-07-14 | 2024 | 7 | Wisley | 21.6
2024-07-15 | 2024 | 7 | Wisley | 21.3
2024-07-16 | 2024 | 7 | Wisley | 25.1
2024-07-17 | 2024 | 7 | Wisley | 28
2024-07-18 | 2024 | 7 | Wisley | 31.4
2024-07-19 | 2024 | 7 | Wisley | 23.5
2024-07-20 | 2024 | 7 | Wisley | 23.7
2024-07-21 | 2024 | 7 | Wisley | 24
2024-07-22 | 2024 | 7 | Wisley | 23.9
2024-07-23 | 2024 | 7 | Wisley | 25.6
2024-07-24 | 2024 | 7 | Wisley | 19.9
2024-07-25 | 2024 | 7 | Wisley | 24.3
2024-07-26 | 2024 | 7 | Wisley | 23.4
2024-07-27 | 2024 | 7 | Wisley | 27.3
2024-07-28 | 2024 | 7 | Wisley | 29.5
2024-07-29 | 2024 | 7 | Wisley | 31.6
2024-07-30 | 2024 | 7 | Wisley | 28.8
2024-07-31 | 2024 | 7 | Wisley | 30.2
2024-08-01 | 2024 | 8 | Wisley | 28.1
2024-08-02 | 2024 | 8 | Wisley | 26.3
2024-08-03 | 2024 | 8 | Wisley | 24.3
2024-08-04 | 2024 | 8 | Wisley | 26.2
2024-08-05 | 2024 | 8 | Wisley | 21.9
2024-08-06 | 2024 | 8 | Wisley | 23.1
2024-08-07 | 2024 | 8 | Wisley | 21.8
2024-08-08 | 2024 | 8 | Wisley | 25.3
2024-08-09 | 2024 | 8 | Wisley | 25.3
2024-08-10 | 2024 | 8 | Wisley | 29.8
2024-08-11 | 2024 | 8 | Wisley | 33.5
2024-08-12 | 2024 | 8 | Wisley | 27.1
2024-08-13 | 2024 | 8 | Wisley | 23.6
2024-08-14 | 2024 | 8 | Wisley | 22.3
2024-08-15 | 2024 | 8 | Wisley | 25.1
2024-08-16 | 2024 | 8 | Wisley | 23.3
2024-08-17 | 2024 | 8 | Wisley | 24
2024-08-18 | 2024 | 8 | Wisley | 21
2024-08-19 | 2024 | 8 | Wisley | 24.6
2024-08-20 | 2024 | 8 | Wisley | 22.1
2024-08-21 | 2024 | 8 | Wisley | 19.6
2024-08-22 | 2024 | 8 | Wisley | 22.5
2024-08-24 | 2024 | 8 | Wisley | 21.6
2024-08-25 | 2024 | 8 | Wisley | 23
2024-08-26 | 2024 | 8 | Wisley | 25.5
2024-08-27 | 2024 | 8 | Wisley | 29.5
2024-08-28 | 2024 | 8 | Wisley | 23.5
2024-08-29 | 2024 | 8 | Wisley | 22.9
2024-08-30 | 2024 | 8 | Wisley | 21.4
2024-08-31 | 2024 | 8 | Wisley | 28.7
2024-09-01 | 2024 | 9 | Wisley | 22.1
2024-09-02 | 2024 | 9 | Wisley | 24.1
2024-09-03 | 2024 | 9 | Wisley | 20.6
2024-09-04 | 2024 | 9 | Wisley | 18.2
2024-09-05 | 2024 | 9 | Wisley | 17.3
2024-09-06 | 2024 | 9 | Wisley | 19.1
2024-09-07 | 2024 | 9 | Wisley | 20.4
2024-09-08 | 2024 | 9 | Wisley | 17.7
2024-09-09 | 2024 | 9 | Wisley | 19.3
2024-09-10 | 2024 | 9 | Wisley | 17.2
2024-09-11 | 2024 | 9 | Wisley | 16.3
2024-09-12 | 2024 | 9 | Wisley | 17.9
2024-09-13 | 2024 | 9 | Wisley | 19.8
2024-09-14 | 2024 | 9 | Wisley | 20.4
2024-09-15 | 2024 | 9 | Wisley | 20.6
2024-09-16 | 2024 | 9 | Wisley | 21.2
2024-09-17 | 2024 | 9 | Wisley | 23.7
2024-09-18 | 2024 | 9 | Wisley | 25
2024-09-19 | 2024 | 9 | Wisley | 22.7
2024-09-20 | 2024 | 9 | Wisley | 23.2
2024-09-21 | 2024 | 9 | Wisley | 20.7
2024-09-22 | 2024 | 9 | Wisley | 18.7
2024-09-23 | 2024 | 9 | Wisley | 16.9
2024-09-24 | 2024 | 9 | Wisley | 17.9
2024-09-25 | 2024 | 9 | Wisley | 18.2
2024-09-27 | 2024 | 9 | Wisley | 15.3
2024-09-28 | 2024 | 9 | Wisley | 16
2024-09-29 | 2024 | 9 | Wisley | 17.8
2024-09-30 | 2024 | 9 | Wisley | 14.2
2025-05-01 | 2025 | 5 | Wisley | 25.8
2025-05-02 | 2025 | 5 | Wisley | 20.8
2025-05-03 | 2025 | 5 | Wisley | 14.7
2025-05-04 | 2025 | 5 | Wisley | 13.9
2025-05-05 | 2025 | 5 | Wisley | 15.7
2025-05-06 | 2025 | 5 | Wisley | 17
2025-05-07 | 2025 | 5 | Wisley | 17.5
2025-05-08 | 2025 | 5 | Wisley | 18.9
2025-05-09 | 2025 | 5 | Wisley | 22.6
2025-05-10 | 2025 | 5 | Wisley | 25.7
2025-05-11 | 2025 | 5 | Wisley | 21.6
2025-05-12 | 2025 | 5 | Wisley | 24.4
2025-05-13 | 2025 | 5 | Wisley | 23.6
2025-05-15 | 2025 | 5 | Wisley | 19.9
2025-05-16 | 2025 | 5 | Wisley | 19.9
2025-05-17 | 2025 | 5 | Wisley | 17.5
2025-05-18 | 2025 | 5 | Wisley | 20.4
2025-05-19 | 2025 | 5 | Wisley | 23.2
2025-05-20 | 2025 | 5 | Wisley | 18.7
2025-05-21 | 2025 | 5 | Wisley | 17.7
2025-05-22 | 2025 | 5 | Wisley | 20.4
2025-05-23 | 2025 | 5 | Wisley | 21
2025-05-24 | 2025 | 5 | Wisley | 20.2
2025-05-25 | 2025 | 5 | Wisley | 19.3
2025-05-26 | 2025 | 5 | Wisley | 17.6
2025-05-27 | 2025 | 5 | Wisley | 21.6
2025-05-28 | 2025 | 5 | Wisley | 24.5
2025-05-29 | 2025 | 5 | Wisley | 24.7
2025-05-30 | 2025 | 5 | Wisley | 26.6
2025-05-31 | 2025 | 5 | Wisley | 22.1
2025-06-01 | 2025 | 6 | Wisley | 21.8
2025-06-02 | 2025 | 6 | Wisley | 17.7
2025-06-03 | 2025 | 6 | Wisley | 19.3
2025-06-04 | 2025 | 6 | Wisley | 16.2
2025-06-05 | 2025 | 6 | Wisley | 20.2
2025-06-06 | 2025 | 6 | Wisley | 17.6
2025-06-07 | 2025 | 6 | Wisley | 19
2025-06-08 | 2025 | 6 | Wisley | 20.3
2025-06-09 | 2025 | 6 | Wisley | 23.4
2025-06-10 | 2025 | 6 | Wisley | 23.5
2025-06-11 | 2025 | 6 | Wisley | 24.8
2025-06-12 | 2025 | 6 | Wisley | 28.5
2025-06-13 | 2025 | 6 | Wisley | 23.9
2025-06-14 | 2025 | 6 | Wisley | 24.2
2025-06-15 | 2025 | 6 | Wisley | 26.2
2025-06-16 | 2025 | 6 | Wisley | 27.1
2025-06-17 | 2025 | 6 | Wisley | 28.9
2025-06-18 | 2025 | 6 | Wisley | 31.6
2025-06-19 | 2025 | 6 | Wisley | 29.8
2025-06-20 | 2025 | 6 | Wisley | 32.5
2025-06-21 | 2025 | 6 | Wisley | 26.2
2025-06-22 | 2025 | 6 | Wisley | 22.8
2025-06-23 | 2025 | 6 | Wisley | 26.6
2025-06-24 | 2025 | 6 | Wisley | 28.2
2025-06-25 | 2025 | 6 | Wisley | 25.1
2025-06-26 | 2025 | 6 | Wisley | 27.3
2025-06-27 | 2025 | 6 | Wisley | 30.5
2025-06-28 | 2025 | 6 | Wisley | 30.1
2025-06-29 | 2025 | 6 | Wisley | 32.8
2025-06-30 | 2025 | 6 | Wisley | 33.9
2025-07-02 | 2025 | 7 | Wisley | 25.5
2025-07-03 | 2025 | 7 | Wisley | 27.3
2025-07-04 | 2025 | 7 | Wisley | 23.3
2025-07-05 | 2025 | 7 | Wisley | 22.3
2025-07-06 | 2025 | 7 | Wisley | 22.1
2025-07-07 | 2025 | 7 | Wisley | 24.7
2025-07-08 | 2025 | 7 | Wisley | 27.9
2025-07-09 | 2025 | 7 | Wisley | 31
2025-07-10 | 2025 | 7 | Wisley | 32.2
2025-07-11 | 2025 | 7 | Wisley | 30.8
2025-07-12 | 2025 | 7 | Wisley | 28.6
2025-07-13 | 2025 | 7 | Wisley | 25.6
2025-07-14 | 2025 | 7 | Wisley | 22.8
2025-07-15 | 2025 | 7 | Wisley | 27
2025-07-16 | 2025 | 7 | Wisley | 26.4
2025-07-17 | 2025 | 7 | Wisley | 30.3
2025-07-19 | 2025 | 7 | Wisley | 22.9
2025-07-20 | 2025 | 7 | Wisley | 25
2025-07-21 | 2025 | 7 | Wisley | 23
2025-07-22 | 2025 | 7 | Wisley | 22
2025-07-23 | 2025 | 7 | Wisley | 21.9
2025-07-24 | 2025 | 7 | Wisley | 26.5
2025-07-25 | 2025 | 7 | Wisley | 24.6
2025-07-26 | 2025 | 7 | Wisley | 21.6
2025-07-27 | 2025 | 7 | Wisley | 25.8
2025-07-28 | 2025 | 7 | Wisley | 21.4
2025-07-29 | 2025 | 7 | Wisley | 25.4
2025-07-30 | 2025 | 7 | Wisley | 22.1
2025-07-31 | 2025 | 7 | Wisley | 22.1
2025-08-01 | 2025 | 8 | Wisley | 22.8
2025-08-02 | 2025 | 8 | Wisley | 23.7
2025-08-03 | 2025 | 8 | Wisley | 21.8
2025-08-04 | 2025 | 8 | Wisley | 22.6
2025-08-05 | 2025 | 8 | Wisley | 23.6
2025-08-06 | 2025 | 8 | Wisley | 23.3
2025-08-07 | 2025 | 8 | Wisley | 25.8
2025-08-08 | 2025 | 8 | Wisley | 25.9
2025-08-09 | 2025 | 8 | Wisley | 27.5
2025-08-10 | 2025 | 8 | Wisley | 30.9
2025-08-11 | 2025 | 8 | Wisley | 32.8
2025-08-12 | 2025 | 8 | Wisley | 26.4
2025-08-13 | 2025 | 8 | Wisley | 28.8
2025-08-14 | 2025 | 8 | Wisley | 30.2
2025-08-16 | 2025 | 8 | Wisley | 26
2025-08-17 | 2025 | 8 | Wisley | 21.6
2025-08-18 | 2025 | 8 | Wisley | 26
2025-08-19 | 2025 | 8 | Wisley | 21.7
2025-08-20 | 2025 | 8 | Wisley | 20.8
2025-08-21 | 2025 | 8 | Wisley | 23.3
2025-08-22 | 2025 | 8 | Wisley | 23.4
2025-08-23 | 2025 | 8 | Wisley | 26.1
2025-08-24 | 2025 | 8 | Wisley | 28.5
2025-08-25 | 2025 | 8 | Wisley | 26
2025-08-26 | 2025 | 8 | Wisley | 22.2
2025-08-27 | 2025 | 8 | Wisley | 22.3
2025-08-28 | 2025 | 8 | Wisley | 21.2
2025-08-29 | 2025 | 8 | Wisley | 22
2025-08-30 | 2025 | 8 | Wisley | 21.9
2025-08-31 | 2025 | 8 | Wisley | 21.2
2025-09-01 | 2025 | 9 | Wisley | 18.6
2025-09-02 | 2025 | 9 | Wisley | 21.4
2025-09-03 | 2025 | 9 | Wisley | 20.2
2025-09-04 | 2025 | 9 | Wisley | 23.3
2025-09-05 | 2025 | 9 | Wisley | 23.7
2025-09-06 | 2025 | 9 | Wisley | 26.2
2025-09-07 | 2025 | 9 | Wisley | 21.4
2025-09-08 | 2025 | 9 | Wisley | 21.6
2025-09-09 | 2025 | 9 | Wisley | 18.5
2025-09-10 | 2025 | 9 | Wisley | 19.6
2025-09-11 | 2025 | 9 | Wisley | 18.9
2025-09-12 | 2025 | 9 | Wisley | 18.8
2025-09-13 | 2025 | 9 | Wisley | 18
2025-09-14 | 2025 | 9 | Wisley | 18.7
2025-09-15 | 2025 | 9 | Wisley | 18.7
2025-09-16 | 2025 | 9 | Wisley | 18.9
2025-09-17 | 2025 | 9 | Wisley | 21.2
2025-09-18 | 2025 | 9 | Wisley | 26.7
2025-09-19 | 2025 | 9 | Wisley | 20.4
2025-09-21 | 2025 | 9 | Wisley | 17
2025-09-22 | 2025 | 9 | Wisley | 17.8
2025-09-23 | 2025 | 9 | Wisley | 18.3
2025-09-24 | 2025 | 9 | Wisley | 19.5
2025-09-25 | 2025 | 9 | Wisley | 14.9
2025-09-26 | 2025 | 9 | Wisley | 18.2
2025-09-27 | 2025 | 9 | Wisley | 17.1
2025-09-28 | 2025 | 9 | Wisley | 19
2025-09-29 | 2025 | 9 | Wisley | 20.6
2025-09-30 | 2025 | 9 | Wisley | 18.5
2026-05-01 | 2026 | 5 | Wisley | 22.5
2026-05-02 | 2026 | 5 | Wisley | 18.9
2026-05-03 | 2026 | 5 | Wisley | 17.9
2026-05-04 | 2026 | 5 | Wisley | 16.7
2026-05-05 | 2026 | 5 | Wisley | 15.2
2026-05-06 | 2026 | 5 | Wisley | 17.5
2026-05-07 | 2026 | 5 | Wisley | 19
2026-05-08 | 2026 | 5 | Wisley | 21.4
2026-05-09 | 2026 | 5 | Wisley | 14.1
2026-05-10 | 2026 | 5 | Wisley | 12.8
2026-05-11 | 2026 | 5 | Wisley | 17.1
2026-05-12 | 2026 | 5 | Wisley | 14.2
2026-05-13 | 2026 | 5 | Wisley | 14.4
2026-05-14 | 2026 | 5 | Wisley | 14.4
2026-05-15 | 2026 | 5 | Wisley | 15.6
2026-05-16 | 2026 | 5 | Wisley | 17.6
2026-05-17 | 2026 | 5 | Wisley | 15
2026-05-18 | 2026 | 5 | Wisley | 17.9
2026-05-19 | 2026 | 5 | Wisley | 19.6
2026-05-20 | 2026 | 5 | Wisley | 23.8
2026-05-21 | 2026 | 5 | Wisley | 27
2026-05-22 | 2026 | 5 | Wisley | 29.4
2026-05-23 | 2026 | 5 | Wisley | 31.6
2026-05-24 | 2026 | 5 | Wisley | 33.3
2026-05-25 | 2026 | 5 | Wisley | 33.8
2026-05-26 | 2026 | 5 | Wisley | 27.8
2026-05-27 | 2026 | 5 | Wisley | 31.3
2026-05-28 | 2026 | 5 | Wisley | 25.3
2026-05-29 | 2026 | 5 | Wisley | 29.9
2026-05-30 | 2026 | 5 | Wisley | 24
2026-05-31 | 2026 | 5 | Wisley | 23.7
2026-06-01 | 2026 | 6 | Wisley | 18.5
2026-06-02 | 2026 | 6 | Wisley | 19.3
2026-06-03 | 2026 | 6 | Wisley | 19.4
2026-06-04 | 2026 | 6 | Wisley | 18.9
2026-06-05 | 2026 | 6 | Wisley | 17.3
2026-06-06 | 2026 | 6 | Wisley | 18.9
2026-06-07 | 2026 | 6 | Wisley | 17.3
2026-06-08 | 2026 | 6 | Wisley | 18.7
2026-06-09 | 2026 | 6 | Wisley | 18.2
2026-06-10 | 2026 | 6 | Wisley | 17.4
2026-06-11 | 2026 | 6 | Wisley | 22.9
2026-06-12 | 2026 | 6 | Wisley | 22.1
2026-06-13 | 2026 | 6 | Wisley | 21.8
2026-06-14 | 2026 | 6 | Wisley | 22.7
2026-06-15 | 2026 | 6 | Wisley | 26.6
2026-06-16 | 2026 | 6 | Wisley | 24.4
2026-06-17 | 2026 | 6 | Wisley | 25.1
2026-06-18 | 2026 | 6 | Wisley | 29.3
2026-06-19 | 2026 | 6 | Wisley | 25.2
2026-06-20 | 2026 | 6 | Wisley | 31.7
2026-06-21 | 2026 | 6 | Wisley | 28.8
2026-06-22 | 2026 | 6 | Wisley | 34.6
2026-06-23 | 2026 | 6 | Wisley | 36
2026-06-24 | 2026 | 6 | Wisley | 34.3
2026-06-25 | 2026 | 6 | Wisley | 35.5
2026-06-26 | 2026 | 6 | Wisley | 31.9
2026-06-27 | 2026 | 6 | Wisley | 26.4
2026-06-28 | 2026 | 6 | Wisley | 24.6
2026-06-29 | 2026 | 6 | Wisley | 25.4
2026-06-30 | 2026 | 6 | Wisley | 27.6
2026-07-01 | 2026 | 7 | Wisley | 26.5
2026-07-02 | 2026 | 7 | Wisley | 27.5
2026-07-03 | 2026 | 7 | Wisley | 28.7
2026-07-04 | 2026 | 7 | Wisley | 29.7
2026-07-05 | 2026 | 7 | Wisley | 32.6
2026-07-06 | 2026 | 7 | Wisley | 32.2
2026-07-07 | 2026 | 7 | Wisley | 33.8
2026-07-08 | 2026 | 7 | Wisley | 35.5
2026-07-09 | 2026 | 7 | Wisley | 31.2
2026-07-10 | 2026 | 7 | Wisley | 29.9
2026-07-11 | 2026 | 7 | Wisley | 30.3
2026-07-12 | 2026 | 7 | Wisley | 28.1
2026-07-13 | 2026 | 7 | Wisley | 29.9
2026-07-14 | 2026 | 7 | Wisley | 28.8
2026-07-15 | 2026 | 7 | Wisley | 29.8
2026-07-16 | 2026 | 7 | Wisley | 29.5
2026-07-17 | 2026 | 7 | Wisley | 24.3
2026-07-18 | 2026 | 7 | Wisley | 23.7
2026-07-19 | 2026 | 7 | Wisley | 26
2026-07-20 | 2026 | 7 | Wisley | 24.1
2026-07-21 | 2026 | 7 | Wisley | 27.7
2026-07-22 | 2026 | 7 | Wisley | 27.7
2026-07-23 | 2026 | 7 | Wisley | 29.4
2026-07-24 | 2026 | 7 | Wisley | 29.7
2026-07-25 | 2026 | 7 | Wisley | 26.5
2026-07-26 | 2026 | 7 | Wisley | 27.8
2026-07-27 | 2026 | 7 | Wisley | 30
2026-07-28 | 2026 | 7 | Wisley | 34.9
2026-07-29 | 2026 | 7 | Wisley | 28.9
2026-07-30 | 2026 | 7 | Wisley | 25.9
2026-07-31 | 2026 | 7 | Wisley | 26.9
2026-08-01 | 2026 | 8 | Wisley | 29.6
2026-08-02 | 2026 | 8 | Wisley | 33.5
2026-08-03 | 2026 | 8 | Wisley | 30.8
2026-08-04 | 2026 | 8 | Wisley | 25.4
2026-08-05 | 2026 | 8 | Wisley | 23.6
2026-08-06 | 2026 | 8 | Wisley | 26.9
2026-08-07 | 2026 | 8 | Wisley | 28.7
2026-08-08 | 2026 | 8 | Wisley | 32.7
2026-08-09 | 2026 | 8 | Wisley | 27.4
2026-08-10 | 2026 | 8 | Wisley | 27.8
2026-08-11 | 2026 | 8 | Wisley | 34.3
2026-08-12 | 2026 | 8 | Wisley | 37.4
2026-08-13 | 2026 | 8 | Wisley | 34.7
2026-08-14 | 2026 | 8 | Wisley | 28.7
2026-08-15 | 2026 | 8 | Wisley | 27.4
2026-08-16 | 2026 | 8 | Wisley | 28.8
2026-08-17 | 2026 | 8 | Wisley | 25.9
2026-08-18 | 2026 | 8 | Wisley | 25.2
2026-08-19 | 2026 | 8 | Wisley | 23.9
2026-08-20 | 2026 | 8 | Wisley | 21.1
2026-08-21 | 2026 | 8 | Wisley | 23.1
2026-08-22 | 2026 | 8 | Wisley | 25.3
2026-08-23 | 2026 | 8 | Wisley | 23.9
2026-08-24 | 2026 | 8 | Wisley | 26.1
2026-08-25 | 2026 | 8 | Wisley | 28.6
2026-08-27 | 2026 | 8 | Wisley | 25.3
2026-08-28 | 2026 | 8 | Wisley | 20.9
2026-08-29 | 2026 | 8 | Wisley | 22.7
2026-08-30 | 2026 | 8 | Wisley | 25
2026-08-31 | 2026 | 8 | Wisley | 24.1
2026-09-01 | 2026 | 9 | Wisley | 21.1
2026-09-02 | 2026 | 9 | Wisley | 26.6
2026-09-04 | 2026 | 9 | Wisley | 23.9
2026-09-05 | 2026 | 9 | Wisley | 27.9
2026-09-06 | 2026 | 9 | Wisley | 24.8
2026-09-08 | 2026 | 9 | Wisley | 19
2026-09-09 | 2026 | 9 | Wisley | 20.9
2026-09-10 | 2026 | 9 | Wisley | 22.4
2026-09-11 | 2026 | 9 | Wisley | 24.3
2026-09-12 | 2026 | 9 | Wisley | 23
2026-09-13 | 2026 | 9 | Wisley | 24.5
2026-09-14 | 2026 | 9 | Wisley | 23.5
2026-09-15 | 2026 | 9 | Wisley | 20.6
2026-09-16 | 2026 | 9 | Wisley | 21.3
2026-09-17 | 2026 | 9 | Wisley | 20.5
2026-09-18 | 2026 | 9 | Wisley | 22.2
2026-09-19 | 2026 | 9 | Wisley | 20.8
2026-09-20 | 2026 | 9 | Wisley | 24.2
2026-09-21 | 2026 | 9 | Wisley | 26.4
2026-09-22 | 2026 | 9 | Wisley | 24.6
2026-09-23 | 2026 | 9 | Wisley | 22.3
2026-09-24 | 2026 | 9 | Wisley | 23.6
2026-09-25 | 2026 | 9 | Wisley | 21.9
2026-09-26 | 2026 | 9 | Wisley | 22.6
2026-09-27 | 2026 | 9 | Wisley | 20.5
2026-09-28 | 2026 | 9 | Wisley | 27.2
2026-09-29 | 2026 | 9 | Wisley | 24.2

## Heat_Forecast
Heat_Forecast: predicting hot-day stoppages for the build (risk R1)
Counts days ≥ the hot-day threshold each May–September at the station chosen on Baseline, fits a linear trend and projects it to the forecast year. Each complete historical year becomes one equally likely 2027 outcome (trend + that year's residual). Years with fewer than 120 valid days are left out.
| Year | Hot days (observed) | Valid days | Hot days (complete years) | Trend | Residual | In basis? (weight) | 2027 outcome (days) | Lost days: no response | Lost days: your response | Impact £k: no response | Cost £k: your response | Delay wk: your response | Impact £k: your response | Forecast summary | Value
| 1979 | 0 | 150 | 0 | 0.72619 | -0.72619 | 1 | 10 | 5 | 5 | 243.75 | 200 | 1.25 | 243.75 | Trend slope (days per year) | 0.21467
| 1980 | 0 | 147 | 0 | 0.94086 | -0.94086 | 1 | 10 | 5 | 5 | 243.75 | 200 | 1.25 | 243.75 | Trend intercept | -424.0971
| 1981 | 0 | 148 | 0 | 1.1555 | -1.1555 | 1 | 10 | 5 | 5 | 243.75 | 200 | 1.25 | 243.75 | Trend value in forecast year (days) | 11.0301
| 1982 | 0 | 153 | 0 | 1.3702 | -1.3702 | 1 | 10 | 5 | 5 | 243.75 | 200 | 1.25 | 243.75 | Expected hot days in forecast year (selected basis) | 11.0417
| 1983 | 9 | 153 | 9 | 1.5849 | 7.4151 | 1 | 18 | 13 | 13 | 633.75 | 520 | 3.25 | 633.75 | Chance of exceeding the allowance (no response) | 93.75%
| 1984 | 4 | 153 | 4 | 1.7995 | 2.2005 | 1 | 13 | 8 | 8 | 390 | 320 | 2 | 390 | R1 inherent EMV £k | 297.5781
| 1985 | 0 | 153 | 0 | 2.0142 | -2.0142 | 1 | 9 | 4 | 4 | 195 | 160 | 1 | 195 | R1 response chosen on Risk_Register | Accept
| 1986 | 3 | 153 | 3 | 2.2289 | 0.77115 | 1 | 12 | 7 | 7 | 341.25 | 280 | 1.75 | 341.25 | Heat exposure with response | 1
| 1987 | 0 | 153 | 0 | 2.4435 | -2.4435 | 1 | 9 | 4 | 4 | 195 | 160 | 1 | 195 | Share of a shift lost on a hot day | 1
| 1988 | 0 | 153 | 0 | 2.6582 | -2.6582 | 1 | 8 | 3 | 3 | 146.25 | 120 | 0.75 | 146.25 | Insured share | 0%
| 1989 | 7 | 152 | 7 | 2.8728 | 4.1272 | 1 | 15 | 10 | 10 | 487.5 | 400 | 2.5 | 487.5 | Residual chance of losing days | 93.75%
| 1990 | 12 | 150 | 12 | 3.0875 | 8.9125 | 1 | 20 | 15 | 15 | 731.25 | 600 | 3.75 | 731.25 | R1 residual expected cost £k | 244.1667
| 1991 | 0 | 153 | 0 | 3.3022 | -3.3022 | 1 | 8 | 3 | 3 | 146.25 | 120 | 0.75 | 146.25 | R1 residual expected delay wk | 1.526
| 1992 | 1 | 153 | 1 | 3.5168 | -2.5168 | 1 | 9 | 4 | 4 | 195 | 160 | 1 | 195 | R1 residual EMV £k | 297.5781
| 1993 | 0 | 153 | 0 | 3.7315 | -3.7315 | 1 | 7 | 2 | 2 | 97.5 | 80 | 0.5 | 97.5 | Trend per decade (days) | 2.1467
| 1994 | 8 | 153 | 8 | 3.9462 | 4.0538 | 1 | 15 | 10 | 10 | 487.5 | 400 | 2.5 | 487.5 | Latest complete summer | 2026
| 1995 | 17 | 153 | 17 | 4.1608 | 12.8392 | 1 | 24 | 19 | 19 | 926.25 | 760 | 4.75 | 926.25 | Hot days in the latest complete summer | 31
| 1996 | 7 | 153 | 7 | 4.3755 | 2.6245 | 1 | 14 | 9 | 9 | 438.75 | 360 | 2.25 | 438.75 | 1991–2020 average hot days (complete years) | 5.5
| 1997 | 3 | 153 | 3 | 4.5902 | -1.5902 | 1 | 9 | 4 | 4 | 195 | 160 | 1 | 195
| 1998 | 1 | 153 | 1 | 4.8048 | -3.8048 | 1 | 7 | 2 | 2 | 97.5 | 80 | 0.5 | 97.5
| 1999 | 4 | 153 | 4 | 5.0195 | -1.0195 | 1 | 10 | 5 | 5 | 243.75 | 200 | 1.25 | 243.75 | Questions to discuss: Which station and which basis can you defend for sites spread across London? The programme allowance was set from the 1991–2020 average. What does the latest summer say about that anchor? Heathrow is an airport and Wisley and Rothamsted are outside London. Does that bias the forecast up or down?
| 2000 | 3 | 153 | 3 | 5.2342 | -2.2342 | 1 | 9 | 4 | 4 | 195 | 160 | 1 | 195
| 2001 | 8 | 153 | 8 | 5.4488 | 2.5512 | 1 | 14 | 9 | 9 | 438.75 | 360 | 2.25 | 438.75
| 2002 | 2 | 153 | 2 | 5.6635 | -3.6635 | 1 | 7 | 2 | 2 | 97.5 | 80 | 0.5 | 97.5
| 2003 | 10 | 153 | 10 | 5.8782 | 4.1218 | 1 | 15 | 10 | 10 | 487.5 | 400 | 2.5 | 487.5
| 2004 | 3 | 153 | 3 | 6.0928 | -3.0928 | 1 | 8 | 3 | 3 | 146.25 | 120 | 0.75 | 146.25
| 2005 | 6 | 153 | 6 | 6.3075 | -0.3075 | 1 | 11 | 6 | 6 | 292.5 | 240 | 1.5 | 292.5
| 2006 | 15 | 153 | 15 | 6.5222 | 8.4778 | 1 | 20 | 15 | 15 | 731.25 | 600 | 3.75 | 731.25
| 2007 | 0 | 153 | 0 | 6.7368 | -6.7368 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| 2008 | 0 | 153 | 0 | 6.9515 | -6.9515 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| 2009 | 3 | 153 | 3 | 7.1662 | -4.1662 | 1 | 7 | 2 | 2 | 97.5 | 80 | 0.5 | 97.5
| 2010 | 2 | 153 | 2 | 7.3808 | -5.3808 | 1 | 6 | 1 | 1 | 48.75 | 40 | 0.25 | 48.75
| 2011 | 4 | 153 | 4 | 7.5955 | -3.5955 | 1 | 7 | 2 | 2 | 97.5 | 80 | 0.5 | 97.5
| 2012 | 3 | 153 | 3 | 7.8102 | -4.8102 | 1 | 6 | 1 | 1 | 48.75 | 40 | 0.25 | 48.75
| 2013 | 6 | 153 | 6 | 8.0248 | -2.0248 | 1 | 9 | 4 | 4 | 195 | 160 | 1 | 195
| 2014 | 1 | 153 | 1 | 8.2395 | -7.2395 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| 2015 | 5 | 153 | 5 | 8.4542 | -3.4542 | 1 | 8 | 3 | 3 | 146.25 | 120 | 0.75 | 146.25
| 2016 | 6 | 153 | 6 | 8.6688 | -2.6688 | 1 | 8 | 3 | 3 | 146.25 | 120 | 0.75 | 146.25
| 2017 | 7 | 152 | 7 | 8.8835 | -1.8835 | 1 | 9 | 4 | 4 | 195 | 160 | 1 | 195
| 2018 | 19 | 151 | 19 | 9.0982 | 9.9018 | 1 | 21 | 16 | 16 | 780 | 640 | 4 | 780
| 2019 | 9 | 153 | 9 | 9.3128 | -0.31282 | 1 | 11 | 6 | 6 | 292.5 | 240 | 1.5 | 292.5
| 2020 | 12 | 153 | 12 | 9.5275 | 2.4725 | 1 | 14 | 9 | 9 | 438.75 | 360 | 2.25 | 438.75
| 2021 | 6 | 145 | 6 | 9.7421 | -3.7421 | 1 | 7 | 2 | 2 | 97.5 | 80 | 0.5 | 97.5
| 2022 | 11 | 146 | 11 | 9.9568 | 1.0432 | 1 | 12 | 7 | 7 | 341.25 | 280 | 1.75 | 341.25
| 2023 | 10 | 149 | 10 | 10.1715 | -0.17148 | 1 | 11 | 6 | 6 | 292.5 | 240 | 1.5 | 292.5
| 2024 | 5 | 145 | 5 | 10.3861 | -5.3861 | 1 | 6 | 1 | 1 | 48.75 | 40 | 0.25 | 48.75
| 2025 | 14 | 147 | 14 | 10.6008 | 3.3992 | 1 | 14 | 9 | 9 | 438.75 | 360 | 2.25 | 438.75
| 2026 | 31 | 150 | 31 | 10.8155 | 20.1845 | 1 | 31 | 26 | 26 | 1267.5 | 1040 | 6.5 | 1267.5

## Risk_Register
Risk_Register: module template extended with responses, residual and secondary risk
Columns B–S follow the module template (likelihood, cost and schedule impact, severity, owner, likelihood £). Choose a response in column T (drop-down; leave blank to accept). Columns U–AN calculate residual and secondary risk. EMV = probability × impact, with delay costed at site overheads.
| ID | Date when occurred | Risk category | Risk description | Owner | Likelihood (P) | Cost min £k | Cost ML £k | Cost max £k | Delay min wk | Delay ML wk | Delay max wk | Impact if it occurs £k | L score | I score | Severity (L×I) | Priority | EMV (likelihood £) £k | Response (option ID) | Strategy | Mitigation cost £k | Weeks added | Residual P | Residual impact £k | Res. L | Res. I | Res. severity | Res. priority | Residual EMV £k | Secondary ID | Secondary risk | Sec. P | Sec. impact £k | Sec. severity | Sec. EMV £k | Contingency / comments | Status | Exp. cost £k (res + sec) | Exp. delay wk (res + sec) | Sec. delay cost £k (helper)
| R1 |  | Weather | Hot days (≥30°C) stop roof work beyond the 5 weather days allowed in the programme | Construction manager | 93.75% | see Heat_Forecast | [5 empty] | 317.4167 | 5 | 3 | 15 | High | 297.5781 |  | Accept | 0 | 0 | 93.75% | 317.4167 | 5 | 3 | 15 | High | 297.5781 |  |  | 0% | 0 |  | 0 |  | Open | 244.1667 | 1.526 | 0
| R2 |  | Supply chain | Cool-roof membrane supplier misses delivery dates | Procurement lead | 45% | 150 | 350 | 700 | 1 | 3 | 6 | 516.6667 | 4 | 4 | 16 | High | 232.5 |  | Accept | 0 | 0 | 45% | 516.6667 | 4 | 4 | 16 | High | 232.5 |  |  | 0% | 0 |  | 0 |  | Open | 180 | 1.5 | 0
| R3 |  | Technical / H&S | Asbestos found in older school roofs once work starts | Principal designer | 40% | 200 | 450 | 900 | 1 | 2 | 5 | 610 | 4 | 5 | 20 | High | 244 |  | Accept | 0 | 0 | 40% | 610 | 4 | 5 | 20 | High | 244 |  |  | 0% | 0 |  | 0 |  | Open | 206.6667 | 1.0667 | 0
| R4 |  | Regulatory | Listed-building consent delayed at heritage sites | Planning lead | 30% | 50 | 120 | 250 | 1 | 3 | 6 | 256.6667 | 3 | 3 | 9 | Medium | 77 |  | Accept | 0 | 0 | 30% | 256.6667 | 3 | 3 | 9 | Medium | 77 |  |  | 0% | 0 |  | 0 |  | Open | 42 | 1 | 0
| R5 |  | Resource | Roofing subcontractor over-committed across London | Procurement lead | 30% | 100 | 220 | 450 | 0.5 | 1.5 | 4 | 326.6667 | 3 | 3 | 9 | Medium | 98 |  | Accept | 0 | 0 | 30% | 326.6667 | 3 | 3 | 9 | Medium | 98 |  |  | 0% | 0 |  | 0 |  | Open | 77 | 0.6 | 0
| R6 |  | Technical | Roofs cannot carry new ventilation plant without strengthening | Structural engineer | 20% | 150 | 300 | 650 | 1 | 2 | 4 | 448.3333 | 2 | 4 | 8 | Medium | 89.6667 |  | Accept | 0 | 0 | 20% | 448.3333 | 2 | 4 | 8 | Medium | 89.6667 |  |  | 0% | 0 |  | 0 |  | Open | 73.3333 | 0.46667 | 0
| R7 |  | Commercial | Material price inflation above the estimate's allowance | Cost manager | 50% | 100 | 250 | 500 | 0 | 0 | 0 | 283.3333 | 4 | 3 | 12 | High | 141.6667 |  | Accept | 0 | 0 | 50% | 283.3333 | 4 | 3 | 12 | High | 141.6667 |  |  | 0% | 0 |  | 0 |  | Open | 141.6667 | 0 | 0
| R8 |  | Stakeholder | Residents object to cooling-centre opening hours | Engagement lead | 20% | 10 | 30 | 70 | 0 | 0.5 | 1 | 54.1667 | 2 | 1 | 2 | Low | 10.8333 |  | Accept | 0 | 0 | 20% | 54.1667 | 2 | 1 | 2 | Low | 10.8333 |  |  | 0% | 0 |  | 0 |  | Open | 7.3333 | 0.1 | 0
|  |  |  | Totals | [13 empty] | 1191.2448 |  |  | 0 | 0 | [6 empty] | 1191.2448 | [5 empty] | 0 |  |  | 972.1667 | 6.2594
Summary: expected-value (EMV) view
|  |  |  | Total inherent EMV £k | 1191.2448
|  |  |  | Total mitigation spend £k | 0
|  |  |  | Residual EMV, original risks £k | 1191.2448
|  |  |  | Secondary-risk EMV £k | 0
|  |  |  | Total residual exposure £k | 1191.2448
|  |  |  | Exposure reduced per £1 of mitigation | 0
|  |  |  | Expected finish week | 28.2594
|  |  |  | Expected final cost £k | 9791.2448
|  |  |  | Expected headroom against the budget £k | 8.7552
|  |  |  | Expected float against the deadline wk | -1.2594
The EMV view shows expected values only. A plan can look affordable on average and still have a low chance of meeting the budget. Read confidence levels from the dashboard's Monte Carlo, and explain any gap between the two views.

## Scenario_Log
Scenario_Log: every what-if scenario your group tests
On the dashboard press Save scenario, then "Copy rows for the workbook". Click the first empty cell in column B and paste. Row 5 is an example (no mitigation): keep it for comparison.
| ID | Group | Scenario | Round | Heat basis | Station | R1 response | R2 response | R3 response | R4 response | R5 response | R6 response | R7 response | R8 response | Weekend weeks (X1) | Fast-track (X2) | Sponsor contingency (X3) | Late night shifts (X4) | Mitigation spend £k | Expected cost £m | P80 cost £m | Budget £m | Confidence within budget | Expected finish week | P80 finish week | Confidence on time | Confidence both | Residual EMV £k | Secondary risks | Meets board targets | CPI forecast | SPI forecast | First-time acceptance | Stakeholder satisfaction | ROI forecast
| S00 | Example | No mitigation (accept all) | 1 | trend | Heathrow | – | – | – | – | – | – | – | – |  |  |  |  | 0 | 9.799 | 10.313 | 9.8 | 52.7% | 28.3 | 31.25 | 37.7% | 36.1% | 1199 | 0 | N | 0.878 | 0.777 | 95% | 6.69 | 35.6%

## Decision
Decision: shortlist, score, vote and decide
1) Agree weights as a group. 2) Shortlist up to five scenario IDs from Scenario_Log. 3) Each member votes. 4) Record the decision, the residual and secondary risks you accept and who owns them, and the dissent.
1. Criteria and weights
| Criterion | Better when | Weight (0–5)
| Confidence within budget | higher | 5
| Confidence on time | higher | 4
| Mitigation spend £k | lower | 2
| Residual EMV £k | lower | 2
| Secondary risks | lower | 1
Weights are a group decision: justify them in your recommendation. Board risk appetite: budget ≥ 70%, on time ≥ 60%.
2. Shortlist (up to five scenario IDs from Scenario_Log)
| Scenario ID | Scenario | Budget conf. | Time conf. | Mitigation £k | Residual EMV £k | Secondary risks | Meets targets | Weighted score | Votes | Rank
| S00 | No mitigation (accept all) | 52.7% | 37.7% | 0 | 1199 | 0 | N | 1 | 0 | 1
Weighted score: each criterion is scaled 0–1 against the best in your shortlist, then weighted. It shows which trade-off your weights favour, not the right answer.
3. Group vote
| Member (initials) | Role this round | Vote (scenario ID) | Why
4. Decision
Chosen scenario ID
Responses in the chosen scenario
Why this trade-off (refer to the dashboard and EMV views)
Residual risks we accept, and who owns them
Secondary risks we created, and how we will monitor them
Contingency we hold back, and the trigger for using it
Target we cannot fully meet (if any), and our case to the board
Strongest objection and our response
5. Dissent log (at least two entries): disagreeing well
| Who | Disagreed about | Evidence tested on the dashboard

## Round2_Update
Round2_Update: week 10 (14 June 2027)
Switch the dashboard to "Round 2 · Week 10 update". Your Round 1 responses are now committed: they have been spent or contracted.
| Status | About half of the works are complete at week 10, 0.8 weeks behind plan. See the earned-value status on the KPIs sheet (PV, EV, AC, SPI, CPI) and the time-phased CBS on WBS_CBS.
| Event: R2 has occurred | The membrane supplier has gone into administration. The impact depends on your Round 1 response to R2: none → 5 weeks and £380k; R2b (second supplier) → 60% of that; R2c (cool-roof paint) → 50%; R2a (bought up front) → no direct impact, but the stored stock (S2a) is now critical.
| Closed risks | R4: listed-building consent granted. R6: structural surveys complete, no strengthening needed. Close them on Risk_Register and explain whether your Round 1 spend on them was wasted or was the right decision under uncertainty.
| New information | The Met Office seasonal outlook favours a hotter-than-normal summer. The dashboard scales the hot-day forecast ×1.35. Set Baseline C18 to 1.35 to see the EMV view.
| R2 impact with your Round 1 response | 380 | 5 | Read from your R2 response on Risk_Register (cell T7).
Recovery actions
| Action | Your decision | Cost £k | Secondary risk created
| X1 Weekend working (0–4 weeks recovered, £55k per week) | 0 | 0 | None identified. Fatigue and safety are worth discussing.
| X2 Overlap trades on site (fast-track, recovers 2 weeks) | N | 0 | SX2: fast-tracking causes rework (35%, £50–120–250k, 0.5–1–2 wk)
| X3 Ask the sponsor for £0.4m client contingency | N | 0 | SX3: sponsor attaches conditions, extra assurance reviews (50%, £10–20–40k, 0–0.5–1 wk)
| X4 Start early and night shifts now (if R1a not chosen) | N | 0 | S1a: night-working noise complaints (30%, £20–50–100k, 0–0.5–1.5 wk)
| Recovery spend £k |  | 0
Questions for Round 2
1. Which Round 1 decisions paid off, and which looked right but cost you now? Separate a good decision from a good outcome.
2. Recovery buys time with money (X1), with quality risk (X2) or with the sponsor's goodwill (X3). Which currency can the project best afford to spend?
3. Update the register: close R4 and R6, record R2 as occurred, add the secondary risks your recovery creates, and re-score the open risks.
4. Save at least three Round 2 scenarios on the dashboard. Does your recovery plan meet the board targets? If not, what would you tell the board?
Our Round 2 recovery decision and rationale

## KPIs
KPIs: project performance measures
Section 1 recalculates from your responses on Risk_Register (expected-value view). Section 2 works the week-10 earned-value status used in Round 2. Section 3 defines every KPI on the dashboard.
1. Forecast at completion (expected-value view)
| Measure | Value | Status | Formula
| Budget at completion, BAC £k | 8600 |  | Base estimate + mitigation spend (the performance baseline, excluding reserve)
| Estimate at completion, EAC £k | 9791.2448 |  | Expected final cost from Risk_Register
| Cost performance index (forecast) | 0.87834 | Off track | BAC ÷ EAC. Target ≥ 0.95
| Variance at completion, VAC £k | -1191.2448 | Off track | BAC − EAC. Target ≥ −2% of BAC
| Budget variance £k | 8.7552 | On track | Authorised budget − EAC. Target ≥ 0
| Planned duration (weeks) | 22 |  | Plan + weeks added by your responses
| Forecast duration (weeks) | 28.2594 |  | Expected finish week from Risk_Register
| Schedule performance index, SPI(t) (forecast) | 0.7785 | Off track | Planned ÷ forecast duration. Target ≥ 0.95
| Schedule variance (weeks) | -6.2594 | Off track | Planned − forecast duration. Target ≥ −1 week
Quality, resource, stakeholder and value KPIs come from the dashboard simulation. Copy them from Scenario_Log (columns for CPI, SPI, first-time acceptance, satisfaction and ROI) or read them from the dashboard.
2. Week-10 earned-value status (Round 2)
| Measure | Value | Status | Formula
| Status week | 10 |  | Input
| Slip to date (weeks) | 0.8 |  | Input: wet spring and access problems (illustrative)
| Cost overrun on work done | 5% |  | Input: productivity below estimate (illustrative)
| Planned duration (weeks) | 22 |  | From section 1
| Works complete | 52.71% |  | Base work earned ÷ base estimate (time-phased CBS on WBS_CBS, shifted by the slip)
| Planned value, PV £k | 4746.7532 |  | Time-phased CBS to the status week (WBS_CBS column K) + mitigation (bought up front)
| Earned value, EV £k | 4533.0909 |  | Base work actually done (WBS_CBS column L) + mitigation
| Actual cost, AC £k | 4759.7455 |  | What has been spent
| Schedule variance, SV £k | -213.6623 |  | EV − PV
| Cost variance, CV £k | -226.6545 |  | EV − AC
| SPI | 0.95499 | On track | EV ÷ PV
| CPI | 0.95238 | On track | EV ÷ AC
| EAC by CPI method £k | 9030 |  | BAC ÷ CPI: assumes the rest performs like the first 10 weeks
| Estimate to complete, ETC £k | 4270.2545 |  | EAC − AC
| To-complete performance index (to budget) | 0.80689 |  | (BAC − EV) ÷ (budget − AC): efficiency needed on the remaining work to finish within the authorised budget
| EAC from the risk simulation (dashboard) £k |  |  | Enter from the dashboard (Round 2, Project KPIs). Why does it differ from the CPI-method EAC?
3. KPI definitions (as calculated on the dashboard)
| KPI | Category | Target (on track) | Definition | Watch band | Why it matters
| SPI(t) | Schedule | ≥ 0.95 | Planned duration ÷ forecast duration (earned-schedule form, at completion). | 0.90–0.95 | Below 1 = forecast to take longer than planned.
| Schedule variance | Schedule | ≥ −1 week | Planned − forecast duration. | down to −5 weeks (the float) | How much float the forecast uses up.
| On-time milestone rate | Schedule | ≥ 80% | Average chance that each of the five milestones (M1–M5) is met; each milestone date carries a pro-rata share of the float. | 60–80% | An early warning before the end date slips.
| CPI | Cost | ≥ 0.95 | BAC ÷ EAC (forecast) or EV ÷ AC (week-10 status). | 0.90–0.95 | Value earned per pound spent.
| Cost variance at completion | Cost | ≥ −2% of BAC | BAC − EAC. | down to −8% | Overspend that the reserve must absorb.
| Budget variance | Cost | ≥ £0 | Authorised budget (incl. reserve) − EAC. | down to −2% of budget | Whether the project needs more money from the sponsor.
| Rework rate | Scope and quality | ≤ 1.5% | Expected cost of redoing work ÷ base estimate (1.2% background + defect-causing secondary risks). | 1.5–2.5% | Rework is paid for twice.
| First-time acceptance | Scope and quality | ≥ 90% | Share of the 20 buildings accepted at handover without remedial work. | 80–90% | The deliverable acceptance rate.
| Defect density | Scope and quality | ≤ 7.5 per building | Snag items per building at handover (illustrative: 6 background + 12 per failed building). | 7.5–9 | Quality of what is handed over.
| Crew utilisation | Resources | ≥ 80% | Planned 90% × planned duration ÷ actual duration: waiting time lowers it. | 70–80% | Idle crews cost money and morale.
| Stakeholder satisfaction | Stakeholders | ≥ 7.0 / 10 | Survey index: 7.5 base, minus objections, complaints and late opening; plus co-design (R8a). | 6.0–7.0 | Schools, care homes and residents must use the centres.
| Return on investment | Value | ≥ 35% | (Benefits realised − final cost) ÷ final cost; planned whole-life benefit £13.5m (illustrative). | 20–35% | Whether the investment is still worth it.
| Benefits realisation | Value | ≥ 97% | Expected benefit ÷ planned benefit (lower-performing roofs or ventilation and late opening reduce it). | 93–97% | Delivering outputs is not the same as delivering outcomes.

## Student_Tasks
Student_Tasks: half-day timetable
Work in your project team. Rotate roles each task: chair, analyst, challenger (disagreeing well), scribe, stakeholder voice.
| Task | Focus (time) | What to do | Frameworks to apply (core modules) | ILOs
| 0 | Orientation (25 min) | Open the dashboard's Project brief tab (or the Project_Brief, Stakeholders_RACI, WBS_CBS and Success_Criteria sheets). Agree as a group which SMART objectives and success criteria matter most, and which stakeholders carry most exposure. Then open the Risk what-if tab: why is the chance of finishing on time so low when the expected delay is only a few weeks beyond the plan? | RRR: decision making under uncertainty (VUCA). STEM: scope, WBS and success criteria. LEAD: stakeholder analysis (power/interest) and roles (RACI). | 1, 4, 5
| 1 | Prioritise and challenge the register (30 min) | Check the inherent scores on Risk_Register against the scoring bands. Do you agree with every High and Medium? Challenge at least two assumptions. For R1, compare the three stations and three forecast bases, look at the summer 2026 chart, and agree which station and basis you will defend. | RRR: risk management (register, probability × impact); heuristics and biases (anchoring, optimism bias). STEM: measures of effectiveness. | 1, 2, 3
| 2 | Round 1 what-if (60 min) | Each member tests at least two scenarios on the dashboard and saves them. Between you, include: one that treats only the High risks; one that buys the cheapest response for every High and Medium risk; one that buys the most expensive. For each response, name the residual risk and the secondary risk it creates. Paste all rows into Scenario_Log. | RRR: risk response strategies (avoid, reduce, transfer, accept); secondary and residual risk. BE: contract types and incentives (fixed price, bonus, insurance). | 2, 6, 7
| 3 | Optimise and decide (30 min) | Use the scenario chart to find your best trade-offs, the ringed points. Check the project KPIs for your shortlist: which KPIs stay off track, and why? Agree weights, shortlist, vote and record the decision in Decision. Complete columns T and AK–AL of Risk_Register for the chosen scenario, and state the contingency you hold back. | RRR: trade studies and decision trees; margin management. BE: finance (cost–benefit, EMV). | 2, 7
| – | Break (15 min)
| 4 | Round 2: week 10 update (45 min) | Switch the dashboard to Round 2. Read the update and the week-10 earned-value status (KPIs sheet). Explain why the earned-value EAC and the risk-based EAC differ. Answer the questions on Round2_Update, choose recovery actions, save at least three Round 2 scenarios and update the register. | RRR: understanding and responding to failure; earned value management (leading and lagging indicators). LEAD: decision making under pressure; communicating with the sponsor. | 5, 7
| 5 | Brief the board (30 min) | Five-minute group briefing: your Round 1 decision, what Round 2 taught you, the residual and secondary risks you are asking the board to accept, and one simplification in the model that could change your answer. | LEAD: communicating a compelling vision. RRR: lessons learnt. | 8, 9
Project Simulation ILOs (SPCE0019 MDD)
1 Analyse data to extract key information
2 Conduct a comprehensive risk assessment, including mitigation strategies and residual risk
3 Understand optimism bias in estimation and risks of low-maturity technologies
4 Perform a stakeholder analysis in a complex environment
5 Understand team roles and exercise initiative as member and leader
6 Understand contract types and incentives for contractor performance
7 Make decisions to control risk, cost, schedule and technical performance in a time-limited context
8 Write a research report in an academic style
9 Present lessons learnt and respond to questions
Deliverable (formative)
This workbook with Scenario_Log, Risk_Register (responses, residual and secondary risks, contingency), Decision and Round2_Update completed, plus a two-page recommendation to the board and a five-minute briefing.

## Sources
Sources, licences and provenance
| Observations | Daily maximum temperature (TX), 1 May–30 September 1979–2026, for Heathrow (STAID 1860), Wisley (11112) and Rothamsted (1844). Series supplied by the Met Office National Climate Information Centre to the European Climate Assessment & Dataset blended data, with recent days completed from Met Office synoptic reports. Klein Tank, A.M.G. et al. (2002) Int. J. Climatol., 22, 1441–1453. https://www.ecad.eu. Only valid observations (quality code 0) are kept.
| Cross-check | Met Office historic station data, Heathrow (monthly): https://www.metoffice.gov.uk/pub/data/weather/uk/climate/stationdata/heathrowdata.txt. © Crown copyright, Open Government Licence v3. Monthly means of the daily series agree with it to within about ±0.25°C for May–September 2025–2026.
| Pipeline | All weather files are downloaded and processed weekly by a GitHub Actions workflow: github.com/SBegUCL/heatwise (pipeline/fetch_weather.py, data/README.md). Met Office MIDAS Open (more London stations, to the end of the previous year) can be added with a free CEDA account.
| Heat policy | The 30°C stop-work threshold is an illustrative HEATWISE site policy for teaching, not a statutory limit. UK law sets no maximum working temperature. Employers must assess heat risk (HSE guidance on temperature in the workplace).
| KPI assumptions | Planned whole-life benefit (£13.5m), stakeholder satisfaction effects, defect counts, rework attributions and the week-10 status (0.8 weeks slip, 5% cost overrun on work done) are illustrative teaching assumptions.
| Project figures | Budget, schedule, overheads, risk probabilities, impacts, response options and secondary risks are illustrative teaching assumptions. They are not estimates for any real programme.
| Dashboard | https://sbegucl.github.io/heatwise/ runs the same model in the browser, with a 4,000-run Monte Carlo simulation and fixed random streams, so that the same choices always give the same answer. It sends no data anywhere.